## Processed Data
Application ID | Application Category | Old Application ID | Applicant Name | Region | Revised Criterion | Nature Of Applicant | Type Of Project | Installed Capacity (MW) | Others IC MW | Solar | Wind | ESS | Installed Capacity (MW) Formula | Tendering Agency | Application Status | Connectivity Granted (MW) | Connectivity Revoked/Relinquished (MW) | Present Connectivity Deemed GNA | Substation Generation Connected | State Connectivity Station | Date Connectivity Intimation Final | Connectivity GNA Start Date Firm | Dedicated Connectivity System | Bays No. At ISTS End | Voltage Level Of Allocated Terminal Bay | Granted On | Associated Transmission System Detail | SCOD Of ATS (Tentative) | Augmentation (Other Than ATS) - Name | Augmentation (Other Than ATS) - Details | SCOD As Per Application | SCOD As per Application Phasewise | Connectivity GNA Made Effective MW | Start Date Connectivity GNA Made Effective | Connectivity GNA To Be Made Effective MW | Bay Number | Updated Revised SCOD Generation Project | Maximum Delay Permitted By REIA DL | Remarks On Updated Revised SCOD | Anticipated COD Of Terminal Bay | SCOD Transmission System Last Element | Anticipated COD/Charging Date Of Transmission System Last Element | Actual COD As Per DOCO Of Last Element | Connectivity Status | Expected Date Connectivity GNA Made Effective | Status Transmission System PMG | Generation Commissioning Status | CoD Declared For Total Quantum | Generation Schedule Details | Status As On Date | PPA Signing Status | Remarks | Updated On | Status | Phase Info | Phase MW | Phase Date | 24.6 Compliance due date
2200000003 | Main-Connectivity under GNA |  | BN HYBRID POWER-1 PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 119.2 | 0 | 40 | 79.2 | 0 | 119.2 |  | Granted | 119.2 | 0 | 119.2 | Fatehgarh-IV (Sec-I) | Rajasthan | 2024-09-23 | 2026-08-22 |  | 1 | 220 KV | Aug without ATS |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | 119.2 | 216 |  |  |  | 2025-10-15 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 119.20 ¦ Date: 2027-07-29 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 2025-06-30 |  | 2025-06-30 | 2027-02-28
2200000006 | Main-Connectivity under GNA |  | SOLARXL BETA ENERGY PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 207 (Solar-138 MW, Wind-69 MW) | 0 | 138 | 69 | 0 | 207 |  | Granted | 207 | 0 | 207 | Gadag-II | Karnataka | 2025-06-19 | 2025-12-31 | •Generation Pooling Station of SolarXL Beta Energy Pvt. Ltd.– Gadag-II PS 220 kV Sc line on Dc tower along with line bays at generation pooling station – under the scope of grantee •1 no. 220 kV line bay at Gadag-II PS` – Under the scope of applicant. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 31-Dec-24 | 31-Dec-24 |  |  | 207 | 227 |  |  |  |  | 2024-07-16 | 2027-04-30 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 138.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 69.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Dec-24 |  | 2024-12-31 | 2027-04-30
2200000008 | Main-Connectivity under GNA |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-III | Rajasthan | 2024-09-23 | 2026-08-22 | ACME Cleantech Solutions Private Limited Solar Power Project – Bikaner-III PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gad | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 31-May-25 | 31-May-25 |  |  | 300 | 201 |  |  |  |  | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-22 ¦ Status: Under Implementation ¦ Type: |  |  | Bay anticipated CoD to be updated | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-09-30
2200000012 | Main-Connectivity under GNA |  | AM GREEN ENERGY PRIVATE LIMITED | SR | Land BG Route | (xi) REGS with an installed capacity of 5 MW and above applying for grant of Connectivity to ISTS through the electrical system of a generating station already having Connectivity to ISTS | Hybrid | 989 (Solar-675MW, Wind314MW) | 0 | 675 | 314 | 0 | 989 |  | Granted | 989 | 0 | 989 | Kurnool (new) | Andhra Pradesh | 2024-01-09 | 2025-09-27 | •Common Generation Pooling Station of Ms Greenko AP01 IREP Pvt. Ltd. and Ms AM Green Energy Pvt. Ltd. at Kunool – Kurnool New 400kV Sc line including terminal bay at generation pooling station – under the scope of the grantee •1 no. 400kV line bay (Main bay & Tie bay) at Kurnool New Ss for termination of above dedicated line - under the scope of grantee | 1 | 400 KV | Aug with ATS | 1x1500 MVA (3rd), 765400 kV ICT at Kurnool New Ss |  | Establishment of 2x500MVA, 400220kV ICTs (1st & 2nd) at Lakadia PS along with associated ICT bays. Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) •ISTS Network Expansion scheme in Western Regio | Establishment of 2x500MVA, 400220kV ICTs (1st & 2nd) at Lakadia PS along with associated ICT bays. Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 15-Nov-23 | 15-Nov-23 |  |  | 989 | [5 empty] | 2024-07-31 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Part Commissioned | 914 | ¦ Phase 1 ¦ MW: 56.10 ¦ Date: 2024-12-04 ¦ Status: COD Declared ¦ Type: ¦ Phase 2 ¦ MW: 69.30 ¦ Date: 2024-12-11 ¦ Status: COD Declared ¦ Type: ¦ Phase 3 ¦ MW: 16.50 ¦ Date: 2024-12-21 ¦ Status: COD Declared ¦ Type: ¦ Phase 4 ¦ MW: 138.60 ¦ Date: 2025-02-01 ¦ Status: COD Declared ¦ Type: ¦ Phase 5 ¦ MW: 288.00 ¦ Date: 2025-02-01 ¦ Status: COD Declared ¦ Type: ¦ Phase 6 ¦ MW: 50.00 ¦ Date: 2025-02-19 ¦ Status: COD Declared ¦ Type: ¦ Phase 7 ¦ MW: 13.70 ¦ Date: 2025-04-12 ¦ Status: COD Declared ¦ Type: ¦ Phase 8 ¦ MW: 6.93 ¦ Date: 2025-04-18 ¦ Status: COD Declared ¦ Type: ¦ Phase 9 ¦ MW: 212.26 ¦ Date: 2025-04-18 ¦ Status: COD Declared ¦ Type: ¦ Phase 10 ¦ MW: 52.14 ¦ Date: 2025-06-28 ¦ Status: COD Declared ¦ Type: ¦ Phase 11 ¦ MW: 3.47 ¦ Date: 2025-09-03 ¦ Status: COD Declared ¦ Type: ¦ Phase 12 ¦ MW: 82.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 23/07/2026 | Pending with Level 2 | 15-Nov-23 |  | 2023-11-15 | 2026-10-31
2200000013 | Main-Connectivity under GNA |  | AVAADA RJBIKANER PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 | 0 | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Common Pooling station for Avaada RJ Bikaner Private Limited (App No. 2200000013 (50 MW), App. No. 2200000254 (600 MW)) & Avaada Energy Private Limited (App No. 2200000289 (300 MW)) RE Power Projects – Bikaner-IV PS 400 kV Sc line on Dc tower (Suitable to carry minimum 950 MW at nominal voltage) -Under Applicant scope Connectivity of 50 MW to Avaada RJ Bikaner Private Limited (App No. 2200000013) & 300 MW to Avaada Energy Private Limited (App No. 2200000289) is granted in sharing with App. No. 2200000254(600 MW) through same bay and DTL | 0 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA 1. Establishment of 6x1500 MVA, 765400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 2. 400kV Sectionalizer bay (1 set) at Bikaner-IV PS 3. STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS 4. LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS 5. Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 6. Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end 7. Siwani – Jind (PG) 400 kV Dc line (Quad) 8. Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end 9. Siwani – Fatehabad (PG) 400 kV Dc line (Quad) 10. Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end 11. STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 12. 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer 1. Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2. Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-Mar-25 | 31-Mar-25 |  |  | 50 | 438 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2027-05-11
2200000018 | Main-Connectivity under GNA |  | SPRNG PAVANA URJA PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2027-06-30 | Common Pooling station of M/s Sprng Pavana Urja Pvt. Ltd for Solar Projects with Appl. Nos. 1200003719(50 MW) ,2200000018 (100 MW) & 2200000034 (150 MW) – Fatehgarh-IV PS (Sec-2) 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage): Under applicant Scope Connectivity of 100 MW(Application no.- 2200000018) & 150 MW(App No. 2200000034) to M/s Sprng Pavana Urja Pvt. Ltd is granted in sharing with application of 50 MW (2200000003) through same DTL & bay | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA : Augmentation of 1x500 MVA (3rd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(1st & 2nd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA : Augmentation of 1x500 MVA (3rd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(1st & 2nd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 31-Dec-25 | 31-Dec-25 |  |  | 100 | 228 |  |  |  | 2026-08-14 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2027-12-30
2200000022 | Main-Connectivity under GNA |  | SPRNG VAYU VIDYUT PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Rajgarh (Sec-II) | Madhya Pradesh | 2024-03-11 | 2026-12-31 | • SVVPL – Rajgarh (PG) 220kV Sc line (on Dc tower) along with associated bay at Generator end (Under the scope of applicant) • 220kV GIS line bay at Rajgarh 400220kV (PG) Ss (on extended bus) for RE interconnection (under the scope of ISTS) | 1 | 220 KV | Aug with ATS | ATS (Under implementation w.r.t subject application) 1x500MVA, 400220kV ICT (3rd) at Rajgarh Ss (on the sectionalized 220kV bus) along with associated bays at both ends (400kV AIS & 220kV GIS). ATS (Awarded & Under implementation) 220kV bus extension (GIS) of Rajgarh (PG) 400220 kV Ss along with 220kV Bus Coupler Bay for extended bus (under the scope of ISTS) 220kV bus sectionaliser bay (GIS) between existing & extended 220 kV bus of Rajgarh Ss. (under the scope of ISTS). | 2025-11-15 |  |  | 31-Dec-26 | 31-Dec-26 |  |  | 100 | 217 |  |  |  | 2024-12-05 | 2025-11-15 | 2026-06-30 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2027-06-30
2200000024 | Main-Connectivity under GNA |  | SPRNG POWER PRIVATE LIMITED | NR | LOA or PPA and Land BG | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower# (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar |  | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 |  |  | 300 | 446 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 | 50 | 2025-12-31
2200000024 | Main-Connectivity under GNA |  | SPRNG POWER PRIVATE LIMITED | NR | LOA or PPA and Land BG | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower# (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar |  | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 |  |  | 300 | 446 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 | 50 | 2026-06-30
2200000024 | Main-Connectivity under GNA |  | SPRNG POWER PRIVATE LIMITED | NR | LOA or PPA and Land BG | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower# (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar |  | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 |  |  | 300 | 446 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 | 50 | 2026-12-31
2200000024 | Main-Connectivity under GNA |  | SPRNG POWER PRIVATE LIMITED | NR | LOA or PPA and Land BG | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower# (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar |  | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 |  |  | 300 | 446 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 | 100 | 2027-06-30
2200000024 | Main-Connectivity under GNA |  | SPRNG POWER PRIVATE LIMITED | NR | LOA or PPA and Land BG | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower# (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar |  | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 |  |  | 300 | 446 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 | 50 | 2027-12-31
2200000026 | Main-Connectivity under GNA |  | RENEW GREEN ENERGY SOLUTIONS PRIVATE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 51 |  | 51 | 0 | 0 | 51 |  | Granted | 51 | 0 | 51 | Solapur | Maharashtra | 2024-02-02 | 2025-03-31 | Ms RGESL shall share Dedicated Transmission System for Connectivity granted to Ms RGESL’s another SPP of 100MW (Stage-II Connectivity appl. No. 231400007) as given below Establishment of 33400kV Pooling Sub-Station PSS4 RGESL PSS 4 – Solapur (PG) 400kV Sc line (on Dc tower) (with HTLS conductor with minimum capacity of 2100MW at nominal voltage) along with associated bays at both ends (under the scope of applicant) Interconnection between RGESL main pooling station (PSS 4) and intermediate pooling stations (under the scope of applicant) Establishment of 33400kV Pooling Sub-station PSS1 Establishment of 33400kV Pooling Sub-station PSS2 Establishment of 33400kV Pooling Sub-station PSS5 PSS 5 – PSS 4 400kV Sc line (on Dc tower) along with associated bay PSS 2 – PSS 1 400kV Sc line (on Dc towers) along with associated bay PSS 1 – PSS 4 400kV Sc line (on Dc towers) along with associated bay | 0 | 400 KV | Existing |  |  | Existing Transmission System | Existing Transmission System | 31-Mar-25 | 31-Mar-25 | 51 | 2025-03-31 |  | 433 | [7 empty] | Effective |  |  | Part Commissioned | 50.1 | ¦ Phase 1 ¦ MW: 41.70 ¦ Date: 2025-10-13 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 8.40 ¦ Date: 2025-10-16 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 0.90 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2025-09-30
2200000032 | Main-Connectivity under GNA |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | Solar-750MW, Wind:960MW, BESS-288) |  | 810 | 900 | 288 | 1998 | SECI | Granted | 1484 | 0 | 1484 | Ananthapuram | Andhra Pradesh | 2025-06-17 | 2026-03-31 | · Generation Pooling station of Renew Vikram Shakti Private Limited – Anantapur PS 400 kV D/c line on D/c Tower# along with line bays at generation pooling station – under the scope of applicant. | 2 | 400 kV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •Transmission scheme for Solar Energy Zone in Ananthpuram (Anantapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •Transmission scheme for Solar Energy Zone in Ananthpuram (Anantapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | 31-Jul-25 | 31-Jul-25 |  |  | 1484 | (i) 422(M)& 423(Tie), (ii) 425(M) & 426(Tie) | 2026-10-27 |  | as per SECI letter 01.09.2025 | 2026-03-31 | 2025-09-27 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2026-10-15 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 235.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 4 ¦ MW: 375.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 5 ¦ MW: 100.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 6 ¦ MW: 150.80 ¦ Date: 2026-10-15 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 7 ¦ MW: 649.20 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 8 ¦ MW: 415.00 ¦ Date: 2028-02-29 ¦ Status: Under Implementation ¦ Type: Standalone ¦ Phase 9 ¦ MW: 185.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Standalone | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 31-Jul-25 |  | 2025-07-31 | 2026-10-31
2200000034 | Main-Connectivity under GNA |  | SPRNG PAVANA URJA PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 | 0 | 150 | 0 | 0 | 150 |  | Granted | 150 | 0 | 150 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2028-06-30 | 2 no. 400 kV line bays at Anantapur PS - under ISTS - under the scope of ISTS | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA : Augmentation of 1x500 MVA (3rd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(1st & 2nd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA : Augmentation of 1x500 MVA (3rd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(1st & 2nd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 50 MW 31.12.2026105 MW 30.06.2027 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 2 ¦ MW: 105.00 ¦ Date: 2027-06-30 |  |  | 150 | 228 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2028-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 | 50 | 2026-12-31 | 2028-12-30
2200000034 | Main-Connectivity under GNA |  | SPRNG PAVANA URJA PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 | 0 | 150 | 0 | 0 | 150 |  | Granted | 150 | 0 | 150 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2028-06-30 | 2 no. 400 kV line bays at Anantapur PS - under ISTS - under the scope of ISTS | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA : Augmentation of 1x500 MVA (3rd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(1st & 2nd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA : Augmentation of 1x500 MVA (3rd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(1st & 2nd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 50 MW 31.12.2026105 MW 30.06.2027 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 2 ¦ MW: 105.00 ¦ Date: 2027-06-30 |  |  | 150 | 228 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2028-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 2 ¦ MW: 105.00 ¦ Date: 2027-06-30 | 105 | 2027-06-30 | 2028-12-30
2200000035 | Main-Connectivity under GNA |  | TEQ GREEN POWER XI PRIVATE LIMITED | WR | Land BG Route | (ii) Generating station(s), including REGS(s), without ESS through a lead generator | Wind | 29.7 |  | 0 | 29.7 | 0 | 29.7 |  | Granted | 29.7 | 0 | 29.7 | kallam | Maharashtra | 2024-05-30 | 2025-10-05 | TGPXIPL in subject application (29.7MW) shall share the DTL provided to TGPXIPL in application no. 1200003901 (200MW), which is detailed below TGPXIPL – Kallam PS 220kV Sc line (on Dc tower) along with associated bay at Generation end (under the scope of applicant) | 0 | 220 KV | Aug without ATS |  |  | Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) along with 220kV bays for RE interconnection Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 n | Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) along with 220kV bays for RE interconnection Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 nos. 220 kV line bays for RE interconnection Western Region Network Expansion scheme in Kallam area of Maharashtra LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS Western Region Network Expansion scheme in Kallam area of Maharashtra (Under Bidding) • LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | 30-Sep-24 | 30-Sep-24 |  |  | 29.7 | 205 |  |  |  |  | 2025-10-05 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Part Commissioned | 13.5 | ¦ Phase 1 ¦ MW: 2.70 ¦ Date: 2025-06-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 5.40 ¦ Date: 2025-08-16 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 5.40 ¦ Date: 2025-02-10 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 16.20 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Sep-24 |  | 2024-09-30 | 2026-10-31
2200000037 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 450 | 0 | 450 | 0 | 0 | 450 |  | Granted | 450 | 0 | 450 | Bhadla-II | Rajasthan | 2024-09-23 | 2026-08-22 | Project Nine Renewable Power Private Limited Solar Power Project- Bhadla-ll PS 220 kV Dc line (suitable to carry minimum 300 MW per circuit at nominal voltage) — Under applicant scope Connectivity of 150 MW to MS Solarcraft Power India 4 Pvt. Ltd. (Application no.- 2200000152) at Bhadla-ll PS is granted in sharing with MS Project Nine Renewable through same DTL & bays | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV lev | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV level & 2x330 MVAr bus reactors at 765kV level at Sikar -II Bhadla-II PS – Sikar-II 765kV Dc line (2nd) Sikar-II – Khetri 765 kV Dc line Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) * with minimum capacity of 2100 MVAcircuit at nominal voltage Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50 MW 01.03.2025,50 MW 31.03.2025, 75 MW 15.04.2025,75 MW 30.04.2025,75 MW 01.05.2025,75 MW 31.05.2025, 50 MW 11.06.2025, | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-03-01 Phase 2 ¦ MW: 50.00 ¦ Date: 2025-03-31 Phase 3 ¦ MW: 75.00 ¦ Date: 2025-04-15 Phase 4 ¦ MW: 75.00 ¦ Date: 2025-04-30 Phase 5 ¦ MW: 75.00 ¦ Date: 2025-05-01 Phase 6 ¦ MW: 75.00 ¦ Date: 2025-05-31 Phase 7 ¦ MW: 50.00 ¦ Date: 2025-06-11 |  |  | 450 | A202,A203 |  |  |  |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-02-28 | Under Construction | Part Commissioned | 350 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-04-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 87.50 ¦ Date: 2026-04-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 12.50 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-14 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 100.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-03-01 | 50 | 2025-03-01 | 2027-03-31
2200000037 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 450 | 0 | 450 | 0 | 0 | 450 |  | Granted | 450 | 0 | 450 | Bhadla-II | Rajasthan | 2024-09-23 | 2026-08-22 | Project Nine Renewable Power Private Limited Solar Power Project- Bhadla-ll PS 220 kV Dc line (suitable to carry minimum 300 MW per circuit at nominal voltage) — Under applicant scope Connectivity of 150 MW to MS Solarcraft Power India 4 Pvt. Ltd. (Application no.- 2200000152) at Bhadla-ll PS is granted in sharing with MS Project Nine Renewable through same DTL & bays | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV lev | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV level & 2x330 MVAr bus reactors at 765kV level at Sikar -II Bhadla-II PS – Sikar-II 765kV Dc line (2nd) Sikar-II – Khetri 765 kV Dc line Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) * with minimum capacity of 2100 MVAcircuit at nominal voltage Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50 MW 01.03.2025,50 MW 31.03.2025, 75 MW 15.04.2025,75 MW 30.04.2025,75 MW 01.05.2025,75 MW 31.05.2025, 50 MW 11.06.2025, | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-03-01 Phase 2 ¦ MW: 50.00 ¦ Date: 2025-03-31 Phase 3 ¦ MW: 75.00 ¦ Date: 2025-04-15 Phase 4 ¦ MW: 75.00 ¦ Date: 2025-04-30 Phase 5 ¦ MW: 75.00 ¦ Date: 2025-05-01 Phase 6 ¦ MW: 75.00 ¦ Date: 2025-05-31 Phase 7 ¦ MW: 50.00 ¦ Date: 2025-06-11 |  |  | 450 | A202,A203 |  |  |  |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-02-28 | Under Construction | Part Commissioned | 350 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-04-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 87.50 ¦ Date: 2026-04-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 12.50 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-14 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 100.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 50.00 ¦ Date: 2025-03-31 | 50 | 2025-03-31 | 2027-03-31
2200000037 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 450 | 0 | 450 | 0 | 0 | 450 |  | Granted | 450 | 0 | 450 | Bhadla-II | Rajasthan | 2024-09-23 | 2026-08-22 | Project Nine Renewable Power Private Limited Solar Power Project- Bhadla-ll PS 220 kV Dc line (suitable to carry minimum 300 MW per circuit at nominal voltage) — Under applicant scope Connectivity of 150 MW to MS Solarcraft Power India 4 Pvt. Ltd. (Application no.- 2200000152) at Bhadla-ll PS is granted in sharing with MS Project Nine Renewable through same DTL & bays | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV lev | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV level & 2x330 MVAr bus reactors at 765kV level at Sikar -II Bhadla-II PS – Sikar-II 765kV Dc line (2nd) Sikar-II – Khetri 765 kV Dc line Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) * with minimum capacity of 2100 MVAcircuit at nominal voltage Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50 MW 01.03.2025,50 MW 31.03.2025, 75 MW 15.04.2025,75 MW 30.04.2025,75 MW 01.05.2025,75 MW 31.05.2025, 50 MW 11.06.2025, | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-03-01 Phase 2 ¦ MW: 50.00 ¦ Date: 2025-03-31 Phase 3 ¦ MW: 75.00 ¦ Date: 2025-04-15 Phase 4 ¦ MW: 75.00 ¦ Date: 2025-04-30 Phase 5 ¦ MW: 75.00 ¦ Date: 2025-05-01 Phase 6 ¦ MW: 75.00 ¦ Date: 2025-05-31 Phase 7 ¦ MW: 50.00 ¦ Date: 2025-06-11 |  |  | 450 | A202,A203 |  |  |  |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-02-28 | Under Construction | Part Commissioned | 350 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-04-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 87.50 ¦ Date: 2026-04-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 12.50 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-14 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 100.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 3 ¦ MW: 75.00 ¦ Date: 2025-04-15 | 75 | 2025-04-15 | 2027-03-31
2200000037 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 450 | 0 | 450 | 0 | 0 | 450 |  | Granted | 450 | 0 | 450 | Bhadla-II | Rajasthan | 2024-09-23 | 2026-08-22 | Project Nine Renewable Power Private Limited Solar Power Project- Bhadla-ll PS 220 kV Dc line (suitable to carry minimum 300 MW per circuit at nominal voltage) — Under applicant scope Connectivity of 150 MW to MS Solarcraft Power India 4 Pvt. Ltd. (Application no.- 2200000152) at Bhadla-ll PS is granted in sharing with MS Project Nine Renewable through same DTL & bays | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV lev | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV level & 2x330 MVAr bus reactors at 765kV level at Sikar -II Bhadla-II PS – Sikar-II 765kV Dc line (2nd) Sikar-II – Khetri 765 kV Dc line Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) * with minimum capacity of 2100 MVAcircuit at nominal voltage Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50 MW 01.03.2025,50 MW 31.03.2025, 75 MW 15.04.2025,75 MW 30.04.2025,75 MW 01.05.2025,75 MW 31.05.2025, 50 MW 11.06.2025, | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-03-01 Phase 2 ¦ MW: 50.00 ¦ Date: 2025-03-31 Phase 3 ¦ MW: 75.00 ¦ Date: 2025-04-15 Phase 4 ¦ MW: 75.00 ¦ Date: 2025-04-30 Phase 5 ¦ MW: 75.00 ¦ Date: 2025-05-01 Phase 6 ¦ MW: 75.00 ¦ Date: 2025-05-31 Phase 7 ¦ MW: 50.00 ¦ Date: 2025-06-11 |  |  | 450 | A202,A203 |  |  |  |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-02-28 | Under Construction | Part Commissioned | 350 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-04-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 87.50 ¦ Date: 2026-04-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 12.50 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-14 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 100.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 4 ¦ MW: 75.00 ¦ Date: 2025-04-30 | 75 | 2025-04-30 | 2027-03-31
2200000037 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 450 | 0 | 450 | 0 | 0 | 450 |  | Granted | 450 | 0 | 450 | Bhadla-II | Rajasthan | 2024-09-23 | 2026-08-22 | Project Nine Renewable Power Private Limited Solar Power Project- Bhadla-ll PS 220 kV Dc line (suitable to carry minimum 300 MW per circuit at nominal voltage) — Under applicant scope Connectivity of 150 MW to MS Solarcraft Power India 4 Pvt. Ltd. (Application no.- 2200000152) at Bhadla-ll PS is granted in sharing with MS Project Nine Renewable through same DTL & bays | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV lev | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV level & 2x330 MVAr bus reactors at 765kV level at Sikar -II Bhadla-II PS – Sikar-II 765kV Dc line (2nd) Sikar-II – Khetri 765 kV Dc line Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) * with minimum capacity of 2100 MVAcircuit at nominal voltage Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50 MW 01.03.2025,50 MW 31.03.2025, 75 MW 15.04.2025,75 MW 30.04.2025,75 MW 01.05.2025,75 MW 31.05.2025, 50 MW 11.06.2025, | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-03-01 Phase 2 ¦ MW: 50.00 ¦ Date: 2025-03-31 Phase 3 ¦ MW: 75.00 ¦ Date: 2025-04-15 Phase 4 ¦ MW: 75.00 ¦ Date: 2025-04-30 Phase 5 ¦ MW: 75.00 ¦ Date: 2025-05-01 Phase 6 ¦ MW: 75.00 ¦ Date: 2025-05-31 Phase 7 ¦ MW: 50.00 ¦ Date: 2025-06-11 |  |  | 450 | A202,A203 |  |  |  |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-02-28 | Under Construction | Part Commissioned | 350 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-04-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 87.50 ¦ Date: 2026-04-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 12.50 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-14 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 100.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 5 ¦ MW: 75.00 ¦ Date: 2025-05-01 | 75 | 2025-05-01 | 2027-03-31
2200000037 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 450 | 0 | 450 | 0 | 0 | 450 |  | Granted | 450 | 0 | 450 | Bhadla-II | Rajasthan | 2024-09-23 | 2026-08-22 | Project Nine Renewable Power Private Limited Solar Power Project- Bhadla-ll PS 220 kV Dc line (suitable to carry minimum 300 MW per circuit at nominal voltage) — Under applicant scope Connectivity of 150 MW to MS Solarcraft Power India 4 Pvt. Ltd. (Application no.- 2200000152) at Bhadla-ll PS is granted in sharing with MS Project Nine Renewable through same DTL & bays | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV lev | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV level & 2x330 MVAr bus reactors at 765kV level at Sikar -II Bhadla-II PS – Sikar-II 765kV Dc line (2nd) Sikar-II – Khetri 765 kV Dc line Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) * with minimum capacity of 2100 MVAcircuit at nominal voltage Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50 MW 01.03.2025,50 MW 31.03.2025, 75 MW 15.04.2025,75 MW 30.04.2025,75 MW 01.05.2025,75 MW 31.05.2025, 50 MW 11.06.2025, | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-03-01 Phase 2 ¦ MW: 50.00 ¦ Date: 2025-03-31 Phase 3 ¦ MW: 75.00 ¦ Date: 2025-04-15 Phase 4 ¦ MW: 75.00 ¦ Date: 2025-04-30 Phase 5 ¦ MW: 75.00 ¦ Date: 2025-05-01 Phase 6 ¦ MW: 75.00 ¦ Date: 2025-05-31 Phase 7 ¦ MW: 50.00 ¦ Date: 2025-06-11 |  |  | 450 | A202,A203 |  |  |  |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-02-28 | Under Construction | Part Commissioned | 350 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-04-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 87.50 ¦ Date: 2026-04-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 12.50 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-14 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 100.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 6 ¦ MW: 75.00 ¦ Date: 2025-05-31 | 75 | 2025-05-31 | 2027-03-31
2200000037 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 450 | 0 | 450 | 0 | 0 | 450 |  | Granted | 450 | 0 | 450 | Bhadla-II | Rajasthan | 2024-09-23 | 2026-08-22 | Project Nine Renewable Power Private Limited Solar Power Project- Bhadla-ll PS 220 kV Dc line (suitable to carry minimum 300 MW per circuit at nominal voltage) — Under applicant scope Connectivity of 150 MW to MS Solarcraft Power India 4 Pvt. Ltd. (Application no.- 2200000152) at Bhadla-ll PS is granted in sharing with MS Project Nine Renewable through same DTL & bays | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV lev | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II) with 1x125 MVAr at 400kV level & 2x330 MVAr bus reactors at 765kV level at Sikar -II Bhadla-II PS – Sikar-II 765kV Dc line (2nd) Sikar-II – Khetri 765 kV Dc line Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) * with minimum capacity of 2100 MVAcircuit at nominal voltage Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50 MW 01.03.2025,50 MW 31.03.2025, 75 MW 15.04.2025,75 MW 30.04.2025,75 MW 01.05.2025,75 MW 31.05.2025, 50 MW 11.06.2025, | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-03-01 Phase 2 ¦ MW: 50.00 ¦ Date: 2025-03-31 Phase 3 ¦ MW: 75.00 ¦ Date: 2025-04-15 Phase 4 ¦ MW: 75.00 ¦ Date: 2025-04-30 Phase 5 ¦ MW: 75.00 ¦ Date: 2025-05-01 Phase 6 ¦ MW: 75.00 ¦ Date: 2025-05-31 Phase 7 ¦ MW: 50.00 ¦ Date: 2025-06-11 |  |  | 450 | A202,A203 |  |  |  |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-02-28 | Under Construction | Part Commissioned | 350 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-04-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 87.50 ¦ Date: 2026-04-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 12.50 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-14 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 100.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 7 ¦ MW: 50.00 ¦ Date: 2025-06-11 | 50 | 2025-06-11 | 2027-03-31
2200000045 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 500 |  | 400 | 0 | 0 | 400 |  | Granted | 400 | 111 | 289 | Gadag-II | Karnataka | 2025-05-07 | 2027-01-17 | •Generation Pooling station of Project Ms Tata Power Renewable Energy Ltd. at Koppal – Gadag-II PS 400 kV Sc line along with 400 kV line at generation pooling station – under the scope of grantee •1 no. 400 kV line bay at Gadag-II PS - under the scope of grantee | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gada | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 01-Jun-25 | 01-Jun-25 |  |  | 289 | 214 |  |  |  | 2026-08-31 | 2027-01-16 | 2027-04-30 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 289.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 01-Jun-25 |  | 2025-06-01 | 2027-07-17
2200000048 | Main-Connectivity under GNA |  | GUJARAT STATE ELECTRICITY CORPORATION LIMITED | WR | Land Route | (x) Renewable Power Park developer | Solar | 3325 |  | 364 | 0 | 0 | 364 |  | Granted | 364 | 0 | 364 | KPS-2 (Sec-I) | Gujarat | 2025-03-20 | 2026-11-19 | For Up to 364MW left in Southern Plot GSECL shall share the connectivity system provided with Stage-II Connectivity to GSECL (Appl. No. 0230700005) which is detailed below GSECL PS1 (South) – Khavda-II PS (Sec-I) 400kV Dc line along with associated bay at Generation end (Under the scope of applicant) Bay at ISTS substation end shall be under the scope of ISTS) #Above 400kV Dc line shall also cater to 600MW St-II connectivity already granted to GSECL with stage-II application number 1200003331 at KPS-2. For balance 1361MW in Northern Plot GSECL PS2 (North) – Khavda-II PS (Sec-II) 400kV Sc line along with associated bay at Generation end (Under the scope of applicant) Bay at ISTS substation end shall be under the scope of ISTS) | 0 | 400 kV | Aug without ATS |  |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV, 4x1500MVA, KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari(New) 765 kV Dc line Khavda Phase-IV • Creation of 765kV bus section-II at KPS3 (GIS) along with 765kV Bus Sectionaliser • Creation of 400kV bus section-II at KPS3 (GIS) along with 400kV Bus Sectionaliser • KPS3 (GIS) – Lakadia (AIS) 765 kV DC line • ±300MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400kV Bus section-2 • KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line • Establishment of 2x1500MVA, 765400kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) • Vadodara(GIS) –South Olpad(GIS) 765 kV DC line • LILO of Gandhar – Hazira 400kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • Ahmedabad – South Olpad(GIS) 765kV Dc line • Establishment of 4X1500 MVA 765400 kV & 2x500MVA 400220kV Boisar-II (GIS) • South Olpad(GIS) – Boisar-II(GIS) 765kV Dc line • LILO of Navsari(New) – Padghe(PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon(MH) 400kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of Babhaleshwar – Padghe(M) 400kV Dc line at Boisar-II (Sec-I) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-I of Boisar-II and ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-II of Boisar-II • ±300 MVAr STATCOM with 3x125 MVAr MSC, 1x125 MVAr MSR at 400 kV level of Navsari(New)(PG) Ss with 1 No. of 400 kV bay (GIS) • Establishment of 2X1500 MVA 765400 kV & 3x500MVA 400220kV Pune-III (GIS) • Boisar-II – Pune-III 765k | 31-Mar-25 | 31-Mar-25 |  |  | 364 | 416 & 421 |  |  |  | 2026-06-30 | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 500.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 29-07-2026 |  |  | 29/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2027-10-30
2200000050 | Main-Connectivity under GNA |  | ASSAM POWER DISTRIBUTION COMPANY LIMITED | NER | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 750 |  | 1000 | 0 | 0 | 1000 |  | Granted | 750 | 0 | 750 | Bokajan | Assam | 2024-08-16 | 2026-12-31 |  | 1 | 400 KV | Aug with ATS | NERGS-I | 2026-12-31 |  | NIL | 01-May-25 | 01-May-25 |  |  | 750 | No |  |  |  |  | 2026-12-31 |  |  | Not effective | 2026-12-31 |  | Not Commissioned | 0 |  | 14-05-2026 |  | Generation project withdrawn by APDCL and decision pending in TL Petition filed in CERC by NERGS-I. Hence, NERGS-I project on hold. | 03/06/2026 | Pending with Group Head | 01-May-25 |  | 2025-05-01 | 2027-06-30
2200000054 | Main-Connectivity under GNA |  | GREEN INFRA CLEAN WIND TECHNOLOGY PRIVATE LIMITED (Formerly known as GREEN INFRA CLEAN WIND TECHNOLO | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 | NHPC | Granted | 300 | 0 | 300 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2026-11-07 | Common Pooling station of M/s Green Infra Clean Wind Technology Limited Power Project(App. No. 2200000054 - 300 MW) & Green Infra Clean Solar Farms Limited(App. No. 220000135 - 110 MW) – Fatehgarh-IV (Section-II) PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 410 MW at nominal voltage) – Under applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA : Augmentation of 2x500 MVA (3rd & 4th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(1st, 2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA : Augmentation of 2x500 MVA (3rd & 4th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(1st, 2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 01-Jun-25 | 01-Jun-25 |  |  | 300 | 233 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-08-30 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 01-Jun-25 |  | 2025-06-01 | 2027-06-30
2200000057 | Main-Connectivity under GNA |  | SOLAR ENERGY CORPORATION OF INDIA LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 | IRDEA | Granted | 100 | 0 | 100 | Pavagada | Karnataka | 2024-05-13 | 2025-08-17 | •Through sharing of dedicated Connectivity transmission system granted to M/s Solar Energy Corporation of India Ltd. as Renewable Power Park Developer for application no. 1200003590 i.e. Generating Pooling Station of Renewable Power Park at Ananthpur (Ramagiri/ Muthavankunta)– Pavagada (Tumkur) PS 220kV S/c line – all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Augmentation of 400/220 kV, 1x500 MVA ICT(7th) at Pavagada (Tumkur) PS •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Augmentation of 400/220 kV, 1x500 MVA ICT(7th) at Pavagada (Tumkur) PS •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 23-Jun-25 | 23-Jun-25 |  |  | 100 | 218 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 23-Jun-25 |  | 2025-06-23 | 2026-10-31
2200000058 | Main-Connectivity under GNA |  | TORRENT SAURYA URJA 2 PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 | SECI | Granted | 300 | 0 | 300 | Koppal-II | Karnataka | 2025-03-03 | 2025-12-27 | •Generation Pooling Station of Ms Torrent Saurya Urja 2 Pvt. Ltd. at Bagalkot – Koppal-II PS 220 kV Sc line on Dc Tower along with 220kV line at generation pooling station – under the scope of grantee •1 no. 220 kV line bay at Koppal-II PS – Under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) in Karnataka •Transmission Scheme for integration | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) in Karnataka •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-B) •ISTS Network Expansion scheme in WR & SR for export of surplus power during high RE scenario in SR | 29-Mar-25 | 29-Mar-25 |  |  | 300 | 208 | 2026-01-23 |  | Torrent Surya Urja 2 Pvt. Ltd. representative informed that Revised SCoD is 23.01.2026 | 2026-06-30 | 2025-12-26 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 60.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 60.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 90.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 4 ¦ MW: 90.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 29-Mar-25 |  | 2025-03-29 | 2026-10-31
2200000061 | Main-Connectivity under GNA |  | ZENATARIS RENEWABLE ENERGY PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 171.6 |  | 100 | 71.6 | 0 | 171.6 |  | Granted | 171.6 | 0 | 171.6 | Hiriyur | Karnataka | 2024-03-08 | 2025-06-30 | •Through dedicated Connectivity transmission system granted to M/s Zenataris Renewable Energy Pvt. Ltd. for application no. 0251100011 i.e. Generation Pooling station of Zenataris Renewable Energy Pvt. Ltd. – Hiriyur PS 220 kV S/c line – all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-Dec-24 | 31-Dec-24 |  |  | 171.6 | 216 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 94.33 ¦ Date: 2026-06-22 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 5.68 ¦ Date: 2026-06-28 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 71.60 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 09/07/2026 | Pending with Level 2 | 31-Dec-24 |  | 2024-12-31 | 2026-10-31
2200000062 | Main-Connectivity under GNA |  | JUNIPER GREEN INDIA SIX PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bhadla-III | Rajasthan | 2026-03-27 |  | Juniper Green India Six Private Limited Renewable Power Park– Bhadla-III PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x500 MVA (4th & 5th) 400220kV ICTs at Bhadla-III PS 2) Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III 3) 765 kV Bhadla-III – Bikane | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x500 MVA (4th & 5th) 400220kV ICTs at Bhadla-III PS 2) Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III 3) 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end 4) Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation 5) Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) 6) Bhadla-III – Bhadla (HVDC) 400 kV Dc (1st & 2nd) quad moose line along with the line bays at both substations 7) Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 8) Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line 9) Augmentation of 5x1500 MVA (1st to 5th ), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor 10) LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur 11) Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 150MW 31.12.2027150MW 30.06.2028 | Phase 1 ¦ MW: 150.00 ¦ Date: 2027-12-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2028-06-30 |  |  | 300 | 218 | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2029-07-20 ¦ Status: Under Implementation ¦ Type: | 30.06.2028 |  |  |  | Pending with Level 2 | Phase 1 ¦ MW: 150.00 ¦ Date: 2027-12-31 | 150 | 2027-12-31 | 2029-07-20
2200000062 | Main-Connectivity under GNA |  | JUNIPER GREEN INDIA SIX PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bhadla-III | Rajasthan | 2026-03-27 |  | Juniper Green India Six Private Limited Renewable Power Park– Bhadla-III PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x500 MVA (4th & 5th) 400220kV ICTs at Bhadla-III PS 2) Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III 3) 765 kV Bhadla-III – Bikane | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x500 MVA (4th & 5th) 400220kV ICTs at Bhadla-III PS 2) Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III 3) 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end 4) Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation 5) Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) 6) Bhadla-III – Bhadla (HVDC) 400 kV Dc (1st & 2nd) quad moose line along with the line bays at both substations 7) Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 8) Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line 9) Augmentation of 5x1500 MVA (1st to 5th ), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor 10) LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur 11) Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 150MW 31.12.2027150MW 30.06.2028 | Phase 1 ¦ MW: 150.00 ¦ Date: 2027-12-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2028-06-30 |  |  | 300 | 218 | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2029-07-20 ¦ Status: Under Implementation ¦ Type: | 30.06.2028 |  |  |  | Pending with Level 2 | Phase 2 ¦ MW: 150.00 ¦ Date: 2028-06-30 | 150 | 2028-06-30 | 2029-07-20
2200000063 | Main-Connectivity under GNA |  | JUNIPER GREEN STELLAR PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Hybrid | 300 | 0 | 200 | 100 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2026-12-31 | M/s Juniper Green Stellar Private Limited Solar PSS - Fatehgarh-IV PS (Sec-l) (high capacity) 220kV S/c line on D/c towers (Suitable to carry minimum 365 MW at nominal voltage) - Under Applicant Scope Internal Interconnection: M/s Juniper Green Stellar Private Limited Wind PSS Solar PSS 220kV S/c line on D/c towers Connectivity of application no. 0412100010 (150MW) and 0412100011 (65MW) is granted in sharing with application по. 0412100009 (150MW). 220kV bay at Fatehgarh-IV PS (Sec-l) shall be implemented under ISTS. | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 150MW 31.12.2026150MW 30.06.2027 | Phase 1 ¦ MW: 150.00 ¦ Date: 2026-12-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2027-06-30 |  |  | 300 | 235 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 1 ¦ MW: 150.00 ¦ Date: 2026-12-31 | 150 | 2026-12-31 | 2027-06-30
2200000063 | Main-Connectivity under GNA |  | JUNIPER GREEN STELLAR PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Hybrid | 300 | 0 | 200 | 100 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2026-12-31 | M/s Juniper Green Stellar Private Limited Solar PSS - Fatehgarh-IV PS (Sec-l) (high capacity) 220kV S/c line on D/c towers (Suitable to carry minimum 365 MW at nominal voltage) - Under Applicant Scope Internal Interconnection: M/s Juniper Green Stellar Private Limited Wind PSS Solar PSS 220kV S/c line on D/c towers Connectivity of application no. 0412100010 (150MW) and 0412100011 (65MW) is granted in sharing with application по. 0412100009 (150MW). 220kV bay at Fatehgarh-IV PS (Sec-l) shall be implemented under ISTS. | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 150MW 31.12.2026150MW 30.06.2027 | Phase 1 ¦ MW: 150.00 ¦ Date: 2026-12-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2027-06-30 |  |  | 300 | 235 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 2 ¦ MW: 150.00 ¦ Date: 2027-06-30 | 150 | 2027-06-30 | 2027-12-30
2200000065 | Main-Connectivity under GNA |  | SPRNG AKSHAYA URJA PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 | 0 | 100 | 0 | 0 | 100 | REMCL | Granted | 100 | 0 | 100 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower# (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay## | 1 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x33 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 30-Jun-25 | 30-Jun-25 |  |  | 100 | 446 | 2025-12-26 |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2027-02-28
2200000067 | Main-Connectivity under GNA |  | UTKRRISHT SOLAR ENERGY PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2026-11-07 | Utkrrisht Solar Energy Private Limited Power Park – Fatehgarh-IV (Section-II) PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage): Under applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA : Augmentation of 2x500 MVA (4th & 5th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA : Augmentation of 2x500 MVA (4th & 5th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 01-Apr-26 | 01-Apr-26 |  |  | 300 | 237 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-01-25 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2027-12-16 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 01-Apr-26 |  | 2026-04-01 | 2027-06-30
2200000069 | Main-Connectivity under GNA |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Wind | 400 |  | 0 | 400 | 190 | 590 | SECI | Granted | 400 | 0 | 400 | Ananthapuram | Andhra Pradesh | 2025-03-20 | 2026-05-31 | • Generation Pooling station of Ms ACME Cleantech Solutions Private Limited – Anantapuram PS 220 kV Dc line [with stringing of both circuit of Dc tower and bunching of both circuits at both ends and terminating on a single bay at both ends] along with line bays at generation pooling station – under the scope of applicant. • 1 no. of 220 kV line bay at Anantapuram PS for termination of above mentioned dedicated Connectivity line - under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Prad | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | 19-Jul-25 | 19-Jul-25 |  |  | 400 | 201 | 2027-10-14 |  | Acme cleantech has informed vide email dtd. 20-06-2025 that 190MW(Hybrid) PPA signed for connectivity app no. 2200000335 and 2200000069 for which vide SECI letter, revised SCD is 27.10.2026. Further extended till 14.10.2027 (190MW). for remaining 190MW PPA SCD as per PPA submitted by applican is 27.02.2028 | 2026-03-31 | 2025-09-27 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-10-14 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2028-02-27 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 380.00 ¦ Date: 2027-10-14 ¦ Status: Under Implementation ¦ Type: Standalone | 16.03.2026 | Yes |  |  | Pending with Level 2 | 19-Jul-25 |  | 2025-07-19 | 2027-10-14
2200000070 | Main-Connectivity under GNA |  | RENEW URJA SHACHAR PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Indore | Madhya Pradesh | 2024-01-19 | 2025-06-30 | Under the scope of Applicant 1. Establishment of 33400 KV Common Pooling Sub-Station-1 (PSS-1) of Renew Samir Urja Private Limited (Appl. No. 2200000298) and Renew Urja Shachar Private Limited (Appl. No. 2200000070). 2. Establishment of 33400 KV Common Pooling Sub-Station-2 (PSS-2) of Renew Samir Urja Private Limited (Appl. No. 2200000298) and Renew Urja Shachar Private Limited (Appl. No. 2200000070). 3. PSS-2– PSS-1 400kV SC line on Dc tower. 4. PSS-1 – Indore (Sec-A With Indore & Khandwa lines) 400kV SC line on Dc tower. Under the scope of ISTS 1. Implementation of 400kV Bay at Indore (PG) Ss is under ISTS (Awarded to POWERGRID vide CTU OM dated 02.01.2024 with implementation timeframe of 30.06.2025) | 1 | 400 KV | Existing |  |  | Nil | Nil | 30-Jun-25 | 30-Jun-25 |  |  | 300 | 422 |  |  |  | 2025-12-02 |  |  |  | Not effective | 2026-08-25 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-09-15 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2025-12-30
2200000072 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 480 | 0 | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Gadag-II | Karnataka | 2025-04-03 | 2025-12-31 | Generation Pooling Station of Project Nine Renewable Power Pvt. Ltd. at Gadag – Gadag-II PS 220 kV S/c line on D/c tower# along with line bays at generation pooling station – under the scope of applicant. 1 no. 220 kV line bay at Gadag-II PS end for termination of above dedicated transmission line- under the scope of applicant. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 80MW 01.02.2025100MW 01.03.2025, 100MW 01.04.2025,100MW 01.05.2025,100MW 02.06.2025 | Phase 1 ¦ MW: 80.00 ¦ Date: 2025-02-01 Phase 2 ¦ MW: 100.00 ¦ Date: 2025-03-01 Phase 3 ¦ MW: 100.00 ¦ Date: 2025-04-01 Phase 4 ¦ MW: 100.00 ¦ Date: 2025-05-01 Phase 5 ¦ MW: 100.00 ¦ Date: 2025-06-02 |  |  | 250 | 230 | 2026-06-28 |  | for 100MW and 200MW PPAs as submitted by applicant vide email dtd. 20.04.2026 |  | 2027-01-16 | 2027-01-16 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 82.50 ¦ Date: 2026-01-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 82.50 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 85.00 ¦ Date: 2027-04-30 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 | Yes |  | 21/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 80.00 ¦ Date: 2025-02-01 | 80 | 2025-02-01 | 2027-01-16
2200000072 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 480 | 0 | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Gadag-II | Karnataka | 2025-04-03 | 2025-12-31 | Generation Pooling Station of Project Nine Renewable Power Pvt. Ltd. at Gadag – Gadag-II PS 220 kV S/c line on D/c tower# along with line bays at generation pooling station – under the scope of applicant. 1 no. 220 kV line bay at Gadag-II PS end for termination of above dedicated transmission line- under the scope of applicant. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 80MW 01.02.2025100MW 01.03.2025, 100MW 01.04.2025,100MW 01.05.2025,100MW 02.06.2025 | Phase 1 ¦ MW: 80.00 ¦ Date: 2025-02-01 Phase 2 ¦ MW: 100.00 ¦ Date: 2025-03-01 Phase 3 ¦ MW: 100.00 ¦ Date: 2025-04-01 Phase 4 ¦ MW: 100.00 ¦ Date: 2025-05-01 Phase 5 ¦ MW: 100.00 ¦ Date: 2025-06-02 |  |  | 250 | 230 | 2026-06-28 |  | for 100MW and 200MW PPAs as submitted by applicant vide email dtd. 20.04.2026 |  | 2027-01-16 | 2027-01-16 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 82.50 ¦ Date: 2026-01-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 82.50 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 85.00 ¦ Date: 2027-04-30 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 | Yes |  | 21/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 100.00 ¦ Date: 2025-03-01 | 100 | 2025-03-01 | 2027-01-16
2200000072 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 480 | 0 | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Gadag-II | Karnataka | 2025-04-03 | 2025-12-31 | Generation Pooling Station of Project Nine Renewable Power Pvt. Ltd. at Gadag – Gadag-II PS 220 kV S/c line on D/c tower# along with line bays at generation pooling station – under the scope of applicant. 1 no. 220 kV line bay at Gadag-II PS end for termination of above dedicated transmission line- under the scope of applicant. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 80MW 01.02.2025100MW 01.03.2025, 100MW 01.04.2025,100MW 01.05.2025,100MW 02.06.2025 | Phase 1 ¦ MW: 80.00 ¦ Date: 2025-02-01 Phase 2 ¦ MW: 100.00 ¦ Date: 2025-03-01 Phase 3 ¦ MW: 100.00 ¦ Date: 2025-04-01 Phase 4 ¦ MW: 100.00 ¦ Date: 2025-05-01 Phase 5 ¦ MW: 100.00 ¦ Date: 2025-06-02 |  |  | 250 | 230 | 2026-06-28 |  | for 100MW and 200MW PPAs as submitted by applicant vide email dtd. 20.04.2026 |  | 2027-01-16 | 2027-01-16 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 82.50 ¦ Date: 2026-01-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 82.50 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 85.00 ¦ Date: 2027-04-30 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 | Yes |  | 21/07/2026 | Pending with Level 2 | Phase 3 ¦ MW: 100.00 ¦ Date: 2025-04-01 | 100 | 2025-04-01 | 2027-01-16
2200000072 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 480 | 0 | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Gadag-II | Karnataka | 2025-04-03 | 2025-12-31 | Generation Pooling Station of Project Nine Renewable Power Pvt. Ltd. at Gadag – Gadag-II PS 220 kV S/c line on D/c tower# along with line bays at generation pooling station – under the scope of applicant. 1 no. 220 kV line bay at Gadag-II PS end for termination of above dedicated transmission line- under the scope of applicant. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 80MW 01.02.2025100MW 01.03.2025, 100MW 01.04.2025,100MW 01.05.2025,100MW 02.06.2025 | Phase 1 ¦ MW: 80.00 ¦ Date: 2025-02-01 Phase 2 ¦ MW: 100.00 ¦ Date: 2025-03-01 Phase 3 ¦ MW: 100.00 ¦ Date: 2025-04-01 Phase 4 ¦ MW: 100.00 ¦ Date: 2025-05-01 Phase 5 ¦ MW: 100.00 ¦ Date: 2025-06-02 |  |  | 250 | 230 | 2026-06-28 |  | for 100MW and 200MW PPAs as submitted by applicant vide email dtd. 20.04.2026 |  | 2027-01-16 | 2027-01-16 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 82.50 ¦ Date: 2026-01-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 82.50 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 85.00 ¦ Date: 2027-04-30 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 | Yes |  | 21/07/2026 | Pending with Level 2 | Phase 4 ¦ MW: 100.00 ¦ Date: 2025-05-01 | 100 | 2025-05-01 | 2027-01-16
2200000072 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 480 | 0 | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Gadag-II | Karnataka | 2025-04-03 | 2025-12-31 | Generation Pooling Station of Project Nine Renewable Power Pvt. Ltd. at Gadag – Gadag-II PS 220 kV S/c line on D/c tower# along with line bays at generation pooling station – under the scope of applicant. 1 no. 220 kV line bay at Gadag-II PS end for termination of above dedicated transmission line- under the scope of applicant. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 80MW 01.02.2025100MW 01.03.2025, 100MW 01.04.2025,100MW 01.05.2025,100MW 02.06.2025 | Phase 1 ¦ MW: 80.00 ¦ Date: 2025-02-01 Phase 2 ¦ MW: 100.00 ¦ Date: 2025-03-01 Phase 3 ¦ MW: 100.00 ¦ Date: 2025-04-01 Phase 4 ¦ MW: 100.00 ¦ Date: 2025-05-01 Phase 5 ¦ MW: 100.00 ¦ Date: 2025-06-02 |  |  | 250 | 230 | 2026-06-28 |  | for 100MW and 200MW PPAs as submitted by applicant vide email dtd. 20.04.2026 |  | 2027-01-16 | 2027-01-16 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 82.50 ¦ Date: 2026-01-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 82.50 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 85.00 ¦ Date: 2027-04-30 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 | Yes |  | 21/07/2026 | Pending with Level 2 | Phase 5 ¦ MW: 100.00 ¦ Date: 2025-06-02 | 100 | 2025-06-02 | 2027-01-16
2200000073 | Main-Connectivity under GNA |  | JUNIPER GREEN COSMIC PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 | 0 | 150 | 0 | 0 | 150 |  | Granted | 150 | 0 | 150 | Bikaner-III | Rajasthan | 2024-09-23 | 2026-08-22 | Juniper Green Cosmic Private Limited Solar Power Project – Bikaner-III PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 350 MW at nominal voltage) Connectivity of 200 MW to Renew Dinkar Urja (App No. 2200000156) is also granted in sharing with M/s Juniper Green Cosmic through same bay## ## In case of sharing of Dedicated Transmission Line/System(DTL/DTS) by multiple entities, the applicant shall ensure availability of DTL/DTS so that the power can be evacuated as per the start date of connectivity of each entity. | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x500 MVA(2nd & 3rd) 400/220 kV ICT at Bikaner-III Pooling Station 2) Augmentation of 2x1500 MVA (3rd & 4th) 765/400 kV ICTs at Bikaner-III Pooling Station 3) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 4) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 5) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 6) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 7) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 8) Neemrana-II -Kotputli 400 kV D/c line (Quad) 9) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 10) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 11) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 12) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x500 MVA(2nd & 3rd) 400/220 kV ICT at Bikaner-III Pooling Station 2) Augmentation of 2x1500 MVA (3rd & 4th) 765/400 kV ICTs at Bikaner-III Pooling Station 3) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 4) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 5) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 6) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 7) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 8) Neemrana-II -Kotputli 400 kV D/c line (Quad) 9) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 10) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 11) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 12) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 50MW 31.01.2025100MW 31.03.2025 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-01-31 Phase 2 ¦ MW: 100.00 ¦ Date: 2025-03-31 |  |  | 150 | 214 |  |  |  |  | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-08-22 ¦ Status: Under Implementation ¦ Type: Solar |  |  | Bay anticipated CoD to be updated |  | Pending with Level 2 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-01-31 | 50 | 2025-01-31 | 2027-09-30
2200000073 | Main-Connectivity under GNA |  | JUNIPER GREEN COSMIC PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 | 0 | 150 | 0 | 0 | 150 |  | Granted | 150 | 0 | 150 | Bikaner-III | Rajasthan | 2024-09-23 | 2026-08-22 | Juniper Green Cosmic Private Limited Solar Power Project – Bikaner-III PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 350 MW at nominal voltage) Connectivity of 200 MW to Renew Dinkar Urja (App No. 2200000156) is also granted in sharing with M/s Juniper Green Cosmic through same bay## ## In case of sharing of Dedicated Transmission Line/System(DTL/DTS) by multiple entities, the applicant shall ensure availability of DTL/DTS so that the power can be evacuated as per the start date of connectivity of each entity. | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x500 MVA(2nd & 3rd) 400/220 kV ICT at Bikaner-III Pooling Station 2) Augmentation of 2x1500 MVA (3rd & 4th) 765/400 kV ICTs at Bikaner-III Pooling Station 3) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 4) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 5) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 6) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 7) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 8) Neemrana-II -Kotputli 400 kV D/c line (Quad) 9) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 10) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 11) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 12) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x500 MVA(2nd & 3rd) 400/220 kV ICT at Bikaner-III Pooling Station 2) Augmentation of 2x1500 MVA (3rd & 4th) 765/400 kV ICTs at Bikaner-III Pooling Station 3) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 4) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 5) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 6) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 7) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 8) Neemrana-II -Kotputli 400 kV D/c line (Quad) 9) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 10) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 11) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 12) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 50MW 31.01.2025100MW 31.03.2025 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-01-31 Phase 2 ¦ MW: 100.00 ¦ Date: 2025-03-31 |  |  | 150 | 214 |  |  |  |  | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-08-22 ¦ Status: Under Implementation ¦ Type: Solar |  |  | Bay anticipated CoD to be updated |  | Pending with Level 2 | Phase 2 ¦ MW: 100.00 ¦ Date: 2025-03-31 | 100 | 2025-03-31 | 2027-09-30
2200000074 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 109 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Gadag-II | Karnataka | 2025-04-15 | 2025-12-31 | • Through dedicated Connectivity transmission system granted to M/s Serentica Renewables India Pvt. Ltd. for application no. 2200000414 i.e. Serentica Renewables India Pvt. Ltd. – Gadag-II PS 400 kV S/c line on D/c tower along with line bays at generation pooling station – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | Solar 51 MW, 31.03.2025, Wind 58 MW, 31.03.2025 | Solar 51 MW, 31.03.2025, Wind 58 MW, 31.03.2025 |  |  | 50 | 416M & 417T |  |  |  |  | 2024-07-31 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31.03.2025 |  | 2025-03-31 | 2026-10-31
2200000074 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 109 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Gadag-II | Karnataka | 2025-04-15 | 2025-12-31 | • Through dedicated Connectivity transmission system granted to M/s Serentica Renewables India Pvt. Ltd. for application no. 2200000414 i.e. Serentica Renewables India Pvt. Ltd. – Gadag-II PS 400 kV S/c line on D/c tower along with line bays at generation pooling station – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | Solar 51 MW, 31.03.2025, Wind 58 MW, 31.03.2025 | Solar 51 MW, 31.03.2025, Wind 58 MW, 31.03.2025 |  |  | 50 | 416M & 417T |  |  |  |  | 2024-07-31 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31.03.2025 |  | 2025-03-31 | 2026-10-31
2200000075 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | kallam | Maharashtra | 2024-05-09 | 2026-09-30 | • AEPL – Kallam PS 220kV S/c line along with associated bay at generation end (under the scope of applicant). • 1 no. 220kV line bay at ISTS substation end (under the scope of ISTS). | 1 | 220 kV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA: Augmentation of Transformation capacity at Kallam PS by 2x500 MVA, 400/220kV ICTs (3rd & 4th) along with 3 nos. 220kV line bays for RE interconnection. LILO of both circuits of Parli(M) – Karjat(M)/ Lonikand-II(M) 400kV D/c line (twin moose) at Kallam PS.LILO of both circuits of Parli(M) – Karjat(M)/ Lonikand-II(M) 400kV D/c line (twin moose) at Kallam PS | Common Transmission System Augmentation for Connectivity under GNA: Augmentation of Transformation capacity at Kallam PS by 2x500 MVA, 400/220kV ICTs (3rd & 4th) along with 3 nos. 220kV line bays for RE interconnection. LILO of both circuits of Parli(M) – Karjat(M)/ Lonikand-II(M) 400kV D/c line (twin moose) at Kallam PS.LILO of both circuits of Parli(M) – Karjat(M)/ Lonikand-II(M) 400kV D/c line (twin moose) at Kallam PS | 31-Dec-24 | 31-Dec-24 |  |  | 50 | 213 |  |  |  | 2026-06-30 | 2025-10-05 | 2026-10-30 |  | Not effective | 2026-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-24 |  | 2024-12-31 | 2026-10-30
2200000076 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 | SECI | Granted | 300 | 0 | 300 | Bhuj-II (Sec-I) | Gujarat | 2024-01-19 | 2024-06-07 | • NTPC REL – Bhuj-II PS 220kV Sc line (on Dc tower) along with 220kV line bay at generation end (Under the scope of applicant). • 220kV line bay at Bhuj-II PS is already existing (implemented under ISTS). | 1 | 220 KV | Existing |  |  | NIL | NIL | 31-Mar-24 | 31-Mar-24 | 300 | 2024-06-07 |  | 202 | 2026-06-30 | 2026-12-31 | NTPC REL representative vide letter dtd.14.10.2025 informed that Revised SCOD as per SECI LoA is 31.12.2025. SECI vide letter dated 31.12.2025 informed that further extension in revised SCOD is 30.06.2026. |  |  |  |  | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 31-Mar-24 |  | 2024-03-31 | 2026-12-31
2200000077 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 | 0 | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-06-05 | 2026-11-07 | (i).Through sharing of dedicated transmission system of M/s Radiant Star Solar Park Private Limited. (200 MW) – Fatehgarh-IV PS(Sec-II) 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) (ii).Infrastructure required for sharing dedicated transmission system shall be under the scope of M/s Avaada Energy Private Limited | 0 | 220 KV | Aug without ATS |  |  | LILO of both circuits of Parli(M) – Karjat(M)/ Lonikand-II(M) 400kV D/c line (twin moose) at Kallam PS.@ Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (6th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | LILO of both circuits of Parli(M) – Karjat(M)/ Lonikand-II(M) 400kV D/c line (twin moose) at Kallam PS.@ Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (6th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 30-Sep-25 | 30-Sep-25 |  |  | 50 | 241 |  |  |  | 2026-08-14 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Sep-25 |  | 2025-09-30 | 2027-06-30
2200000081 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Dhule (Sec-I) | Maharashtra | 2024-10-16 | 2026-12-31 | • AEPL – Dhule PS (Sec-I) 220kV Sc line (on Dc and Mc towers*) along with associated bay at AEPL end (Under scope of Ms AEPL) • Bay at Dhule PS (Sec-I) end is included in scope of Dhule PS establishment scheme (presently under implementation) *The total line length is approximately 21 km. out of which approx. 19 km would be implemented on Dc towers of Ms AEPL and balance on Mc towers of Ms AEPL towards entry into Dhule PS | 1 | 220 KV | Aug without ATS |  |  | Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAACAL59 Moose equivalent (60 km) • Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule • Dhule PS – Dhule (BDTCL) 400 kV | Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAACAL59 Moose equivalent (60 km) • Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAACAL59 Moose equivalent (60 km) | 30-Jun-26 | 30-Jun-26 |  |  | 50 | 203 |  |  |  | 2026-10-31 | 2026-02-09 | 2026-10-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2026-12-31
2200000082 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 |  | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Pachora (Sec-II) | Madhya Pradesh | 2024-04-08 | 2026-12-31 | • AEPL - Pachora PS 220 kV Sc line (on Dc tower) along with associated bay at generation end (Under scope of applicant). • 220 kV bay at Pachora PS is under implementation under ISTS as part of Rajgarh Ph-II (1 GW) scheme • Ms AEPL (application no. 2200000082) shall utilise the Dc tower of 220 kV Sc line (on Dc tower) of Ms AEPL (application no. 2200000956) for stringing of second circuit. | 1 | 220 KV | Aug without ATS |  |  | Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP Pachora SEZ PP - Bhopal (Sterlite) 400kV Dc line (QuadTwin HTLS) (with minimum capacity of 2100 MVAckt at nominal voltage) 400220 kV, 3x500 MVA ICT augmentation (4th, 5th and 6th) at Pachora P | Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP Pachora SEZ PP - Bhopal (Sterlite) 400kV Dc line (QuadTwin HTLS) (with minimum capacity of 2100 MVAckt at nominal voltage) 400220 kV, 3x500 MVA ICT augmentation (4th, 5th and 6th) at Pachora PS Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) Under Implementation • Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP • Pachora SEZ PP - Bhopal (Sterlite) 400kV Dc line (QuadTwin HTLS) (with minimum capacity of 2100 MVAckt at nominal voltage) Under Implementation • 400220 kV, 3x500 MVA ICT augmentation (4th, 5th and 6th) at Pachora PS • Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) | 31-Mar-25 | 31-Mar-25 |  |  | 50 | 214 |  |  |  | 2026-04-15 | 2026-02-14 | 2026-05-30 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2027-06-30
2200000083 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Solapur Pool (Sec-I) | Maharashtra | 2024-08-21 | 2026-12-31 | Ms AEPL shall share the connectivity system granted to AEPLs another Hybrid (RHGS) application (No. 2200000132) which is detailed below · AEPL - Solapur PS 220kV Sc line along with associated bay at generation end (Under scope of applicant) 1 no. 220kV line bay at Solapur PS shall be implemented under ISTS as part of the pooling station | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Evacuation of Power from RE Projects in Solapur (1500 MW) SEZ in Maharashtra | Establishment of 400220kV, 4x500 MVA ICTs at Solapur PS Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAAACAL59 moose equivalent) · | 31-Dec-24 | 31-Dec-24 |  |  | 50 | 201 |  |  |  | 2026-06-30 | 2026-03-20 | 2026-10-30 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-24 |  | 2024-12-31 | 2026-12-31
2200000084 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 150 |  | 0 | 150 | 0 | 150 | SECI | Granted | 150 | 0 | 150 | Bhuj-II (Sec-I) | Gujarat | 2024-01-19 | 2025-05-16 | • NTPC REL – Bhuj-II PS 220kV Sc line (on Dc tower) along with 220kV line bay at generation end (Under the scope of applicant). • 220kV line bay at Bhuj-II PS is already existing (implemented under ISTS). | 1 | 220 KV | Existing |  |  | Nil | Nil | 11-Jan-25 | 11-Jan-25 | 150 | 2025-05-16 |  | 205 | 2027-11-29 |  | SECI vide letter dated 12.06.2025 informed that Revised SCOD should be “Actual date of GNA effectiveness (Solar component - 330700007) + 60 days |  |  |  |  | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 | Yes |  | 21/07/2026 | Pending with Level 2 | 11-Jan-25 |  | 2025-01-11 | 2027-11-29
2200000086 | Main-Connectivity under GNA |  | Oyster Renewable Energy Private Limited (formerly Known as ABENERGIA RENEWABLES PRIVATE LIMITED) | WR | Land BG Route | (vi) Captive generating plant | Hybrid | 100 | 0 | 33 | 67 | 0 | 100 |  | Granted | 100 | 0 | 100 | Pachora (Sec-II) | Madhya Pradesh | 2024-04-08 | 2026-02-14 | OREPL – Pachora PS 220kV Sc line (on Dc towers) along with associated bay at both Generation & ISTS end (Under the scope of applicant). • 220kV bay at Pachora PS is already under tendering under ISTS as part of Rajgarh Ph-II (1GW) scheme. | 1 | 220 KV | Aug without ATS |  |  | • Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP •Pachora SEZ PP - Bhopal (Sterlite) 400kV Dc line (Quad Twin HTLS) (with minimum capacity of 2100 MVA ckt at nominal voltage) •400220 kV, 3x500 MVA ICT augmentation (4th, 5th and 6th) at Pachora P | • Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP •Pachora SEZ PP - Bhopal (Sterlite) 400kV Dc line (Quad Twin HTLS) (with minimum capacity of 2100 MVA ckt at nominal voltage) •400220 kV, 3x500 MVA ICT augmentation (4th, 5th and 6th) at Pachora PS •Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) | Solar 33 MW, 30.09.2024, Wind 67 MW, 31.12.2024 | Phase 1 ¦ MW: 33.00 ¦ Date: 2024-09-30 Phase 2 ¦ MW: 67.00 ¦ Date: 2024-12-31 | 100 | 2026-06-26 |  | 224 |  |  |  |  | 2026-02-14 | 2026-05-30 |  | Effective |  | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 33.00 ¦ Date: 2026-08-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 67.00 ¦ Date: 2026-08-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | Phase 1 ¦ MW: 33.00 ¦ Date: 2024-09-30 | 33 | 2024-09-30 | 2026-08-14
2200000086 | Main-Connectivity under GNA |  | Oyster Renewable Energy Private Limited (formerly Known as ABENERGIA RENEWABLES PRIVATE LIMITED) | WR | Land BG Route | (vi) Captive generating plant | Hybrid | 100 | 0 | 33 | 67 | 0 | 100 |  | Granted | 100 | 0 | 100 | Pachora (Sec-II) | Madhya Pradesh | 2024-04-08 | 2026-02-14 | OREPL – Pachora PS 220kV Sc line (on Dc towers) along with associated bay at both Generation & ISTS end (Under the scope of applicant). • 220kV bay at Pachora PS is already under tendering under ISTS as part of Rajgarh Ph-II (1GW) scheme. | 1 | 220 KV | Aug without ATS |  |  | • Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP •Pachora SEZ PP - Bhopal (Sterlite) 400kV Dc line (Quad Twin HTLS) (with minimum capacity of 2100 MVA ckt at nominal voltage) •400220 kV, 3x500 MVA ICT augmentation (4th, 5th and 6th) at Pachora P | • Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP •Pachora SEZ PP - Bhopal (Sterlite) 400kV Dc line (Quad Twin HTLS) (with minimum capacity of 2100 MVA ckt at nominal voltage) •400220 kV, 3x500 MVA ICT augmentation (4th, 5th and 6th) at Pachora PS •Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) | Solar 33 MW, 30.09.2024, Wind 67 MW, 31.12.2024 | Phase 1 ¦ MW: 33.00 ¦ Date: 2024-09-30 Phase 2 ¦ MW: 67.00 ¦ Date: 2024-12-31 | 100 | 2026-06-26 |  | 224 |  |  |  |  | 2026-02-14 | 2026-05-30 |  | Effective |  | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 33.00 ¦ Date: 2026-08-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 67.00 ¦ Date: 2026-08-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | Phase 2 ¦ MW: 67.00 ¦ Date: 2024-12-31 | 67 | 2024-12-31 | 2026-08-14
2200000093 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | Land Route | (x) Renewable Power Park developer | Solar | 1995 |  | 1995 | 0 | 0 | 1995 |  | Granted | 1995 | 0 | 1995 | KPS-2 (Sec-I) | Gujarat | 2025-03-20 | 2026-11-19 | • Khavda-II PS (Sec-I) – NTPC REL Common Point 400kV Dc (on Dc towers) (Twin ACSS HTLS) line. • NTPC REL Common Point - NTPC REL PSS-03 400kV Sc (on Dc towers) (Twin ACSS HTLS) line along with associated bay at Generation end (Under the scope of applicant). • NTPC REL Common Point - NTPC REL PSS-04 400kV Sc (on Dc towers) (Twin ACSS HTLS) line along with associated bay at Generation end (Under the scope of applicant). • 2nos. 400kV Bays at ISTS substation end being implemented under “Transmission System for Evacuation of Power from potential REZ in Khavda area of Gujarat under Phase-IV (7GW) Part E2” scheme by Khavda IV E2 Power Transmission Ltd. (a subsidiary of POWERGRID) | 2 | 400 KV | Aug without ATS |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV, 4x1500MVA, KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 7654 | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV, 4x1500MVA, KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari(New) 765 kV Dc line Khavda Phase-IV • Creation of 765kV bus section-II at KPS3 (GIS) along with 765kV Bus Sectionaliser • Creation of 400kV bus section-II at KPS3 (GIS) along with 400kV Bus Sectionaliser • KPS3 (GIS) – Lakadia (AIS) 765 kV DC line • ±300MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400kV Bus section-2 • KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line • Establishment of 2x1500MVA, 765400kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) • Vadodara(GIS) –South Olpad(GIS) 765 kV DC line • LILO of Gandhar – Hazira 400kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • Ahmedabad – South Olpad(GIS) 765kV Dc line • Establishment of 4X1500 MVA 765400 kV & 2x500MVA 400220kV Boisar-II (GIS) • South Olpad(GIS) – Boisar-II(GIS) 765kV Dc line • LILO of Navsari(New) – Padghe(PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon(MH) 400kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of Babhaleswar – Padghe(M) 400kV Dc line at Boisar-II (Sec-I) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-I of Boisar-II and ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400kV bus section-II of Boisar-II • ±300 MVAr STATCOM with 3x125 MVAr MSC, 1x125 MVAr MSR at 400 kV level of Navsari(New)(PG) Ss with 1 No. of 400 kV bay (GIS) • Establishment of 2X1500 MVA 765400 kV & 3x500MVA 400220kV Pune-III (GIS) •Boisar-II – Pune-III 765kV D | 30-Jun-25 | 30-Jun-25 |  |  | 1995 | 412 & 415 |  |  |  | 2027-03-31 | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 795.00 ¦ Date: 2027-10-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 1200.00 ¦ Date: 2027-10-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2027-10-30
2200000096 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 109 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Gadag-II | Karnataka | 2025-04-15 | 2025-12-31 | • Through dedicated Connectivity transmission system granted to M/s Serentica Renewables India Pvt. Ltd. for application no. 2200000414 i.e. Serentica Renewables India Pvt. Ltd. – Gadag-II PS 400 kV S/c line on D/c tower along with line bays at generation pooling station – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | Solar 51 MW, 31.03.2025, Wind 58 MW, 31.03.2025 | Phase 1 ¦ MW: 51.00 ¦ Date: 2025-03-31 Phase 2 ¦ MW: 58.00 ¦ Date: 2025-03-31 |  |  | 50 | 416M and 417T |  |  |  |  | 2025-12-30 | 2026-10-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | Phase 1 ¦ MW: 51.00 ¦ Date: 2025-03-31 | 51 | 2025-03-31 | 2026-10-31
2200000096 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 109 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Gadag-II | Karnataka | 2025-04-15 | 2025-12-31 | • Through dedicated Connectivity transmission system granted to M/s Serentica Renewables India Pvt. Ltd. for application no. 2200000414 i.e. Serentica Renewables India Pvt. Ltd. – Gadag-II PS 400 kV S/c line on D/c tower along with line bays at generation pooling station – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | Solar 51 MW, 31.03.2025, Wind 58 MW, 31.03.2025 | Phase 1 ¦ MW: 51.00 ¦ Date: 2025-03-31 Phase 2 ¦ MW: 58.00 ¦ Date: 2025-03-31 |  |  | 50 | 416M and 417T |  |  |  |  | 2025-12-30 | 2026-10-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | Phase 2 ¦ MW: 58.00 ¦ Date: 2025-03-31 | 58 | 2025-03-31 | 2026-10-31
2200000098 | Main-Connectivity under GNA |  | MRS BUILDVISION PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 1000 | 0 | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | Bikaner-III | Rajasthan | 2024-10-25 | 2026-08-22 | MRS Buildvision Private Limited Renewable Power Park – Bikaner-III PS 400 kV S/c line on D/c tower# (Siutable to carry minimum 1000 MW at nominal voltage) – Under applicant scope | 1 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 1) Augmentation of 2x1500 MVA (4th & 5th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: 1) Augmentation of 2x1500 MVA (4th & 5th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 300MW 30.06.2025300MW 31.07.2025400MW 31.08.2025 | Phase 1 ¦ MW: 300.00 ¦ Date: 2025-06-30 Phase 2 ¦ MW: 300.00 ¦ Date: 2025-07-31 Phase 3 ¦ MW: 400.00 ¦ Date: 2025-08-31 |  |  | 1000 | 452(Main Bay),451(Tie Bay) |  |  |  | 2026-08-31 | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 1000.00 ¦ Date: 2027-04-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 300.00 ¦ Date: 2025-06-30 | 300 | 2025-06-30 | 2027-09-30
2200000098 | Main-Connectivity under GNA |  | MRS BUILDVISION PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 1000 | 0 | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | Bikaner-III | Rajasthan | 2024-10-25 | 2026-08-22 | MRS Buildvision Private Limited Renewable Power Park – Bikaner-III PS 400 kV S/c line on D/c tower# (Siutable to carry minimum 1000 MW at nominal voltage) – Under applicant scope | 1 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 1) Augmentation of 2x1500 MVA (4th & 5th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: 1) Augmentation of 2x1500 MVA (4th & 5th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 300MW 30.06.2025300MW 31.07.2025400MW 31.08.2025 | Phase 1 ¦ MW: 300.00 ¦ Date: 2025-06-30 Phase 2 ¦ MW: 300.00 ¦ Date: 2025-07-31 Phase 3 ¦ MW: 400.00 ¦ Date: 2025-08-31 |  |  | 1000 | 452(Main Bay),451(Tie Bay) |  |  |  | 2026-08-31 | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 1000.00 ¦ Date: 2027-04-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 300.00 ¦ Date: 2025-07-31 | 300 | 2025-07-31 | 2027-09-30
2200000098 | Main-Connectivity under GNA |  | MRS BUILDVISION PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 1000 | 0 | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | Bikaner-III | Rajasthan | 2024-10-25 | 2026-08-22 | MRS Buildvision Private Limited Renewable Power Park – Bikaner-III PS 400 kV S/c line on D/c tower# (Siutable to carry minimum 1000 MW at nominal voltage) – Under applicant scope | 1 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 1) Augmentation of 2x1500 MVA (4th & 5th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: 1) Augmentation of 2x1500 MVA (4th & 5th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 300MW 30.06.2025300MW 31.07.2025400MW 31.08.2025 | Phase 1 ¦ MW: 300.00 ¦ Date: 2025-06-30 Phase 2 ¦ MW: 300.00 ¦ Date: 2025-07-31 Phase 3 ¦ MW: 400.00 ¦ Date: 2025-08-31 |  |  | 1000 | 452(Main Bay),451(Tie Bay) |  |  |  | 2026-08-31 | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 1000.00 ¦ Date: 2027-04-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 3 ¦ MW: 400.00 ¦ Date: 2025-08-31 | 400 | 2025-08-31 | 2027-09-30
2200000099 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 109 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Gadag-II | Karnataka | 2025-04-15 | 2025-12-31 | • Through dedicated Connectivity transmission system granted to M/s Serentica Renewables India Pvt. Ltd. for application no. 2200000414 i.e. Serentica Renewables India Pvt. Ltd. – Gadag-II PS 400 kV S/c line on D/c tower along with line bays at generation pooling station – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | Solar 51 MW, 31.03.2025, | Phase 1 ¦ MW: 51.00 ¦ Date: 2025-03-31 |  |  | 50 | 416M and 417T |  |  |  |  | 2025-12-30 | 2026-10-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 06/05/2026 | Pending with Level 2 | Phase 1 ¦ MW: 51.00 ¦ Date: 2025-03-31 | 51 | 2025-03-31 | 2026-10-31
2200000100 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 109 |  | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Gadag-II | Karnataka | 2025-04-15 | 2025-12-31 | • Through dedicated Connectivity transmission system granted to M/s Serentica Renewables India Pvt. Ltd. for application no. 2200000414 i.e. Serentica Renewables India Pvt. Ltd. – Gadag-II PS 400 kV S/c line on D/c tower along with line bays at generation pooling station – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | Solar: 51 MW, 31.03.2025, Wind: 58 MW, 31.03.2025 | Solar: 51 MW, 31.03.2025, Wind: 58 MW, 31.03.2025 |  |  | 50 | 416M and 417T |  |  |  |  | 2025-12-30 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 06/05/2026 | Pending with Level 2 | 31.03.2025 |  | 2025-03-31 | 2026-10-31
2200000100 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 109 |  | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Gadag-II | Karnataka | 2025-04-15 | 2025-12-31 | • Through dedicated Connectivity transmission system granted to M/s Serentica Renewables India Pvt. Ltd. for application no. 2200000414 i.e. Serentica Renewables India Pvt. Ltd. – Gadag-II PS 400 kV S/c line on D/c tower along with line bays at generation pooling station – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | Solar: 51 MW, 31.03.2025, Wind: 58 MW, 31.03.2025 | Solar: 51 MW, 31.03.2025, Wind: 58 MW, 31.03.2025 |  |  | 50 | 416M and 417T |  |  |  |  | 2025-12-30 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 06/05/2026 | Pending with Level 2 | 31.03.2025 |  | 2025-03-31 | 2026-10-31
2200000102 | Main-Connectivity under GNA |  | BN HYBRID POWER-1 PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 180.8 | 0 | 110 | 70.8 | 0 | 180.8 |  | Granted | 180.8 | 0 | 180.8 | Fatehgarh-IV (Sec-I) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling station of M/s BN Hybrid Power-1 Private Limited Hybrid Power Projects with Appl. Nos. 2200000003 ( 119.2 MW) & 2200000102 (180.8 MW) – FatehgarhIV PS (Section-1) 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) – Under applicant scope | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA : 1) Augmentation of 2x500 MVA (4th &5th) 400/220 kV ICT at Fatehgarh-IV PS (Sec-1) 2) Augmentation of 2x1500 MVA (5th & 6th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) 3) Fatehgarh-IV (Sec-1)- Fatehgarh-III 400 kV D/c (Twin HLTS*) line 4) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor 5) Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) 6) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line 7) LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation 8) LILO of 400kV Kota –Merta line at Beawar substation 9) Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor 10) LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line 11) LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line 12) Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end 13) STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR * with minimum capacity of 2100 MVA/ckt at nominal voltage; Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA : 1) Augmentation of 2x500 MVA (4th &5th) 400/220 kV ICT at Fatehgarh-IV PS (Sec-1) 2) Augmentation of 2x1500 MVA (5th & 6th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) 3) Fatehgarh-IV (Sec-1)- Fatehgarh-III 400 kV D/c (Twin HLTS*) line 4) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor 5) Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) 6) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line 7) LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation 8) LILO of 400kV Kota –Merta line at Beawar substation 9) Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor 10) LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line 11) LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line 12) Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end 13) STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR * with minimum capacity of 2100 MVA/ckt at nominal voltage; Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Solar 110 MW, 30.06.2025, Wind 70.8 MW, 30.06.2025 | Phase 1 ¦ MW: 110.00 ¦ Date: 2025-06-30 Phase 2 ¦ MW: 70.80 ¦ Date: 2025-06-30 |  |  | 180.8 | 216 |  |  |  | 2025-12-07 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 180.80 ¦ Date: 2027-07-29 ¦ Status: Under Implementation ¦ Type: |  |  | Bay charged on 07-12-2025 |  | Pending with Level 2 | Phase 1 ¦ MW: 110.00 ¦ Date: 2025-06-30 | 110 | 2025-06-30 | 2027-02-28
2200000102 | Main-Connectivity under GNA |  | BN HYBRID POWER-1 PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 180.8 | 0 | 110 | 70.8 | 0 | 180.8 |  | Granted | 180.8 | 0 | 180.8 | Fatehgarh-IV (Sec-I) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling station of M/s BN Hybrid Power-1 Private Limited Hybrid Power Projects with Appl. Nos. 2200000003 ( 119.2 MW) & 2200000102 (180.8 MW) – FatehgarhIV PS (Section-1) 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) – Under applicant scope | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA : 1) Augmentation of 2x500 MVA (4th &5th) 400/220 kV ICT at Fatehgarh-IV PS (Sec-1) 2) Augmentation of 2x1500 MVA (5th & 6th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) 3) Fatehgarh-IV (Sec-1)- Fatehgarh-III 400 kV D/c (Twin HLTS*) line 4) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor 5) Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) 6) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line 7) LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation 8) LILO of 400kV Kota –Merta line at Beawar substation 9) Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor 10) LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line 11) LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line 12) Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end 13) STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR * with minimum capacity of 2100 MVA/ckt at nominal voltage; Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA : 1) Augmentation of 2x500 MVA (4th &5th) 400/220 kV ICT at Fatehgarh-IV PS (Sec-1) 2) Augmentation of 2x1500 MVA (5th & 6th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) 3) Fatehgarh-IV (Sec-1)- Fatehgarh-III 400 kV D/c (Twin HLTS*) line 4) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor 5) Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) 6) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line 7) LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation 8) LILO of 400kV Kota –Merta line at Beawar substation 9) Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor 10) LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line 11) LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line 12) Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end 13) STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR * with minimum capacity of 2100 MVA/ckt at nominal voltage; Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Solar 110 MW, 30.06.2025, Wind 70.8 MW, 30.06.2025 | Phase 1 ¦ MW: 110.00 ¦ Date: 2025-06-30 Phase 2 ¦ MW: 70.80 ¦ Date: 2025-06-30 |  |  | 180.8 | 216 |  |  |  | 2025-12-07 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 180.80 ¦ Date: 2027-07-29 ¦ Status: Under Implementation ¦ Type: |  |  | Bay charged on 07-12-2025 |  | Pending with Level 2 | Phase 2 ¦ MW: 70.80 ¦ Date: 2025-06-30 | 70.8 | 2025-06-30 | 2027-02-28
2200000103 | Main-Connectivity under GNA |  | BN DISPATCHABLE-1 PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 300 | 0 | 111 | 189 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-05-05 | 2026-11-07 | BN Dispatchable-1 Private Limited Hybrid Power Project – Fatehgarh-IV (Section-II) PS 220 kV S/c line on D/c towers#(suitable to carry minimum 300 MW at nominal voltage) – Under applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA : Augmentation of 2x500 MVA (5th & 6th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA : Augmentation of 2x500 MVA (5th & 6th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Solar 150 MW, 30.06.2025, Wind 150 MW, 30.06.2025 | Phase 1 ¦ MW: 150.00 ¦ Date: 2025-06-30 Phase 2 ¦ MW: 150.00 ¦ Date: 2025-06-30 |  |  | 300 | 239 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  | Yes |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 150.00 ¦ Date: 2025-06-30 | 150 | 2025-06-30 | 2027-06-30
2200000103 | Main-Connectivity under GNA |  | BN DISPATCHABLE-1 PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 300 | 0 | 111 | 189 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-05-05 | 2026-11-07 | BN Dispatchable-1 Private Limited Hybrid Power Project – Fatehgarh-IV (Section-II) PS 220 kV S/c line on D/c towers#(suitable to carry minimum 300 MW at nominal voltage) – Under applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA : Augmentation of 2x500 MVA (5th & 6th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA : Augmentation of 2x500 MVA (5th & 6th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Solar 150 MW, 30.06.2025, Wind 150 MW, 30.06.2025 | Phase 1 ¦ MW: 150.00 ¦ Date: 2025-06-30 Phase 2 ¦ MW: 150.00 ¦ Date: 2025-06-30 |  |  | 300 | 239 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  | Yes |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 150.00 ¦ Date: 2025-06-30 | 150 | 2025-06-30 | 2027-06-30
2200000111 | Main-Connectivity under GNA |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 400 |  | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Bikaner-III | Rajasthan | 2024-11-22 | 2026-08-22 | Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS1- Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS2 400 kV Sc line Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS2– Bikaner-III PS 400 kV Dc line (Suitable to carry minimum 900 MW per circuit at nominal voltage) (Common for Application no. 2200000111 & 2200000163 of Ms Sunbreeze for 400 MW & 1000 MW respectively) | 1 | 400 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x1500 MVA (4th & 5th) 765400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) 3) LILO of both ck | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x1500 MVA (4th & 5th) 765400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) 5) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765400 kV ICTs at Neemrana-II Ss 7) Neemrana-II -Kotputli 400 kV Dc line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss 9) Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 01-May-25 | 01-May-25 |  |  | 400 | 449(Main bay), 448(Tie bay) |  |  |  | 2026-08-31 | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2026-07-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 01-May-25 |  | 2025-05-01 | 2027-09-30
2200000116 | Main-Connectivity under GNA |  | SPRNG ENERGY PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 400 | 0 | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50MW 3112202550MW 3006202650MW 31122026100MW 3006202750MW 31122027100MW 31122028 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 Phase 6 ¦ MW: 100.00 ¦ Date: 2028-12-31 |  |  | 400 | 446 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: ¦ Phase 3 ¦ MW: 100.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: ¦ Phase 4 ¦ MW: 100.00 ¦ Date: 2028-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 | 50 | 2025-12-31 | 2027-02-28
2200000116 | Main-Connectivity under GNA |  | SPRNG ENERGY PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 400 | 0 | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50MW 3112202550MW 3006202650MW 31122026100MW 3006202750MW 31122027100MW 31122028 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 Phase 6 ¦ MW: 100.00 ¦ Date: 2028-12-31 |  |  | 400 | 446 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: ¦ Phase 3 ¦ MW: 100.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: ¦ Phase 4 ¦ MW: 100.00 ¦ Date: 2028-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 | 50 | 2026-06-30 | 2027-02-28
2200000116 | Main-Connectivity under GNA |  | SPRNG ENERGY PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 400 | 0 | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50MW 3112202550MW 3006202650MW 31122026100MW 3006202750MW 31122027100MW 31122028 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 Phase 6 ¦ MW: 100.00 ¦ Date: 2028-12-31 |  |  | 400 | 446 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: ¦ Phase 3 ¦ MW: 100.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: ¦ Phase 4 ¦ MW: 100.00 ¦ Date: 2028-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 | 50 | 2026-12-31 | 2027-06-30
2200000116 | Main-Connectivity under GNA |  | SPRNG ENERGY PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 400 | 0 | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50MW 3112202550MW 3006202650MW 31122026100MW 3006202750MW 31122027100MW 31122028 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 Phase 6 ¦ MW: 100.00 ¦ Date: 2028-12-31 |  |  | 400 | 446 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: ¦ Phase 3 ¦ MW: 100.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: ¦ Phase 4 ¦ MW: 100.00 ¦ Date: 2028-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 | 100 | 2027-06-30 | 2027-12-30
2200000116 | Main-Connectivity under GNA |  | SPRNG ENERGY PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 400 | 0 | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50MW 3112202550MW 3006202650MW 31122026100MW 3006202750MW 31122027100MW 31122028 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 Phase 6 ¦ MW: 100.00 ¦ Date: 2028-12-31 |  |  | 400 | 446 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: ¦ Phase 3 ¦ MW: 100.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: ¦ Phase 4 ¦ MW: 100.00 ¦ Date: 2028-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 | 50 | 2027-12-31 | 2028-06-30
2200000116 | Main-Connectivity under GNA |  | SPRNG ENERGY PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 400 | 0 | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Common Pooling point for Sprng Power Private Limited(App No.2200000024 300 MW), Sprng Akshaya Urja Private Limited(App No.220000065 100 MW) & Sprng Energy Private Limited(App No. 2200000116 400MW) Solar Project - Fatehgarh-III PS(Sec-II) 400 kV Sc line on Dc tower (Suitable to carry minimum 900 MW at nominal voltage) Under applicant Scope Connectivity of 400 MW to Sprng Energy Pvt. Ltd(App No. 2200000116) and 300 MW to Sprng Power Private Limited(App No. 2200000024)is granted in sharing with application of 100 MW by Ms Sprng Akshaya Urja Private Limited (Application no.- 2200000065) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III – Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III - Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 50MW 3112202550MW 3006202650MW 31122026100MW 3006202750MW 31122027100MW 31122028 | Phase 1 ¦ MW: 50.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 Phase 5 ¦ MW: 50.00 ¦ Date: 2027-12-31 Phase 6 ¦ MW: 100.00 ¦ Date: 2028-12-31 |  |  | 400 | 446 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: ¦ Phase 3 ¦ MW: 100.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: ¦ Phase 4 ¦ MW: 100.00 ¦ Date: 2028-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 6 ¦ MW: 100.00 ¦ Date: 2028-12-31 | 100 | 2028-12-31 | 2029-06-30
2200000118 | Main-Connectivity under GNA |  | FRUGAL ENERGY PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 250 | 0 | 250 | 0 | 0 | 250 |  | Granted | 250 | 0 | 250 | Bhadla-III | Rajasthan | 2026-03-27 |  | Common Pooling station for Renewable Power Park of Ms Frugal Energy Private Limited (App. No. 0212100031 of 50 MW & 2200000118 of 250 MW) – Bhadla-III PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 1x500 MVA (6th) 400220kV ICTs at Bhadla-III PS 2) Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 3) 765 kV Bhadla-III – Bikaner-I | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 1x500 MVA (6th) 400220kV ICTs at Bhadla-III PS 2) Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 3) 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end 4) Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation 5) Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) 6) Bhadla-III – Bhadla (HVDC) 400 kV Dc (1st & 2nd) quad moose line along with the line bays at both substations 7) Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 8) Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line 9) Augmentation of 5x1500 MVA (1st to 5th ), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor 10) LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur 11) Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 15-Jun-25 | 15-Jun-25 |  |  | 250 | 204 | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2029-07-20 ¦ Status: Under Implementation ¦ Type: | 30.06.2028 |  |  | 08/07/2026 | Pending with Level 2 | 15-Jun-25 |  | 2025-06-15 | 2029-07-20
2200000120 | Main-Connectivity under GNA |  | HELIA ENERGY PARK PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 100 | 0 | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-06-05 | 2026-11-07 | Common pooling station of M/s Helia Energy Park Private Limited Renewable Power Park (Appl. Nos. 2200000120 (100 MW) & Appl. Nos. 212100035(200 MW)) – Fatehgarh-IV PS (Section-2) 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) - Under applicant scope Connectivity of 100 MW to M/s Helia Energy Park Pvt. Ltd.(Application no.- 2200000120) is granted in sharing with application of 200 MW by M/s Helia Energy Park Pvt. Ltd.(App No. 0212100035) through same DTL & bay | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA : Augmentation of 1x500 MVA (6th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA : Augmentation of 1x500 MVA (6th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 31-Dec-25 | 31-Dec-25 |  |  | 100 | 226 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2027-06-30
2200000121 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 327MW [Solar-153 MW & Wind-174MW] | 0 | 0 | 150 | 0 | 150 |  | Granted | 150 | 0 | 150 | Gadag-II | Karnataka | 2025-04-15 | 2025-12-31 | • Through dedicated Connectivity transmission system granted to M/s Serentica Renewables India Pvt. Ltd. for application no. 2200000414 i.e. Serentica Renewables India Pvt. Ltd. – Gadag-II PS 400 kV S/c line on D/c tower along with line bays at generation pooling station – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | Solar 153 MW, 30.06.2025, Wind 174 MW, 30.06.2025, | Phase 1 ¦ MW: 153.00 ¦ Date: 2025-06-30 Phase 2 ¦ MW: 174.00 ¦ Date: 2025-06-30 |  |  | 150 | 416M and 417T |  |  |  |  | 2025-12-30 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 06/05/2026 | Pending with Level 2 | Phase 1 ¦ MW: 153.00 ¦ Date: 2025-06-30 | 153 | 2025-06-30 | 2026-10-31
2200000121 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 327MW [Solar-153 MW & Wind-174MW] | 0 | 0 | 150 | 0 | 150 |  | Granted | 150 | 0 | 150 | Gadag-II | Karnataka | 2025-04-15 | 2025-12-31 | • Through dedicated Connectivity transmission system granted to M/s Serentica Renewables India Pvt. Ltd. for application no. 2200000414 i.e. Serentica Renewables India Pvt. Ltd. – Gadag-II PS 400 kV S/c line on D/c tower along with line bays at generation pooling station – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | Solar 153 MW, 30.06.2025, Wind 174 MW, 30.06.2025, | Phase 1 ¦ MW: 153.00 ¦ Date: 2025-06-30 Phase 2 ¦ MW: 174.00 ¦ Date: 2025-06-30 |  |  | 150 | 416M and 417T |  |  |  |  | 2025-12-30 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 06/05/2026 | Pending with Level 2 | Phase 2 ¦ MW: 174.00 ¦ Date: 2025-06-30 | 174 | 2025-06-30 | 2026-10-31
2200000123 | Main-Connectivity under GNA |  | TEQ GREEN POWER XV PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 95 | 0 | 95 | 0 | 0 | 95 |  | Granted | 95 | 0 | 95 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | (i). Through sharing of dedicated transmission system of Ms Energizent Power Private Limited. (125 80 MW) – Fatehgarh-III PS(Sec-II) 220 kV Sc line on Dc towers(Suitable to carry minimum 300 MW at nominal voltage) (ii). Infrastructure required for sharing dedicated transmission system - under the scope of Ms Teq Green Power XV Private Limited | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA (4th & 5th), 400220kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA (4th & 5th), 400220kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 2x1500 MVA (5th & 6th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III- Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS–Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 01-Jan-26 | 01-Jan-26 |  |  | 95 | 229 |  |  |  | 2025-10-18 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 45.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: |  |  | Bay charged on 18-10-2025 |  | Pending with Level 2 | 01-Jan-26 |  | 2026-01-01 | 2027-02-28
2200000126 | Main-Connectivity under GNA |  | VEH GREEN ENERGY PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 153.6 |  | 0 | 153.6 | 0 | 153.6 |  | Granted | 153.6 | 0 | 153.6 | Koppal-II | Karnataka | 2025-03-20 | 2025-12-27 | •Generation Pooling Station of M/s VEH Green Energy Pvt. Ltd. at Koppal– Koppal-II PS 220 kV S/c line along with 220kV line at generation pooling station – under the scope of grantee •1 no. 220 kV line bay at Koppal-II PS – Under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) in Karnataka •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-B) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) in Karnataka •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-B) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 30-05-2025 | 30-05-2025 |  |  | 153.6 | 214 |  |  |  | 2026-06-30 | 2025-12-26 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 53.60 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 30-05-2025 |  | 2025-05-30 | 2026-10-31
2200000127 | Main-Connectivity under GNA |  | VENA ENERGY AURA PRIVATE LIMITED | SR | Land Route | (xi) REGS with an installed capacity of 5 MW and above applying for grant of Connectivity to ISTS through the electrical system of a generating station already having Connectivity to ISTS | Wind | 50 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Koppal-II | Karnataka | 2025-02-28 | 2026-12-31 | Through sharing of dedicated Connectivity transmission system granted to M/s VEH Green Energy Pvt. Ltd. for application no. 2200000126 i.e. Generation Pooling Station of M/s VEH Green Energy Pvt. Ltd. at Koppal – Koppal-II PS 220 kV S/c line along with 220 kV line at generation pooling station – all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Part of transmission Scheme for Integration of Renewable Energy Zone (Phase-II), in Koppal (Phase-A & B) and Gadag-II (Phase-A) in Karnataka•ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Part of transmission Scheme for Integration of Renewable Energy Zone (Phase-II), in Koppal (Phase-A & B) and Gadag-II (Phase-A) in Karnataka as per Annexure-II | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Part of transmission Scheme for Integration of Renewable Energy Zone (Phase-II), in Koppal (Phase-A & B) and Gadag-II (Phase-A) in Karnataka•ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Part of transmission Scheme for Integration of Renewable Energy Zone (Phase-II), in Koppal (Phase-A & B) and Gadag-II (Phase-A) in Karnataka as per Annexure-II | 01-Oct-24 | 01-Oct-24 |  |  | 50 | 214 |  |  |  |  | 2025-12-26 | 2026-10-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 01-Oct-24 |  | 2024-10-01 | 2027-06-30
2200000132 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 50 (Wind) revised from Hybrid (25S & 25W)after final grant | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Solapur Pool (Sec-I) | Maharashtra | 2024-08-21 | 2026-12-31 | · AEPL - Solapur PS 220kV Sc line along with associated bay at generation end (Under scope of applicant) 1 no. 220kV line bay at Solapur PS shall be implemented under ISTS as part of the pooling station | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Evacuation of Power from RE Projects in Solapur (1500 MW) SEZ in Maharashtra | · Establishment of 400220kV, 4x500 MVA ICTs at Solapur PS. Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAAACAL59 moose equivalent) | 31-Dec-25 | 31-Dec-25 |  |  | 50 | 201 |  |  |  | 2026-06-30 | 2026-03-20 | 2026-10-30 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2026-12-31
2200000133 | Main-Connectivity under GNA |  | SPRNG AKSHAYA URJA PRIVATE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 67.2 |  | 0 | 67.2 | 0 | 67.2 |  | Granted | 67.2 | 0 | 67.2 | Rajgarh (Sec-II) | Madhya Pradesh | 2024-11-20 | 2026-12-31 | SAUPL in present application shall share the same DTL provided to SVVPL in application no. 2200000022 (for 100MW) at Rajgarh SS (on extended bus), which is detailed below • SVVPL – Rajgarh (PG) 220kV Sc line (on Dc tower) along with associated bay at Generator end (Under the scope of applicant) • 220kV GIS line bay at Rajgarh 400220kV (PG) Ss (on extended bus) for RE interconnection (under the scope of ISTS) | 0 | 220 kV | Aug without ATS |  |  | 1. 1x500MVA, 400220kV ICT (4th) at Rajgarh Ss (on the sectionalized 220kV bus) along with associated bays at both ends (400kV AIS & 220kV GIS). 2. 220kV bus extension (GIS) of Rajgarh (PG) 400220 kV Ss along with 220kV Bus Coupler Bay for extended bus (u | 1. 1x500MVA, 400220kV ICT (4th) at Rajgarh Ss (on the sectionalized 220kV bus) along with associated bays at both ends (400kV AIS & 220kV GIS). 2. 220kV bus extension (GIS) of Rajgarh (PG) 400220 kV Ss along with 220kV Bus Coupler Bay for extended bus (under the scope of ISTS- already under implementation) 3. 220kV bus sectionaliser bay (GIS) between existing & extended 220 kV bus of Rajgarh Ss. (under the scope of ISTS- already under implementation). | 30-Jun-25 | 30-Jun-25 |  |  | 67.2 | 217 |  |  |  | 2026-12-31 | 2026-02-14 | 2026-12-31 |  | Not effective | 2026-12-31 | Under Construction | Part Commissioned | 0 | ¦ Phase 1 ¦ MW: 2.30 ¦ Date: 2025-12-27 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 16.50 ¦ Date: 2025-12-31 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 6.60 ¦ Date: 2026-01-03 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 6.60 ¦ Date: 2026-01-24 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 5 ¦ MW: 13.20 ¦ Date: 2026-01-28 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 6 ¦ MW: 6.60 ¦ Date: 2026-02-02 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 7 ¦ MW: 9.90 ¦ Date: 2026-02-16 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 8 ¦ MW: 5.50 ¦ Date: 2027-05-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2027-06-30
2200000135 | Main-Connectivity under GNA |  | GREEN INFRA CLEAN SOLAR FARMS PRIVATE LIMITED (Formerly known as GREEN INFRA CLEAN SOLAR FARMS LIMI | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 110 | 0 | 110 | 0 | 0 | 110 |  | Granted | 110 | 0 | 110 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-06-05 | 2026-11-07 | Common Pooling station of M/s Green Infra Clean Wind Technology Limited Power Project(App. No. 2200000054 - 300 MW) & Green Infra Clean Solar Farms Limited(App. No. 220000135 - 110 MW) – Fatehgarh-IV (Section-II) PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 410 MW at nominal voltage) – Under applicant Scope | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA : Augmentation of 1x500 MVA (7th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(3rd & 4th), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA : Augmentation of 1x500 MVA (7th), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(3rd & 4th), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 01-Jun-25 | 01-Jun-25 |  |  | 110 | 233 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 110.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 01-Jun-25 |  | 2025-06-01 | 2027-06-30
2200000138 | Main-Connectivity under GNA |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED | NR | Land Route | (vi) Captive generating plant | Hybrid | 390 | 0 | 180 | 210 | 0 | 390 |  | Granted | 390 | 0 | 390 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | i. Solar PSS of Ms ABRSL (App. No. 2200000138 (390 MW) & ABREL (RJ) App. 2200000140 (260 MW) No. Fatehgarh-III PS (Section-II) 400 kV Sc line* (Suitable to carry minimum 900 MW at nominal voltage) Under Applicant Scope Internal Interconnection ii. Wind PSS of Ms ABRSL (App. No. 2200000138 (390 MW) Solar PSS of Ms ABRSL (App. No. 2200000138 (390 MW) & ABREL (RJ) App. No. 2200000140 (260 MW) 400kV Sc line* Scope - Under Applicant Connectivity of 100 MW to Azure Power India Pvt Ltd (App. No. 0412100002) & 260 MW to Ms ABREL (RJ) Projects Limited (App. No. 2200000140) is granted in sharing with Aditya Birla Renewables Subsidiary Limited (Appl. Nos. 2200000138) through same bay & DTL## | 1 |  | Aug without ATS |  |  | Transmission system for Connectivity under GNA (Augmentation without ATS) Augmentation of 2x500 MVA (6th & 7th), 400220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(3rd & 4th), 765400 kV ICT at Fatehgarh-IV (Section-2) Pooli | Transmission system for Connectivity under GNA (Augmentation without ATS) Augmentation of 2x500 MVA (6th & 7th), 400220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(3rd & 4th), 765400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV Dc line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar Dc line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar Dc line (formed after LILO) Establishment of 3x1500 MVA, 765400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV Dc line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV Dc line (Quad) Barmer-I PS– Sirohi PS 765 kV Dc line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta Dc line at Rishabdeo Ss Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line Establishment of 765400 kV (2x1500 MVA Kurawar Ss (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for linebus reactor) Mandsaur – | 31-05-2025 | Phase 1 ¦ MW: 390.00 ¦ Date: 2025-05-31 |  |  | 390 | 449 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-06-20 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: ¦ Phase 3 ¦ MW: 40.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 390.00 ¦ Date: 2025-05-31 | 390 | 2025-05-31 | 2027-02-28
2200000139 | Main-Connectivity under GNA |  | ABREL (RJ) PROJECTS LIMITED | SR | Land BG Route | (vi) Captive generating plant | Wind | 184 |  | 0 | 184 | 0 | 184 |  | Granted | 184 | 0 | 184 | Gadag-II | Karnataka | 2025-04-03 | 2025-12-31 | •Generation Pooling Station of M/s ABREL (RJ) Projects Ltd. at Dharwad/Gadag– Gadag-II PS 220 kV S/c line along with 220kV line bays at generation pooling station – under the scope of grantee •1 no. 220 kV line bay at Gadag-II PS – Under the scope of grantee | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 31-May-25 | 31-May-25 |  |  | 184 | 232 |  |  |  |  | 2027-01-16 | 2027-04-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 184.00 ¦ Date: 2027-06-23 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-04-30
2200000140 | Main-Connectivity under GNA |  | ABREL (RJ) PROJECTS LIMITED | NR | Land BG Route | (vi) Captive generating plant | Solar | 260 | 0 | 130 | 130 | 0 | 260 |  | Granted | 260 | 0 | 260 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-09-23 | 2026-08-22 | Amended Provision i. Solar PSS of Ms ABRSL (App. No. 2200000138 (390 MW) & ABREL (RJ) App. No. 2200000140 (260 MW) Fatehgarh-III PS (Section-II) 400 kV Sc line* (Suitable to carry minimum 900 MW at nominal voltage) Under Applicant Scope Internal Interconnection ii. Wind PSS of Ms ABRSL (App. No. 2200000138 (390 MW) Solar PSS of Ms ABRSL (App. No. 2200000138 (390 MW) & ABREL (RJ) App. No. 2200000140 (260 MW) 400kV Sc line* Under Applicant Scope Connectivity of 100 MW to Azure Power India Pvt Ltd (App. No. 0412100002) & 260 MW to Ms ABREL (RJ) Projects Limited (App. No. 2200000140) is granted in sharing with Aditya Birla Renewables Subsidiary Limited (Appl. Nos. 2200000138) through same bay & DTL | 0 |  | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (6th), 400220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Sec | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (6th), 400220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA(2nd & 3rd), 765400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV Dc line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar Dc line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar Dc line (formed after LILO) Establishment of 3x1500 MVA, 765400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV Dc line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV Dc line (Quad) Barmer-I PS– Sirohi PS 765 kV Dc line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta Dc line at Rishabdeo Ss Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line Establishment of 765400 kV (2x1500 MVA Kurawar Ss (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for linebus reactor) Mandsaur – Kurawar 765 kV Dc line along with | 31-May-25 | 31-May-25 |  |  | 260 | 449 |  |  |  | 2026-04-25 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 130.00 ¦ Date: 2026-07-20 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 65.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: ¦ Phase 3 ¦ MW: 65.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-02-28
2200000141 | Main-Connectivity under GNA |  | ABREL (RJ) PROJECTS LIMITED | SR | Land BG Route | (vi) Captive generating plant | Wind | 184 |  | 0 | 184 | 0 | 184 |  | Granted | 184 | 0 | 184 | Koppal-II | Karnataka | 2025-02-28 | 2025-12-27 | •Generation Pooling Station of M/s ABREL (RJ) Projects Ltd. at Koppal– Koppal-II PS 220 kV S/c line along with 220kV line bay at generation pooling station – under the scope of grantee •1 no. 220 kV line bay at Koppal-II PS – Under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) in Karnataka •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-B) •ISTS Network Expansion scheme in WR & SR for export of surplus power during high RE scenario in SR | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) in Karnataka •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-B) •ISTS Network Expansion scheme in WR & SR for export of surplus power during high RE scenario in SR | 31-May-25 | 31-May-25 |  |  | 184 | 212 |  |  |  |  | 2025-12-26 | 2026-10-31 |  | Not effective | 2027-01-16 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 184.00 ¦ Date: 2027-05-02 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2026-10-31
2200000142 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 25 MW Wind + 25 MW Solar |  | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Jam Khambhaliya | Gujarat | 2024-02-01 | 2025-09-30 | • AEPL – Jam Khambhaliya PS 220kV Sc line (on Dc towers) along with associated bay at generation end (Under scope of Ms AEPL) • 1 no. 220kV line bay at Jam Khambhaliya PS has been implemented under ISTS as part of the pooling station. | 1 | 220 KV | Existing |  |  | Nil | Nil | 30-Sep-25 | 30-Sep-25 | 50 | 2025-09-30 |  | 207 | [7 empty] | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-07-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Not Submitted For Approval | 30-Sep-25 |  | 2025-09-30 | 2026-03-30
2200000144 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bhadla-III | Rajasthan | 2026-03-27 |  | Serentica Renewables India Private Limited Solar Power Project– Bhadla-III PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x500 MVA (7th & 8th) 400220kV ICTs at Bhadla-III PS 2) Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 3) 765 kV Bhadla-III – Bik | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 2x500 MVA (7th & 8th) 400220kV ICTs at Bhadla-III PS 2) Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 3) 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end 4) Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation 5) Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) 6) Bhadla-III – Bhadla (HVDC) 400 kV Dc (1st & 2nd) quad moose line along with the line bays at both substations 7) Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 8) Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line 9) Augmentation of 5x1500 MVA (1st to 5th), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor 10) LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur 11) Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 30-Jun-25 | 30-Jun-25 |  |  | 300 | 220 | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2029-07-20 ¦ Status: Under Implementation ¦ Type: | 30.06.2028 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2029-07-20
2200000150 | Main-Connectivity under GNA |  | AMPIN Energy Green Private Limited (Formerly known as AMP ENERGY GREEN PRIVATE LIMITED) | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | Total: 187 MW Solar: 137.5 MW Wind: 49.5 MW |  | 137.5 | 49.5 | 0 | 187 | CESC Limited | Granted | 150 | 0 | 150 | Kurnool-III | Andhra Pradesh | 2024-06-14 | 2025-06-28 | • Generation Pooling station of M/s AMP Energy Green Pvt. Ltd. – Kurnool-III PS 220 kV S/c line om D/c tower along with line bays at generation pooling station – under the scope of applicant. • 1 no. 220kV line bay at Kurnool-III PS for termination of above dedicated line - under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 28-06-2025 | 28-06-2025 |  |  | 150 | 203 | 2026-12-30 |  | AMPIN representative informed that vide CESC letter revised SCD date is 30.12.2026 or 60 days subsequent to readiness of the delivery point and power evacuation infrastructure whichever is earlier. |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 110.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: Solar | 16-03-2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 28-06-2025 |  | 2025-06-28 | 2026-12-30
2200000152 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 | 0 | 150 | 0 | 0 | 150 |  | Granted | 150 | 0 | 150 | Bhadla-II | Rajasthan | 2025-03-05 | 2026-09-30 | Common Pooling station of Ms Solarcraft Power India 4 Private Limited for Solar Power Projects with Appl. Nos.2200000152 (150 MW) & 2200000192 (110 MW) – Bhadla-III PS 220 kV Sc line on Dc towers# (Suitable to carry minimum 300 MW at nominal voltage)-Under Applicant Scope Connectivity of 110 MW to Solarcraft Power(App. No. 2200000192) is granted in sharing with App. No. 220000152 through same bay and DTL | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (7th) 400220kV ICT at Bhadla-III PS Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr swit | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (7th) 400220kV ICT at Bhadla-III PS Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) Bhadla-III – Bhadla (HVDC) 400 kV Dc (1st & 2nd) quad moose line along with the line bays at both substations Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line Augmentation of 5x1500 MVA (1st to 5th), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 16-Jun-25 | 16-Jun-25 |  |  | 150 | A202,A203 |  |  |  | 2026-06-30 | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 16-Jun-25 |  | 2025-06-16 | 2027-03-31
2200000153 | Main-Connectivity under GNA |  | TEQ GREEN POWER XV PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Barmer-I | Rajasthan | 2025-01-23 | 2026-11-07 | Teq Green Power XV Private Limited Power Park – Barmer-I PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 1x500 MVA (1st), 400/220 kV ICT at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 1x500 MVA (1st), 400/220 kV ICT at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | 50MW 30092650MW 311226 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-09-30 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-12-31 |  |  | 300 | 204 |  |  |  |  | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-09-30 | 50 | 2026-09-30 | 2027-06-30
2200000153 | Main-Connectivity under GNA |  | TEQ GREEN POWER XV PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Barmer-I | Rajasthan | 2025-01-23 | 2026-11-07 | Teq Green Power XV Private Limited Power Park – Barmer-I PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 1x500 MVA (1st), 400/220 kV ICT at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 1x500 MVA (1st), 400/220 kV ICT at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | 50MW 30092650MW 311226 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-09-30 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-12-31 |  |  | 300 | 204 |  |  |  |  | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 50.00 ¦ Date: 2026-12-31 | 50 | 2026-12-31 | 2027-06-30
2200000154 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 |  | 0 | 200 | 0 | 200 | SECI | Granted | 200 | 0 | 200 | Bhuj-II (Sec-I) | Gujarat | 2024-01-19 | 2025-03-29 | NTPC REL shall share the Dedicated Transmission System for Connectivity proposed to be granted to NTPC REL for its WPP of 150MW (GNA Connectivity appl. no. 2200000084) as given below • NTPC REL – Bhuj-II PS 220kV Sc line (on Dc tower) along with 220kV line bay at generation end (Under the scope of applicant) • 220kV line bay at Bhuj-II PS is already existing (implemented under ISTS). | 0 | 220 KV | Existing |  |  | Nil | Nil | 29-Mar-25 | 29-Mar-25 | 200 | 2025-03-29 |  | 205 | 2026-01-23 | 2026-10-20 | SECI vide letter dated 07.06.2024 informed that Revised SCOD date 23.01.2026 Further, as per Article 4.6 of the PPA dated 06.06.2023, the Project is allowed a maximum period of 270 days beyond SCOD for commissioning of the full contracted capacity. The effective last date for commissioning of the full 200 MW contracted capacity, as per PPA provisions, would be 20.10.2026. |  |  |  |  | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-02-26 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 150.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 29-Mar-25 |  | 2025-03-29 | 2026-10-20
2200000159 | Main-Connectivity under GNA |  | GUJARAT INDUSTRIES POWER COMPANY LTD. | WR | Land Route | (x) Renewable Power Park developer | Solar | 2375 |  | 600 | 0 | 0 | 600 |  | Granted | 600 | 0 | 600 | KPS-2 (Sec-I) | Gujarat | 2025-03-20 | 2028-11-19 | For up to 600MW, GIPCL shall share the Dedicated Transmission System for Connectivity granted to GIPCL for its SPP of 600MW (St-II Connectivity appl. no. 1200003371) as given below • GIPCL PS1 – KPS2 (Sec-I) 400kV Sc line (on Dc tower) along with associated line bay at generating station (under the scope of applicant) • 1 no. 400kV Bay at ISTS substation end [being implemented under “Establishment of Khavda Pooling Station-2 (KPS2) in Khavda RE Park” scheme by by KPS2 Transmission Ltd. (a subsidiary of POWERGRID)] For Balance 1175MW • GIPCL PS2 – KPS2 (Sec-II) 400kV Sc line along with associated line bay at generating station (under the scope of applicant) • 1 no. 400kV Bay at ISTS substation end [being implemented under “Transmission System for Evacuation of Power from potential REZ in Khavda area of Gujarat under Phase-IV (7 GW) Part E2” scheme by Khavda IV E2 Power Transmission Ltd. (a subsidiary of POWERGRID)] • GIPCL PSS1 – PSS 2 400kV Sc line (shall be kept in normally open condition and closed only in case of contingency conditions). | 0 | 400 kV | Aug without ATS |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV, 4x1500MVA, KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 7654 | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV, 4x1500MVA, KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari (New) 765 kV Dc line Khavda Phase-IV • Creation of 765kV bus section-II at KPS3 (GIS) along with 765kV Bus Sectionaliser • Creation of 400kV bus section-II at KPS3 (GIS) along with 400kV Bus Sectionaliser • KPS3 (GIS) – Lakadia (AIS) 765 kV DC line • ±300MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400kV Bus Section-2 • KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line • Establishment of 2x1500MVA, 765400kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) • Vadodara(GIS) –South Olpad(GIS) 765 kV DC line • LILO of Gandhar – Hazira 400kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • Ahmedabad – South Olpad(GIS) 765kV Dc line • Establishment of 4X1500 MVA 765400 kV & 2x500MVA 400220kV Boisar-II (GIS) • South Olpad(GIS) – Boisar-II(GIS) 765kV Dc line • LILO of Navsari (New) – Padghe(PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon(MH) 400kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of Babhaleswar – Padghe(M) 400kV Dc line at Boisar-II (Sec-I) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-I of Boisar-II and ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-II of Boisar-II • ± 300 MVAr STATCOM with 3x125 MVAr MSC, 1x125 MVAr MSR at 400 kV level of Navsari (New)(PG) Ss with 1 No. of 400 kV bay (GIS) • Establishment of 2X1500 MVA 765400 kV & 3x500MVA 400220kV Pune-III (GIS) • Boisar-II – Pune-III 76 | 31-Dec-24 | 31-Dec-24 |  |  | 600 | 418 (for 575MW) 1 no 400kV bay for the balance 1200MW to be taken up for implementation under ISTS |  |  |  | 2026-09-30 | 2028-11-19 | 2028-11-19 |  | Not effective | 2028-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2026-07-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 100.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 4 ¦ MW: 200.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 5 ¦ MW: 100.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 6 ¦ MW: 100.00 ¦ Date: 2026-09-29 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 7 ¦ MW: 100.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 8 ¦ MW: 100.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 9 ¦ MW: 100.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 10 ¦ MW: 500.00 ¦ Date: 2027-02-20 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 11 ¦ MW: 75.00 ¦ Date: 2027-12-25 ¦ Status: Under Implementation ¦ Type: Solar | 29-07-2026 |  |  | 29/07/2026 | Pending with Level 2 | 31-Dec-24 |  | 2024-12-31 | 2029-05-19
2200000161 | Main-Connectivity under GNA |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 400 | 0 | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Barmer-I | Rajasthan | 2025-01-23 | 2026-11-07 |  | 1 | 220 KV | Aug without ATS |  |  | Establishment of 4x1500MVA 765/400kV ICTs at South Kalamb S/s. LILO of Pune-III Boisar-II line at South Kalamb S/s. | Establishment of 4x1500MVA 765/400kV ICTs at South Kalamb S/s. LILO of Pune-III Boisar-II line at South Kalamb S/s. | 16-Jun-25 | 16-Jun-25 |  |  | 400 | 206 |  |  |  |  | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  | Yes |  | 08/07/2026 | Pending with Level 2 | 16-Jun-25 |  | 2025-06-16 | 2027-06-30
2200000162 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 295 | 0 | 0 | 295 | 0 | 295 | REMCL | Granted | 295 | 0 | 295 | Ananthapuram | Andhra Pradesh | 2025-03-03 | 2025-09-28 | •Generation Pooling Station of M/s Project Nine Renewable Power Pvt. Ltd. -Ananthpuram PS 220 kV S/c line on D/c Tower along with line bays at generation pooling station – under the scope of applicant •1 no. 220 kV line bay at Ananthpuram PS – Under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 100 MW 30.04.2025100 MW 30.05.202595 MW 25.07.2025 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-04-30 Phase 2 ¦ MW: 100.00 ¦ Date: 2025-05-30 Phase 3 ¦ MW: 95.00 ¦ Date: 2025-07-25 |  |  | 295 | 203 | 2026-12-31 |  | for 100MW and 200MW PPAs as submitted by Applicant vide email dtd 20.04.2026 | 2026-03-31 | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 95.70 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 52.80 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 29.70 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 4 ¦ MW: 116.80 ¦ Date: 2027-03-17 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-04-30 | 100 | 2025-04-30 | 2026-12-31
2200000162 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 295 | 0 | 0 | 295 | 0 | 295 | REMCL | Granted | 295 | 0 | 295 | Ananthapuram | Andhra Pradesh | 2025-03-03 | 2025-09-28 | •Generation Pooling Station of M/s Project Nine Renewable Power Pvt. Ltd. -Ananthpuram PS 220 kV S/c line on D/c Tower along with line bays at generation pooling station – under the scope of applicant •1 no. 220 kV line bay at Ananthpuram PS – Under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 100 MW 30.04.2025100 MW 30.05.202595 MW 25.07.2025 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-04-30 Phase 2 ¦ MW: 100.00 ¦ Date: 2025-05-30 Phase 3 ¦ MW: 95.00 ¦ Date: 2025-07-25 |  |  | 295 | 203 | 2026-12-31 |  | for 100MW and 200MW PPAs as submitted by Applicant vide email dtd 20.04.2026 | 2026-03-31 | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 95.70 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 52.80 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 29.70 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 4 ¦ MW: 116.80 ¦ Date: 2027-03-17 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 100.00 ¦ Date: 2025-05-30 | 100 | 2025-05-30 | 2026-12-31
2200000162 | Main-Connectivity under GNA |  | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 295 | 0 | 0 | 295 | 0 | 295 | REMCL | Granted | 295 | 0 | 295 | Ananthapuram | Andhra Pradesh | 2025-03-03 | 2025-09-28 | •Generation Pooling Station of M/s Project Nine Renewable Power Pvt. Ltd. -Ananthpuram PS 220 kV S/c line on D/c Tower along with line bays at generation pooling station – under the scope of applicant •1 no. 220 kV line bay at Ananthpuram PS – Under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 100 MW 30.04.2025100 MW 30.05.202595 MW 25.07.2025 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-04-30 Phase 2 ¦ MW: 100.00 ¦ Date: 2025-05-30 Phase 3 ¦ MW: 95.00 ¦ Date: 2025-07-25 |  |  | 295 | 203 | 2026-12-31 |  | for 100MW and 200MW PPAs as submitted by Applicant vide email dtd 20.04.2026 | 2026-03-31 | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 95.70 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 52.80 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 29.70 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 4 ¦ MW: 116.80 ¦ Date: 2027-03-17 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | Phase 3 ¦ MW: 95.00 ¦ Date: 2025-07-25 | 95 | 2025-07-25 | 2026-12-31
2200000163 | Main-Connectivity under GNA |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 1000 | 0 | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | Bikaner-III | Rajasthan | 2024-12-30 | 2026-08-22 | Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS1- Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS2 400 kV S/c line Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS2– Bikaner-III PS 400 kV D/c line (Suitable to carry minimum 900 MW per circuit at nominal voltage) (Common for Application no. 2200000111 & 2200000163 of M/s Sunbreeze for 400 MW & 1000 MW respectively) | 1 | 400 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 3x1500 MVA (4th, 5th & 6th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 12) 400 kV Bareilly(765/400kV) – Bareilly(PG) D/c line (Quad) (2nd) 13) Augmentation with 1x1500 MVA, 765/400 kV ICT at Bareilly (765/400kV) S/s (3rd) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 3x1500 MVA (4th, 5th & 6th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 12) 400 kV Bareilly(765/400kV) – Bareilly(PG) D/c line (Quad) (2nd) 13) Augmentation with 1x1500 MVA, 765/400 kV ICT at Bareilly (765/400kV) S/s (3rd) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 300 MW 31.03.2025300 MW 30.04.2025400 MW 31.05.2025 | Phase 1 ¦ MW: 300.00 ¦ Date: 2025-03-31 Phase 2 ¦ MW: 300.00 ¦ Date: 2025-04-30 Phase 3 ¦ MW: 400.00 ¦ Date: 2025-05-31 |  |  | 1000 | 446(Main bay),445(Tie bay) |  |  |  | 2026-08-31 | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 500.00 ¦ Date: 2026-07-10 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 500.00 ¦ Date: 2026-07-20 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 300.00 ¦ Date: 2025-03-31 | 300 | 2025-03-31 | 2027-09-30
2200000163 | Main-Connectivity under GNA |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 1000 | 0 | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | Bikaner-III | Rajasthan | 2024-12-30 | 2026-08-22 | Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS1- Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS2 400 kV S/c line Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS2– Bikaner-III PS 400 kV D/c line (Suitable to carry minimum 900 MW per circuit at nominal voltage) (Common for Application no. 2200000111 & 2200000163 of M/s Sunbreeze for 400 MW & 1000 MW respectively) | 1 | 400 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 3x1500 MVA (4th, 5th & 6th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 12) 400 kV Bareilly(765/400kV) – Bareilly(PG) D/c line (Quad) (2nd) 13) Augmentation with 1x1500 MVA, 765/400 kV ICT at Bareilly (765/400kV) S/s (3rd) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 3x1500 MVA (4th, 5th & 6th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 12) 400 kV Bareilly(765/400kV) – Bareilly(PG) D/c line (Quad) (2nd) 13) Augmentation with 1x1500 MVA, 765/400 kV ICT at Bareilly (765/400kV) S/s (3rd) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 300 MW 31.03.2025300 MW 30.04.2025400 MW 31.05.2025 | Phase 1 ¦ MW: 300.00 ¦ Date: 2025-03-31 Phase 2 ¦ MW: 300.00 ¦ Date: 2025-04-30 Phase 3 ¦ MW: 400.00 ¦ Date: 2025-05-31 |  |  | 1000 | 446(Main bay),445(Tie bay) |  |  |  | 2026-08-31 | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 500.00 ¦ Date: 2026-07-10 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 500.00 ¦ Date: 2026-07-20 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 300.00 ¦ Date: 2025-04-30 | 300 | 2025-04-30 | 2027-09-30
2200000163 | Main-Connectivity under GNA |  | SUNBREEZE RENEWABLES NINE PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 1000 | 0 | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | Bikaner-III | Rajasthan | 2024-12-30 | 2026-08-22 | Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS1- Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS2 400 kV S/c line Sunbreeze Renewables Nine Pvt. Ltd. RE Power park PSS2– Bikaner-III PS 400 kV D/c line (Suitable to carry minimum 900 MW per circuit at nominal voltage) (Common for Application no. 2200000111 & 2200000163 of M/s Sunbreeze for 400 MW & 1000 MW respectively) | 1 | 400 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 3x1500 MVA (4th, 5th & 6th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 12) 400 kV Bareilly(765/400kV) – Bareilly(PG) D/c line (Quad) (2nd) 13) Augmentation with 1x1500 MVA, 765/400 kV ICT at Bareilly (765/400kV) S/s (3rd) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Common Transmission system for Connectivity under GNA (Augmentation without ATS) 1) Augmentation of 3x1500 MVA (4th, 5th & 6th) 765/400 kV ICTs at Bikaner-III Pooling Station 2) Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) 3) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS 4) Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) 5) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 6) Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s 7) Neemrana-II -Kotputli 400 kV D/c line (Quad) 8) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s 9) Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 10) Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end 11) Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 12) 400 kV Bareilly(765/400kV) – Bareilly(PG) D/c line (Quad) (2nd) 13) Augmentation with 1x1500 MVA, 765/400 kV ICT at Bareilly (765/400kV) S/s (3rd) Additional Transmission system for Inter-regional power transfer: 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 300 MW 31.03.2025300 MW 30.04.2025400 MW 31.05.2025 | Phase 1 ¦ MW: 300.00 ¦ Date: 2025-03-31 Phase 2 ¦ MW: 300.00 ¦ Date: 2025-04-30 Phase 3 ¦ MW: 400.00 ¦ Date: 2025-05-31 |  |  | 1000 | 446(Main bay),445(Tie bay) |  |  |  | 2026-08-31 | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 500.00 ¦ Date: 2026-07-10 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 500.00 ¦ Date: 2026-07-20 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 3 ¦ MW: 400.00 ¦ Date: 2025-05-31 | 400 | 2025-05-31 | 2027-09-30
2200000164 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 | 0 | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Bikaner-III | Rajasthan | 2024-12-30 | 2026-08-22 |  | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA(3rd & 4th) 400220 kV ICT at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (5th & 6th) 765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 1x15 | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA(3rd & 4th) 400220 kV ICT at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (5th & 6th) 765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation of 2x1500 MVA (3rd & 4th), 765400 kV ICTs at Neemrana-II Ss Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 400 kV Bareilly(765400kV) – Bareilly(PG) Dc line (Quad) (2nd) Augmentation with 1x1500 MVA, 765400 kV ICT at Bareilly (765400kV) Ss (3rd) Additional Transmission system for Inter-regional power transfer Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-Dec-25 | 31-Dec-25 |  |  | 50 | 207 |  |  |  |  | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  | Bay ant CoD to be updated | 08/07/2026 | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2027-09-30
2200000165 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 | 0 | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Bikaner-III | Rajasthan | 2024-12-30 | 2026-08-22 |  | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA(3rd & 4th) 400220 kV ICT at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (5th & 6th) 765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 1x15 | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA(3rd & 4th) 400220 kV ICT at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (5th & 6th) 765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation of 2x1500 MVA (3rd & 4th), 765400 kV ICTs at Neemrana-II Ss Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 400 kV Bareilly(765400kV) – Bareilly(PG) Dc line (Quad) (2nd) Augmentation with 1x1500 MVA, 765400 kV ICT at Bareilly (765400kV) Ss (3rd) Additional Transmission system for Inter-regional power transfer Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-Oct-25 | 31-Oct-25 |  |  | 50 | 207 |  |  |  |  | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  | Bay anticipated CoD to be updated |  | Pending with Level 2 | 31-Oct-25 |  | 2025-10-31 | 2027-09-30
2200000171 | Main-Connectivity under GNA |  | APRAAVA ENERGY PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 | SECI | Granted | 300 | 0 | 300 | Bijapur | Karnataka | 2025-04-01 | 2027-01-17 | • Generating Pooling Station of M/s Apraava Energy Pvt. Ltd.– Bijapur PS 220 kV S/c line on D/c tower# along with line bays at generation pooling station – under the scope of applicant. • 1 no. of 220 kV line bay at Bijapur PS - under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | 23-09-2025 | 23-09-2025 |  |  | 300 | 201 |  |  |  | 2027-01-16 | 2027-01-16 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-15 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 23-09-2025 |  | 2025-09-23 | 2027-03-31
2200000172 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 | 0 | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Bikaner-III | Rajasthan | 2024-12-30 | 2026-08-22 |  | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system for Connectivity under GNA (Augmentation without ATS) Augmentation of 1x500 MVA(3rd) 400/220 kV ICT at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (5th & 6th) 765/400 kV ICTs at Bikaner-III Pooling Station Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s Neemrana-II -Kotputli 400 kV D/c line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 400 kV Bareilly(765/400kV) – Bareilly(PG) D/c line (Quad) (2nd) Augmentation with 1x1500 MVA, 765/400 kV ICT at Bareilly (765/400kV) S/s (3rd) Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Common Transmission system for Connectivity under GNA (Augmentation without ATS) Augmentation of 1x500 MVA(3rd) 400/220 kV ICT at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (5th & 6th) 765/400 kV ICTs at Bikaner-III Pooling Station Augmentation of 1x1500 MVA (4th) 765/400kV ICT at Bikaner (PG) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II D/c line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV D/c line (Quad) Bikaner-III - Neemrana-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation of 2x1500 MVA (3rd & 4th), 765/400 kV ICTs at Neemrana-II S/s Neemrana-II -Kotputli 400 kV D/c line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) D/c line (Quad) at Neemrana-II S/s Bikaner-III - Neemrana-II 765 kV D/c line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400/220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 400 kV Bareilly(765/400kV) – Bareilly(PG) D/c line (Quad) (2nd) Augmentation with 1x1500 MVA, 765/400 kV ICT at Bareilly (765/400kV) S/s (3rd) Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 28-Feb-26 | 28-Feb-26 |  |  | 50 | 207 |  |  |  |  | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  | bay ant CoD to be updated | 08/07/2026 | Pending with Level 2 | 28-Feb-26 |  | 2026-02-28 | 2027-09-30
2200000179 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 500 | 0 | 500 | 0 | 0 | 500 | SECI | Granted | 500 | 0 | 500 | Bikaner-III | Rajasthan | 2024-12-30 | 2026-11-11 | Common pooling station for NTPC Renewable Energy Limited Solar Power Projects (App No.2200000179(500 MW) & 2200000244(150 MW) – Bikaner-IV PS 400 kV Sc line on Dc towers# (Suitable to carry minimum 900 MW at nominal voltage)-Under Applicant scope Connectivity of 150 MW to NTPC Renewable Energy Limited (App No. 220000244) is granted in sharing with App. No. 2200000179(500 MW) through same bay and DTL | 2 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Establishment of 2x1500 MVA, 765400 kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor at a suitable location near Bikaner LILO of one ckt o | Transmission system for Connectivity under GNA Establishment of 2x1500 MVA, 765400 kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor at a suitable location near Bikaner LILO of one ckt of 765 kV Bikaner-III -Neemrana-II Dc line (2nd) at Bikaner-IV PS along with 330 MVAR switchable line reactor at Bikaner-IV PS end of each ckt of 765 kV Bikaner-IV -Neemrana-II line (formed after LILO) Establishment of 765400 kV, 2x1500 MVA Ss at suitable location near Churu along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Churu 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Bikaner-IV PS end LILO of one ckt of 765 kV Sikar-II (PG) -Khetri (PG) Dc line at Churu Ss Churu – Fatehabad (PG) 400 kV Dc line (Quad Moose) along with 63 MVAr switchable line reactor for each circuit at Churu Ss end Establishment of 765400 kV, 3x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Siwani – Jind (PG) 400 kV Dc line (Quad Moose) Siwani – Patran (Indi Grid) 400 kV Dc line (Quad Moose) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV line bays at Bikaner-IV PS Additional Transmission system for Inter-regional power transfer Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 28-Jun-25 | 28-Jun-25 |  |  | 500 | 216,218 |  |  |  | 2026-07-30 | 2026-11-11 | 2027-09-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 300.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar |  | Yes |  |  | Pending with Level 2 | 28-Jun-25 |  | 2025-06-28 | 2027-09-30
2200000180 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 500 |  | 0 | 500 | 0 | 500 | REMCL | Granted | 500 | 0 | 500 | Jam Khambhaliya | Gujarat | 2024-02-07 | 2025-06-28 | NTPC REL – Jam Khambhaliya PS 220kV line along with associated bay at generation end (under the scope of applicant) as detailed below The 500MW wind power shall be pooled with two PSS-1 (250MW) and PSS-2 (250MW) at generation end and connected with two nos. ISTS bays at Jam Khambhaliya ISTS with sharing Dc tower for some portion as detailed below 220kV Sc Line on Dc tower from PSS-01 to Common point 220kV Sc Line on Dc tower from PSS-02 to Common point 220kV Dc line on Dc tower from Common point to Jam Khambhaliya PS 2 nos. 220kV bays at Jam Khambhaliya PS (already existing, implemented under ISTS). | 2 | 220 KV | Existing |  |  | Nil | Nil | 28-Jun-25 | 28-Jun-25 | 500 | 2025-06-28 |  | 211 & 212 | 2026-12-28 |  | PPA signed with Central Railway SCOD extension received under PPA till 26.12.2025. Central Railway letter dated 24.12.2025, provided further extension on SCOD by six months i.e. 28.06.2026 |  |  |  |  | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 400.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 | Yes |  | 21/07/2026 | Pending with Level 2 | 28-Jun-25 |  | 2025-06-28 | 2026-12-28
2200000181 | Main-Connectivity under GNA |  | EDEN RENEWABLE CADET PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 | SECI | Granted | 300 | 0 | 300 | Barmer-I | Rajasthan | 2025-01-23 | 2026-11-07 | Eden Renewable Cadet Private Limited – Barmer-I PS 220 kV S/c line on D/c towers# (Suitable to carry minimum 300 MW at nominal voltage) -Under Applicant scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 1x500 MVA (2nd), 400/220 kV ICT at Barmer-I Pooling Station 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | Transmission system for Connectivity under GNA: 1x500 MVA (2nd), 400/220 kV ICT at Barmer-I Pooling Station 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | 26-Apr-25 | 26-Apr-25 |  |  | 300 | 208 | 2027-02-25 |  | As per the email from OA dated 27.03.2026 |  | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-08-29 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 26-Apr-25 |  | 2025-04-26 | 2027-06-30
2200000184 | Main-Connectivity under GNA |  | DESHRAJ SOLAR ENERGY PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-III | Rajasthan | 2024-12-30 | 2026-11-11 | Deshraj Solar Energy Private Limited Solar Power Project – Bikaner-IV PS 220 kV Sc line on Dc towers# (Suitable to carry minimum 300 MW at nominal voltage) -Under Applicant scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Establishment of 2x1500 MVA, 765400 kV & 1x500MVA 400220kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor at a suitable location near Bikaner | Transmission system for Connectivity under GNA Establishment of 2x1500 MVA, 765400 kV & 1x500MVA 400220kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor at a suitable location near Bikaner LILO of one ckt of 765 kV Bikaner-III -Neemrana-II Dc line (2nd) at Bikaner-IV PS along with 330 MVAR switchable line reactor at Bikaner-IV PS end of each ckt of 765 kV Bikaner-IV -Neemrana-II line (formed after LILO) Establishment of 765400 kV, 2x1500 MVA Ss at suitable location near Churu along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Churu 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Bikaner-IV PS end LILO of one ckt of 765 kV Sikar-II (PG) -Khetri (PG) Dc line at Churu Ss Churu – Fatehabad (PG) 400 kV Dc line (Quad Moose) along with 63 MVAr switchable line reactor for each circuit at Churu Ss end Establishment of 765400 kV, 3x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Siwani – Jind (PG) 400 kV Dc line (Quad Moose) Siwani – Patran (Indi Grid) 400 kV Dc line (Quad Moose) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV line bays at Bikaner-IV PS Additional Transmission system for Inter-regional power transfer 1. Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2. Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 25-Jun-25 | 25-Jun-25 |  |  | 300 | 219 |  |  |  | 2026-08-31 | 2026-11-11 | 2027-09-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 150.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 25-Jun-25 |  | 2025-06-25 | 2027-09-30
2200000186 | Main-Connectivity under GNA |  | RENEW SOLAR POWER PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 | SECI | Granted | 300 | 0 | 300 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-03-05 | 2026-11-07 | 2 No. 400kV line bays at South Kalamb under ISTS under “Network Expansion scheme in Western Region to cater to Pumped storage potential near Talegaon (Pune)” scheme by M/s. Adani Energy Solutions Limited | 1 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 2x1500 MVA(3rd & 4th), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at FatehgarhIV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA: Augmentation of 2x1500 MVA(3rd & 4th), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at FatehgarhIV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 30-Jun-25 | 30-Jun-25 |  |  | 300 | 448(Main),449(Tie) |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-08-31 ¦ Status: Under Implementation ¦ Type: |  | Yes |  | 08/07/2026 | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2027-06-30
2200000187 | Main-Connectivity under GNA |  | RENEW SOLAR POWER PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 | SECI | Granted | 300 | 0 | 300 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-03-05 | 2026-11-07 | Common Pooling station of M/s Renew Solar Power Private Limited Solar Power Projects (Appl. No. 2200000186 (300 MW) & Appl. No. 2200000187 (300 MW))– Fatehgarh-IV PS (Section-II) 400 kV S/c line on D/c towers (Suitable to carry minimum 900 MW per circuit at nominal voltage)-Under Applicant Scope Connectivity of 300 MW to Renew Solar Power Pvt. Ltd.(App No. 2200000187) is granted in sharing with app. No. 2200000186 throguh same bay & DTL | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 2x1500 MVA(3rd & 4th), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at FatehgarhIV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA: Augmentation of 2x1500 MVA(3rd & 4th), 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at FatehgarhIV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of 2x1500 MVA, 765/400 kV Barmer-I Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR, 420 kV Bus Reactor Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA/ckt at nominal voltage | 30-Jun-25 | 30-Jun-25 |  |  | 300 | 448(Main),449(Tie) |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-02-25 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2027-08-31 ¦ Status: Under Implementation ¦ Type: |  | Yes |  | 08/07/2026 | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2027-06-30
2200000190 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Jam Khambhaliya | Gujarat | 2024-01-29 | 2025-12-31 | JGEPL – Jam Khambhaliya PS 220kV Sc (on Dc towers) line along with associated bay at generation end (under the scope of the applicant). 1 no. 220kV line bay at Jam Khambhaliya PS is already existing (already existing, implemented under ISTS). | 1 | 220 KV | Existing |  |  | Nil | Nil | 31-Dec-25 | 31-Dec-25 | 100 | 2025-12-31 |  | 202 | 2026-07-30 | 2026-11-30 | PPA signed between Juniper Green and SJVN on 30.04.2024 and the revised SCOD till 24 months from effective date i.e 30.04.2026 SJVN vide letter dtd. 20.01.2026 provided further extension in SCOD, till 30.07.2026 or 30 days subsequent to start/operationalization date of connectivity, whichever is later. |  |  |  |  | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 23-07-2026 | Yes |  | 23/07/2026 | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2026-11-30
2200000192 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 110 |  | 110 | 0 | 0 | 110 |  | Granted | 110 | 0 | 110 | Bhadla-III | Rajasthan | 2026-03-27 |  | Common Pooling station of Ms Solarcraft Power India 4 Private Limited for Solar Power Projects with Appl. Nos.2200000152 (150 MW) & 2200000192 (110 MW) – Bhadla-III PS 220 kV Sc line on Dc towers (Suitable to carry minimum 300 MW at nominal voltage)-Under Applicant Scope Connectivity of 110 MW to Solarcraft Power(App. No. 2200000192) is granted in sharing with App. No. 220000152(150 MW) through same bay and DTL | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA (7th & 8th) 400220kV ICT at Bhadla-III PS Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA (7th & 8th) 400220kV ICT at Bhadla-III PS Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) Bhadla-III – Bhadla (HVDC) 400 kV Dc (1st & 2nd) quad moose line along with the line bays at both substations Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line Augmentation of 5x1500 MVA (1st to 5th), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 16-Jun-25 | 16-Jun-25 |  |  | 110 | 222 | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 110.00 ¦ Date: 2029-07-20 ¦ Status: Under Implementation ¦ Type: | 30.06.2028 |  |  |  | Pending with Level 2 | 16-Jun-25 |  | 2025-06-16 | 2029-07-20
2200000193 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 101 |  | 0 | 101 | 0 | 101 |  | Granted | 101 | 0.2 | 100.8 | kallam | Maharashtra | 2026-06-26 | 2025-10-05 | TPREL in present application shall share the DTL identified to Torrent Solar Power Private Limited (TSPPL) in application no. 1670224223993 (for 66MW), which is detailed below TSPPL Common PS - Kallam PS 400kV Sc line (on double circuit towers) alongwith associated bay at generator end (Under the scope of TSPPL) 1 no. 400kV line bay at ISTS substation end (under the scope of ISTS). Interconnection between TSPPL Common PS and TPREL 40033kV PS TSPPL Common PS – TPREL PS 400kV Sc line on Sc towers. | 0 | 400 KV | Aug without ATS |  |  | Western Region Network Expansion Scheme in Kallam area of Maharashtra | LILO of both circuits of Parli(M) – Karjat(M)Loni kand II(M) 400kV Dc line (twin moose) at Kallam PS | 01-Jun-25 | 01-Jun-25 |  |  | 100.8 | 421 |  |  |  | 2025-03-31 | 2025-10-05 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 101.00 ¦ Date: 2026-08-01 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 06/08/2026 | Pending with Level 2 | 01-Jun-25 |  | 2025-06-01 | 2026-10-31
2200000198 | Main-Connectivity under GNA |  | TORRENT SOLAR POWER PRIVATE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 250 |  | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | kallam | Maharashtra | 2024-05-29 | 2025-10-05 | TSPPL in present application shall share the DTL identified to TSPPL in application no. 1670224223993 (for 66MW), which is detailed below TSPPL Common PS - Kallam PS 400kV Sc line (on double circuit towers) alongwith associated bay at generator end (Under the scope of applicant) TSPPL Common PS – TSPPL Hybrid PS 400kV Sc line (on double circuit towers) 1 no. 400kV line bay at ISTS substation end (under the scope of ISTS). | 0 | 400 KV | Aug without ATS |  |  | Western Region Network Expansion Scheme in Kallam area of maharashtra | LILO of both circuits of Parli(M) – Karjat(M)Loni kand II(M) 400kV Dc line (twin moose) at Kallam PS | 31-May-25 | 31-May-25 |  |  | 250 | 421 |  |  |  | 2025-03-31 | 2025-10-05 | 2027-06-30 |  | Not effective | 2026-10-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-06-30
2200000199 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Gadag-II | Karnataka | 2025-04-03 | 2027-01-17 | Through dedicated Connectivity transmission system of M/s Avaada Energy Pvt. Ltd. (for application no 2200000385) i.e Generating pooling station of M/s Avaada Energy Pvt. Ltd.– Gadag-II PS 220 kV S/c line : all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 30-Sep-25 | 30-Sep-25 |  |  | 50 | 216 |  |  |  |  | 2027-01-16 | 2027-04-30 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Sep-25 |  | 2025-09-30 | 2027-04-30
2200000209 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 | 0 | 0 | 200 | 0 | 200 |  | Granted | 200 | 0 | 200 | Jam Khambhaliya | Gujarat | 2024-01-30 | 2026-06-30 | Ms JGEPL shall share the Dedicated Transmission System for Connectivity proposed to Ms JGEPL for Connectivity of its another WPP of 100MW against appl. no. 2200000190 as given below • JGEPL – Jam Khambhaliya PS 220kV Sc line along with associated bay at generation end (under the scope of the applicant). • 1 no. 220kV bay at JK PS (already existing, implemented under ISTS). | 0 | 220 KV | Existing |  |  | Nil | Nil | 100 MW 30.06.2026100 MW 31.12.2026 | Phase 1 ¦ MW: 100.00 ¦ Date: 2026-06-30 Phase 2 ¦ MW: 100.00 ¦ Date: 2026-12-31 | 200 | 2026-06-30 |  | 202 | [7 empty] | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2026-10-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 100.00 ¦ Date: 2026-06-30 | 100 | 2026-06-30 | 2026-12-30
2200000209 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 | 0 | 0 | 200 | 0 | 200 |  | Granted | 200 | 0 | 200 | Jam Khambhaliya | Gujarat | 2024-01-30 | 2026-06-30 | Ms JGEPL shall share the Dedicated Transmission System for Connectivity proposed to Ms JGEPL for Connectivity of its another WPP of 100MW against appl. no. 2200000190 as given below • JGEPL – Jam Khambhaliya PS 220kV Sc line along with associated bay at generation end (under the scope of the applicant). • 1 no. 220kV bay at JK PS (already existing, implemented under ISTS). | 0 | 220 KV | Existing |  |  | Nil | Nil | 100 MW 30.06.2026100 MW 31.12.2026 | Phase 1 ¦ MW: 100.00 ¦ Date: 2026-06-30 Phase 2 ¦ MW: 100.00 ¦ Date: 2026-12-31 | 200 | 2026-06-30 |  | 202 | [7 empty] | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2026-10-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 100.00 ¦ Date: 2026-12-31 | 100 | 2026-12-31 | 2027-06-30
2200000210 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 17 PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Solarcraft Power India 17 Private Limited Solar Power Project – Bikaner-IV PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) -Under Applicant scope | 1 | 220 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA 1. Establishment of 6x1500 MVA, 765400 kV & 6x500 MVA, 400220 kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 2. 400kV Sectionalizer bay (1 set) at Bikaner-IV PS 3. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS 4. LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS 5. Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 6. Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end 7. Siwani – Jind (PG) 400 kV Dc line (Quad) 8. Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end 9. Siwani – Fatehabad (PG) 400 kV Dc line (Quad) 10. Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end 11. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 12. 400kV Sectionalizer bay (1 set) at Siwani Ss Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore (PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 30-Dec-25 | 30-Dec-25 |  |  | 300 | 201 | 2027-06-23 |  | 150MW: 23.06.2025; 150MW: 31.08.2026 (60 days from Tr.) | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-08-30 ¦ Status: Under Implementation ¦ Type: Solar |  | Yes |  | 08/07/2026 | Pending with Level 2 | 30-Dec-25 |  | 2025-12-30 | 2027-06-23
2200000212 | Main-Connectivity under GNA |  | RADIANT STAR SOLAR PARK PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 100 | 0 | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-06-05 | 2026-11-07 | Radiant Star Solar Park Pvt. Ltd.–Barmer-I PS 220 kV S/c line on D/c towers# (Suitable to carry minimum 300 MW at nominal voltage) -Under Applicant scope | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 1x500 MVA (2nd), 400/220 kV ICT at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | Transmission system for Connectivity under GNA: 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 1x500 MVA (2nd), 400/220 kV ICT at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | 31-Dec-25 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-12-31 |  |  | 100 | 224 |  |  |  | 2026-08-14 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-12-31 | 100 | 2025-12-31 | 2027-06-30
2200000213 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 |  | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Solapur Pool (Sec-I) | Maharashtra | 2024-08-21 | 2026-03-20 | SPI7PL – Solapur PS 220kV Sc line on Dc Towers along with associated bay at generation end (under the scope of the SPI7PL). 1 no. 220kV line bay at Solapur PS is being implemented under ISTS as part of the pooling station. | 1 | 220 KV | Aug without ATS |  |  | Establishment of 400220 kV, 4x500 MVA ICTs at Solapur PS Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAAACAL59 moose equivalent) | Establishment of 400220 kV, 4x500 MVA ICTs at Solapur PS Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAAACAL59 moose equivalent) | 30-Sep-25 | 30-Sep-25 |  |  | 50 | 202 |  |  |  | 2026-10-30 | 2026-03-20 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Sep-25 |  | 2025-09-30 | 2026-10-30
2200000218 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 155 | 0 | 0 | 155 | 0 | 155 | REMCL | Granted | 155 | 0 | 155 | Bhuj | Gujarat | 2024-01-29 | 2025-06-28 | NTPC REL shall share the Dedicated Transmission System for Connectivity granted to Ayana Renewable Power Four Private Limited (ARP4PL) for Hybrid RE project of 100MW against Connectivity appl. no. 2200000239 as given below · ARP4PL – Bhuj PS 220kV Sc line along with associated line bay at generating station (under the scope of applicant) · Bay No. 206 at Bhuj PS shall be implemented under ISTS. | 0 | 220 KV | Existing |  |  | Nil | Nil | 28-Jun-25 | 28-Jun-25 |  |  | 155 | 206 | 2026-12-28 |  | PPA signed with Northern Railway SCOD extension received under PPA till 31.12.2025. Central Railway letter dated 24.12.2025, provided further extension on SCOD by six months i.e. 28.06.2026 | 2025-04-01 |  |  |  | Not effective | 2026-08-25 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 155.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 | Yes | Bay charged on 11.02.2025, POWERGRID has filed petition in CERC for DOCO of the bay as 01.04.2025 | 21/07/2026 | Pending with Level 2 | 28-Jun-25 |  | 2025-06-28 | 2026-12-28
2200000221 | Main-Connectivity under GNA |  | FIRST ENERGY PRIVATE LIMITED | NR | Land BG Route | (vi) Captive generating plant | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Bikaner-III | Rajasthan | 2024-12-30 | 2026-11-11 | Through sharing of dedicated transmission system of Ms Juniper Green Cosmic Pvt. Ltd.(App no. 2200000073)– Bikaner-III PS 220 kV Sc line on Dc tower (Suitable to carry minimum 300 MW at nominal voltage) Infrastructure required for sharing shall be under the scope of Ms First Energy Pvt. Ltd. | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (5th & 6th)765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 2x500 MVA (5th) 400220 kV IC | Transmission system for Connectivity under GNA Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (5th & 6th)765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 2x500 MVA (5th) 400220 kV ICTs at Bikaner-III Pooling Station LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation of 2x1500 MVA (3rd & 4th), 765400 kV ICTs at Neemrana-II Ss Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 400 kV Bareilly(765400kV) – Bareilly(PG) Dc line (Quad) (2nd) Augmentation with 1x1500 MVA, 765400 kV ICT at Bareilly (765400kV) Ss (3rd) Establishment of 6x1500 MVA, 765400 kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV Dc line (Quad) Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end Siwani – Fatehabad (PG) 400 kV Dc line (Quad) Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer | 31-May-25 | 31-May-25 |  |  | 100 | 214 |  |  |  |  | 2026-11-11 | 2027-09-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  | Bay anticipated CoD to be updated |  | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-09-30
2200000226 | Main-Connectivity under GNA |  | SEVEN RENEWABLE POWER PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 150 |  | 0 | 150 | 0 | 150 |  | Granted | 150 | 0 | 150 | Ananthapuram | Andhra Pradesh | 2025-03-03 | 2026-09-30 | • Generation Pooling station of M/s Seven Renewable Power Pvt. Ltd. – Ananthapuram PS 220 kV S/c line on D/c tower# along with line bays at generation pooling station – under the scope of applicant. • 1 no. 220 kV line bay at Ananthapuram PS for termination of dedicated Connectivity line - under the scope of ISTS • Applicant shall ensure that dedicated connectivity transmission line is capable of transferring atleast 300 MW. | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-Mar-25 | 31-Mar-25 |  |  | 150 | 205 |  |  |  | 2026-03-31 | 2025-09-27 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-01-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2028-02-28 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 50.00 ¦ Date: 2028-04-28 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2027-03-30
2200000227 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 | 0 | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Bikaner-III | Rajasthan | 2024-12-30 | 2026-08-22 | Common pooling station for Sunsure Solarpark RJ One Private Limited Solar Projects(App. No. 2200000172(50 MW), 2200000165(50 MW),2200000164(50 MW) & 2200000227(50 MW)– Bikaner-III PS 220 kV Sc line on Dc towers(Suitable to carry minimum 350 MW at nominal voltage)-Under Applicant Scope Connectivity of 150 MW to Ms Saimaa Solar Pvt. Ltd. is granted in sharing with Ms Sunsure Solarpark RJ One Energy Pvt. Ltd.(App. No. 220000172) through same bay & DTL | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (4th) 400220 kV ICT at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (5th & 6th) 765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 1x1500 MVA (4 | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (4th) 400220 kV ICT at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (5th & 6th) 765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation of 2x1500 MVA (3rd & 4th ),765400 kV ICTs at Neemrana-II Ss Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 400 kV Bareilly(765400kV) – Bareilly(PG) Dc line (Quad) (2nd) Augmentation with 1x1500 MVA, 765400 kV ICT at Bareilly (765400kV) Ss (3rd) Additional Transmission system for Inter-regional power transfer Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-Mar-26 | 31-Mar-26 |  |  | 50 | 207 |  |  |  |  | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  |  | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-09-30
2200000228 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 | 0 | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Bikaner-III | Rajasthan | 2024-12-30 | 2026-08-22 | Through sharing of dedicated transmission system of Ms Proteus Energy Pvt. Limited– Bikaner-III PS 220 kV Sc line (Suitable to carry minimum 317 MW at nominal voltage) (220 kV bay at Bikaner-III PS shall be common for Proteus(217 MW)Ms Avaada(50 MW) & Ms Sunsure(50 MW))-Under Applicant scope Infrastructure required for sharing dedicated transmission system - under the scope of Ms Sunsure Solarpark RJ One | 0 | 220 KV | Aug without ATS |  |  | · ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-ITransmission system for Connectivity under GNA Augmentation of 1x500 MVA (4th) 400220 | · ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-ITransmission system for Connectivity under GNA Augmentation of 1x500 MVA (4th) 400220 kV ICT at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (5th & 6th) 765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation of 2x1500 MVA (3rd & 4th ),765400 kV ICTs at Neemrana-II Ss Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) 400 kV Bareilly(765400kV) – Bareilly(PG) Dc line (Quad) (2nd) Augmentation with 1x1500 MVA, 765400 kV ICT at Bareilly (765400kV) Ss (3rd) Additional Transmission system for Inter-regional power transfer Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-Mar-26 | 31-Mar-26 |  |  | 50 | 203 |  |  |  |  | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  | Bay anticipated CoD to be updated | 08/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-09-30
2200000229 | Main-Connectivity under GNA |  | AMPIN Energy Green Private Limited (Formerly known as AMP ENERGY GREEN PRIVATE LIMITED) | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | Solar: 85 MW Wind:118.8 MW |  | 85 | 118.8 | 100 | 303.8 | SECI | Granted | 200 | 0 | 200 | Kurnool-III | Andhra Pradesh | 2024-06-14 | 2027-03-31 | •Through dedicated Connectivity transmission system already granted to M/s Amp Energy Green Pvt. Ltd. for application no. 2200000150 i.e. M/s Generation Pooling station of AMP Energy Green Pvt. Ltd. – Kurnool-III PS 220 kV S/c line on D/c Tower – all arrangement under the scope of applicant. •Applicant shall ensure that dedicated connectivity transmission line is capable to transfer atleast 350 MW | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-Dec-25 | 31-Dec-25 |  |  | 200 | 203 | 2026-10-27 |  | AMPIN representative informed that vide SECI letter revised SCD date is 27.10.2026 |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 85.00 ¦ Date: 2026-10-27 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 18.00 ¦ Date: 2026-10-27 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 100.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2027-03-31
2200000231 | Main-Connectivity under GNA |  | AMP ENERGY C&I TWELVE PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Kurnool-III | Andhra Pradesh | 2024-06-14 | 2025-06-30 | •Generation Pooling station of Amp Energy C&l Twelve Pvt. Ltd. – Kurnool-III PS 220 kV S/c line along with line bays at generation pooling station – under the scope of applicant. •1 no. 220 kV line bay at Kurnool-III PS - under the scope of ISTS. •Applicant shall ensure that dedicated connectivity transmission line is capable to transfer atleast 300 MW | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 30-Nov-24 | 30-Nov-24 |  |  | 100 | 205 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Solar | 16-03-2026 |  |  |  | Pending with Level 2 | 30-Nov-24 |  | 2024-11-30 | 2026-10-31
2200000232 | Main-Connectivity under GNA |  | GREEN INFRA CLEAN ENERGY GENERATION PRIVATE LIMITED (Formerly known as GREEN INFRA CLEAN ENERGY GENERATION LIMITED) | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bhadla-III | Rajasthan | 2026-03-27 |  | Green Infra Clean Energy Generation Ltd Solar Power Project – Bhadla-III PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) -Under Applicant scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (8th) 400220kV ICT at Bhadla-III PS Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVA | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (8th) 400220kV ICT at Bhadla-III PS Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) Bhadla-III – Bhadla (HVDC) 400 kV Dc (1st & 2nd) quad moose line along with the line bays at both substations Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line Augmentation of 5x1500 MVA (1st to 5th), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 01-Jun-25 | 01-Jun-25 |  |  | 300 | 226 | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2029-07-20 ¦ Status: Under Implementation ¦ Type: Solar | Expected b |  |  |  | Pending with Level 2 | 01-Jun-25 |  | 2025-06-01 | 2029-07-20
2200000236 | Main-Connectivity under GNA |  | HERO SOLAR ENERGY PRIVATE LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | Solar: 150 MW Wind:159 MW |  | 150 | 159 | 120 | 429 | SECI | Granted | 270 | 0 | 270 | Kurnool-III | Andhra Pradesh | 2024-08-14 | 2026-12-31 | •Common Generation pooling Station of M/s Hero Solar Energy Pvt. Ltd. for application no. 2200000236 (270 MW) and 2200000383 (270 MW)- Kurnool-III PS 220kV S/c line on D/c tower along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Kurnool-III PS for termination of above mentioned dedicated Connectivity line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B | 30-Mar-26 | 30-Mar-26 |  |  | 270 | 217 | 2026-10-27 |  | Hero Solar representative informed that vide SECI letter, revised SCD is 27.10.2026 |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 77.10 ¦ Date: 2026-10-27 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 77.10 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 77.10 ¦ Date: 2026-10-27 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 4 ¦ MW: 77.10 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 5 ¦ MW: 60.00 ¦ Date: 2026-10-27 ¦ Status: Under Implementation ¦ Type: Standalone ¦ Phase 6 ¦ MW: 60.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Standalone | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 30-Mar-26 |  | 2026-03-30 | 2026-12-31
2200000237 | Main-Connectivity under GNA |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED | SR | Land BG Route | (vi) Captive generating plant | Wind | 102 |  | 0 | 102 | 0 | 102 |  | Granted | 102 | 0 | 102 | Koppal-II | Karnataka | 2025-02-28 | 2025-12-31 | •Through Sharing of dedicated transmission infrastructure of M/s ABREL (RJ) Ltd. already granted for application no. 2200000141 i.e. Generating Pooling Station of M/s ABREL (RJ) Ltd – Koppal-II PS 220 kV S/c line – all arrangement under the scope of applicant •M/s ABREL (RJ) Projects. Ltd. shall ensure that dedicated transmission line has capability to transfer atleast 336 MW power | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | 31-May-25 | 31-May-25 |  |  | 102 | 212 |  |  |  |  | 2025-12-30 | 2027-03-31 |  | Not effective | 2027-01-16 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 102.00 ¦ Date: 2027-03-05 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-03-31
2200000238 | Main-Connectivity under GNA |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED | SR | Land BG Route | (vi) Captive generating plant | Wind | 102 |  | 0 | 102 | 0 | 102 |  | Granted | 102 | 0 | 102 | Gadag-II | Karnataka | 2025-04-03 | 2025-12-31 | •Through Sharing of dedicated transmission infrastructure of M/s ABREL (RJ) Ltd. already granted for application no. 2200000139 i.e. Generating Pooling Station of M/s ABREL (RJ) Ltd at Dharwad –Gadag-II PS 220 kV S/c line – all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 31-May-25 | 31-May-25 |  |  | 102 | 232 |  |  |  |  | 2027-01-16 | 2027-04-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 102.00 ¦ Date: 2027-04-08 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-04-30
2200000241 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 545 |  | 0 | 45 | 0 | 45 | REMCL | Granted | 45 | 0 | 45 | Jam Khambhaliya | Gujarat | 2024-11-22 | 2026-10-14 | NTPC REL in present application shall share the same DTL provided to NTPC REL in application no. 2200000180 for 500MW at Jam Khambhaliya PS, which is detailed below • NTPC REL – Jam Khambhaliya PS 220kV Dc line along with associated bay at generation end (under the scope of applicant). • 2 nos. 220kV bays at Jam Khambhaliya PS (already existing, implemented under ISTS). | 0 | 220 KV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA Part A • Establishment of 2x1500MVA 765400kV Jamnagar(GIS) PS • Halvad – Jamnagar 765kV Dc line • LILO of Jam Khambhaliya PS – Lakadia 400 kV Dc (triple snowbird) line at Jamnagar • J | Common Transmission System Augmentation for Connectivity under GNA Part A • Establishment of 2x1500MVA 765400kV Jamnagar(GIS) PS • Halvad – Jamnagar 765kV Dc line • LILO of Jam Khambhaliya PS – Lakadia 400 kV Dc (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of CGPL– Jetpur 400kV Dc (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad– Bhogat 400kV Dc line (Twin AL-59) at Jam Khambhaliya PS Part B • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 2x500MVA, 400220kV ICT (5th& 6th) | 28-Jun-25 | 28-Jun-25 |  |  | 45 | 211 & 212 |  |  |  |  | 2026-10-14 | 2027-09-30 |  | Not effective | 2026-10-14 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 45.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 28-Jun-25 |  | 2025-06-28 | 2027-09-30
2200000243 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 288 |  | 0 | 288 | 0 | 288 |  | Granted | 288 | 0 | 288 | Koppal-II | Karnataka | 2025-02-28 | 2025-12-31 | •Generating Pooling Station of M/s TATA Power Renewable Energy Ltd.– Koppal-II PS 220 kV S/c line on D/c tower# along with line bays at generation pooling station – under the scope of applicant. •1 no. of 220 kV line bay at Koppal-II PS - under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | 01-Jun-25 | 01-Jun-25 |  |  | 288 | 216 |  |  |  | 2026-06-30 | 2025-12-30 | 2027-03-31 |  | Not effective | 2027-01-16 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 288.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar | 30.06.2026 |  |  | 27/07/2026 | Pending with Level 2 | 01-Jun-25 |  | 2025-06-01 | 2027-03-31
2200000244 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 | 0 | 150 | 0 | 0 | 150 | REMCL | Granted | 150 | 0 | 150 | Bikaner-IV | Rajasthan | 2025-02-19 | 2026-11-11 | Common pooling station for NTPC Renewable Energy Limited RE Power Projects (App No. 2200000244 (150 MW), 2200000308 (700 MW), 2200000373 (400 MW), 2200000358 (250 MW) & 2200000420 (400 MW) – Bikaner-IV PS 400 kV Dc line (Suitable to carry minimum 950 MW per circuit at nominal voltage) – under applicant scope Connectivity of 150 MW (App No. 2200000244) & 400MW (App No. 2200000420) to NTPCREL is granted in sharing with App. No. 2200000308(700 MW) through same bay and common DTL | 0 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA 1. Establishment of 6x1500 MVA, 765400 kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 2. 400kV Sectionalizer bay (1 set) at Bikaner-IV PS 3. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS 4. LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS 5. Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 6. Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end 7. Siwani – Jind (PG) 400 kV Dc line (Quad) 8. Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end 9. Siwani – Fatehabad (PG) 400 kV Dc line (Quad) 10. Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end 11. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 12. 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore (PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 28-Jun-25 | 28-Jun-25 |  |  | 150 | 432 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar |  | Yes |  | 08/07/2026 | Pending with Level 2 | 28-Jun-25 |  | 2025-06-28 | 2027-04-30
2200000246 | Main-Connectivity under GNA |  | MOUNTING RENEWABLE POWER LIMITED | WR | Land BG Route | (vi) Captive generating plant | Hybrid | 250 | 0 | 88.3 | 161.7 | 0 | 250 |  | Granted | 250 | 0 | 250 | Jam Khambhaliya | Gujarat | 2024-11-06 | 2026-10-14 | • MRPL– Jam Khambhaliya PS 220kV Sc line (on Dc tower) along with associated bay at MRPL end (under the scope of applicant) • 1 No. 220kV Bay on New 220 kV bus section-II of Jam Khambhaliya PS is being implemented under ISTS [under “Augmentation of transformation capacity at Jam Khambhaliya PS (GIS)” scheme by POWERGRID (TBCB route)]. | 1 | 220 KV | Aug without ATS |  |  | Part A (Network Expansion scheme in Gujarat for drawl of about 3.6 GW load under Phase-I in Jamnagar area, being implemented under ISTS by Ms AESL under TBCB Route) • Establishment of 2x1500 MVA 765400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV Dc | Part A (Network Expansion scheme in Gujarat for drawl of about 3.6 GW load under Phase-I in Jamnagar area, being implemented under ISTS by Ms AESL under TBCB Route) • Establishment of 2x1500 MVA 765400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV Dc line • LILO of Jam Khambhaliya PS – Lakadia 400 kV Dc (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of CGPL – Jetpur 400kV Dc (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad – Bhogat 400kV Dc line (Twin AL-59) at Jam Khambhaliya PS Part B (Augmentation of transformation capacity at Jam Khambhaliya PS (GIS), being implemented under ISTS by POWERGRID under TBCB Route) • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 2x500MVA, 400220kV ICTs (5th & 6th) (terminated on New 220 kV bus section-II) along with associated ICT bays | 31-Mar-25 | 31-Mar-25 |  |  | 250 | 216 |  |  |  | 2027-06-30 | 2026-10-14 | 2027-06-30 |  | Not effective | 2026-10-14 | Under Construction | Part Commissioned | 174.9 | ¦ Phase 1 ¦ MW: 92.40 ¦ Date: 2026-06-19 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 33.00 ¦ Date: 2026-06-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 6.60 ¦ Date: 2026-06-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 26.40 ¦ Date: 2026-06-30 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 16.50 ¦ Date: 2026-07-03 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 6 ¦ MW: 46.20 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 7 ¦ MW: 28.90 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar | 09-07-2026 |  |  | 16/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2027-06-30
2200000247 | Main-Connectivity under GNA |  | SPRNG POWER EARTH PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 250 |  | 250 | 0 | 0 | 250 |  | Granted | 250 | 0 | 250 | Radhanesda | Gujarat | 2024-01-29 | 2026-06-30 | SPEPL – Radhanesda PS 220kV Sc line (ON Dc towers) along with associated line bay at generating station (under the scope of applicant) 1 no. bay out of 2 nos. spare bays which were originally constructed for GPCL’s Radhanesda solar park and remain unutilized till date shall be allocated to Ms SPEPL to ensure its utilization. | 1 | 220 KV | Existing |  |  | Nil | Nil | 30-Jun-26 | 30-Jun-26 | 250 | 2026-06-30 |  | 204 | 2026-08-29 | [6 empty] | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 | Yes |  | 10/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2026-08-29
2200000250 | Main-Connectivity under GNA |  | NHPC LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 | IRDEA | Granted | 100 | 0 | 100 | NP Kunta | Andhra Pradesh | 2024-04-26 | 2025-03-23 | •Generation Pooling station of M/s NHPC Ltd. –NP Kunta PS 220 kV S/c line on D/c tower along with line bays at generation pooling station – under the scope of applicant. • 1 no. 220 kV line bay at NP Kunta PS for termination of above dedicated Connectivity transmission line – under the scope of Applicant | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 30-Sep-24 | 30-Sep-24 |  |  | 100 | 221 | 2026-06-30 |  | NHPC informed in the meeting: 335/375 acres of land acquisition done for solar park. NHPC representative informed that Revised SCD is 30.06.2026. |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-10-15 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 | Yes |  |  | Pending with Level 2 | 30-Sep-24 |  | 2024-09-30 | 2026-10-31
2200000253 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Jam Khambhaliya | Gujarat | 2024-10-30 | 2027-06-30 | • JGEPL – Jam Khambhaliya PS 220kV Sc line (on Dc tower) along with associated bay at generation end (under the scope of applicant) • 1 no. 220kV Bay on New 220 kV bus section-II of Jam Khambhaliya PS is being implemented under ISTS [under “Augmentation of transformation capacity at Jam Khambhaliya PS (GIS)” scheme by POWERGRID (TBCB route)]. | 1 | 220 KV | Existing |  |  | Nil | Nil | 30-Jun-27 | 30-Jun-27 |  |  | 100 | 221 |  |  |  | 2027-06-30 |  |  |  | Not effective | 2027-06-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-12-30
2200000254 | Main-Connectivity under GNA |  | AVAADA RJBIKANER PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 600 | 0 | 600 | 0 | 0 | 600 |  | Granted | 600 | 0 | 600 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Common Pooling station for Avaada RJ Bikaner Private Limited (App No. 2200000013 (50 MW), App. No. 2200000254 (600 MW)) & Avaada Energy Private Limited (App No. 2200000289 (300 MW)) RE Power Projects – Bikaner-IV PS 400 kV Sc line on Dc tower# (Suitable to carry minimum 950 MW at nominal voltage)-Under applicant scope Connectivity of 50 MW to Avaada RJ Bikaner Private Limited (App No. 2200000013) & 300 MW to Avaada Energy Private Limited (App No. 2200000289) is granted in sharing with App. No. 2200000254(600 MW) through same bay and DTL | 1 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA 1. Establishment of 6x1500 MVA, 765400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 2. 400kV Sectionalizer bay (1 set) at Bikaner-IV PS 3. STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS 4. LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS 5. Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 6. Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end 7. Siwani – Jind (PG) 400 kV Dc line (Quad) 8. Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end 9. Siwani – Fatehabad (PG) 400 kV Dc line (Quad) 10. Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end 11. STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 12. 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer 1. Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2. Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-Mar-25 | 31-Mar-25 |  |  | 600 | 438 |  |  |  |  | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 600.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2027-05-11
2200000261 | Main-Connectivity under GNA |  | AIRPOWER WINDFARMS PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 175 | 0 | 0 | 175 | 0 | 175 |  | Granted | 175 |  | 175 | Jam Khambhaliya |  | 2024-11-06 | 2026-10-14 | Ms AWPL has applied under Reg. 5.6 for sharing of terminal bay, switchyard and the dedicated transmission line with Ms Torrent Power Limited (app. no. 1200003335) granted 115 MW Connectivity at Jam Khambhaliya PS. Hence, applicant shall share the following system of Ms TPL • TPL – Jam Khambhaliya PS 220kV Sc line alongwith associated line bay at generating station (under the scope of applicant) • Bay at ISTS substation end is existing as a part of ISTS. (No. 206) | 0 |  |  |  |  | Part A (Agreed in 15th NCT meeting) • Establishment of 2x1500 MVA 765400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV Dc line • LILO of Jam Khambhaliya PS – Lakadia 400 kV Dc (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV Dc | Part A (Agreed in 15th NCT meeting) • Establishment of 2x1500 MVA 765400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV Dc line • LILO of Jam Khambhaliya PS – Lakadia 400 kV Dc (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of CGPL – Jetpur 400kV Dc (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad – Bhogat 400kV Dc line (Twin AL-59) at Jam Khambhaliya PS Part B (To be taken up for approval in ensuing NCT meeting) • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 2x500MVA, 400220kV ICTs (5th & 6th) along with associated ICT bays | 30-May-25 | 30-May-25 |  |  | 175 | 206 |  |  |  |  | 2026-10-14 | 2027-09-30 |  | Not effective | 2026-10-14 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 59.40 ¦ Date: 2026-06-27 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 15.60 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 4 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-May-25 |  | 2025-05-30 | 2027-09-30
2200000262 | Main-Connectivity under GNA |  | Jindal Green Wind 1 Private Limited (Formerly known as JSP GREEN WIND 1 PRIVATE LIMITED) | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 400 |  | 0 | 400 | 0 | 400 |  | Granted | 400 | 0 | 400 | Koppal-II | Karnataka | 2025-02-28 | 2025-12-31 | •Generation Pooling station of M/s JSP Green Wind 1 Pvt. Ltd at Raichur – Koppal-II PS 220 kV D/c line along with line bays at generation pooling station – under the scope of applicant. •02 nos. 220 kV line bay at Koppal-II PS for termination of above dedicated line - under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | 31-May-25 | 31-May-25 |  |  | 400 | 218 & 224 |  |  |  |  | 2025-12-31 | 2027-03-31 |  | Not effective | 2027-01-16 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-03-31
2200000263 | Main-Connectivity under GNA |  | ACME SUN POWER PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 400 | 0 | 0 | 400 | 0 | 400 |  | Granted | 400 | 0 | 400 | Jam Khambhaliya | Gujarat | 2024-10-30 | 2026-10-14 | • ACME SPPL – Jam Khambhaliya PS 220kV S/c line (on D/c tower) (refer Note-A) along with associated bay at generation end (under the scope of applicant) • 1 no. 220kV Bay on New 220 kV bus section-II of Jam Khambhaliya PS is being implemented under ISTS [under “Augmentation of transformation capacity at Jam Khambhaliya PS (GIS)” scheme by POWERGRID (TBCB route)]. | 1 | 220 kV | Aug without ATS |  |  | Part A (Agreed in 15th NCT meeting) • Establishment of 2x1500 MVA 765/400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV D/c line • LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part B (To be taken up for approval in ensuing NCT meeting): • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 2x500MVA, 400/220kV ICTs (5th & 6th) along with associated ICT bays | Part A (Agreed in 15th NCT meeting) • Establishment of 2x1500 MVA 765/400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV D/c line • LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part B (To be taken up for approval in ensuing NCT meeting): • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 2x500MVA, 400/220kV ICTs (5th & 6th) along with associated ICT bays | 30-Mar-26 | 30-Mar-26 |  |  | 400 | 217 |  |  |  | 2027-06-30 | 2026-10-14 | 2027-09-30 |  | Not effective | 2026-10-14 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2027-12-25 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Mar-26 |  | 2026-03-30 | 2027-09-30
2200000266 | Main-Connectivity under GNA |  | MALUR RENEWABLES PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 650 |  | 650 | 0 | 0 | 650 |  | Granted | 650 | 0 | 650 | Bhadla-III | Rajasthan | 2026-03-27 |  | Ms Malur Renewables Private Limited Renewable Power Park– Bhadla-III PS 400 kV Sc line on Dc tower# (Suitable to carry minimum 900 MW at nominal voltage) | 1 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end | Transmission system for Connectivity under GNA Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) Bhadla-III – Bhadla (HVDC) 400 kV 2xDc quad moose line along with the line bays at both substations Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- BhadlaIII 400kV Dc line Augmentation of 5x1500 MVA (1st to 5th), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 30-May-25 | 30-May-25 |  |  | 650 | 433(Main),434(Tie) | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2029-07-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 350.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  |  | Pending with Level 2 | 30-May-25 |  | 2025-05-30 | 2029-07-20
2200000267 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 250 | 0 | 250 | 0 | 0 | 250 |  | Granted | 250 | 0 | 250 | Pachora (Sec-II) | Madhya Pradesh | 2024-10-11 | 2026-12-31 | Ms AEPL shall share Dedicated Transmission System for Connectivity granted to its other SPP of 50 MW against App. No. 2200000082 as given below • AEPL - Pachora PS 220 kV line (on Dc tower) along with associated bay at generation end (Under scope of applicant). • 220 kV bay at Pachora PS is already under implementation under ISTS as part of Rajgarh Ph-II (1 GW) scheme. • Ms AEPL (application no. 2200000082) shall utilise the Dc tower of 220 kV Sc line (on Dc tower) of Ms AEPL (application no. 2200000956) for stringing of second circuit. | 0 | 220 KV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA 400220 kV, 3x500 MVA ICT augmentation (4th, 5th & 6th) at Pachora PS. Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent). | Common Transmission System Augmentation for Connectivity under GNA 400220 kV, 3x500 MVA ICT augmentation (4th, 5th & 6th) at Pachora PS. Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent). | 31-Mar-25 | 31-Mar-25 |  |  | 250 | 214 |  |  |  | 2026-04-15 | 2026-02-14 | 2026-05-30 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2026-12-31
2200000270 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 52.8 |  | 0 | 52.8 | 0 | 52.8 |  | Granted | 52.8 | 0 | 52.8 | Solapur Pool (Sec-I) | Maharashtra | 2024-09-24 | 2026-03-20 | SPI7PL shall share Dedicated Transmission System for Connectivity of its other WPP of 50MW (appl. no. 2200000213) as given below • SPI7PL – Solapur PS 220kV Sc line along with associated bay at generation end (under the scope of the applicant). • 1 no. 220kV line bay at Solapur PS is being implemented under ISTS as part of the pooling station. | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Evacuation of Power from RE Projects in Solapur (1500 MW) SEZ in Maharashtra | Common Transmission System Augmentation for Connectivity under GNA • Establishment of 400220 kV, 4x500 MVA ICTs at Solapur PS • Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAAACAL59 moose equivalent) | 30-Sep-25 | 30-Sep-25 |  |  | 52.8 | 202 |  |  |  | 2026-10-30 | 2026-03-20 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 52.80 ¦ Date: 2026-09-20 ¦ Status: Under Implementation ¦ Type: Wind | 08.06.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Sep-25 |  | 2025-09-30 | 2026-10-30
2200000271 | Main-Connectivity under GNA |  | ABC CLEANTECH PRIVATE LIMITED | SR | Land BG Route | (x) Renewable Power Park developer | Wind | 250 |  | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Ananthapuram | Andhra Pradesh | 2025-03-04 | 2026-03-31 | •Generating Pooling Station of M/s ABC Cleantech Pvt. Ltd – Ananthapuram PS 400 kV S/c line including terminal bay at generation end –under the scope of applicant. •1 no. 400 kV line bay at Ananthapuram PS for termination of above mentioned dedicated Connectivity line - under the scope of ISTS | 1 | 400 kV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | 31-Mar-26 | 31-Mar-26 |  |  | 250 | 419 |  |  |  | 2026-03-31 | 2025-09-27 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 70.00 ¦ Date: 2027-10-01 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 180.00 ¦ Date: 2028-04-01 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2026-10-31
2200000273 | Main-Connectivity under GNA |  | ABC CT RE PARK (03) PRIVATE LIMITED | SR | Land BG Route | (x) Renewable Power Park developer | Wind | 250 |  | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Ananthapuram | Andhra Pradesh | 2025-03-04 | 2026-03-31 | •Through sharing of dedicated Connectivity transmission system of M/s ABC Cleantech Pvt. Ltd. (for application no.2200000271) i.e. generating Pooling Station of M/s ABC Cleantech Pvt. Ltd – Ananthapuram PS 400 kV S/c line – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | 30-Jun-25 | 30-Jun-25 |  |  | 250 | 419 |  |  |  | 2026-03-31 | 2025-09-27 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2026-10-31
2200000274 | Main-Connectivity under GNA |  | ABC CT RE PARK (02) PRIVATE LIMITED | SR | Land BG Route | (x) Renewable Power Park developer | Wind | 250 |  | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Ananthapuram | Andhra Pradesh | 2025-03-04 | 2026-06-30 | •Through sharing of dedicated Connectivity transmission system of M/s ABC Cleantech Pvt. Ltd. (for application no.2200000271) i.e. generating Pooling Station of M/s ABC Cleantech Pvt. Ltd – Ananthapuram PS 400 kV S/c line – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | 30-Jun-26 | 30-Jun-26 |  |  | 250 | 419 |  |  |  | 2026-03-31 | 2025-09-27 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-04-11 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2026-12-30
2200000275 | Main-Connectivity under GNA |  | RENEW SOLAR (SHAKTI SIX) PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 400 |  | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Bhadla-III | Rajasthan | 2026-03-27 |  | Common Pooling Station for Renew Solar (Shakti Six) Private Limited (App. No. 120003848(550 MW), 0312100004(450 MW) ,2200000275(400MW)&2200000309(400 MW)) – Bhadla-III PS 400 kV Dc line (Suitable to carry minimum 900 MW per circuit at nominal voltage)-Under Applicant Scope Connectivity of 400 MW to RSS6PL(App No. 220000309) is granted in sharing with App. No. 2200000275(400 MW) through same bay and common DTL | 1 | 400 KV | Aug without ATS |  |  |  | 1. Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 2. 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end 3. Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation 4. Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) 5. Bhadla-III – Bhadla (HVDC) 400 kV 2xDc quad moose line along with the line bays at both substations 6. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 7. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- BhadlaIII 400kV Dc line 8. Augmentation of 5x1500 MVA (1st to 5th), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor 9. LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur 10. Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 30-Jun-26 | 30-Jun-26 |  |  | 400 | 430(Main),431(Tie) | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2029-07-20 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  |  | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2029-07-20
2200000276 | Main-Connectivity under GNA |  | ABC CT RE PARK (01) PRIVATE LIMITED | SR | Land BG Route | (x) Renewable Power Park developer | Wind | 250 |  | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Ananthapuram | Andhra Pradesh | 2025-03-04 | 2026-06-30 | •Through sharing of dedicated Connectivity transmission system of M/s ABC Cleantech Pvt. Ltd. (for application no. 2200000271) i.e. generating Pooling Station of M/s ABC Cleantech Pvt. Ltd – Ananthapuram PS 400 kV S/c line – all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | 30-Jun-26 | 30-Jun-26 |  |  | 250 | 419 |  |  |  | 2026-03-31 | 2025-09-27 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-04-11 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2026-12-30
2200000281 | Main-Connectivity under GNA |  | ANBOTO SOLAR PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 250 | 0 | 250 | 0 | 0 | 250 |  | Granted | 250 | 0 | 250 | Barmer-I | Rajasthan | 2025-05-08 | 2026-11-07 | Anboto Solar Private Limited Solar Power Project– Barmer-I PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 2x500 MVA (3rd & 4th), 400/220 kV ICTs at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Transmission system for Connectivity under GNA: 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 2x500 MVA (3rd & 4th), 400/220 kV ICTs at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | Transmission system for Connectivity under GNA: 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 2x500 MVA (3rd & 4th), 400/220 kV ICTs at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Transmission system for Connectivity under GNA: 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 2x500 MVA (3rd & 4th), 400/220 kV ICTs at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | 30-Nov-25 | 30-Nov-25 |  |  | 250 | 211 |  |  |  | 2027-03-31 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  | Yes |  | 08/07/2026 | Pending with Level 2 | 30-Nov-25 |  | 2025-11-30 | 2027-06-30
2200000282 | Main-Connectivity under GNA |  | VENA ENERGY AURA PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Koppal-II | Karnataka | 2025-02-28 | 2026-12-31 | •Through sharing of dedicated Connectivity transmission system granted to M/s VEH Green Energy Pvt. Ltd. for application no. 2200000126 i.e. Generation Pooling Station of M/s VEH Green Energy Pvt. Ltd. at Koppal – Koppal-II PS 220 kV S/c line along with 220 kV line at generation pooling station – all arrangement under the scope of applicant. •Note: M/s Vena Energy Aura Pvt. Ltd. has already been granted Connectivity for 50 MW through above mentioned dedicated Connectivity transmission system for application no. 2200000127. | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | 01-Oct-25 | 01-Oct-25 |  |  | 50 | 214 |  |  |  |  | 2025-12-31 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 01-Oct-25 |  | 2025-10-01 | 2027-06-30
2200000285 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK FOURTEEN PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-IV | Rajasthan | 2025-01-16 | 2027-03-31 | Sunsure Solarpark Fourteen Private Limited Solar Power Project– Bikaner-IV PS 220 kV Sc line on Dc towers# (Suitable to carry minimum 300 MW at nominal voltage)-Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Establishment of 6x1500 MVA, 765400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) | Transmission system for Connectivity under GNA Establishment of 6x1500 MVA, 765400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV Dc line (Quad) Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end Siwani – Fatehabad (PG) 400 kV Dc line (Quad) Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-Mar-27 | 31-Mar-27 |  |  | 300 | 205 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2027-09-30
2200000286 | Main-Connectivity under GNA |  | ENREN-I ENERGY PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Barmer-I | Rajasthan | 2025-05-26 | 2026-11-07 | Enren-I Energy Private Limited Solar Power Project – Barmer-I PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage)-under applicant scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 1x500 MVA (3rd), 400/220 kV ICT at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | Transmission system for Connectivity under GNA: 2x1500 MVA (2nd & 3rd), 765/400 kV ICTs at Barmer-I Pooling Station 1x500 MVA (3rd), 400/220 kV ICT at Barmer-I Pooling Station Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | 25-Feb-26 | 25-Feb-26 |  |  | 300 | 210 |  |  |  |  | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 25-Feb-26 |  | 2026-02-25 | 2027-06-30
2200000288 | Main-Connectivity under GNA |  | ABREL (RJ) PROJECTS LIMITED | WR | Land BG Route | (vi) Captive generating plant | Wind | 368 | 0 | 0 | 368 | 0 | 368 |  | Granted | 314 | 0 | 314 | Bhuj-II (Sec-II) | Gujarat | 2025-06-20 | 2026-11-24 | • ABREL(RJ)PL – Bhuj-II PS 220kV Sc line (on Dc tower) (# refer Note-A) along with associated bay at Generation end. (Under the scope of applicant). • 220kV line bay at Bhuj-II PS has already been implemented under ISTS | 1 | 220 KV | Aug without ATS |  |  | • Augmentation of transformation capacity at Bhuj-II PS by 2x500MVA, 400220kV ICT (5th& 6th) and by 1x1500MVA, 765400kV ICT (3rd) | • Augmentation of transformation capacity at Bhuj-II PS by 2x500MVA, 400220kV ICT (5th& 6th) and by 1x1500MVA, 765400kV ICT (3rd) | 31-May-25 | Phase 1 ¦ MW: 368.00 ¦ Date: 2025-05-31 |  |  | 314 | 217 |  |  |  | 2027-03-31 | 2026-11-24 | 2027-06-30 |  | Not effective | 2026-11-24 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 184.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 30.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 100.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 368.00 ¦ Date: 2025-05-31 | 368 | 2025-05-31 | 2027-06-30
2200000289 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Common Pooling station for Avaada RJ Bikaner Private Limited (App No. 2200000013 (50 MW), App. No. 2200000254 (600 MW)) & Avaada Energy Private Limited (App No. 2200000289 (300 MW)) RE Power Projects – Bikaner-IV PS 400 kV Sc line on Dc tower (Suitable to carry minimum 950 MW at nominal voltage)-Under Applicant Scope Connectivity of 50 MW to Avaada RJ Bikaner Private Limited (App No. 2200000013) & 300 MW to Avaada Energy Private Limited (App No. 2200000289) is granted in sharing with App. No. 2200000254(600 MW) through same bay and DTL | 0 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA 1. Establishment of 6x1500 MVA, 765400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 2. 400kV Sectionalizer bay (1 set) at Bikaner-IV PS 3. STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS 4. LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS 5. Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 6. Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end 7. Siwani – Jind (PG) 400 kV Dc line (Quad) 8. Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end 9. Siwani – Fatehabad (PG) 400 kV Dc line (Quad) 10. Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end 11. STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 12. 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer 1. Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2. Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 30-Nov-25 | 30-Nov-25 |  |  | 300 | 438 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Nov-25 |  | 2025-11-30 | 2027-04-30
2200000290 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 250 |  | 250 | 0 | 0 | 250 |  | Granted | 250 | 0 | 250 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-06-05 | 2026-11-07 | Common Pooling station for Avaada Energy Private Limited Solar Power Projects (App No. 220000077(50 MW) & App. No. 2200000290(250 MW)) – Barmer-I PS 220 kV S/c line on D/c towers#(Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Augmentation of 2x500 MVA, 400/ 220 kV (9th & 10th) ICTs at Tumkur (Pavagada) PS | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Augmentation of 2x500 MVA, 400/ 220 kV (9th & 10th) ICTs at Tumkur (Pavagada) PS | 30-Sep-25 | 30-Sep-25 |  |  | 250 | 241 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Sep-25 |  | 2025-09-30 | 2027-06-30
2200000292 | Main-Connectivity under GNA |  | RENEW VAYU ENERGY PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 300 Solar-200 MW Wind-100 MW |  | 200 | 100 | 0 | 300 |  | Granted | 300 | 0 | 300 | Gadag-II | Karnataka | 2025-05-07 | 2027-03-31 | •Generating Pooling Station of M/s Renew Vayu Energy Pvt. Ltd. – Gadag-II PS 220 kV S/c line on D/c tower* along with line bays at generation pooling station – under the scope of applicant. •1 no. 220 kV line bay at Gadag-II PS for termination of above dedicated line - under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 31-Mar-26 | 31-Mar-26 |  |  | 300 | 221 |  |  |  | 2027-03-31 | 2027-01-16 | 2027-04-30 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-09-30
2200000298 | Main-Connectivity under GNA |  | RENEW SAMIR URJA PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Indore | Madhya Pradesh | 2024-03-22 | 2026-03-31 | RSUPL shall share Dedicated Transmission System for Connectivity granted to RUSPL for its WPP of 300MW (Appl. no. 2200000070) Under the scope of Ms RUSPL 1. Establishment of 33400 KV Common Pooling Sub-Station-1 (PSS-1) of ReNew Samir Urja Private Limited (Appl. No. 2200000298) and ReNew Urja Shachar Private Limited (Appl. No. 2200000070). 2. Establishment of 33400 KV Common Pooling Sub-Station-2 (PSS-2) of ReNew Samir Urja Private Limited (Appl. No. 2200000298) and ReNew Urja Shachar Private Limited (Appl. No. 2200000070). 3. PSS-2– PSS-1 400kV SC line on Dc tower. 4. PSS-1 – Indore (Sec-A With Indore & Khandwa lines) 400kV SC line on Dc tower. Under the scope of ISTS 1. Implementation of 400kV Bay at Indore (PG) Ss is under ISTS (Awarded to POWERGRID vide CTU OM dated 02.01.2024 with implementation timeframe of 30.06.2025) | 0 | 400 KV | Existing |  |  | Nil | Nil | 30-Jun-25 | 30-Jun-25 |  |  | 300 | 422 |  |  |  | 2025-12-02 |  |  |  | Not effective | 2026-08-25 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 60.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 90.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2026-09-30
2200000300 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 |  | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Bhadla-III | Rajasthan | 2026-03-27 |  | Common Pooling station of Ms Solarcraft Power India 4 Pvt. Ltd. for Solar Power Projects (Appl. Nos.2200000152 (150 MW), 2200000192 (110 MW) & 220000300(50 MW) – Bhadla-III PS 220 kV Sc line on Dc tower (Suitable to carry minimum 310 MW at nominal voltage) | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (9th), 400220 kV ICT at Bhadla-III PS Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with 240 M | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (9th), 400220 kV ICT at Bhadla-III PS Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) Bhadla-III – Bhadla (HVDC) 400 kV 2xDc quad moose line along with the line bays at both substations Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- BhadlaIII 400kV Dc line Augmentation of 5x1500 MVA (1st to 5th), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 16-Jun-25 | 16-Jun-25 |  |  | 50 | 222 | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2029-07-20 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 16-Jun-25 |  | 2025-06-16 | 2029-07-20
2200000302 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | kallam | Maharashtra | 2024-05-09 | 2025-10-05 | SRIPL in present application no. 2200000302 alongwith SRIPL (in application no. 2200000277) shall share the following Dedicated Transmission System for Connectivity granted to TSPPL for its WPP of 66MW with application no. 1670224223993 Kallam PS - TSPPL Common PS 400kV Sc line (on double circuit towers) alongwith associated bay at generator end (Under the scope of applicant). Interconnections between TSPPL Common PS and SRIPL TSPPL Common PS – SRIPL PS 220kV Sc line (on double circuit towers) w.r.t SRIPL application number-2200000277 (200MW) & 2200000302 (100MW). | 0 | 400 KV | Aug without ATS |  |  | LILO of both circuits of Parli(M) – Karjat(M) Lonikand-II(M) 400kV Dc line (twin moose) at Kallam PS | LILO of both circuits of Parli(M) – Karjat(M) Lonikand-II(M) 400kV Dc line (twin moose) at Kallam PS | 31-Mar-25 | 31-Mar-25 |  |  | 100 | 421 |  |  |  | 2025-03-31 | 2025-10-05 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2026-10-31
2200000305 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 | 0 | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Barmer-I | Rajasthan | 2025-05-26 | 2027-03-31 | Juniper Green Energy Private Limited Solar Power Project– Barmer-I PS 220 kV S/c line on D/c tower#(Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220 kV ICT at Barmer-I PS Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 400kV Sectionalizer bay (1 set) at Barmer-I S/s Barmer-I PS – Merta-II 765 kV D/c line along with 240 MVAr switchable line reactor at Barmer-I PS end and 330MVAr switchable line reactor at Merta-II PS end for each circuit of Barmer-I PS – Merta-II 765 kV D/c line Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur(PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220 kV ICT at Barmer-I PS Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 400kV Sectionalizer bay (1 set) at Barmer-I S/s Barmer-I PS – Merta-II 765 kV D/c line along with 240 MVAr switchable line reactor at Barmer-I PS end and 330MVAr switchable line reactor at Merta-II PS end for each circuit of Barmer-I PS – Merta-II 765 kV D/c line Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur(PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | 150 MW 31.03.2027150 MW 30.09.2027 | Phase 1 ¦ MW: 150.00 ¦ Date: 2027-03-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2027-09-30 |  |  | 300 | [5 empty] | 2026-12-30 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 150.00 ¦ Date: 2027-03-31 | 150 | 2027-03-31 | 2027-09-30
2200000305 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 | 0 | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Barmer-I | Rajasthan | 2025-05-26 | 2027-03-31 | Juniper Green Energy Private Limited Solar Power Project– Barmer-I PS 220 kV S/c line on D/c tower#(Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220 kV ICT at Barmer-I PS Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 400kV Sectionalizer bay (1 set) at Barmer-I S/s Barmer-I PS – Merta-II 765 kV D/c line along with 240 MVAr switchable line reactor at Barmer-I PS end and 330MVAr switchable line reactor at Merta-II PS end for each circuit of Barmer-I PS – Merta-II 765 kV D/c line Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur(PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220 kV ICT at Barmer-I PS Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 400kV Sectionalizer bay (1 set) at Barmer-I S/s Barmer-I PS – Merta-II 765 kV D/c line along with 240 MVAr switchable line reactor at Barmer-I PS end and 330MVAr switchable line reactor at Merta-II PS end for each circuit of Barmer-I PS – Merta-II 765 kV D/c line Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur(PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | 150 MW 31.03.2027150 MW 30.09.2027 | Phase 1 ¦ MW: 150.00 ¦ Date: 2027-03-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2027-09-30 |  |  | 300 | [5 empty] | 2026-12-30 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 150.00 ¦ Date: 2027-09-30 | 150 | 2027-09-30 | 2028-03-30
2200000306 | Main-Connectivity under GNA |  | SHUDH SOLAR POWER PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 250 |  | 250 | 0 | 0 | 250 |  | Granted | 250 | 0 | 250 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Shudh Solar Power Private Limited Solar Power Project – Bikaner-IV PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Establishment of 6x1500 MVA, 765400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) | Transmission system for Connectivity under GNA Establishment of 6x1500 MVA, 765400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV Dc line (Quad) Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end Siwani – Fatehabad (PG) 400 kV Dc line (Quad) Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-May-25 | 31-May-25 |  |  | 250 | 203 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-08-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-05-11
2200000308 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 700 | 0 | 700 | 0 | 0 | 700 | SECI | Granted | 700 | 0 | 700 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Common pooling station for NTPC Renewable Energy Limited RE Power Projects (App No. 2200000244 (150 MW), 2200000308 (700 MW), 2200000373 (400 MW), 2200000358 (250 MW) & 2200000420 (400 MW) – Bikaner-IV PS 400 kV Dc line (Suitable to carry minimum 950 MW per circuit at nominal voltage) – under applicant scope Connectivity of 150 MW (App No. 2200000244) & 400MW (App No. 2200000420) to NTPCREL is granted in sharing with App. No. 2200000308(700 MW) through same bay and common DTL | 1 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA 1. Establishment of 6x1500 MVA, 765400 kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 2. 400kV Sectionalizer bay (1 set) at Bikaner-IV PS 3. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS 4. LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS 5. Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 6. Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end 7. Siwani – Jind (PG) 400 kV Dc line (Quad) 8. Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end 9. Siwani – Fatehabad (PG) 400 kV Dc line (Quad) 10. Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end 11. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 12. 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore (PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-Mar-26 | 31-Mar-26 |  |  | 700 | 432 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 700.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-05-11
2200000309 | Main-Connectivity under GNA |  | RENEW SOLAR (SHAKTI SIX) PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 400 |  | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Bhadla-III | Rajasthan | 2026-03-27 |  | Common Pooling Station for Renew Solar (Shakti Six) Private Limited (App. No. 120003848 (550 MW), 0312100004 (450 MW), 2200000275 (400 MW) & 2200000309 (400 MW)) Solar power projects – Bhadla-III PS 400 kV Dc line (Suitable to carry minimum 900 MW per circuit at nominal voltage)-Under Applicant Scope Connectivity of 400 MW to RSS6PL(App No. 220000309) is granted in sharing with App. No. 2200000275(400 MW) through same bay and common DTL | 0 | 400 KV | Aug without ATS |  |  |  | 1. Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 2. 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end 3. Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation 4. Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) 5. Bhadla-III – Bhadla (HVDC) 400 kV 2xDc quad moose line along with the line bays at both substations 6. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 7. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- BhadlaIII 400kV Dc line 8. Augmentation of 5x1500 MVA (1st to 5th), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor 9. LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur 10. Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 30-Jun-26 | 30-Jun-26 |  |  | 400 | 430(Main),431(Tie) | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2029-07-20 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2029-07-20
2200000310 | Main-Connectivity under GNA |  | TEQ GREEN POWER XVIII PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 250 | 0 | 0 | 200 | 0 | 200 |  | Granted | 200 | 0 | 200 | Pavagada | Karnataka | 2024-11-06 | 2026-05-22 | •Generating Pooling Station of M/s TEQ Green Power XVIII Pvt. Ltd.– Tumkur (Pavagada) PS 220 kV S/c line on D/c tower* along with line bay at generation pooling station – under the scope of applicant. •1 no. 220 kV line bay at Tumkur (Pavagada) PS for termination of above mentioned dedicated Connectivity line - under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Augmentation of transformation capacity by 2x500 MVA, 400/220 kV ICTs (7th and 8th) at Tumkur (Pavagada) PS* •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Augmentation of transformation capacity by 2x500 MVA, 400/220 kV ICTs (7th and 8th) at Tumkur (Pavagada) PS* •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 100MW-31.12.2515030.06.26 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2026-06-30 |  |  | 200 | 227 |  |  |  | 2026-05-20 | 2026-05-20 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-12-31 | 100 | 2025-12-31 | 2026-11-22
2200000310 | Main-Connectivity under GNA |  | TEQ GREEN POWER XVIII PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 250 | 0 | 0 | 200 | 0 | 200 |  | Granted | 200 | 0 | 200 | Pavagada | Karnataka | 2024-11-06 | 2026-05-22 | •Generating Pooling Station of M/s TEQ Green Power XVIII Pvt. Ltd.– Tumkur (Pavagada) PS 220 kV S/c line on D/c tower* along with line bay at generation pooling station – under the scope of applicant. •1 no. 220 kV line bay at Tumkur (Pavagada) PS for termination of above mentioned dedicated Connectivity line - under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Augmentation of transformation capacity by 2x500 MVA, 400/220 kV ICTs (7th and 8th) at Tumkur (Pavagada) PS* •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •Augmentation of transformation capacity by 2x500 MVA, 400/220 kV ICTs (7th and 8th) at Tumkur (Pavagada) PS* •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 100MW-31.12.2515030.06.26 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2026-06-30 |  |  | 200 | 227 |  |  |  | 2026-05-20 | 2026-05-20 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | Phase 2 ¦ MW: 150.00 ¦ Date: 2026-06-30 | 150 | 2026-06-30 | 2026-12-30
2200000311 | Main-Connectivity under GNA |  | TEQ GREEN POWER XVII PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 300(200MW Solar & 100MW Wind as per letter dated 30.11.2023 from applicant) | 0 | 200 | 100 | 0 | 300 |  | Granted | 300 | 0 | 300 | Lakadiya | Gujarat | 2025-07-15 | 2026-08-14 | • TGPXVIIPL – Lakadia 220kV Sc line on Dc tower# along with associated bay at generation end (under the scope of applicant) • 1 no. 220kV line bay at ISTS substation end shall be under ISTS. | 1 | 220 KV | Aug without ATS |  |  | Establishment of 2x500MVA, 400220kV ICTs (1st & 2nd) at Lakadia PS along with associated ICT bays. | Common Transmission System augmentation identified for grant of GNA Under Implementation (under ISTS) “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited Establishment of 2x500MVA, 400220kV ICTs (1st & 2nd) at Lakadia PS along with associated ICT bays The above scheme is presently under implementation by Ms WRSS XXI(A) Transco Ltd. | 150 MW (100 wind 50 solar) 31.12.2025150 MW (100 wind 50 solar) 30.06.2026 | Phase 1 ¦ MW: 150.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2026-06-30 |  |  | 300 | 206 |  |  |  | 2026-08-14 | 2025-08-16 | 2026-02-10 |  | Not effective | 2026-08-14 | Commissioned | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 150.00 ¦ Date: 2025-12-31 | 150 | 2025-12-31 | 2027-02-14
2200000311 | Main-Connectivity under GNA |  | TEQ GREEN POWER XVII PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 300(200MW Solar & 100MW Wind as per letter dated 30.11.2023 from applicant) | 0 | 200 | 100 | 0 | 300 |  | Granted | 300 | 0 | 300 | Lakadiya | Gujarat | 2025-07-15 | 2026-08-14 | • TGPXVIIPL – Lakadia 220kV Sc line on Dc tower# along with associated bay at generation end (under the scope of applicant) • 1 no. 220kV line bay at ISTS substation end shall be under ISTS. | 1 | 220 KV | Aug without ATS |  |  | Establishment of 2x500MVA, 400220kV ICTs (1st & 2nd) at Lakadia PS along with associated ICT bays. | Common Transmission System augmentation identified for grant of GNA Under Implementation (under ISTS) “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited Establishment of 2x500MVA, 400220kV ICTs (1st & 2nd) at Lakadia PS along with associated ICT bays The above scheme is presently under implementation by Ms WRSS XXI(A) Transco Ltd. | 150 MW (100 wind 50 solar) 31.12.2025150 MW (100 wind 50 solar) 30.06.2026 | Phase 1 ¦ MW: 150.00 ¦ Date: 2025-12-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2026-06-30 |  |  | 300 | 206 |  |  |  | 2026-08-14 | 2025-08-16 | 2026-02-10 |  | Not effective | 2026-08-14 | Commissioned | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 150.00 ¦ Date: 2026-06-30 | 150 | 2026-06-30 | 2027-02-14
2200000312 | Main-Connectivity under GNA |  | AUXO SUNLIGHT PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Barmer-I | Rajasthan | 2025-05-26 | 2026-12-30 | Auxo Sunlight Private Limited Solar Power Project – Barmer-I PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 6x500 MVA (4th to 9th), 400/220 kV ICTs at Barmer-I PS Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 400kV Sectionalizer bay (1 set) at Barmer-I S/s Barmer-I PS – Merta-II 765 kV D/c line along with 240 MVAr switchable line reactor at Barmer-I PS end and 330MVAr switchable line reactor at Merta-II PS end for each circuit of Barmer-I PS – Merta-II 765 kV D/c line Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur(PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | Transmission system for Connectivity under GNA: Augmentation of 6x500 MVA (4th to 9th), 400/220 kV ICTs at Barmer-I PS Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 400kV Sectionalizer bay (1 set) at Barmer-I S/s Barmer-I PS – Merta-II 765 kV D/c line along with 240 MVAr switchable line reactor at Barmer-I PS end and 330MVAr switchable line reactor at Merta-II PS end for each circuit of Barmer-I PS – Merta-II 765 kV D/c line Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur(PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | 30-Sep-26 | 30-Sep-26 |  |  | 300 | 217 |  |  |  |  | 2026-12-30 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Sep-26 |  | 2026-09-30 | 2027-06-30
2200000316 | Main-Connectivity under GNA |  | RENEW SUN POWER PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Barmer-I | Rajasthan | 2025-01-23 | 2026-12-30 | Renew Sun power Private Limited RE Power Project – Barmer-I PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 400kV Sectionalizer bay (1 set) at Barmer-I S/s Barmer-I PS – Merta-II 765 kV D/c line along with 240 MVAr switchable line reactor at Barmer-I PS end and 330MVAr switchable line reactor at Merta-II PS end for each circuit of Barmer-I PS – Merta-II 765 kV D/c line Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur(PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur(PG) line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | Transmission system for Connectivity under GNA: Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 400kV Sectionalizer bay (1 set) at Barmer-I S/s Barmer-I PS – Merta-II 765 kV D/c line along with 240 MVAr switchable line reactor at Barmer-I PS end and 330MVAr switchable line reactor at Merta-II PS end for each circuit of Barmer-I PS – Merta-II 765 kV D/c line Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur(PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur(PG) line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | 30-Sep-26 | 30-Sep-26 |  |  | 300 | 221 |  |  |  |  | 2026-12-30 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Sep-26 |  | 2026-09-30 | 2027-06-30
2200000317 | Main-Connectivity under GNA |  | SEVEN RENEWABLE POWER PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 |  | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Bhuj | Gujarat | 2024-03-22 | 2025-07-01 | SRPPL shall share the Dedicated Transmission System for Connectivity being granted to Ayana Renewable Power Four Private Limited (ARP4PL) for Hybrid RE project of 100MW (Connectivity appl. no. 2200000239) as given below • ARP4PL – Bhuj PS 220kV Sc line alongwith associated line bay at generating station (under the scope of applicant) • Bay at ISTS substation shall be implemented under ISTS. [No. 206(AISGIS)] | 0 | 220 KV | Aug without ATS |  |  | Augmentation of transformation capacity at Bhuj-I PS by 1x500MVA, 400220kV ICT (9th) along with associated bays | Augmentation of transformation capacity at Bhuj-I PS by 1x500MVA, 400220kV ICT (9th) along with associated bays | 30-Jun-25 | 30-Jun-25 |  |  | 50 | 206 |  |  |  | 2025-04-01 | 2025-07-02 |  | 2026-01-15 | Not effective | 2026-08-25 | Charged/Physically Completed | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2028-09-23 ¦ Status: Under Implementation ¦ Type: Wind | 01-04-2026 |  |  |  | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2026-01-01
2200000318 | Main-Connectivity under GNA |  | AYANA RENEWABLE POWER FOUR PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 |  | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Ananthapuram | Andhra Pradesh | 2025-03-03 | 2025-09-28 | •Through sharing of dedicated Connectivity transmission system of M/s Project Nine Renewable Power Pvt. Ltd. granted connectivity for application no. 2200000162 i.e. generating Pooling Station of M/s Project Nine Renewable Power Pvt. Ltd. – Ananthapuram PS 220 kV S/c line – all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | 31-Mar-25 | 31-Mar-25 |  |  | 50 | 203 |  |  |  | 2026-03-31 | 2024-07-31 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2026-10-31
2200000319 | Main-Connectivity under GNA |  | AM GREEN ENERGY PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | AM Green Energy Private Limited Solar Power Project – Bikaner-IV PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Establishment of 6x1500 MVA, 765400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) | Transmission system for Connectivity under GNA Establishment of 6x1500 MVA, 765400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV Dc line (Quad) Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end Siwani – Fatehabad (PG) 400 kV Dc line (Quad) Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-May-25 | 31-May-25 |  |  | 300 | 207 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2027-04-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-05-11
2200000320 | Main-Connectivity under GNA |  | AYANA RENEWABLE POWER PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 150 | 0 | 0 | 150 | 0 | 150 |  | Granted | 150 | 0 | 150 | Pavagada | Karnataka | 2025-06-06 | 2026-11-09 | • Generation Pooling Station of Ms Ayana Renewable Power Pvt. Ltd. – Tumkur (Pavagada) PS 220 kV Sc line along with line bay at generation pooling end – under the scope of applicant. • 1 no. 220 kV line bay at Tumkur (Pavagada) PS for termination of above mentioned line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region . Augmentation of 2x500 MVA, 400 220 kV (9th & 10th) ICTs at Tumkur (Pavagada PS). | ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region . Augmentation of 2x500 MVA, 400 220 kV (9th & 10th) ICTs at Tumkur (Pavagada PS). | 30-Jun-25 | 30-Jun-25 |  |  | 150 | 231 |  |  |  |  | 2026-05-20 | 2026-12-31 |  | Not effective | 2026-11-09 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2028-09-23 ¦ Status: Under Implementation ¦ Type: Solar | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2027-05-09
2200000321 | Main-Connectivity under GNA |  | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED | WR | Land BG Route | (vi) Captive generating plant | Hybrid | 362 | 0 | 175 | 187 | 0 | 362 |  | Granted | 362 | 0 | 362 | Bhuj-II (Sec-II) | Gujarat | 2025-06-20 | 2026-12-18 | • ABRSL – Bhuj-II PS 220kV Sc line on Dc tower along with associated bay at Generation end. (Under the scope of applicant). • 1no. 220kV bay at Bhuj-II PS shall be implemented under ISTS scheme “Provision of ICT Augmentation & Bus Reactor at BHUJ-II PS” by Ms PBTL. | 1 | 220 KV | Aug without ATS |  |  | • Augmentation of transformation capacity at Bhuj-II PS by 2x500MVA, 400220kV ICT (5th, 6th & 7th) and by 1x1500MVA, 765400kV ICT (3rd). • Augmentation of transformation capacity at Bhuj-II PS (GIS) by 1x500 MVA, 400220 kV ICT (7th). | • Augmentation of transformation capacity at Bhuj-II PS by 2x500MVA, 400220kV ICT (5th, 6th & 7th) and by 1x1500MVA, 765400kV ICT (3rd). • Augmentation of transformation capacity at Bhuj-II PS (GIS) by 1x500 MVA, 400220 kV ICT (7th). | 31-May-25 | Phase 1 ¦ MW: 362.00 ¦ Date: 2025-05-31 |  |  | 362 | 218 |  |  |  | 2027-03-31 | 2026-11-24 | 2027-06-30 |  | Not effective | 2026-12-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 362.00 ¦ Date: 2027-01-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | Phase 1 ¦ MW: 362.00 ¦ Date: 2025-05-31 | 362 | 2025-05-31 | 2027-06-30
2200000324 | Main-Connectivity under GNA |  | ARCELORMITTAL NIPPON STEEL INDIA LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 550 (Wind 250MWSolar 300MW) | 0 | 300 | 250 | 0 | 550 |  | Granted | 350 | 0 | 350 | Lakadiya | Gujarat | 2025-06-26 | 2026-08-14 | Under the scope of Ms AMNSIL 1. Establishment of AMNSIL Solar PSS. 2. Establishment of AMNSIL Wind PSS. 3. AMNSIL Wind PSS to AMNSIL Solar PSS 220kV Sc line on DC tower. 4. (A) Approx. 6.94km 220kV Sc line on Dc tower from AMNSIL Solar PSS to common sharing tower of Ms RDSSPPL(AP-02) and (B) Approx 18.92km 220kV Sc strung on Dc tower on common sharing tower of Ms RDSSPPL Solar PSS (AP-02)(Appl. No. 2200000639) to Lakadia ISTS PS (under the scope of applicant). Under the scope of ISTS 1. 1 no. 220kV line bay at ISTS substation end is under implementation under ISTS scheme “Augmentation of transformation capacity at 765400kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” by Ms LBPTL. | 1 | 220 KV | Aug without ATS |  |  | • Establishment of 4x500MVA, 400220kV ICTs (3rd to 6th) & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | • Establishment of 4x500MVA, 400220kV ICTs (3rd to 6th) & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | 31-May-25 | 31-May-25 |  |  | 350 | 204 |  |  |  | 2026-08-14 | 2026-08-14 | 2026-08-14 |  | Not effective | 2026-08-14 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 250.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-02-14
2200000333 | Main-Connectivity under GNA |  | FURIES SOLREN PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Furies Solren Private Limited Solar Power Project – Bikaner-IV PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 31-Jan-26 | 31-Jan-26 |  |  | 300 | 219 |  |  |  | 2026-11-11 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  | Yes |  | 08/07/2026 | Pending with Level 2 | 31-Jan-26 |  | 2026-01-31 | 2027-04-30
2200000334 | Main-Connectivity under GNA |  | HAZEL HYBREN PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Hazel Hybren Private Limited Solar Power Project – Bikaner-IV PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 31-Jan-26 | 31-Jan-26 |  |  | 300 | 215 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  | Yes |  | 08/07/2026 | Pending with Level 2 | 31-Jan-26 |  | 2026-01-31 | 2027-04-30
2200000337 | Main-Connectivity under GNA |  | MALAREN SOLAR PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 | 0 | 150 | 0 | 0 | 150 |  | Granted | 150 | 0 | 150 | Jam Khambhaliya | Gujarat | 2025-05-19 | 2026-10-14 | MSPL shall share the connectivity system of 50MW Hybrid RHGS of AEPL (Appl. No. 2200000142) which is detailed below • AEPL – Jam Khambhaliya PS 220kV Sc line (on Dc towers) along with associated bay at generation end (Under scope of Ms AEPL) • 1 no. 220kV line bay at Jam Khambhaliya PS has been implemented under ISTS as part of the pooling station. | 0 | 220 KV | Aug without ATS |  |  | Part A (Network Expansion scheme in Gujarat for drawl of about 3.6 GW load under Phase-I in Jamnagar area, being implemented under ISTS by Ms AESL under TBCB Route) • Establishment of 2x1500 MVA 765400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV Dc | Part A (Network Expansion scheme in Gujarat for drawl of about 3.6 GW load under Phase-I in Jamnagar area, being implemented under ISTS by Ms AESL under TBCB Route) • Establishment of 2x1500 MVA 765400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV Dc line • LILO of Jam Khambhaliya PS – Lakadia 400 kV Dc (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of CGPL – Jetpur 400kV Dc (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad – Bhogat 400kV Dc line (Twin AL-59) at Jam Khambhaliya PS Part B (Augmentation of transformation capacity at Jam Khambhaliya PS (GIS), being implemented under ISTS by POWERGRID under TBCB Route) • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 2x500MVA, 400220kV ICTs (5th & 6th) (terminated on New 220 kV bus section-II) along with associated ICT bays | 30-May-26 | 30-May-26 |  |  | 150 | 207 |  |  |  |  | 2026-10-14 |  |  | Not effective | 2026-10-14 |  | Not commissioned | 0 | [5 empty] | Not Submitted For Approval | 30-May-26 |  | 2026-05-30 | 2027-04-14
2200000339 | Main-Connectivity under GNA |  | KARNATAKA SOLAR POWER DEVELOPMENT CORPORATION LIMITED | SR | Land Route | (x) Renewable Power Park developer | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Pavagada | Karnataka | 2025-06-05 | 2026-05-22 | • Generation Pooling Station of M/s Ayana Renewable Power Pvt. Ltd. – Tumkur (Pavagada) PS 220 kV S/c line along with line bay at generation pooling end – under the scope of applicant. • 1 no. 220 kV line bay at Tumkur (Pavagada) PS for termination of above mentioned line – under the scope of Applicant. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 2x500 MVA, 400/ 220 kV (9th & 10th) ICTs at Tumkur (Pavagada) PS | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 2x500 MVA, 400/ 220 kV (9th & 10th) ICTs at Tumkur (Pavagada) PS | 06-Apr-26 | 06-Apr-26 |  |  | 300 | 230 |  |  |  |  | 2025-05-20 | 2026-12-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-07-15 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 80.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 70.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 06-Apr-26 |  | 2026-04-06 | 2026-12-31
2200000340 | Main-Connectivity under GNA |  | SPRNG VAYU VIDYUT PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 82 |  | 0 | 82 | 0 | 82 |  | Granted | 82 | 0 | 82 | Rajgarh (Sec-II) | Madhya Pradesh | 2024-11-20 | 2027-06-30 | SVVPL in present application shall share the DTL already identified to SVVPL in application no. 2200000022, which is detailed below • SVVPL – Rajgarh (PG) 220kV Sc line along with associated bay at Generator end (Under the scope of applicant) • 220kV GIS line bay at Rajgarh 400220kV (PG) Ss (on extended bus) for RE interconnection (under the scope of ISTS) | 0 | 220 KV | Aug without ATS |  |  | 1. 1x500MVA, 400220kV ICT (4th) at Rajgarh Ss (on the sectionalized 220kV bus) along with associated bays at both ends (400kV AIS & 220kV GIS) ATS (Awarded & Under implementation) 2. 220kV bus extension (GIS) of Rajgarh (PG) 400220 kV Ss along with 2 | 1. 1x500MVA, 400220kV ICT (4th) at Rajgarh Ss (on the sectionalized 220kV bus) along with associated bays at both ends (400kV AIS & 220kV GIS) ATS (Awarded & Under implementation) 2. 220kV bus extension (GIS) of Rajgarh (PG) 400220 kV Ss along with 220kV Bus Coupler Bay for extended bus (under the scope of ISTS) 3. 220kV bus sectionaliser bay (GIS) between existing & extended 220 kV bus of Rajgarh Ss. (under the scope of ISTS). | 30-Jun-27 | 30-Jun-27 |  |  | 82 | 217 |  |  |  |  | 2026-12-31 | 2026-12-31 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 82.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-12-30
2200000341 | Main-Connectivity under GNA |  | RENEW SOLAR (SHAKTI EIGHT) PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 | 0 | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Lakadiya | Gujarat | 2025-06-24 | 2026-09-30 | • RS(S8)PL – Lakadia 220kV Sc line on Dc tower# along with associated bay at generation end (under the scope of applicant) • 1 no. 220kV line bay at ISTS substation end shall be under ISTS scheme “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” by Ms LBPTL. | 1 | 220 KV | Aug without ATS |  |  | • Establishment of 6x500MVA, 400220kV ICTs (3rd to 8th) & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | • Establishment of 6x500MVA, 400220kV ICTs (3rd to 8th) & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | 31-Mar-26 | 31-Mar-26 |  |  | 200 | 205 |  |  |  | 2026-09-30 | 2026-08-14 | 2026-08-14 |  | Not effective | 2026-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-03-30
2200000342 | Main-Connectivity under GNA |  | Oyster Renewable Energy Private Limited (formerly Known as ABENERGIA RENEWABLES PRIVATE LIMITED) | WR | Land BG Route | (vi) Captive generating plant | Hybrid | 81 |  | 67 | 14 | 0 | 81 |  | Granted | 81 | 0 | 81 | Pachora (Sec-I) | Madhya Pradesh | 2024-04-09 | 2026-02-14 | Ms OREPL shall share the DTL identified for Ms Veh Saur Urja Private Limited (VSUPL) in application no. 2200000085 (for 163.2MW) at Pachora PS (at Bay No. 206), which is detailed below • VSUPL – Pachora PS 220kV Sc line (on Dc towers) along with associated bay at Generation end. (Under the scope of applicant). • 220kV bay at Pachora PS has been implemented under ISTS. | 0 | 220 KV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA • Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP • Pachora SEZ PP - Bhopal (Sterlite) 400kV Dc line (QuadTwin HTLS) (with minimum capacity of 2100 MVAckt at nominal voltage) | Common Transmission System Augmentation for Connectivity under GNA • Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP • Pachora SEZ PP - Bhopal (Sterlite) 400kV Dc line (QuadTwin HTLS) (with minimum capacity of 2100 MVAckt at nominal voltage) • 400220 kV, 3x500 MVA ICT augmentation (4th, 5th and 6th) at Pachora PS • Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) | 31/03/2025 (67 MW - Solar, 14MW - Wind) | 31/03/2025 (67 MW - Solar, 14MW - Wind) | 81 | 2026-06-27 |  | 224 |  |  |  |  | 2026-02-14 | 2026-05-30 |  | Effective |  | Under Construction | Part Commissioned | 52.8 | ¦ Phase 1 ¦ MW: 52.80 ¦ Date: 2026-03-25 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 28.20 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31/03/2025 |  | 2025-03-31 | 2026-08-14
2200000343 | Main-Connectivity under GNA |  | Iraax International Private Limited (Formerly known as IRAAX INTERNATIONAL (OPC) PRIVATE LIMITED) | NR | Land Route | (x) Renewable Power Park developer | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Iraax International (Opc) Private Limited Renewable Power Park – Bikaner-IV PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Establishment of 6x1500 MVA, 765400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) | Transmission system for Connectivity under GNA Establishment of 6x1500 MVA, 765400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV Dc line (Quad) Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end Siwani – Fatehabad (PG) 400 kV Dc line (Quad) Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-Mar-26 | 31-Mar-26 |  |  | 300 | 220 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-05-11
2200000344 | Main-Connectivity under GNA |  | CLEAN MAX GAMMA PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Clean Max Gamma Private Limited Renewable Power Park – Bikaner-IV PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 100 MW 25062025200 MW 30122025 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-06-25 Phase 2 ¦ MW: 200.00 ¦ Date: 2025-12-30 |  |  | 300 | 217 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-06-25 | 100 | 2025-06-25 | 2027-05-11
2200000344 | Main-Connectivity under GNA |  | CLEAN MAX GAMMA PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Clean Max Gamma Private Limited Renewable Power Park – Bikaner-IV PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 100 MW 25062025200 MW 30122025 | Phase 1 ¦ MW: 100.00 ¦ Date: 2025-06-25 Phase 2 ¦ MW: 200.00 ¦ Date: 2025-12-30 |  |  | 300 | 217 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 200.00 ¦ Date: 2025-12-30 | 200 | 2025-12-30 | 2027-05-11
2200000345 | Main-Connectivity under GNA |  | BUNDELKHAND SAUR URJA LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 1200 |  | 1200 | 0 | 0 | 1200 |  | Granted | 1200 | 0 | 1200 | Orai | Uttar Pradesh | 2024-05-01 | 2026-12-31 | Bundelkhand Saur Urja Limited Renewable Power Park – Orai (PG) 400 kV S/c (high capacity) line on D/c tower# (Suitable to carry minimum 1200 MW at nominal voltage) | 0 |  | Existing |  |  |  |  | 02-Oct-25 | 02-Oct-25 |  |  | 1200 | 409(Main),408(Tie) | [5 empty] | 2026-12-31 |  | Not effective | 2026-12-31 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 1200.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: |  |  | Transmission System to be checked |  | Pending with Level 2 | 02-Oct-25 |  | 2025-10-02 | 2027-06-30
2200000348 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 900 |  | 900 | 0 | 0 | 900 |  | Granted | 900 | 0 | 900 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-06-05 | 2026-12-30 | NTPC Renewable Energy Limited Solar Power Project– Fatehgarh-IV PS(Sec-II) 400 kV Sc line on Dc tower# (Suitable to carry minimum 900 MW at nominal voltage) | 1 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation with 765400kV, 2x1500MVA Transformer (3rd & 4th ) at Fatehgarh-IV PS (Sec-II) Augmentation with 765400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-IV PS( | Transmission system for Connectivity under GNA Augmentation with 765400kV, 2x1500MVA Transformer (3rd & 4th ) at Fatehgarh-IV PS (Sec-II) Augmentation with 765400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-IV PS(Sec-II) – Bhinmal (PG) 400 kV Dc line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar Dc line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar Dc line (formed after LILO) Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV Dc line (Quad) Establishment of 2x1500 MVA, 765400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV Dc line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV Dc line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Fatehgarh-IV (Sec-II) PS – Sirohi PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta Dc line at Rishabdeo Ss Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end Mandsaur PS–Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line Establishment of 765400 kV (2x1500 MVA Kurawar Ss with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line LILO of Indore – Bhopal 765 kV Sc line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV Dc line at Astha Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line | 31-Mar-26 | 31-Mar-26 |  |  | 900 | 451(Main),452(Tie) |  |  |  | 2026-08-14 | 2026-12-30 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 900.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-06-30
2200000353 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 250 | 0 | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | kallam | Maharashtra | 2024-05-09 | 2026-09-30 | EPL for its another WPP of 50MW as given below: • AEPL – Kallam PS 220kV S/c line along with associated bay at generation end (under the scope of applicant). • 1 no. 220kV line bay at ISTS substation end (under the scope of ISTS). | 0 | 220 kV | Aug without ATS |  |  | LILO of both circuits of Parli(M) – Karjat(M)/ Lonikand-II(M) 400kV D/c line (twin moose) at Kallam PS | LILO of both circuits of Parli(M) – Karjat(M)/ Lonikand-II(M) 400kV D/c line (twin moose) at Kallam PS | 31-12-2024 | 31-12-2024 |  |  | 250 | 213 |  |  |  | 2026-06-30 | 2025-10-05 | 2026-10-30 |  | Not effective | 2026-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2026-10-30
2200000355 | Main-Connectivity under GNA |  | GAMMA RENEWABLES INDIA PROJECT ONE PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-06-05 | 2026-12-30 | Gamma Renewables India Project One Private Limited Renewable Power Park– Barmer-I PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 400kV Sectionalizer bay (1 set) at Barmer-I S/s Barmer-I PS – Merta-II 765 kV D/c line along with 240 MVAr switchable line reactor at Barmer-I PS end and 330MVAr switchable line reactor at Merta-II PS end for each circuit of Barmer-I PS – Merta-II 765 kV D/c line Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur(PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | Transmission system for Connectivity under GNA: Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 400kV Sectionalizer bay (1 set) at Barmer-I S/s Barmer-I PS – Merta-II 765 kV D/c line along with 240 MVAr switchable line reactor at Barmer-I PS end and 330MVAr switchable line reactor at Merta-II PS end for each circuit of Barmer-I PS – Merta-II 765 kV D/c line Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur(PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | 01-Jun-26 | 01-Jun-26 |  |  | 300 | 243 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 01-Jun-26 |  | 2026-06-01 | 2027-06-30
2200000356 | Main-Connectivity under GNA |  | VEH DAMEN POWER PRIVATE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 76.8 |  | 0 | 76.8 | 0 | 76.8 |  | Granted | 76.8 | 0 | 76.8 | Pachora (Sec-II) | Madhya Pradesh | 2024-04-09 | 2026-03-30 | Ms VDPPL shall share the DTL identified for Ms Oyster Renewable Energy Private Limited (OREPL) in application no. 2200000086 (for 100MW) at Pachora PS (at Bay No. 224), which is detailed below • OREPL – Pachora PS 220kV Sc line (on Dc towers) along with associated bay at both Generation & ISTS end (Under the scope of applicant). | 1 | 220 KV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA • Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP • Pachora SEZ PP - Bhopal (Sterlite) 400kV Dc line (QuadTwin HTLS) (with minimum capacity of 2100 MVAckt at nominal voltage) | Common Transmission System Augmentation for Connectivity under GNA • Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP • Pachora SEZ PP - Bhopal (Sterlite) 400kV Dc line (QuadTwin HTLS) (with minimum capacity of 2100 MVAckt at nominal voltage) • 400220 kV, 3x500 MVA ICT augmentation (4th 5th and 6th) at Pachora PS • Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) | 31-Mar-26 | 31-Mar-26 | 76.8 | 2026-06-27 |  | 206 |  |  |  | 2024-04-02 | 2026-02-14 | 2026-05-30 |  | Effective |  | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 26.80 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2026-09-30
2200000358 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 250 | 0 | 250 | 0 | 0 | 250 |  | Granted | 250 | 0 | 250 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Common pooling station for NTPC Renewable Energy Limited RE Power Projects (App No. 2200000244 (150 MW), 2200000308 (700 MW), 2200000373 (400 MW), 2200000358 (250 MW) & 2200000420 (400 MW) – Bikaner-IV PS 400 kV Dc line (Suitable to carry minimum 950 MW per circuit at nominal voltage) – Under applicant scope Connectivity of 250 MW (App No. 2200000358) & 400MW (App No. 2200000420) to NTPCREL is granted in sharing with App. No. 2200000373(400 MW) through same bay and common DTL | 0 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA 1. Establishment of 6x1500 MVA, 765400 kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 2. 400kV Sectionalizer bay (1 set) at Bikaner-IV PS 3. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS 4. LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS 5. Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 6. Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end 7. Siwani – Jind (PG) 400 kV Dc line (Quad) 8. Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end 9. Siwani – Fatehabad (PG) 400 kV Dc line (Quad) 10. Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end 11. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 12. 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore (PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 150 MW 30062026100 MW 30062026 | Phase 1 ¦ MW: 150.00 ¦ Date: 2026-06-30 Phase 2 ¦ MW: 100.00 ¦ Date: 2026-06-30 |  |  | 250 | 435 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 150.00 ¦ Date: 2026-06-30 | 150 | 2026-06-30 | 2027-05-11
2200000358 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 250 | 0 | 250 | 0 | 0 | 250 |  | Granted | 250 | 0 | 250 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Common pooling station for NTPC Renewable Energy Limited RE Power Projects (App No. 2200000244 (150 MW), 2200000308 (700 MW), 2200000373 (400 MW), 2200000358 (250 MW) & 2200000420 (400 MW) – Bikaner-IV PS 400 kV Dc line (Suitable to carry minimum 950 MW per circuit at nominal voltage) – Under applicant scope Connectivity of 250 MW (App No. 2200000358) & 400MW (App No. 2200000420) to NTPCREL is granted in sharing with App. No. 2200000373(400 MW) through same bay and common DTL | 0 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA 1. Establishment of 6x1500 MVA, 765400 kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 2. 400kV Sectionalizer bay (1 set) at Bikaner-IV PS 3. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS 4. LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS 5. Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 6. Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end 7. Siwani – Jind (PG) 400 kV Dc line (Quad) 8. Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end 9. Siwani – Fatehabad (PG) 400 kV Dc line (Quad) 10. Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end 11. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 12. 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore (PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 150 MW 30062026100 MW 30062026 | Phase 1 ¦ MW: 150.00 ¦ Date: 2026-06-30 Phase 2 ¦ MW: 100.00 ¦ Date: 2026-06-30 |  |  | 250 | 435 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 100.00 ¦ Date: 2026-06-30 | 100 | 2026-06-30 | 2027-05-11
2200000360 | Main-Connectivity under GNA |  | PRERAK SOLAR URJA PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 400 |  | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Bhadla-III | Rajasthan | 2026-03-27 |  | Prerak Solar Urja Private Limited Renewable Power Park– Bhadla-III PS 220 kV Sc (high capacity) line on Dc tower# (Suitable to carry minimum 400 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA (7th & 8th), 400220 kV ICT at Bhadla-III PS Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA (7th & 8th), 400220 kV ICT at Bhadla-III PS Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III – Bhadla-III 400kV Dc line Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) Bhadla-III – Bhadla (HVDC) 400 kV 2xDc quad moose line along with the line bays at both substations ±800 kV HVDC line between Bhadla (HVDC) & Fatehpur (HVDC) (with Dedicated Metallic Return) Augmentation of 5x1500 MVA (1st to 5th), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 31-May-25 | 31-May-25 |  |  | 400 | 227 | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2029-07-20 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2029-07-20
2200000372 | Main-Connectivity under GNA |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 160 (Solar:40 MW, Wind: 120 MW) |  | 40 | 120 | 0 | 160 |  | Granted | 160 | 0 | 160 | Ananthapuram | Andhra Pradesh | 2025-12-17 | 2028-02-29 | Through dedicated Connectivity transmission system of Ms Renew Vikram Shakti Pvt. Ltd. granted for application no. 2200000583 for 140 MW) i.e. Generation Pooling Station of Ms Renew Vikram Shakti Pvt. Ltd. – Ananthapuram PS 220 kV Sc line on Dc tower – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (augmentation other than ATS) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmis | Common Transmission system required for effectiveness of connectivityGNA (augmentation other than ATS) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | 29-Feb-28 | 29-Feb-28 |  |  | 160 | 207 |  |  |  | 2026-03-31 | 2025-09-27 | 2026-10-31 |  | Not effective | 2028-02-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 40.00 ¦ Date: 2028-02-29 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 120.00 ¦ Date: 2028-02-29 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 29-Feb-28 |  | 2028-02-29 | 2028-08-29
2200000373 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 400 | 0 | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Common pooling station for NTPC Renewable Energy Limited RE Power Projects (App No. 2200000244 (150 MW), 2200000308 (700 MW), 2200000373 (400 MW), 2200000358 (250 MW) & 2200000420 (400 MW) – Bikaner-IV PS 400 kV Dc line (Suitable to carry minimum 950 MW per circuit at nominal voltage) – under applicant scope Connectivity of 250 MW (App No. 2200000358) & 400MW (App No. 2200000420) to NTPCREL is granted in sharing with App. No. 2200000373(400 MW) through same bay and common DTL. | 1 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA 1. Establishment of 6x1500 MVA, 765400 kV Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 2. 400kV Sectionalizer bay (1 set) at Bikaner-IV PS 3. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS 4. LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS 5. Establishment of 765400 kV, 6x1500 MVA Ss at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 6. Bikaner-IV PS – Siwani 765 kV 2xDc line along with 240 MVAr switchable line reactor for each circuit at each end 7. Siwani – Jind (PG) 400 kV Dc line (Quad) 8. Siwani – Patran (Indi Grid) 400 kV Dc line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani Ss end 9. Siwani – Fatehabad (PG) 400 kV Dc line (Quad) 10. Siwani – Sonipat (PG) 400 kV Dc line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani Ss end 11. STATCOM (2x300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani Ss 12. 400kV Sectionalizer bay (1 set) at at Siwani Ss Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore (PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-Mar-26 | 31-Mar-26 |  |  | 400 | 435 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-05-11
2200000376 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Lakadiya | Gujarat | 2025-06-25 | 2027-06-30 | • JGEPL – Lakadia 220kV Sc line along with associated bay at generation end (under the scope of applicant). • 1 no. 220kV line bay at Lakadia PS was agreed under ISTS scheme. | 1 | 220 KV | Aug without ATS |  |  | Establishment of 6x500MVA, 400220kV ICTs & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | Establishment of 6x500MVA, 400220kV ICTs & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | 30-Jun-28 | 30-Jun-28 |  |  | 300 | 229 |  |  |  | 2027-06-30 | 2027-06-30 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-28 |  | 2028-06-30 | 2028-12-30
2200000379 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 |  | 0 | 200 | 0 | 200 |  | Granted | 200 | 0 | 200 | Jam Khambhaliya | Gujarat | 2024-11-11 | 2028-06-30 | M/s JGEPL shall share the Dedicated Transmission System proposed for M/s JGEPL for its 100MW REGS against application No. 2200000253, as given below: JGEPL – Jam Khambhaliya PS 220kV S/c line (on D/c tower) along with 220kV line bay at generation station (Under the scope of M/s JGEPL). 1 no. 220kV line bay at Jam Khambhaliya PS shall be implemented under ISTS (expected by 30.06.2027). | 0 | 220 kV | Aug without ATS |  |  | Part A: Establishment of 2x1500MVA 765/400kV Jamnagar (GIS) PS Halvad – Jamnagar 765 kV D/c line LILO of Jam Khambhaliya PS – Lakadia 400kV D/c (triple snowbird) line at Jamnagar Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/ AL59 moose equivalent) line LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar LILO of both circuits of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part B: Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 3x500MVA, 400/220kV ICT (5th, 6th & 7th) | Part A: Establishment of 2x1500MVA 765/400kV Jamnagar (GIS) PS Halvad – Jamnagar 765 kV D/c line LILO of Jam Khambhaliya PS – Lakadia 400kV D/c (triple snowbird) line at Jamnagar Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/ AL59 moose equivalent) line LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar LILO of both circuits of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part B: Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 3x500MVA, 400/220kV ICT (5th, 6th & 7th) | 30-Jun-28 | 30-Jun-28 |  |  | 200 | 221 |  |  |  | 2027-06-30 | 2026-10-14 | 2027-06-30 |  | Not effective | 2028-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-28 |  | 2028-06-30 | 2028-12-30
2200000383 | Main-Connectivity under GNA |  | HERO SOLAR ENERGY PRIVATE LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | Solar: 150MW Wind: 150MW BESS: 30MWh |  | 150 | 150 | 27 | 327 | SJVN | Granted | 270 | 0 | 270 | Kurnool-III | Andhra Pradesh | 2024-08-14 | 2026-06-30 | •Common Generation pooling Station of M/s Hero Solar Energy Pvt. Ltd. for application no. 2200000383 (270 MW) and 2200000236 (270 MW)- Kurnool-III PS 220kV S/c line [through stringing of second circuit on 220kV D/c tower of DTL for application no. 2200000236] along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Kurnool-III PS for termination of above mentioned dedicated Connectivity line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B | 30-Jun-26 | 30-Jun-26 |  |  | 270 | 215 | 2026-06-03 |  | for 120MW PPA as submitted by applicant vide email dtd 08.05.2026 |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 150.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 27.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Standalone | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2026-10-31
2200000385 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 250 | 0 | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Gadag-II | Karnataka | 2025-04-03 | 2027-01-17 | Generating Pooling Station of M/s Avaada Energy Pvt. Ltd. – Gadag-II PS 220 kV S/c on D/c tower# along with line bays at generation pooling station –under the scope of applicant. 1 no. 220 kV line bay at Gadag-II PS end for termination of above dedicated transmission line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 30-Sep-25 | 30-Sep-25 |  |  | 250 | 216 |  |  |  | 2026-08-31 | 2027-01-16 | 2027-04-30 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Sep-25 |  | 2025-09-30 | 2027-04-30
2200000387 | Main-Connectivity under GNA |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 600 | 0 | 600 | 0 | 0 | 600 |  | Granted | 600 | 0 | 600 | Fatehgarh-II | Rajasthan | 2025-05-05 | 2026-12-21 | Dedicated Transmission Line (DTL) : Common Pooling Station for Acme Cleantech Solutions Pvt Ltd. (App. No. 2200000387(600 MW) & 2200000396(250 MW)) Solar Power Projects – Fatehgarh-II PS 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW at nominal voltage)# - Under Applicant Scope | 1 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 1. Establishment Augmentation with 765/400kV, 2x1500 MVA Transformer (6th & 7th) at Fatehgarh-II PS 2. Fatehgarh-II PS – Bhadla-II PS 765kV D/c line (2nd) 3. Bhadla-II PS – Sikar-II 765kV D/c line(2nd) 4. Sikar-II – Khetri 765 kV D/c line 5. Sikar-II – Narela 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV D/c line 6. Jhatikara – Dwarka 400kV D/c line (Twin HTLS*) 7. Augmentation of 1x1500 MVA ICT (3rd), 765/400kV ICT at Jhatikara Substation (Bamnoli/Dwarka section) * with minimum capacity of 2100 MVA/ckt at nominal voltage Additional Transmission system for Inter-regional power transfer: 1. Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2. Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3. Mandsaur PS – Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line OR 4. Establishment of 765kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 5. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 6. LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: 1. Establishment Augmentation with 765/400kV, 2x1500 MVA Transformer (6th & 7th) at Fatehgarh-II PS 2. Fatehgarh-II PS – Bhadla-II PS 765kV D/c line (2nd) 3. Bhadla-II PS – Sikar-II 765kV D/c line(2nd) 4. Sikar-II – Khetri 765 kV D/c line 5. Sikar-II – Narela 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV D/c line 6. Jhatikara – Dwarka 400kV D/c line (Twin HTLS*) 7. Augmentation of 1x1500 MVA ICT (3rd), 765/400kV ICT at Jhatikara Substation (Bamnoli/Dwarka section) * with minimum capacity of 2100 MVA/ckt at nominal voltage Additional Transmission system for Inter-regional power transfer: 1. Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2. Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3. Mandsaur PS – Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line OR 4. Establishment of 765kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 5. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 6. LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 31-Mar-26 | 31-Mar-26 |  |  | 600 | 438(Main),437(Tie) | [5 empty] | 2027-02-28 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 320.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 280.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-06-21
2200000388 | Main-Connectivity under GNA |  | FIRST ENERGY PRIVATE LIMITED | SR | Land BG Route | (vi) Captive generating plant | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | NP Kunta | Andhra Pradesh | 2024-08-08 | 2025-09-23 | Through Sharing of dedicated transmission infrastructure of M/s NHPC Ltd. already granted connectivity for application no. 2200000250 (with start date as 30.09.2025) i.e. Generating Pooling Station of M/s NHPC Ltd.– NP Kunta PS 220 kV S/c line along – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (augmentation other than ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 1x500 MVA, 400/220 kV ICT (5th ICT) at N P Kunta | Common Transmission system required for effectiveness of connectivity/GNA (augmentation other than ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 1x500 MVA, 400/220 kV ICT (5th ICT) at N P Kunta | 15-Jun-25 | 15-Jun-25 |  |  | 100 | 221 |  |  |  |  | 2025-09-21 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  |  | Pending with Level 2 | 15-Jun-25 |  | 2025-06-15 | 2026-10-31
2200000389 | Main-Connectivity under GNA |  | CGE RENEWABLES PRIVATE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | Wind: 30 MW Solar: 60 MW |  | 60 | 30 | 0 | 90 |  | Granted | 90 | 0 | 90 | Bhuj-II (Sec-I) | Gujarat | 2025-06-20 | 2026-12-18 | Ms CGERPL shall share the dedicated transmission system for Connectivity granted to Ms Srijan Energy Systems Pvt. Ltd. (SESPL) against appl No. 1200002419 (St-II Conn) as given below • SESPL-Bhuj-II PS 220kV Sc line along with associated bays at generation end (under the scope of the applicant). • Bay at ISTS is existing which was implemented as a part of the PS. • The above line was implemented on Dc Towers (Approx. 25Kms) & Mc Towers (Approx. 2Kms near the ISTS Ss end). | 0 | 220 KV | Aug without ATS |  |  | Under Implementation (under ISTS) 1. Augmentation of transformation capacity at Bhuj-II PS (GIS) (Part System) POWERGRID Bhuj Transmission Limited) (SCOD24-NOV-2026) Augmentation of transformation capacity at Bhuj-II PS (GIS) by 2x5 | Under Implementation (under ISTS) 1. Augmentation of transformation capacity at Bhuj-II PS (GIS) (Part System)POWERGRID Bhuj Transmission Limited) (SCOD24-NOV-2026) Augmentation of transformation capacity at Bhuj-II PS (GIS) by 2x500 MVA, 400220 kV ICT (5th & 6th) and by 1x1500 MVA, 765400 kV ICT (3rd). 2.Provision of ICT Augmentation and Bus Reactor at Bhuj-II PS(Part System) (POWERGRID Bhuj Transmission Limited) (SCOD18-DEC-2026) Augmentation of transformation capacity at Bhuj-II PS (GIS) by 2x500 MVA, 400220 kV ICT (7th & 8th) and by 1x1500 MVA, 765400 kV ICT (4th). | 31-Dec-25 | 31-Dec-25 |  |  | 90 | 207 |  |  |  |  | 2026-12-18 | 2027-06-30 |  | Not effective | 2026-12-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 30.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 60.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2027-06-30
2200000393 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 252 |  | 0 | 252 | 0 | 252 | SJVN | Granted | 252 | 0 | 252 | Bijapur | Karnataka | 2025-04-01 | 2027-01-17 | •Generation Pooling station of Ms Tata Power Renewable Energy Ltd. – Bijapur PS 220 kV Sc line on Dc Tower# along with line bays at generation pooling station – under the scope of applicant. •1 no. 220 kV line bay at Bijapur PS for termination of above dedicated line - under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | 01-Mar-26 | 01-Mar-26 |  |  | 252 | 202 |  |  |  | 2027-01-16 | 2027-01-16 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 252.00 ¦ Date: 2027-02-16 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 01-Mar-26 |  | 2026-03-01 | 2027-03-31
2200000394 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 151 |  | 0 | 151 | 0 | 151 | SJVN | Granted | 151 | 0 | 151 | Pugalur | Tamil Nadu | 2024-06-28 | 2026-03-01 | •Generating Pooling Station of Ms Tata Power Renewable Energy Ltd. – Pugalur Ss 230 kV Sc line on Dc towers# along with line bay at generation pooling station- under the scope of applicant. •1 no. 230 kV line bay at Pugalur Ss for termination of above mentioned dedicated Connectivity line - under the scope of ISTS. | 1 | 230 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 01-Mar-26 | 01-Mar-26 |  |  | 151 | 213 |  |  |  | 2026-08-31 | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 151.00 ¦ Date: 2027-02-01 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 01-Mar-26 |  | 2026-03-01 | 2026-10-31
2200000396 | Main-Connectivity under GNA |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 250 | 0 | 250 | 0 | 0 | 250 | SJVN | Granted | 250 | 0 | 250 | Fatehgarh-II | Rajasthan | 2025-05-05 | 2026-12-21 | Common Pooling Station for Acme Cleantech Solutions Pvt Ltd. (App. No. 2200000387(600 MW) & 2200000396(250 MW)) Solar Power & Hybrid RE Projects – Fatehgarh-II PS 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW at nominal voltage) - Under Applicant Scope | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 1. Establishment Augmentation with 765/400kV, 2x1500 MVA Transformer (6th & 7th) at Fatehgarh-II PS 2. Fatehgarh-II PS – Bhadla-II PS 765kV D/c line (2nd) 3. Bhadla-II PS – Sikar-II 765kV D/c line(2nd) 4. Sikar-II – Khetri 765 kV D/c line 5. Sikar-II – Narela 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV D/c line 6. Jhatikara – Dwarka 400kV D/c line (Twin HTLS*) 7. Augmentation of 1x1500 MVA ICT (3rd), 765/400kV ICT at Jhatikara Substation (Bamnoli/Dwarka section) * with minimum capacity of 2100 MVA/ckt at nominal voltage Additional Transmission system for Inter-regional power transfer: 1. Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2. Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3. Mandsaur PS – Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line OR 4. Establishment of 765kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 5. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 6. LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: 1. Establishment Augmentation with 765/400kV, 2x1500 MVA Transformer (6th & 7th) at Fatehgarh-II PS 2. Fatehgarh-II PS – Bhadla-II PS 765kV D/c line (2nd) 3. Bhadla-II PS – Sikar-II 765kV D/c line(2nd) 4. Sikar-II – Khetri 765 kV D/c line 5. Sikar-II – Narela 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV D/c line 6. Jhatikara – Dwarka 400kV D/c line (Twin HTLS*) 7. Augmentation of 1x1500 MVA ICT (3rd), 765/400kV ICT at Jhatikara Substation (Bamnoli/Dwarka section) * with minimum capacity of 2100 MVA/ckt at nominal voltage Additional Transmission system for Inter-regional power transfer: 1. Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2. Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3. Mandsaur PS – Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line OR 4. Establishment of 765kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 5. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 6. LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 31-Mar-26 | 31-Mar-26 |  |  | 250 | 438(Main),437(Tie) | [5 empty] | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: | 08.07.2026 | Yes |  |  | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-06-30
2200000397 | Main-Connectivity under GNA |  | TEQ GREEN POWER XVI PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 125 |  | 0 | 125 | 0 | 125 | SJVN | Granted | 125 | 0 | 125 | Bijapur | Karnataka | 2025-04-01 | 2027-01-17 | •Generation Pooling station of Ms TEQ Green Power XVI Pvt. Ltd. – Bijapur PS 220 kV Sc line on Dc tower along with line bays at generation pooling station – under the scope of applicant. •1 no. 220 kV line bay at Bijapur PS for termination of above dedicated line - under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | 28-Feb-26 | 28-Feb-26 |  |  | 125 | 204 |  |  |  | 2027-01-16 | 2027-01-16 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 52.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  | Remaining surrender. | 08/07/2026 | Pending with Level 2 | 28-Feb-26 |  | 2026-02-28 | 2027-03-31
2200000402 | Main-Connectivity under GNA |  | Jindal Green Wind 1 Private Limited (Formerly known as JSP GREEN WIND 1 PRIVATE LIMITED) | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Koppal-II | Karnataka | 2025-03-04 | 2025-12-31 | Dedicated connectivity transmission system of M/s M/s JSP Green Wind 1 Pvt. Ltd. granted for application no. 2200000262 (400 MW) i.e. Generation Pooling Station of M/s JSP Green Wind 1 Pvt. Ltd. at Raichur – Koppal-II PS 220 kV D/c line | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | 31-May-25 | 31-May-25 |  |  | 300 | 218 & 224 |  |  |  |  | 2025-12-31 | 2027-03-31 |  | Not effective | 2027-01-16 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-03-31
2200000403 | Main-Connectivity under GNA |  | RENEW SOLAR (SHAKTI EIGHT) PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 | 0 | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Lakadiya | Gujarat | 2025-06-24 | 2026-09-30 | Ms RS(S8)PL shall share the Dedicated Transmission System for Connectivity proposed for its other SPP of 200MW against application no. 2200000341 as given below · RS(S8)PL –Lakadia 220kV Sc line on Dc tower along with associated bay at generation end (under the scope of applicant) 1 no. 220kV line bay at ISTS substation end shall be under ISTS | 0 | 220 KV | Aug without ATS |  |  | Common Transmission System augmentation identified for grant of GNA Under Implementation (under ISTS) “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limi | Common Transmission System augmentation identified for grant of GNA Under Implementation (under ISTS) “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited Establishment of 4x500MVA, 400220kV ICTs (3rd to 6th) & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | 30-Sep-26 | 30-Sep-26 |  |  | 100 | 205 |  |  |  | 2026-09-30 | 2026-08-14 | 2026-08-14 |  | Not effective | 2026-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Sep-26 |  | 2026-09-30 | 2027-03-30
2200000404 | Main-Connectivity under GNA |  | BHOJRAJ DEVELOPERS PRIVATE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | Wind: 160 MW Solar: 26 MW |  | 26 | 160 | 0 | 186 |  | Granted | 186 | 0 | 186 | Pachora (Sec-II) | Madhya Pradesh | 2024-11-11 | 2026-02-14 | BDPL – Pachora PS 220kV Sc line along with 220kV line bay at generation station (Under the scope of Ms BDPL). 1 no. 220kV line bay at Pachora PS shall be implemented under ISTS (as a part of the Rajgarh Phase-II Scheme). | 1 | 220 KV | Aug without ATS |  |  | Phase-I (Commissioned) Establishment of 400220kV, 3x500MVA at Pachora SEZ PP Pachora SEZ PP – Bhopal (Sterlite) 400kV Dc line (quadtwin HLTS) (with minimum capacity of 2100 MVAckt at nominal voltage) Phase-II (SCOD 14.02.2026) 400220kV, 3x500M | Phase-I (Commissioned) Establishment of 400220kV, 3x500MVA at Pachora SEZ PP Pachora SEZ PP – Bhopal (Sterlite) 400kV Dc line (quadtwin HLTS) (with minimum capacity of 2100 MVAckt at nominal voltage) Phase-II (SCOD 14.02.2026) 400220kV, 3x500MVA ICT augmentation (4th 5th & 6th) at Pachora PS. Pachora PS – Ujjain (MPPTCL) 400kV Dc line (quad ACSRAAACAL59 Moose equivalent) | 30-Jun-25 | 30-Jun-25 | 186 | 2026-06-27 |  | 215 |  |  |  | 2026-04-15 | 2026-02-14 | 2026-05-30 |  | Effective |  | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 26.00 ¦ Date: 2026-08-15 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 160.00 ¦ Date: 2026-08-15 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2026-08-14
2200000407 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 1000 |  | 300 | 0 | 0 | 300 | NHPC | Granted | 300 | 0 | 300 | Bhadla-III | Rajasthan | 2026-03-27 |  | Avaada Energy Private Limited Solar Power Project – Bhadla-III PS 220 kV Sc line on Dc tower# (suitable to carry minimum 300 MW at nominal voltage) - under applicant scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA 1. Augmentation of 2x500 MVA (8th & 9th), 400220 kV ICT at Bhadla-III PS 2. Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 3. 765 kV Bhadla-III – Bikaner-III Dc line along with 240 | Transmission system for Connectivity under GNA 1. Augmentation of 2x500 MVA (8th & 9th), 400220 kV ICT at Bhadla-III PS 2. Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS 3. 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end 4. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 5. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III – Bhadla-III 400kV Dc line 6. Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation 7. Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) 8. Bhadla-III – Bhadla (HVDC) 400 kV 2xDc quad moose line along with the line bays at both substations 9. ±800 kV HVDC line between Bhadla (HVDC) & Fatehpur (HVDC) (with Dedicated Metallic Return) 10. Augmentation of 5x1500 MVA (1st to 5th), 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor 11. LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur 12. Augmentation by 1x1500 MVA ICT at 765400kV Kanpur (GIS) substation | 31-Dec-25 | 31-Dec-25 |  |  | 300 | 231 | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2029-06-30 ¦ Status: Under Implementation ¦ Type: Solar |  | Yes |  | 08/07/2026 | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2029-07-20
2200000408 | Main-Connectivity under GNA |  | GREEN INFRA CLEAN SOLAR FARMS PRIVATE LIMITED (Formerly known as GREEN INFRA CLEAN SOLAR FARMS LIMITED) | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 130 |  | 130 | 0 | 0 | 130 |  | Granted | 130 | 0 | 130 | Barmer-II | Rajasthan | 2026-01-19 |  | Green Infra Clean Solar Farms Limited Solar Power Project – Barmer-II PS 220 kV Sc line (Suitable to carry minimum 300 MW at nominal voltage) - under applicant scope | 1 | 220 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA (Tentative) 1. Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 2. LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS 3. Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation 4. Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) 5. Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor 6. LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss 7. ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) Additional Transmission system for connectivity at 220kV level of Barmer-II PS 1. 400220kV, 6x500MVA, ICTs at Barmer-II PS | 01-Jun-27 | 01-Jun-27 |  |  | 130 | N | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 130.00 ¦ Date: 2030-09-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 01-Jun-27 |  | 2027-06-01 | 2030-12-30
2200000409 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 47.2 |  | 0 | 47.2 | 0 | 47.2 |  | Granted | 47.2 | 0 | 47.2 | Solapur Pool (Sec-I) | Maharashtra | 2024-08-21 | 2026-03-20 | Ms SPI7PL shall share Dedicated Transmission System for Connectivity proposed for its other WPP of 50MW against application no. 2200000213 as given below • SPI7PL – Solapur PS 220kV Sc line along with associated bay at generation end (under the scope of the applicant). • 1 no. 220kV line bay at Solapur PS is being implemented under ISTS as part of the pooling station. | 0 | 220 KV | Aug without ATS |  |  | • Establishment of 400220 kV, 4x500 MVA ICTs at Solapur PS. • Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAAACAL59 moose equivalent) | • Establishment of 400220 kV, 4x500 MVA ICTs at Solapur PS. • Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAAACAL59 moose equivalent) | 31-Dec-25 | 31-Dec-25 |  |  | 47.2 | 202 |  |  |  | 2026-06-30 | 2026-03-20 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 47.20 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2026-10-30
2200000410 | Main-Connectivity under GNA |  | GREEN INFRA RENEWABLE PROJECTS LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 600 |  | 600 | 0 | 0 | 600 |  | Granted | 600 | 0 | 600 | Barmer-I | Rajasthan | 2025-01-23 | 2027-06-01 | Green Infra Renewable Projects Limited Solar Power Project – Barmer-I PS 220 kV D/c line (Suitable to carry minimum 300 MW per circuit at nominal voltage) - under applicant scope | 2 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA (Tentative): 1. Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS 2. Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS 3. Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) 4. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 5. Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end 6. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 7. Establishment of 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 8. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 9. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 10. LILO of one circuit of 765 kV Chittorgarh-Banaskantha D/c line at Rishabdeo S/s 11. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 12. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 13. Establishment of 765/400 kV 2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 14. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 15. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 17. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 18. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 19. Establishment of 765/400 kV, 2x1500 MVA & 2x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s 20. STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 21. 400kV Sectionalizer bay (1 set) at Barmer-I S/s 22. Barmer-I PS – Merta-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end of Barmer-I PS – Merta-II 765 kV D/c line 23. Merta-II – Beawar 400 kV D/c line (Quad) 24. Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line 25. Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) 26. Dausa - Ghiror 765 kV D/c line along with 330MVAr switchable line reactor at Ghiror end and 240 MVAr switchable line reactor at Dausa end for each circuit of Dausa - Ghiror 765 kV D/c line 27. LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line 28. LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV 2xS/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 29. 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | Transmission system for Connectivity under GNA (Tentative): 1. Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS 2. Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS 3. Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) 4. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 5. Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end 6. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 7. Establishment of 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 8. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 9. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 10. LILO of one circuit of 765 kV Chittorgarh-Banaskantha D/c line at Rishabdeo S/s 11. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 12. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 13. Establishment of 765/400 kV 2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 14. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 15. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 17. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 18. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 19. Establishment of 765/400 kV, 2x1500 MVA & 2x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s 20. STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 21. 400kV Sectionalizer bay (1 set) at Barmer-I S/s 22. Barmer-I PS – Merta-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end of Barmer-I PS – Merta-II 765 kV D/c line 23. Merta-II – Beawar 400 kV D/c line (Quad) 24. Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line 25. Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) 26. Dausa - Ghiror 765 kV D/c line along with 330MVAr switchable line reactor at Ghiror end and 240 MVAr switchable line reactor at Dausa end for each circuit of Dausa - Ghiror 765 kV D/c line 27. LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line 28. LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV 2xS/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 29. 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | 01-Jun-27 | 01-Jun-27 |  |  | 600 | 227,229 |  |  |  |  | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 600.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 01-Jun-27 |  | 2027-06-01 | 2027-12-01
2200000411 | Main-Connectivity under GNA |  | ENFINITY GLOBAL SURYA KIRAN PRIVATE LIMITED | NR | Land Route | (x) Renewable Power Park developer | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Barmer-I | Rajasthan | 2025-01-23 | 2026-12-30 | Enfinity Global Surya Kiran Private Limited Renewable Power Park– Barmer-I PS 220 kV S/c line on D/c tower# (suitable to carry minimum 300 MW at nominal voltage) - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  |  |  | 30-Jun-26 | 30-Jun-26 |  |  | 300 | 231 |  |  |  |  | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-04-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-06-30
2200000412 | Main-Connectivity under GNA |  | EG Mega Urja Private Limited (Formerly knwon as Andhra Pradesh Resco Rooftop Solar Private Limited) | NR | Land Route | (x) Renewable Power Park developer | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Barmer-I | Rajasthan | 2025-01-23 | 2026-12-30 | EG Mega Urja Private Limited Renewable Power Park – Barmer-I PS 220 kV S/c line on D/c towers# (Suitable to carry minimum 300 MW at nominal voltage) - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 1. Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS 2. Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS 3. Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) 4. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 5. Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end 6. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 7. Establishment of 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 8. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 9. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 10. LILO of one circuit of 765 kV Chittorgarh-Banaskantha D/c line at Rishabdeo S/s 11. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 12. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 13. Establishment of 765/400 kV 2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 14. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 15. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 17. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 18. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 19. Establishment of 765/400 kV, 2x1500 MVA & 2x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s 20. STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 21. 400kV Sectionalizer bay (1 set) at Barmer-I S/s 22. Barmer-I PS – Merta-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end of Barmer-I PS – Merta-II 765 kV D/c line 23. Merta-II – Beawar 400 kV D/c line (Quad) 24. Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line 25. Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) 26. Dausa - Ghiror 765 kV D/c line along with 330MVAr switchable line reactor at Ghiror end and 240 MVAr switchable line reactor at Dausa end for each circuit of Dausa - Ghiror 765 kV D/c line 27. LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line 28. LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV 2xS/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 29. 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | Transmission system for Connectivity under GNA: 1. Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS 2. Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS 3. Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) 4. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 5. Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end 6. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 7. Establishment of 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 8. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 9. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 10. LILO of one circuit of 765 kV Chittorgarh-Banaskantha D/c line at Rishabdeo S/s 11. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 12. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 13. Establishment of 765/400 kV 2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 14. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 15. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 17. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 18. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 19. Establishment of 765/400 kV, 2x1500 MVA & 2x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s 20. STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 21. 400kV Sectionalizer bay (1 set) at Barmer-I S/s 22. Barmer-I PS – Merta-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end of Barmer-I PS – Merta-II 765 kV D/c line 23. Merta-II – Beawar 400 kV D/c line (Quad) 24. Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line 25. Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) 26. Dausa - Ghiror 765 kV D/c line along with 330MVAr switchable line reactor at Ghiror end and 240 MVAr switchable line reactor at Dausa end for each circuit of Dausa - Ghiror 765 kV D/c line 27. LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line 28. LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV 2xS/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 29. 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | 30-Jun-26 | 30-Jun-26 |  |  | 300 | 233 |  |  |  |  | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-06-30
2200000414 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 1204(Solar:563 MW; Wind: 641) |  | 0 | 550 | 0 | 550 |  | Granted | 550 | 0 | 550 | Gadag-II | Karnataka | 2025-04-15 | 2027-01-17 | •Generating Pooling Station of M/s Serentica Renewables India Private Limited – Gadag-II PS 400 kV S/c line on D/c tower along with line bays at generation pooling station – under the scope of applicant. •1 no. 400 kV line bay at ISTS end for termination of dedicated line – under the scope of ISTS | 1 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 30-Jun-26 | 30-Jun-26 |  |  | 550 | 416M & 417T |  |  |  |  | 2027-01-16 | 2027-04-30 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 550.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-07-17
2200000419 | Main-Connectivity under GNA |  | FURIES SOLREN PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bikaner-IV | Rajasthan | 2025-06-17 | 2027-02-05 | Furies Solren Private Limited Solar Power Project– Bikaner-IV PS 220 kV S/c line D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 31-Jan-26 | 31-Jan-26 |  |  | 300 | 227 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Jan-26 |  | 2026-01-31 | 2027-08-05
2200000420 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 1000 | 0 | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Common pooling station for NTPC Renewable Energy Limited Solar Power Projects (App No. 2200000244 (150 MW), 2200000308 (700 MW), 2200000373 (400 MW), 2200000358 (250 MW) & 2200000420 (400 MW) – Bikaner-IV PS 400 kV D/c line (Suitable to carry minimum 950 MW per circuit at nominal voltage) – under applicant scope | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 600MW 30062026400 MW 30062026 | Phase 1 ¦ MW: 600.00 ¦ Date: 2026-06-30 Phase 2 ¦ MW: 400.00 ¦ Date: 2026-06-30 |  |  | 400 | 432,435 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 600.00 ¦ Date: 2026-06-30 | 600 | 2026-06-30 | 2027-05-11
2200000420 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 1000 | 0 | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Bikaner-IV | Rajasthan | 2025-01-16 | 2026-11-11 | Common pooling station for NTPC Renewable Energy Limited Solar Power Projects (App No. 2200000244 (150 MW), 2200000308 (700 MW), 2200000373 (400 MW), 2200000358 (250 MW) & 2200000420 (400 MW) – Bikaner-IV PS 400 kV D/c line (Suitable to carry minimum 950 MW per circuit at nominal voltage) – under applicant scope | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: Establishment of 6x1500 MVA, 765/400 Bikaner-IV Pooling Station along with 2x240 MVAr (765kV) & 2x125 MVAr (420kV) Bus Reactors at a suitable location near Bikaner 400kV Sectionalizer bay (1 set) at Bikaner-IV PS STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Bikaner-IV PS LILO of both ckts of 400kV Bikaner II PS- Bikaner III PS (Quad) direct line at Bikaner-IV PS Establishment of 765/400 kV, 6x1500 MVA S/s at suitable location near Siwani (Distt. Bhiwani) along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Bikaner-IV PS – Siwani 765 kV 2xD/c line along with 240 MVAr switchable line reactor for each circuit at each end Siwani – Jind (PG) 400 kV D/c line (Quad) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) along with 80 MVAr switchable line reactor for each circuit at Siwani S/s end Siwani – Fatehabad (PG) 400 kV D/c line (Quad) Siwani – Sonipat (PG) 400 kV D/c line (Quad) along with 63 MVAr switchable line reactor for each circuit at Siwani S/s end STATCOM (2x±300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Siwani S/s 400kV Sectionalizer bay (1 set) at at Siwani S/s Additional Transmission system for Inter-regional power transfer: Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line OR 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 600MW 30062026400 MW 30062026 | Phase 1 ¦ MW: 600.00 ¦ Date: 2026-06-30 Phase 2 ¦ MW: 400.00 ¦ Date: 2026-06-30 |  |  | 400 | 432,435 |  |  |  | 2027-03-31 | 2026-11-11 | 2027-04-30 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 400.00 ¦ Date: 2026-06-30 | 400 | 2026-06-30 | 2027-05-11
2200000422 | Main-Connectivity under GNA |  | HERO SOLAR ENERGY PRIVATE LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | Solar: 188MW Wind: 201 MW BESS: 30MWh |  | 188 | 201 | 38 | 427 | SJVN | Granted | 300 | 0 | 300 | Bidar | Karnataka | 2025-03-28 | 2026-12-31 | •Generation Pooling Station of M/s Hero Solar Energy Private Limited – Bidar PS 220 kV S/c line along with line bay at generation pooling station –under the scope of applicant. •1 no. 220 kV line bay at Bidar PS end for termination of dedicated line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | 31-Dec-26 | 31-Dec-26 |  |  | 300 | 202 |  |  |  | 2026-06-30 | 2026-02-09 | 2026-10-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 188.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 201.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 38.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Standalone | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2026-12-31
2200000425 | Main-Connectivity under GNA |  | HINDUJA RENEWABLES ENERGY PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 250 |  | 250 | 0 | 0 | 250 | NHPC | Granted | 250 | 0 | 250 | Barmer-I | Rajasthan | 2025-01-23 | 2026-12-30 | Hinduja Renewables Energy Private Ltd Solar Power Project – Barmer-I PS 220 kV S/c line on D/c towers# (Suitable to carry minimum 300 MW at nominal voltage) - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 1. Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS 2. Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS 3. Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) 4. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 5. Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end 6. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 7. Establishment of 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 8. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 9. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 10. LILO of one circuit of 765 kV Chittorgarh-Banaskantha D/c line at Rishabdeo S/s 11. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 12. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 13. Establishment of 765/400 kV 2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 14. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 15. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 17. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 18. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 19. Establishment of 765/400 kV, 2x1500 MVA & 2x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s 20. STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 21. 400kV Sectionalizer bay (1 set) at Barmer-I S/s 22. Barmer-I PS – Merta-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end of Barmer-I PS – Merta-II 765 kV D/c line 23. Merta-II – Beawar 400 kV D/c line (Quad) 24. Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line 25. Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) 26. Dausa - Ghiror 765 kV D/c line along with 330MVAr switchable line reactor at Ghiror end and 240 MVAr switchable line reactor at Dausa end for each circuit of Dausa - Ghiror 765 kV D/c line 27. LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line 28. LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV 2xS/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 29. 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | Transmission system for Connectivity under GNA: 1. Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS 2. Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS 3. Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) 4. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 5. Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end 6. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 7. Establishment of 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 8. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 9. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 10. LILO of one circuit of 765 kV Chittorgarh-Banaskantha D/c line at Rishabdeo S/s 11. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 12. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 13. Establishment of 765/400 kV 2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 14. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 15. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 17. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 18. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 19. Establishment of 765/400 kV, 2x1500 MVA & 2x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s 20. STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 21. 400kV Sectionalizer bay (1 set) at Barmer-I S/s 22. Barmer-I PS – Merta-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end of Barmer-I PS – Merta-II 765 kV D/c line 23. Merta-II – Beawar 400 kV D/c line (Quad) 24. Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line 25. Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) 26. Dausa - Ghiror 765 kV D/c line along with 330MVAr switchable line reactor at Ghiror end and 240 MVAr switchable line reactor at Dausa end for each circuit of Dausa - Ghiror 765 kV D/c line 27. LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line 28. LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV 2xS/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 29. 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | 07-Mar-26 | 07-Mar-26 |  |  | 250 | 223 |  |  |  |  | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: |  | Yes |  | 08/07/2026 | Pending with Level 2 | 07-Mar-26 |  | 2026-03-07 | 2027-06-30
2200000428 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 100 | 200 | 0 | 300 |  | Granted | 300 | 0 | 300 | Mandsaur (Sec-I) | Madhya Pradesh | 2024-11-11 | 2028-06-30 |  | 1 | 220 kV | Aug without ATS |  |  |  |  | 30-Jun-28 | 30-Jun-28 |  |  | 300 | 202 |  |  |  | 2027-03-31 | 2026-10-15 | 2027-06-30 |  | Not effective | 2028-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-28 |  | 2028-06-30 | 2028-12-30
2200000429 | Main-Connectivity under GNA |  | TEQ GREEN POWER XVI PRIVATE LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Wind | 175 |  | 0 | 175 | 0 | 175 | SJVN | Granted | 175 | 0 | 175 | Bijapur | Karnataka | 2025-04-01 | 2027-01-17 | • Through dedicated connectivity transmission system of M/s TEQ Green Power XVI Pvt. Ltd. granted connectivity for 125 MW (application no. 2200000397) at Bijapur PS i.e. Generating Pooling Station of M/s TEQ Green Power XVI Private Limited – Bijapur PS 220 kV S/c line on D/c tower – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | 31-Mar-26 | 31-Mar-26 |  |  | 175 | 204 |  |  |  | 2027-01-16 | 2027-01-16 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 175.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-03-31
2200000434 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 350 |  | 0 | 350 | 0 | 350 | REMCL | Granted | 350 | 0 | 350 | Gadag-II | Karnataka | 2025-05-07 | 2027-01-17 | •Generating Pooling Station of M/s NTPC Renewable Energy Limited – Gadag-II PS 220 kV S/c line on D/c tower along with line bays at generation pooling station – under the scope of applicant. •1 no. 220 kV line bay at ISTS end for termination of dedicated line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 28-Jun-25 | 28-Jun-25 |  |  | 350 | 219 |  |  |  | 2026-07-31 | 2027-01-16 | 2027-04-30 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 300.00 ¦ Date: 2027-01-17 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 | Yes |  | 21/07/2026 | Pending with Level 2 | 28-Jun-25 |  | 2025-06-28 | 2027-04-30
2200000435 | Main-Connectivity under GNA |  | GREEN INFRA RENEWABLE PROJECTS LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Gadag-II | Karnataka | 2025-04-03 | 2027-06-02 | Generation Pooling Station of M /s Green Infra Renewable projects Ltd-Gadag-II PS 220 kV S/c line on D/c tower along with line bay at generation pooling station-under the scope of applicant. 1 no. 220 kV line bay at Gadag-II PS for termination of dedicated line-under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka • System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 01-Jun-27 | 01-Jun-27 |  |  | 300 | 225 |  |  |  | 2027-06-01 | 2027-01-16 | 2027-04-30 |  | Not effective | 2027-06-02 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 01-Jun-27 |  | 2027-06-01 | 2027-12-02
2200000437 | Main-Connectivity under GNA |  | GREEN INFRA CLEAN WIND PRIVATE LIMITED (Formerly known as GREEN INFRA CLEAN WIND LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bhadla-II | Rajasthan | 2025-03-05 | 2027-06-01 | Through sharing of dedicated transmission system of Ms Azure Power India Pvt. Ltd. (650 MW) (App. No. – 1200003586, 1200003587 & 1200003843)– Bhadla-II PS 400 kV Sc line (Suitable to carry minimum 1000 MW at nominal voltage) | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA 1. Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station 2. Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II Substation) with 1x125 MVAr at 4 | Transmission system for Connectivity under GNA 1. Augmentation of 2x1500 MVA, 765400 kV ICT (4th & 5th) at Bhadla-II Pooling station 2. Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Sikar (Sikar-II Substation) with 1x125 MVAr at 400kV level & 2x330 MVAr bus reactors at 765kV level at Sikar -II 3. Bhadla-II PS – Sikar-II 765kV Dc line (2nd) 4. Sikar-II – Khetri 765 kV Dc line 5. Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line 6. Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) 7. Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) *minimum 2100 MVA per ckt at nominal voltage Additional Transmission system for Inter-regional power transfer 1. Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2. Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3. Mandsaur PS – Indore (PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV Dc Line OR 4. Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 5. Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 6. LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 01-Jun-27 | 01-Jun-27 |  |  | 300 | 412(Main),411(Tie) |  |  |  |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-01 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 01-Jun-27 |  | 2027-06-01 | 2027-12-01
2200000438 | Main-Connectivity under GNA |  | Jindal Green Wind 1 Private Limited (Formerly known as JSP GREEN WIND 1 PRIVATE LIMITED) | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Karur | Tamil Nadu | 2024-06-28 | 2025-12-25 | •Generation Pooling Station of M/s JSP Green Wind 1 Pvt. Ltd – Karur PS 230 kV S/c line on D/c tower# along with line bay at generation pooling station – under the scope of applicant. •1 no. 230 kV line bay at Karur PS for termination of dedicated line – under the scope of ISTS. | 1 | 230 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-May-25 | 31-May-25 |  |  | 300 | 208 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2026-10-31
2200000440 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 16 PRIVATE LIMITED | WR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | Wind - 191.4 MW, Solar - 56 MW, BESS - 91 MW) |  | 56 | 191.4 | 91 | 338.4 | SJVN | Granted | 150 | 0 | 150 | Solapur Pool (Sec-I) | Maharashtra | 2024-08-21 | 2026-04-01 | Ms SPI16PL shall share Dedicated Transmission System for Connectivity proposed for its other WPP of 50MW against application no. 2200000213 as given below • SPI7PL – Solapur PS 220kV Sc line along with associated bay at generation end (under the scope of the applicant). • 1 no. 220kV line bay at Solapur PS is being implemented under ISTS as part of the pooling station. | 0 | 220 KV | Aug without ATS |  |  | • Establishment of 400220 kV, 4x500 MVA ICTs at Solapur PS. • Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAAACAL59 moose equivalent) | • Establishment of 400220 kV, 4x500 MVA ICTs at Solapur PS. • Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAAACAL59 moose equivalent) | 01-Apr-26 | 01-Apr-26 |  |  | 150 | 202 | 2026-07-30 |  | As per PPA signed between SPI16PL & SJVN, SCOD of generation project is 13.05.2026.SJVN provided further extension upto 30.07.2026 | 2026-08-31 | 2026-03-20 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 105.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 211.20 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 100.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Standalone | 09-07-2026 | Yes |  | 09/07/2026 | Pending with Level 2 | 01-Apr-26 |  | 2026-04-01 | 2026-10-31
2200000441 | Main-Connectivity under GNA |  | FIRST ENERGY PRIVATE LIMITED | SR | Land BG Route | (vi) Captive generating plant | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Karur | Tamil Nadu | 2025-03-20 | 2025-09-12 | Through dedicated connectivity transmission system of M/s JWS Neo Energy Ltd. [erstwhile JSW Future Energy Ltd.] granted connectivity for 150 MW (application no. 12000003212) at Karur PS i.e. Generating Pooling Station of M/s JSW Future Energy Ltd – Karur PS 230 kV S/c line – all arrangement under the scope of applicant | 1 | 230 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for evacuation of power from RE sources in Karur/ Tirpur wind Energy Zone (Tamil Nadu) (1000 MW) under Phase-II | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for evacuation of power from RE sources in Karur/ Tirpur wind Energy Zone (Tamil Nadu) (1000 MW) under Phase-II | 30-Jun-25 | 30-Jun-25 |  |  | 100 | 203 |  |  | First Energy representative informed that 14/17 locations have been acquired. |  | 2026-02-28 | 2027-01-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2027-01-31
2200000444 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 | 0 | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Bhuj-II (Sec-II) | Gujarat | 2025-06-06 | 2026-12-18 | • AEPL – Bhuj-II PS (Section-II) 220kV Sc line (On Dc towers) (# refer Note-A) along with 220kV line bay at generation end (Under the scope of applicant) • 220kV line bay at Bhuj-II PS is under implementation under ISTS scheme “Provision of ICT Augmentation & Bus Reactor at BHUJ-II PS” by Ms PBTL | 1 | 220 KV | Aug without ATS |  |  | A. Under Implementation (under ISTS) 1. Augmentation of transformation capacity at Bhuj-II PS (GIS) (Part System) POWERGRID Bhuj Transmission Limited) (SCOD24-NOV-2026) • Augmentation of transformation capacity at Bhuj-II PS (GIS) by 2x500 MVA, 400 | A. Under Implementation (under ISTS) 1. Augmentation of transformation capacity at Bhuj-II PS (GIS) (Part System) POWERGRID Bhuj Transmission Limited) (SCOD24-NOV-2026) • Augmentation of transformation capacity at Bhuj-II PS (GIS) by 2x500 MVA, 400220 kV ICT (5th & 6th) and by 1x1500 MVA, 765400 kV ICT (3rd). 2. Provision of ICT Augmentation and Bus Reactor at Bhuj-II PS(Part System) (POWERGRID Bhuj Transmission Limited) (SCOD18-DEC-2026) • Augmentation of transformation capacity at Bhuj-II PS (GIS) by 2x500 MVA, 400220 kV ICT (7th & 8th) and by 1x1500 MVA, 765400 kV ICT (4th). | 31-Mar-26 | 31-Mar-26 |  |  | 100 | 219 | 2026-03-31 | 2027-05-30 | PPA signed with SECI for 300MW w.e.f. 31.03.2024. As per PPA revised SCOD is 31.03.2026. SECI wide letter dated 23.07.2025 provided further extension till “60 days subsequent to the reediness of the Delivery point and Power evacuation infrastructure and/or Opr. of GNA” | 2027-03-31 | 2026-12-18 | 2027-06-30 |  | Not effective | 2026-12-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-05-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-06-30
2200000445 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 | 0 | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Jam Khambhaliya | Gujarat | 2024-11-22 | 2026-10-14 | AEPL in present application shall share the DTL already identified to AEPL in application no. 2200000142, which is detailed below: • AEPL – Jam Khambhaliya PS 220kV S/c line along with associated bay at generation end (Under scope of M/s AEPL) • 1 no. 220kV line bay at Jam Khambhaliya PS has been implemented under ISTS as part of the pooling station. | 0 | 220 kV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA Part-A • Establishment of 2x1500 MVA 765/400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV D/c line • LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part-B • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 3x500MVA, 400/220kV ICT (5th, 6th & 7th) | Common Transmission System Augmentation for Connectivity under GNA Part-A • Establishment of 2x1500 MVA 765/400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV D/c line • LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part-B • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 3x500MVA, 400/220kV ICT (5th, 6th & 7th) | 30-Sep-25 | 30-Sep-25 |  |  | 100 | 207 |  |  |  |  | 2026-10-14 | 2027-09-30 |  | Not effective | 2026-10-14 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Sep-25 |  | 2025-09-30 | 2027-09-30
2200000447 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 50.4 |  | 0 | 50.4 | 0 | 50.4 | SJVN | Granted | 50.4 | 0 | 50.4 | Bijapur | Karnataka | 2025-04-01 | 2027-01-17 | Through dedicated connectivity transmission system of M/s Tata Power Renewable Energy Ltd. granted connectivity for 252 MW (application no. 2200000393) at Bijapur PS i.e. Generating Pooling Station of M/s Tata Power Renewable Energy Ltd.– Bijapur PS 220 kV S/c line – all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | 01-Mar-26 | 01-Mar-26 |  |  | 50.4 | 202 |  |  |  | 2027-01-16 | 2027-01-16 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.40 ¦ Date: 2027-02-16 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 01-Mar-26 |  | 2026-03-01 | 2027-03-31
2200000448 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 93.6 |  | 0 | 93.6 | 0 | 93.6 | SJVN | Granted | 93.6 | 0 | 93.6 | Karur | Tamil Nadu | 2024-08-08 | 2026-03-01 | •Through dedicated connectivity transmission system of M/s Tata Power Renewable Energy Ltd. granted connectivity for 198 MW (application no. 2200000242) at Karur PS i.e. Generating Pooling Station of M/s Tata Power Renewable Energy Ltd.–Karur PS 230 kV S/c line – all arrangement under the scope of applicant. | 0 | 230 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for evacuation of power from RE sources in Karur/ Tirpur wind Energy Zone (Tamil Nadu) (1000 MW) under Phase-II | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for evacuation of power from RE sources in Karur/ Tirpur wind Energy Zone (Tamil Nadu) (1000 MW) under Phase-II | 01-Mar-26 | 01-Mar-26 |  |  | 93.6 | 207 | 2026-05-02 | 2026-11-02 | As per PPA submitted vide email |  | 2025-09-11 | 2027-01-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 93.60 ¦ Date: 2026-09-01 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 01-Mar-26 |  | 2026-03-01 | 2027-01-31
2200000449 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 151.2 |  | 0 | 151.2 | 0 | 151.2 | SJVN | Granted | 151.2 | 0 | 151.2 | Pugalur | Tamil Nadu | 2024-06-28 | 2026-03-01 | •Through dedicated connectivity transmission system of Ms Tata Power Renewable Energy Ltd. granted connectivity for 151 MW (application no. 2200000394) at Pugalur Ss i.e. Generating Pooling Station of Ms Tata Power Renewable Energy Ltd.–Pugalur SS 230 kV Sc line on Dc tower# – all arrangement under the scope of applicant. | 0 | 230 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 01-Mar-26 | 01-Mar-26 |  |  | 151.2 | 213 |  |  |  | 2026-08-31 | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 151.20 ¦ Date: 2027-02-01 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 01-Mar-26 |  | 2026-03-01 | 2026-10-31
2200000450 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 100.8 |  | 0 | 100.8 | 0 | 100.8 | SJVN | Granted | 100.8 | 0 | 100.8 | kallam | Maharashtra | 2024-09-19 | 2026-03-01 | Ms TPREL shall share the DTL for Connectivity granted to Ms TSPPL for its WPP of 66MW (appl. No. 1670224223993) as given below TSPPL – Kallam PS 400kV Sc line along with associated bay at generation end (under the scope of TSPPL). 1 no. 400kV line bay at ISTS substation end (under the scope of ISTS). | 0 | 400 KV | Aug without ATS |  |  | LILO of both circuits of Parli(M) – Karjat(M) Lonikand-II(M) 400kV Dc line (twin moose) at Kallam PS. | LILO of both circuits of Parli(M) – Karjat(M) Lonikand-II(M) 400kV Dc line (twin moose) at Kallam PS. | 01-Mar-26 | 01-Mar-26 |  |  | 100.8 | 421 |  |  |  | 2025-03-31 | 2025-10-05 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.80 ¦ Date: 2026-08-01 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 01-Mar-26 |  | 2026-03-01 | 2026-10-30
2200000452 | Main-Connectivity under GNA |  | PRAVAT RENEWABLES INDIA PROJECT PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ramgarh | Rajasthan | 2026-07-06 |  | • Pravat Renewables India Project Pvt. Ltd. Renewable Power Park – Ramgarh PS 220 kV Sc line on Dc tower# (suitable to carry minimum 300 MW at nominal voltage)-Under Applicant Scope • Implementation of 1 No. of 220 kV Bay at Ramgarh PS is under ISTS Scope | 1 | 220 KV | Aug without ATS |  |  | A. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part B1- Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 3x500 MVA , 400220 kV pooling station at Bhadla-3 along with 2x330 MVAr (765kV) Bus Reactor & 2x1 | A. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part B1- Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 3x500 MVA , 400220 kV pooling station at Bhadla-3 along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 2. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line B. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part C1 - Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 2x500 MVA, 400220 kV pooling station at Ramgarh along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus reactor 2. Ramgarh PS – Bhadla-III PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Ramgarh end C. Additional Transmission system for evacuation of power from Bhadla-III PS as part of Rajasthan REZ Phase-III scheme (20 GW) 1. Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS D. Transmission system strengthening for interconnections of Bhadla-III & Bikaner-III complex 1. Bhadla-III – Bikaner-III 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end as well as associated 2 Nos. of 765kV line bay(s) at each at Bhadla-III & Bikaner-III end E. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part A3 1. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III–Bhadla-III 400kV Dc line F. Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under Phase-III Part I 1. Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation 2. Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) 3. Bhadla-III – Bhadla (HVDC) 400 kV 2xDc line (Quad) along with the line bays at both substations 4. ±800 kV HVDC line (Hexa Lapwing) between Bhadla (HVDC) & Fatehpur (HVDC) (with Dedicated Metallic Return) 5. Augmentation of 5x1500 MVA, 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor 6. LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur G. Augmentation at Bhadla-III, Ramgarh PS and Kanpur (PG) 1. Augmentation of 765400kV, 1x1500 MVA (3rd) ICT at 765400kV Kanpur (PG) substation | 01-May-28 | 01-May-28 |  |  | 300 | 204 | [7 empty] | Not effective | 2029-07-20 |  | Not commissioned | 0 | [5 empty] | Not Submitted For Approval | 01-May-28 |  | 2028-05-01 | 2028-11-01
2200000458 | Main-Connectivity under GNA |  | GANEKO SOLAR PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 337.36 |  | 241.66 | 95.7 | 0 | 337.36 |  | Granted | 290 | 0 | 290 | Lakadiya | Gujarat | 2025-07-15 | 2026-12-31 | • GSPL –Lakadia 220kV Sc line on Dc tower along with associated bay at generation end (under the scope of applicant) • 1 no. 220kV line bay at ISTS substation end under ISTS (as per request of applicant). | 1 | 220 KV | Aug without ATS |  |  | Establishment of 5x500MVA, 400220kV ICTs & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | Establishment of 5x500MVA, 400220kV ICTs & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | 31-Mar-27 | 31-Mar-27 |  |  | 290 | 227 |  |  |  | 2026-12-31 | 2026-12-31 | 2026-12-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 241.66 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 95.70 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2027-09-30
2200000460 | Main-Connectivity under GNA |  | SPRNG ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 |  | 150 | 0 | 0 | 150 |  | Granted | 150 | 0 | 150 | Radhanesda | Gujarat | 2025-07-30 | 2027-06-30 | SEPL in present application shall share the DTL already identified to SEPL in application no. 2200000461, which is detailed below • SEPL – Radhanesda PS 220kV Sc line (on Dc tower) along with associated line bay at generating station (under the scope of applicant) • 1 no. bay out of 2 nos. spare bays which were originally constructed for GPCL’s Radhanesda solar park and remain unutilised till date may be utilised for subject applicant. | 0 | 220 KV | Aug without ATS |  |  | Augmentation of transformation capacity at Banaskantha (Radhanesda) PS by 2x500MVA, 400220kV ICT (3rd) & (4th) | Augmentation of transformation capacity at Banaskantha (Radhanesda) PS by 2x500MVA, 400220kV ICT (3rd) & (4th) | 30-Jun-27 | 30-Jun-27 |  |  | 150 | 206 |  |  |  | 2026-03-28 | 2027-03-24 | 2027-03-24 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-12-30
2200000461 | Main-Connectivity under GNA |  | SPRNG ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Radhanesda | Gujarat | 2025-07-30 | 2027-03-24 | • SEPL – Radhanesda PS 220kV Sc line (on Dc tower) along with associated line bay at generating station (under the scope of applicant) • 1 no. bay out of 2 nos. spare bays which were originally constructed for GPCL’s Radhanesda solar park and remain unutilised till date may be utilised for subject applicant. | 1 | 220 KV | Aug without ATS |  |  | Augmentation of transformation capacity at Banaskantha (Radhanesda) PS by 2x500MVA, 400220kV ICT (3rd) & (4th) | Augmentation of transformation capacity at Banaskantha (Radhanesda) PS by 2x500MVA, 400220kV ICT (3rd) & (4th) | 31-Dec-26 | 31-Dec-26 |  |  | 100 | 206 |  |  |  | 2026-03-28 | 2027-03-24 | 2027-03-24 |  | Not effective | 2027-03-24 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2027-03-24
2200000472 | Main-Connectivity under GNA |  | GADAG POWER INDIA PRIVATE LIMITED | SR | Land BG Route | (x) Renewable Power Park developer | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Koppal-II | Karnataka | 2025-03-20 | 2025-12-31 | •Generation Pooling Station of M/s Gadag Power India Private Limited – Koppal-II PS 220 kV S/c line on D/c tower# along with line bay at generation pooling station –under the scope of applicant. •1 no. 220 kV line bay at Koppal-II PS end for termination of dedicated line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | 30-Dec-25 | 30-Dec-25 |  |  | 300 | 234 |  |  |  | 2026-08-31 | 2025-12-31 | 2027-03-31 |  | Not effective | 2027-01-16 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 150.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 30-Dec-25 |  | 2025-12-30 | 2027-03-31
2200000473 | Main-Connectivity under GNA |  | POWERICA LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Jam Khambhaliya | Gujarat | 2024-11-22 | 2026-10-14 | POWERICA Limited in present application shall share the DTL already identified to POWERICA Limited in application no. 1200001924, which is detailed below: • POWERICA Limited – Jam Khambhaliya PS 220kV S/c line (on D/c towers) along with associated bay at generation end (Under scope of M/s POWERICA Limited) • 1 no. 220kV line bay at Jam Khambhaliya PS has been implemented under ISTS as part of the pooling station. | 0 | 220 kV | Aug without ATS |  |  | Part-A • Establishment of 2x1500 MVA 765/400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV D/c line • LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part-B • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 3x500MVA, 400/220kV ICT (5th, 6th & 7th) | Part-A • Establishment of 2x1500 MVA 765/400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV D/c line • LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part-B • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 3x500MVA, 400/220kV ICT (5th, 6th & 7th) | 31-Dec-25 | 31-Dec-25 |  |  | 50 | 203 |  |  |  |  | 2026-10-14 | 2027-09-30 |  | Not effective | 2026-10-14 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2027-09-30
2200000474 | Main-Connectivity under GNA |  | TORRENT SOLAR POWER PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 125.4 |  | 0 | 125.4 | 0 | 125.4 |  | Granted | 125.4 | 0 | 125.4 | Koppal-II | Karnataka | 2025-03-04 | 2026-02-01 | •Generation Pooling Station of M/s Torrent Solar Power Private Limited – Koppal-II PS 220 kV S/c line along with line bay at generation pooling station –under the scope of applicant. •1 no. 220 kV line bay at Koppal-II PS end for termination of dedicated line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | 31-Jan-26 | 31-Jan-26 |  |  | 125.4 | 236 | 2026-06-19 |  | Torrent representative informed that vide SECI letter , revised Scheduled commencement of Power supply date is 19.06.2026. | 2026-01-15 | 2025-12-30 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 53.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 53.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 19.40 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 31-Jan-26 |  | 2026-01-31 | 2027-03-31
2200000476 | Main-Connectivity under GNA |  | ADANI GREEN ENERGY LIMITED | WR | Land Route | (x) Renewable Power Park developer | Hybrid | 1250 |  | 1100 | 170 | 0 | 1270 |  | Granted | 1250 | 0 | 1250 | KPS-3 (Sec-II) | Gujarat | 2025-01-09 | 2029-05-19 | • AGEL (PSS-13) – KPS3 400kV Sc line on Dc Tower (with minimum capacity of 1325MW at nominal voltage) along with associated bays at generation end (under the scope of AGEL) • 1 no. 400kV bays on Bus Section-II at KPS3 (under ISTS) | 1 | 400 KV | Aug without ATS |  |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari(New) 765 kV Dc line Khavda Phase-IV • Creation of 765kV bus section-II at KPS3 (GIS) along with 765kV Bus Sectionaliser • Creation of 400kV bus section-II at KPS3 (GIS) along with 400kV Bus Sectionaliser • KPS3 (GIS) – Lakadia (AIS) 765 kV DC line • ±300MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400kV Bus section-2 • KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line • Establishment of 2x1500MVA, 765400kV & 2x500MVA, 400220kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) • Vadodara(GIS) –South Olpad(GIS) 765 kV DC line • LILO of Gandhar – Hazira 400kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • Ahmedabad – South Olpad(GIS) 765kV Dc line • Establishment of 4X1500 MVA 765400 kV & 2x500MVA 400220kV Boisar-II (GIS) • South Olpad(GIS) – Boisar-II(GIS) 765kV Dc line • LILO of Navsari(New) – Padghe(PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon(MH) 400kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of Babhaleswar – Padghe(M) 400kV Dc line at Boisar-II (Sec-I) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-I of Boisar-II and ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-II of Boisar-II • ±300 MVAr STATCOM with 3x125 MVAr MSC, 1x125 MVAr MSR at 400 kV level of Navsari(New)(PG) Ss with 1 No. of 400 kV bay (GIS) • Establishment of 2X1500 MVA 765400 kV & 3x500MVA 400220kV Pune-III (GIS) • Boisar-II – Pune- | 31-May-25 | 31-May-25 |  |  | 1250 | 432M & 431T |  |  |  | 2026-08-30 | 2029-12-12 | 2029-12-12 |  | Not effective | 2029-12-12 | Under Construction | Part Commissioned | 902 | ¦ Phase 1 ¦ MW: 52.00 ¦ Date: 2025-02-16 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2025-02-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 112.50 ¦ Date: 2025-03-29 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 37.50 ¦ Date: 2025-03-31 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 50.00 ¦ Date: 2025-04-02 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 87.50 ¦ Date: 2025-04-27 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 7 ¦ MW: 50.00 ¦ Date: 2025-05-04 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 8 ¦ MW: 50.00 ¦ Date: 2025-05-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 9 ¦ MW: 62.50 ¦ Date: 2025-05-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 10 ¦ MW: 75.00 ¦ Date: 2025-06-20 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 11 ¦ MW: 50.00 ¦ Date: 2025-06-26 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 12 ¦ MW: 50.00 ¦ Date: 2025-06-30 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 13 ¦ MW: 25.00 ¦ Date: 2025-11-27 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 14 ¦ MW: 100.00 ¦ Date: 2025-11-27 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 15 ¦ MW: 348.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2029-12-12
2200000477 | Main-Connectivity under GNA |  | ADANI GREEN ENERGY LIMITED | WR | Land Route | (x) Renewable Power Park developer | Hybrid | 75 | 0 | 50 | 26 | 0 | 76 |  | Granted | 75 | 0 | 75 | KPS-3 (Sec-II) | Gujarat | 2025-01-09 | 2029-12-12 | AGEL shall share the DTL & 40033 kV Switchyard (PSS-14) of AGEL’s Application no. 2200000953 (Hybrid 1530 MW) as given below • AGEL (PSS-14) – KPS3 (Sec-II) 400kV Dc line (with minimum capacity of 1965MW at nominal voltage) along with associated bays at generation end (under the scope of AGEL) • 2 nos. 400kV bays on Bus Section-II at KPS3 (under ISTS) | 0 | 400 KV | Aug without ATS |  |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari(New) 765 kV Dc line Khavda Phase-IV • Creation of 765kV bus section-II at KPS3 (GIS) along with 765kV Bus Sectionaliser • Creation of 400kV bus section-II at KPS3 (GIS) along with 400kV Bus Sectionaliser • KPS3 (GIS) – Lakadia (AIS) 765 kV DC line • ±300MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400kV Bus section-2 • KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line • Establishment of 2x1500MVA, 765400kV & 2x500MVA, 400220kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) • Vadodara(GIS) –South Olpad(GIS) 765 kV DC line • LILO of Gandhar – Hazira 400kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • Ahmedabad – South Olpad(GIS) 765kV Dc line • Establishment of 4X1500 MVA 765400 kV & 2x500MVA 400220kV Boisar-II (GIS) • South Olpad(GIS) – Boisar-II(GIS) 765kV Dc line • LILO of Navsari(New) – Padghe(PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon(MH) 400kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of Babhaleswar – Padghe(M) 400kV Dc line at Boisar-II (Sec-I) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-I of Boisar-II and ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-II of Boisar-II • ±300 MVAr STATCOM with 3x125 MVAr MSC, 1x125 MVAr MSR at 400 kV level of Navsari(New)(PG) Ss with 1 No. of 400 kV bay (GIS) • Establishment of 2X1500 MVA 765400 kV & 3x500MVA 400220kV Pune-III (GIS) • Boisar-II – Pune- | 31-May-25 | 31-May-25 |  |  | 75 | 435M 434T & 438M 437T |  |  |  | 2026-08-30 | 2029-05-19 | 2029-05-19 |  | Not effective | 2029-12-12 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2029-12-12 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 26.00 ¦ Date: 2029-12-12 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2030-06-12
2200000478 | Main-Connectivity under GNA |  | ADANI GREEN ENERGY LIMITED | WR | Land Route | (x) Renewable Power Park developer | Hybrid | 655.20 | 0 | 650 | 5.2 | 0 | 655.2 |  | Granted | 650 | 0 | 650 | KPS-1 (Sec-II) | Gujarat | 2025-01-09 | 2029-12-12 | Ms AGEL shall share the DTL & 40033 kV Switchyard (PSS-5) granted to Ms AGEL for its 1000MW HPP against application no. 230700006 as given below • AGEL (PSS-5) – Khavda-I PS 400kV Sc line (with minimum capacity of 1650MW at nominal voltage) along with associated bay at Generation end (Under the scope of applicant) • Bay at ISTS substation end shall be under the scope of ISTS. | 0 | 400 KV | Aug without ATS |  |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari(New) 765 kV Dc line Khavda Phase-IV • Creation of 765kV bus section-II at KPS3 (GIS) along with 765kV Bus Sectionaliser • Creation of 400kV bus section-II at KPS3 (GIS) along with 400kV Bus Sectionaliser • KPS3 (GIS) – Lakadia (AIS) 765 kV DC line • ±300MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400kV Bus section-2 • KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line • Establishment of 2x1500MVA, 765400kV & 2x500MVA, 400220kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) • Vadodara(GIS) –South Olpad(GIS) 765 kV DC line • LILO of Gandhar – Hazira 400kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • Ahmedabad – South Olpad(GIS) 765kV Dc line • Establishment of 4X1500 MVA 765400 kV & 2x500MVA 400220kV Boisar-II (GIS) • South Olpad(GIS) – Boisar-II(GIS) 765kV Dc line • LILO of Navsari(New) – Padghe(PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon(MH) 400kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of Babhaleswar – Padghe(M) 400kV Dc line at Boisar-II (Sec-I) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-I of Boisar-II and ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-II of Boisar-II • ±300 MVAr STATCOM with 3x125 MVAr MSC, 1x125 MVAr MSR at 400 kV level of Navsari(New)(PG) Ss with 1 No. of 400 kV bay (GIS) • Establishment of 2X1500 MVA 765400 kV & 3x500MVA 400220kV Pune-III (GIS) • Boisar-II – Pune- | 31-May-25 | 31-May-25 |  |  | 650 | 420 |  |  |  | 2026-08-30 | 2029-05-19 | 2029-05-19 |  | Not effective | 2029-12-12 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 50.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2030-06-12
2200000481 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | 232.5 (Solar:200, BESS:32.5MW) |  | 200 | 0 | 32.5 | 232.5 | SJVN | Granted | 232.5 | 0 | 232.5 | Koppal-II | Karnataka | 2025-03-04 | 2026-03-02 | •Generation Pooling Station of Ms Tata Power Renewable Energy Limited – Koppal-II PS 220 kV Sc line along with line bay at generation pooling station –under the scope of applicant. •1 no. 220 kV line bay at Koppal-II PS end for termination of dedicated line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | 01-Mar-26 | 01-Mar-26 |  |  | 232.5 | 230 |  |  |  |  | 2025-12-31 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 32.50 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Standalone | 16.03.2026 |  |  |  | Pending with Level 2 | 01-Mar-26 |  | 2026-03-01 | 2027-03-31
2200000485 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 | 0 | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Fatehgarh-IV (Sec-II) | Rajasthan | 2025-06-05 | 2027-12-31 | Common Pooling Station for Juniper Green Steller Pvt. Ltd. Renewable Power Park (App. No. 2200000063-300 MW) & Juniper Green Energy Pvt. Ltd. Solar Power Project (App. No. 2200000485-50 MW)– Fatehgarh-IV PS(Sec-II) 220 kV Sc line on Dc tower (Suitable to carry minimum 350 MW at nominal voltage) - Under Applicant Scope | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gad | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) • Part of System strengthening at Koppal-II and Gadag-II for integration of RE generation projects | 31-Dec-27 | 31-Dec-27 |  |  | 50 | 235 |  |  |  | 2026-08-14 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2028-06-30
2200000492 | Main-Connectivity under GNA |  | ANBOTO SOLAR PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Barmer-I | Rajasthan | 2025-05-08 | 2026-12-30 | Common Pooling Station for Anboto Solar Private Limited Solar Power Projects (App. No. 2200000281-250 MW & 2200000492-50 MW)– Barmer-I PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage) - Under Applicant Scope | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 1. Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS 2. Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS 3. Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) 4. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 5. Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end 6. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 7. Establishment of 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 8. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 9. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 10. LILO of one circuit of 765 kV Chittorgarh-Banaskantha D/c line at Rishabdeo S/s 11. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 12. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 13. Establishment of 765/400 kV 2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 14. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 15. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 17. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 18. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 19. Establishment of 765/400 kV, 2x1500 MVA & 2x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s 20. STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 21. 400kV Sectionalizer bay (1 set) at Barmer-I S/s 22. Barmer-I PS – Merta-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end of Barmer-I PS – Merta-II 765 kV D/c line 23. Merta-II – Beawar 400 kV D/c line (Quad) 24. Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line 25. Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) 26. Dausa - Ghiror 765 kV D/c line along with 330MVAr switchable line reactor at Ghiror end and 240 MVAr switchable line reactor at Dausa end for each circuit of Dausa - Ghiror 765 kV D/c line 27. LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line 28. LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV 2xS/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 29. 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | Transmission system for Connectivity under GNA: 1. Augmentation of 5x500 MVA (5th to 9th), 400/220 kV ICTs at Barmer-I PS 2. Augmentation with 765/400 kV, 3x1500 MVA Transformer (3rd, 4th & 5th) at Barmer-I PS 3. Fatehgarh-III (Section-2) PS – Barmer-I PS 400 kV D/c line (Quad) 4. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 5. Barmer-I PS– Sirohi PS 765 kV D/c line along with 240 MVAR switchable line reactor for each circuit at each end 6. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 7. Establishment of 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 8. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 9. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 10. LILO of one circuit of 765 kV Chittorgarh-Banaskantha D/c line at Rishabdeo S/s 11. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 12. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 13. Establishment of 765/400 kV 2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 14. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 15. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 17. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 18. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 19. Establishment of 765/400 kV, 2x1500 MVA & 2x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s 20. STATCOM (2x+300MVAr) along with MSC (4x125 MVAr) & MSR (2x125 MVAr) along with 2 nos. 400kV bays at Barmer-I PS 21. 400kV Sectionalizer bay (1 set) at Barmer-I S/s 22. Barmer-I PS – Merta-II 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at each end of Barmer-I PS – Merta-II 765 kV D/c line 23. Merta-II – Beawar 400 kV D/c line (Quad) 24. Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line 25. Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) 26. Dausa - Ghiror 765 kV D/c line along with 330MVAr switchable line reactor at Ghiror end and 240 MVAr switchable line reactor at Dausa end for each circuit of Dausa - Ghiror 765 kV D/c line 27. LILO of both ckt of 765 kV Aligarh (PG) -Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line 28. LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV 2xS/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror -Fatehpur line 29. 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) | 30-Nov-25 | 30-Nov-25 |  |  | 50 | 211 |  |  |  | 2027-03-31 | 2026-11-07 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Nov-25 |  | 2025-11-30 | 2027-06-30
2200000499 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 |  | 150 | 0 | 0 | 150 |  | Granted | 150 | 0 | 150 | Ramgarh | Rajasthan | 2026-07-06 |  | • Common Pooling station for Juniper Green Energy Limited (App. No. 2200000499 (150 MW) & 2200000550 (150 MW)) Solar Power Projects –– Ramgarh PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage)-Under Applicant Scope • Implementation of 1 No. of 220 kV Bay at Ramgarh PS is under ISTS Scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA A. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part B1- Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 3x500 MVA , 400220 kV pooling station at Bhadla | Transmission system for Connectivity under GNA A. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part B1- Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 3x500 MVA , 400220 kV pooling station at Bhadla-3 along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 2. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line B. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part C1 - Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 2x500 MVA, 400220 kV pooling station at Ramgarh along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus reactor 2. Ramgarh PS – Bhadla-III PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Ramgarh end C. Additional Transmission system for evacuation of power from Bhadla-III PS as part of Rajasthan REZ Phase-III scheme (20 GW) 1. Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS D. Transmission system strengthening for interconnections of Bhadla-III & Bikaner-III complex 1. Bhadla-III – Bikaner-III 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end as well as associated 2 Nos. of 765kV line bay(s) at each at Bhadla-III & Bikaner-III end E. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part A3 1. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III–Bhadla-III 400kV Dc line F. Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under Phase-III Part I 1. Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation 2. Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) 3. Bhadla-III – Bhadla (HVDC) 400 kV 2xDc line (Quad) along with the line bays at both substations 4. ±800 kV HVDC line (Hexa Lapwing) between Bhadla (HVDC) & Fatehpur (HVDC) (with Dedicated Metallic Return) 5. Augmentation of 5x1500 MVA, 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor 6. LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur G. Augmentation at Bhadla-III, Ramgarh PS and Kanpur (PG) 1. Augmentation of 765400kV, 1x1500 MVA ( | 30-Jun-28 | 30-Jun-28 |  |  | 150 | 206 | [7 empty] | Not effective | 2029-07-20 |  | Not commissioned | 0 | [5 empty] | Not Submitted For Approval | 30-Jun-28 |  | 2028-06-30 | 2028-12-30
2200000500 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 150 |  | 0 | 150 | 0 | 150 |  | Granted | 150 | 0 | 150 | Lakadiya | Gujarat | 2025-06-25 | 2027-03-31 | JGEPL – Lakadia 220kV Sc line (on Dc tower) along with associated bay at generation end (under the scope of applicant). 1 no. 220kV line bay (on Section-II) at Lakadia PS was agreed under ISTS. | 1 |  | Aug without ATS |  |  | Establishment of 5x500MVA, 400220kV ICTs & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | Establishment of 5x500MVA, 400220kV ICTs & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | 31-Mar-28 | 31-Mar-28 |  |  | 150 | 228 |  |  |  | 2027-03-31 | 2026-12-31 | 2026-12-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 02-04-2026 |  |  |  | Pending with Level 2 | 31-Mar-28 |  | 2028-03-31 | 2028-09-30
2200000502 | Main-Connectivity under GNA |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 400 | 0 | 0 | 400 | 0 | 400 |  | Granted | 400 |  | 400 | Pachora (Sec-II) | Madhya Pradesh | 2026-06-11 | 2027-09-29 | • ACSPL – Pachora PS 220kV Dc line on Dc towers with phase-to-phase bunching prior to Mc Tower towards entry into Pachora PS and at ACME Pooling Ss, so as to form Sc line at both ends, to be terminated into 1 no. 220kV line bay at Pachora PS and 1 no. 220kV line bay at ACME Pooling Ss (Under the scope of Ms ACSPL). • 1 no. 220kV line bay at Pachora PS shall be implemented under ISTS as a part of the Rajgarh Phase-II Scheme. | 1 | 220 KV | Aug without ATS |  |  | Part-1 Rajgarh Phase-I (1.5GW) (Commissioned) Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP. Pachora SEZ PP – Bhopal (Sterlite) 400kV Dc line (QuadTwin HTLS) (with minimum capacity of 2100 MVAckt at nominal voltage). Part-2 Rajgarh Phase- | Part-1 Rajgarh Phase-I (1.5GW) (Commissioned) Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP. Pachora SEZ PP – Bhopal (Sterlite) 400kV Dc line (QuadTwin HTLS) (with minimum capacity of 2100 MVAckt at nominal voltage). Part-2 Rajgarh Phase-II (1GW) (SCOD-14022026) 400220 kV, 3x500 MVA ICT augmentation (4th 5th and 6th) at Pachora PS. Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent). Part-3 Rajgarh Phase-III (part system) (for balance 50MW only) (Tentatively by 31.01.2027) 400220 kV, 1x500 MVA ICT augmentation (7th) at Pachora PS. | 30-Apr-26 | 30-Apr-26 | 350 | 2026-06-27 |  | 218 | [7 empty] | Effective |  |  |  | 0 | ¦ Phase 1 ¦ MW: 48.00 ¦ Date: 2026-12-21 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 52.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 64.00 ¦ Date: 2027-10-14 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 4 ¦ MW: 64.00 ¦ Date: 2028-02-27 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 5 ¦ MW: 136.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind | Rajgarh Ph |  |  |  | Pending with Level 2 | 30-Apr-26 |  | 2026-04-30 | 2028-03-29
2200000502 | Main-Connectivity under GNA |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 400 | 0 | 0 | 400 | 0 | 400 |  | Granted | 400 |  | 400 | Pachora (Sec-II) | Madhya Pradesh | 2026-06-11 | 2027-09-29 | • ACSPL – Pachora PS 220kV Dc line on Dc towers with phase-to-phase bunching prior to Mc Tower towards entry into Pachora PS and at ACME Pooling Ss, so as to form Sc line at both ends, to be terminated into 1 no. 220kV line bay at Pachora PS and 1 no. 220kV line bay at ACME Pooling Ss (Under the scope of Ms ACSPL). • 1 no. 220kV line bay at Pachora PS shall be implemented under ISTS as a part of the Rajgarh Phase-II Scheme. | 1 | 220 KV | Aug without ATS |  |  | Part-1 Rajgarh Phase-I (1.5GW) (Commissioned) Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP. Pachora SEZ PP – Bhopal (Sterlite) 400kV Dc line (QuadTwin HTLS) (with minimum capacity of 2100 MVAckt at nominal voltage). Part-2 Rajgarh Phase- | Part-1 Rajgarh Phase-I (1.5GW) (Commissioned) Establishment of 400220 kV, 3x500MVA at Pachora SEZ PP. Pachora SEZ PP – Bhopal (Sterlite) 400kV Dc line (QuadTwin HTLS) (with minimum capacity of 2100 MVAckt at nominal voltage). Part-2 Rajgarh Phase-II (1GW) (SCOD-14022026) 400220 kV, 3x500 MVA ICT augmentation (4th 5th and 6th) at Pachora PS. Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent). Part-3 Rajgarh Phase-III (part system) (for balance 50MW only) (Tentatively by 31.01.2027) 400220 kV, 1x500 MVA ICT augmentation (7th) at Pachora PS. | 30-Apr-26 | 30-Apr-26 |  |  | 50 | 218 | [7 empty] | Not Effective |  |  |  | 0 | ¦ Phase 1 ¦ MW: 48.00 ¦ Date: 2026-12-21 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 52.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 64.00 ¦ Date: 2027-10-14 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 4 ¦ MW: 64.00 ¦ Date: 2028-02-27 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 5 ¦ MW: 136.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind | Rajgarh Ph |  |  |  | Pending with Level 2 | 30-Apr-26 |  | 2026-04-30 | 2028-03-29
2200000503 | Main-Connectivity under GNA |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 308.49 |  | 0 | 147 | 0 | 147 |  | Granted | 147 | 0 | 147 | Jam Khambhaliya | Gujarat | 2024-11-22 | 2026-10-14 | INGEPL in present application shall share the DTL already identified to POWERICA Limited in application no. 1200001924, which is detailed below: • POWERICA Limited – Jam Khambhaliya PS 220kV S/c line (on D/c towers) along with associated bay at generation end (Under scope of M/s POWERICA Limited) • 1 no. 220kV line bay at Jam Khambhaliya PS has been implemented under ISTS as part of the pooling station. | 0 | 220 kV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA Part-A • Establishment of 2x1500 MVA 765/400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV D/c line • LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part-B • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 3x500MVA, 400/220kV ICT (5th, 6th & 7th) | Common Transmission System Augmentation for Connectivity under GNA Part-A • Establishment of 2x1500 MVA 765/400 kV Jamnagar (GIS) PS • Halvad – Jamnagar 765 kV D/c line • LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of CGPL – Jetpur 400kV D/c (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad – Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part-B • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 3x500MVA, 400/220kV ICT (5th, 6th & 7th) | 27-03-2025 | 27-03-2025 |  |  | 147 | 203 |  |  |  |  | 2026-10-14 | 2027-09-30 |  | Not effective | 2026-10-14 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 147.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 27-03-2025 |  | 2025-03-27 | 2027-09-30
2200000504 | Main-Connectivity under GNA |  | AYANA RENEWABLE POWER PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Koppal-II | Karnataka | 2025-02-28 | 2025-12-31 | Through sharing of dedicated connectivity transmission system of M/s Tata Power Renewable Energy Ltd. granted connectivity for 85 MW (application no. 0251100013) at Koppal-II PS i.e. Generating Pooling Station of M/s Tata Power Renewable Energy Ltd – Koppal-II PS 220 kV S/c line – all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | 01-Dec-25 | 01-Dec-25 |  |  | 100 | 202 |  |  |  | 2026-06-30 | 2025-12-31 | 2027-03-31 |  | Not effective | 2027-01-16 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2028-09-23 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 01-Dec-25 |  | 2025-12-01 | 2027-03-31
2200000511 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Lakadiya | Gujarat | 2025-06-25 | 2029-03-31 | Ms JGEPL shall share the Dedicated Transmission system proposed for Ms JGEPL for its 150MW WPP against application no. 2200000500 as given below JGEPL – Lakadia 220kV Sc line (on Dc tower) along with associated bay at generation end (under the scope of applicant). 1 no. 220kV line bay (on Section-II) at Lakadia PS was agreed under ISTS. | 0 | 220 KV | Aug without ATS |  |  | Under Implementation (under ISTS) “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited • Establishment of 6x500MVA, 400220kV ICTs (3rd to 8th) & 1x1500MVA | Under Implementation (under ISTS) “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited • Establishment of 6x500MVA, 400220kV ICTs (3rd to 8th) & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | 31-Mar-29 | 31-Mar-29 |  |  | 200 | 228 |  |  |  | 2027-03-31 | 2027-06-30 | 2027-06-30 |  | Not effective | 2029-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2029-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-29 |  | 2029-03-31 | 2029-09-30
2200000513 | Main-Connectivity under GNA |  | VENA ENERGY AURA PRIVATE LIMITED | SR | Land Route | (xi) REGS with an installed capacity of 5 MW and above applying for grant of Connectivity to ISTS through the electrical system of a generating station already having Connectivity to ISTS | Wind | 40 | 0 | 0 | 24 | 0 | 24 |  | Granted | 24 | 0 | 24 | Koppal-II | Karnataka | 2025-02-28 | 2026-12-31 | Through sharing of dedicated Connectivity transmission system granted to M/s VEH Green Energy Pvt. Ltd. for application no. 2200000126 i.e. Generation Pooling Station of M/s VEH Green Energy Pvt. Ltd. at Koppal – Koppal-II PS 220 kV S/c line along with 220 kV line at generation pooling station – all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A & Phase-B) and Gadag-II (Phase- A) in Karnataka as per Annexure-II • Part of System strengthening at Koppal-II PS and Gadag-II PS for integration of RE generation as per Annexure-III | 31-Dec-25 | 31-Dec-25 |  |  | 24 | 214 |  |  |  |  | 2025-12-31 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 24.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2027-06-30
2200000514 | Main-Connectivity under GNA |  | ADANI GREEN ENERGY THIRTY TWO LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 260.5 | 0 | 260.5 |  | Granted | 260.5 | 0 | 260.5 | Bhuj-II (Sec-II) | Gujarat | 2025-06-06 | 2026-12-18 |  | 1 | 220 kV | Aug without ATS |  |  |  |  | 15-Jun-25 | 15-Jun-25 |  |  | 260.5 | 221 |  |  |  | 2027-03-31 | 2027-03-31 | 2027-06-30 |  | Not effective | 2026-12-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 260.50 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 15-Jun-25 |  | 2025-06-15 | 2027-06-30
2200000515 | Main-Connectivity under GNA |  | GANEKO SOLAR PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 11.63 |  | 8.33 | 3.3 | 0 | 11.63 |  | Granted | 10 | 0 | 10 | Lakadiya | Gujarat | 2025-07-15 | 2026-12-31 | Ms GSPL shall share the Dedicated Transmission system proposed for Ms GSPL for its 290MW Hybrid Power Plant against application no. 2200000458 as given below • GSPL – Lakadia 220kV Sc line (on Dc Towers) along with associated bay at generation end (under the scope of applicant). • 1 no. 220kV line bay on Section-II at ISTS substation end is under implementation under ISTS scheme “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” by Ms LBPTL. | 0 | 220 KV | Aug without ATS |  |  | Under Implementation (under ISTS) “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited • Establishment of 5x500MVA, 400220kV ICTs (3rd to 8th) & 1x1500MVA | Under Implementation (under ISTS) “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited • Establishment of 5x500MVA, 400220kV ICTs (3rd to 8th) & 1x1500MVA 765400kV ICT (3rd) at Lakadia PS along with associated ICT bays. | 31-Dec-26 | 31-Dec-26 |  |  | 10 | 227 |  |  |  | 2026-12-31 | 2026-12-31 | 2026-12-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 3.30 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 8.33 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2027-06-30
2200000518 | Main-Connectivity under GNA |  | CESC LTD | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Sirohi | Rajasthan | 2025-05-27 | 2027-03-24 | CESC Ltd. Solar Power Project– Sirohi PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage)- Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 1. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 2. Augmentation with 5x500 MVA, 400/220kV ICTs at Sirohi PS 3. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 4. Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 5. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 6. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 7. LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s 8. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 9. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 10. Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 11. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 12. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 13. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 14. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 15. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line 17. Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Transmission system for Connectivity under GNA: 1. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 2. Augmentation with 5x500 MVA, 400/220kV ICTs at Sirohi PS 3. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 4. Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 5. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 6. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 7. LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s 8. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 9. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 10. Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 11. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 12. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 13. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 14. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 15. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line 17. Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 31-Jan-26 | 31-Jan-26 |  |  | 300 | 202 |  |  |  | 2027-03-31 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-23 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Jan-26 |  | 2026-01-31 | 2027-09-24
2200000531 | Main-Connectivity under GNA |  | SPRNG RENEWABLE RESOURCES PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Barmer-II | Rajasthan | 2026-01-19 |  | Common Pooling Station for Sprng Renewable Resources Private Limited (App. No. 2200000531(200 MW) & Sprng Urja Private Limited (App. No. 2200000539 (200 MW) Solar Power Projects– Barmer-II PS 220 kV Sc (high capacity) line on Dc tower (Suitable to carry minimum 400 MW at nominal voltage)- Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA (Tentative) 1. Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 2. LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS 3. Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation 4. Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) 5. Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor 6. LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss 7. ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) Additional system for connectivity at 220kV level only of Barmer-II PS 1. 400220kV, 6x500 MVA ICTs at Barmer-II PS | 30-Jun-27 | 30-Jun-27 |  |  | 200 | N | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2030-03-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  |  | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2030-12-30
2200000537 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 200 | 0 | 0 | 200 | SECI | Granted | 200 | 0 | 200 | Bhuj-II (Sec-II) | Gujarat | 2025-06-06 | 2026-12-18 | Ms AEPL shall share the Dedicated Transmission System proposed for Ms AEPL for its 100MW SPP against application No. 2200000444 as given below • AEPL - Bhuj II PS (Section-II) 220kV Sc line along with associated bays at generation end (under the scope of applicant). • 1 No. 220kV bay at Bhuj-II (Sec-II) PS under ISTS (currently under approval). | 0 | 220 KV | Aug without ATS |  |  | Under Implementation (under ISTS) Augmentation of transformation capacity at Bhuj-II PS (GIS) (Part System) POWERGRID Bhuj Transmission Limited) (SCOD24-NOV-2026) Augmentation of transformation capacity at Bhuj-II PS (GIS) by 2x500 MVA, | Under Implementation (under ISTS) Augmentation of transformation capacity at Bhuj-II PS (GIS) (Part System) POWERGRID Bhuj Transmission Limited) (SCOD24-NOV-2026) Augmentation of transformation capacity at Bhuj-II PS (GIS) by 2x500 MVA, 400220 kV ICT (5th & 6th) and by 1x1500 MVA, 765400 kV ICT (3rd). Provision of ICT Augmentation and Bus Reactor at Bhuj-II PS(Part System) (POWERGRID Bhuj Transmission Limited) (SCOD18-DEC-2026) Augmentation of transformation capacity at Bhuj-II PS (GIS) by 3x500 MVA, 400220 kV ICT (7th, 8th & 9th) and by 1x1500 MVA, 765400 kV ICT (4th). | 31-Dec-25 | 31-Dec-25 |  |  | 200 | 219 |  |  |  | 2027-03-31 | 2026-12-18 | 2027-06-30 |  | Not effective | 2026-12-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-05-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 | Yes |  |  | Pending with Level 2 | 31-Dec-25 |  | 2025-12-31 | 2027-06-30
2200000539 | Main-Connectivity under GNA |  | SPRNG URJA PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 | 0 | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Barmer-II | Rajasthan | 2026-01-19 |  | Common Pooling Station for Sprng Renewable Resources Private Limited (App. No. 2200000531(200 MW) & Sprng Urja Private Limited (App. No. 2200000539 (200 MW) Solar Power Projects– Barmer-II PS 220 kV Sc (high capacity) line on Dc tower (Suitable to carry minimum 400 MW at nominal voltage)- Under Applicant Scope | 0 | 220 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA (Tentative) 1. Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 2. LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS 3. Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation 4. Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) 5. Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor 6. LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss 7. ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) Additional system for connectivity at 220kV level only of Barmer-II PS 1. 400220kV, 6x500 MVA ICTs at Barmer-II PS | 100 MW 30062029100 MW 31122029 | Phase 1 ¦ MW: 100.00 ¦ Date: 2029-06-30 Phase 2 ¦ MW: 100.00 ¦ Date: 2029-12-31 |  |  | 200 | N | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2029-09-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 100.00 ¦ Date: 2029-06-30 | 100 | 2029-06-30 | 2030-12-30
2200000539 | Main-Connectivity under GNA |  | SPRNG URJA PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 | 0 | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Barmer-II | Rajasthan | 2026-01-19 |  | Common Pooling Station for Sprng Renewable Resources Private Limited (App. No. 2200000531(200 MW) & Sprng Urja Private Limited (App. No. 2200000539 (200 MW) Solar Power Projects– Barmer-II PS 220 kV Sc (high capacity) line on Dc tower (Suitable to carry minimum 400 MW at nominal voltage)- Under Applicant Scope | 0 | 220 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA (Tentative) 1. Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 2. LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS 3. Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation 4. Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) 5. Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor 6. LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss 7. ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) Additional system for connectivity at 220kV level only of Barmer-II PS 1. 400220kV, 6x500 MVA ICTs at Barmer-II PS | 100 MW 30062029100 MW 31122029 | Phase 1 ¦ MW: 100.00 ¦ Date: 2029-06-30 Phase 2 ¦ MW: 100.00 ¦ Date: 2029-12-31 |  |  | 200 | N | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2029-09-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 100.00 ¦ Date: 2029-12-31 | 100 | 2029-12-31 | 2030-12-30
2200000543 | Main-Connectivity under GNA |  | AMPLUS EVEREST SOLAR PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 228(Solar105MW; Wind 126 MW) | 0 | 102 | 126 | 0 | 228 |  | Granted | 130 | 0 | 130 | Kurnool-III | Andhra Pradesh | 2024-11-06 | 2026-12-31 | •Generating Pooling Station of Ms Amplus Everest Solar Pvt. Ltd.- Kunool-III PS 220 kV Sc line on Dc tower# along with line bay at generation pooling station – under the scope of applicant. •1 no. of 220 kV line bay at Kurnool-III PS for termination of above mentioned dedicated Connectivity line - under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmissi | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)Solar Energy Zone (AP) (1500MW) - Part-A and Part-B | 31-May-26 | 31-May-26 |  |  | 130 | 211 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 102.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 126.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  |  | Pending with Level 2 | 31-May-26 |  | 2026-05-31 | 2027-06-30
2200000544 | Main-Connectivity under GNA |  | AMPLUS IIFA SOLAR PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 228(Solar105MW; Wind 126 MW) | 0 | 102 | 126 | 0 | 228 |  | Granted | 130 | 0 | 130 | Kurnool-III | Andhra Pradesh | 2024-11-06 | 2026-12-31 | •Through sharing of dedicated Connectivity Transmission System of Ms Amplus Everest Solar Pvt. Ltd. [granted application no. 2200000543] i.e. Generation Pooling station of Ms Amplus Everest Solar Pvt. Ltd. – Kurnool-III PS 220 kV Sc line on Dc tower– all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmissi | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)Solar Energy Zone (AP) (1500MW) - Part-A and Part-B | 31-May-26 | 31-May-26 |  |  | 130 | 211 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 102.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 126.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 31-May-26 |  | 2026-05-31 | 2027-06-30
2200000545 | Main-Connectivity under GNA |  | ADANI RENEWABLE ENERGY EIGHT LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 115 | 0 | 115 | 0 | 0 | 115 |  | Granted | 115 | 0 | 115 | Bhuj-II (Sec-II) | Gujarat | 2025-06-06 | 2026-12-18 | • ARE8L – Bhuj-II PS 220kV Sc line (on Dc tower) along with associated bays at generation end (under the scope of applicant). • 1 no. 220kV line bay at Bhuj-II PS (under approval in ISTS) | 1 | 220 KV | Aug without ATS |  |  | Augmentation of transformation capacity at Bhuj-II PS by 4x500MVA, 400220kV ICT (5th, 6th, 7th, 8th & 9th) and by 2x1500MVA, 765400kV ICT (3rd & 4th). | Augmentation of transformation capacity at Bhuj-II PS by 4x500MVA, 400220kV ICT (5th, 6th, 7th, 8th & 9th) and by 2x1500MVA, 765400kV ICT (3rd & 4th). | 15-Jun-25 | 15-Jun-25 |  |  | 115 | 223 |  |  |  | 2027-03-31 | 2026-12-18 | 2027-06-30 |  | Not effective | 2026-12-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 115.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 15-Jun-25 |  | 2025-06-15 | 2027-06-30
2200000546 | Main-Connectivity under GNA |  | SPRNG VAYU VIDYUT PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 |  | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Radhanesda | Gujarat | 2025-07-30 | 2027-06-30 | SVVPL in present application shall share the DTL already identified to SEPL in application no. 2200000461, which is detailed below • SEPL – Radhanesda PS 220kV Sc line (on Dc tower) along with associated line bay at generating station (under the scope of applicant) • 1 no. bay out of 2 nos. spare bays which were originally constructed for GPCL’s Radhanesda solar park and remain unutilised till date shall be utilised for subject applicant. | 0 | 220 KV | Aug without ATS |  |  | · Augmentation of transformation capacity at Banaskantha PS by 2x500MVA, 400220kV ICT (3rd & 4th) | · Augmentation of transformation capacity at Banaskantha PS by 2x500MVA, 400220kV ICT (3rd & 4th) | 30-Jun-27 | 30-Jun-27 |  |  | 50 | 206 |  |  |  | 2026-03-28 | 2027-03-24 | 2027-03-24 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-12-30
2200000550 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 |  | 150 | 0 | 0 | 150 |  | Granted | 150 | 0 | 150 | Ramgarh | Rajasthan | 2026-07-06 |  | Ms JGEL (App. No. 2200000550) shall share dedicated transmission system for connectivity granted to Ms Juniper Green Energy Limited under App. No. 2200000499 • Common Pooling Station for Juniper Green Energy Ltd (App. No. 2200000499 (150 MW) & 2200000550 (150 MW)) Solar Power Projects –– Ramgarh PS 220 kV Sc line on Dc tower (Suitable to carry minimum 300 MW at nominal voltage)-Under Applicant Scope • Implementation of 1 No. of 220 kV Bay at Ramgarh PS is under ISTS Scope | 0 | 220 KV | Aug without ATS |  |  | A. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part B1- Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 3x500 MVA , 400220 kV pooling station at Bhadla-3 along with 2x330 MVAr (765kV) Bus Reactor & 2x1 | A. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part B1- Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 3x500 MVA , 400220 kV pooling station at Bhadla-3 along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 2. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line B. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part C1 - Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 2x500 MVA, 400220 kV pooling station at Ramgarh along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus reactor 2. Ramgarh PS – Bhadla-III PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Ramgarh end C. Additional Transmission system for evacuation of power from Bhadla-III PS as part of Rajasthan REZ Phase-III scheme (20 GW) 1. Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS D. Transmission system strengthening for interconnections of Bhadla-III & Bikaner-III complex 1. Bhadla-III – Bikaner-III 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end as well as associated 2 Nos. of 765kV line bay(s) at each at Bhadla-III & Bikaner-III end E. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part A3 1. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III–Bhadla-III 400kV Dc line F. Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under Phase-III Part I 1. Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation 2. Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) 3. Bhadla-III – Bhadla (HVDC) 400 kV 2xDc line (Quad) along with the line bays at both substations 4. ±800 kV HVDC line (Hexa Lapwing) between Bhadla (HVDC) & Fatehpur (HVDC) (with Dedicated Metallic Return) 5. Augmentation of 5x1500 MVA, 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor 6. LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur G. Augmentation at Bhadla-III, Ramgarh PS and Kanpur (PG) 1. Augmentation of 765400kV, 1x1500 MVA (3rd) ICT at 765400kV Kanpur (PG) substation | 31-Dec-28 | 31-Dec-28 |  |  | 150 | 206 | [7 empty] | Not effective | 2029-07-20 |  | Not commissioned | 0 | [5 empty] | Not Submitted For Approval | 31-Dec-28 |  | 2028-12-31 | 2029-06-30
2200000551 | Main-Connectivity under GNA |  | RENEW SOLAR POWER PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 400 |  | 400 | 0 | 0 | 400 | NTPC | Granted | 400 | 0 | 400 | Sirohi | Rajasthan | 2025-05-27 | 2027-03-24 | Common Pooling Station for Renew Solar Power Private Limited Solar Power Projects (App. No. 2200000551-400 MW & 2200000779 -300 MW) – Sirohi PS 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW at nominal voltage) - Under Applicant Scope | 1 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: 1. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 2. Augmentation of 5x500 MVA, 400/220kV ICTs at Sirohi PS 3. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 4. Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 5. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 6. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 7. LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s 8. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 9. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 10. Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 11. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 12. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 13. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 14. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 15. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line 17. Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Transmission system for Connectivity under GNA: 1. Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 2. Augmentation of 5x500 MVA, 400/220kV ICTs at Sirohi PS 3. Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) 4. Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor 5. Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end 6. Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end 7. LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s 8. Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors 9. Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line 10. Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor 11. Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 12. Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 13. LILO of Indore – Bhopal 765 kV S/c line at Kurawar 14. LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha 15. Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line 16. Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line 17. Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 01-Aug-26 | 01-Aug-26 |  |  | 400 | 412 |  |  |  | 2027-03-31 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2028-09-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 01-Aug-26 |  | 2026-08-01 | 2027-06-30
2200000560 | Main-Connectivity under GNA |  | SPRNG POWERINFRA PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 | 0 | 0 | 200 | 0 | 200 |  | Granted | 200 | 0 | 200 | Bidar | Karnataka | 2025-03-03 | 2027-06-30 | •Generation Pooling Station of M/s Sprng Powerinfra Pvt. Ltd. – Bidar PS 220 kV S/c line along with line bay at generation pooling station – under the scope of applicant. •1 no. 220 kV line bay at Bidar PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | 100 MW 30062027100MW 30062028 | 100 MW 30062027100MW 30062028 |  |  | 200 | 208 |  |  |  | 2026-06-30 | 2026-02-09 | 2026-10-31 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 100 MW 30062027 | 100 | 2027-06-30 | 2027-12-30
2200000560 | Main-Connectivity under GNA |  | SPRNG POWERINFRA PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 | 0 | 0 | 200 | 0 | 200 |  | Granted | 200 | 0 | 200 | Bidar | Karnataka | 2025-03-03 | 2027-06-30 | •Generation Pooling Station of M/s Sprng Powerinfra Pvt. Ltd. – Bidar PS 220 kV S/c line along with line bay at generation pooling station – under the scope of applicant. •1 no. 220 kV line bay at Bidar PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | 100 MW 30062027100MW 30062028 | 100 MW 30062027100MW 30062028 |  |  | 200 | 208 |  |  |  | 2026-06-30 | 2026-02-09 | 2026-10-31 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 100 MW 30062028 | 100 | 2028-06-30 | 2028-12-30
2200000565 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 80 |  | 0 | 14 | 0 | 14 | SECI | Granted | 14 | 0 | 14 | Jam Khambhaliya | Gujarat | 2024-11-11 | 2026-10-14 | M/s NTPC REL shall share the Dedicated Transmission System proposed for M/s NTPC REL for its 500MW REGS at Jam Khambhaliya PS against application No. 2200000180, as given below: • NTPC REL – Jam Khambhaliya PS 220kV D/c line along with 220kV line bays at generation station (Under the scope of M/s NTPC REL) as detailed below:  500MW wind power shall be pooled with two PPS-1 (250MW) and PSS-2 (250MW) at generation end and connected with two nos. ISTS bays at Jam Khambhaliya ISTS with sharing D/c tower for some portion as detailed below: 220kV S/c line on D/c tower from PSS-01 to Common point 220kV S/c line on D/c tower from PSS-02 to Common point 220kV D/c line on D/c tower from Common point to Jam Khambhaliya PS. • 2 nos. 220kV line bay at Jam Khambhaliya PS implemented under ISTS | 0 | 220 kV | Aug without ATS |  |  | Part A • Establishment of 2x1500MVA 765/400kV Jamnagar(GIS) PS • Halvad – Jamnagar 765kV D/c line • LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of CGPL– Jetpur 400kV D/c (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad– Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part B: • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 3x500MVA, 400/220kV ICT (5th, 6th & 7th) | Part A • Establishment of 2x1500MVA 765/400kV Jamnagar(GIS) PS • Halvad – Jamnagar 765kV D/c line • LILO of Jam Khambhaliya PS – Lakadia 400 kV D/c (triple snowbird) line at Jamnagar • Jamnagar – Jam Khambhaliya 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of CGPL– Jetpur 400kV D/c (triple snowbird) line at Jamnagar • LILO of both ckts of Kalavad– Bhogat 400kV D/c line (Twin AL-59) at Jam Khambhaliya PS Part B: • Augmentation of transformation capacity at Jam Khambhaliya PS (GIS) by 3x500MVA, 400/220kV ICT (5th, 6th & 7th) | 16-Apr-26 | 16-Apr-26 |  |  | 14 | 211 & 212 |  |  |  |  | 2026-10-14 | 2027-06-30 |  | Not effective | 2026-10-14 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 14.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 16-Apr-26 |  | 2026-04-16 | 2027-06-30
2200000566 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 20 |  | 0 | 20 | 0 | 20 | SECI | Granted | 10 | 0 | 10 | Bhuj | Gujarat | 2024-10-01 | 2026-04-16 | NTPC REL shall share the Dedicated Transmission System for Connectivity granted to Ayana Renewable Power Four Private Limited (ARP4PL) for Hybrid RE project of 100MW against Connectivity appl. no. 2200000239 as given below · ARP4PL – Bhuj PS 220kV Sc line along with associated line bay at generating station (under the scope of applicant) · Bay No. 206 at Bhuj PS shall be implemented under ISTS. | 0 | 220 KV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA • Installation of 1x500MVA, 400220kV 9th ICT at Bhuj PS (Awarded to POWERGRID vide CTU letter dated 02.01.2024 with Implementation time-frame of 18 months) | Common Transmission System Augmentation for Connectivity under GNA • Installation of 1x500MVA, 400220kV 9th ICT at Bhuj PS (Awarded to POWERGRID vide CTU letter dated 02.01.2024 with Implementation time-frame of 18 months) | 16-Apr-26 | 16-Apr-26 |  |  | 10 | 206 | 2027-01-09 |  | PPA has been signed between NTPC REL and SECI w.e.f. 21.06.2024, SCD of the project is 20.06.2026. Further amendment was issued in the PPA on 27.01.2025, the revised SCD is 09.01.2027. | 2025-04-01 | 2025-07-02 |  | 2026-01-15 | Not effective | 2026-08-25 | Commissioned | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 10.00 ¦ Date: 2026-10-30 ¦ Status: Under Implementation ¦ Type: Wind | 01-04-2026 | Yes | Bay charged on 11.02.2025, POWERGRID is filling petition in CERC for DOCO of the bay w.e.f. 01.04.2025 | 08/07/2026 | Pending with Level 2 | 16-Apr-26 |  | 2026-04-16 | 2027-01-09
2200000567 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Barmer-II | Rajasthan | 2026-01-19 |  | Common Pooling station for NTPC Renewable Energy Limited Solar Power Projects (2200000567 (300MW) & 22000000906 (500 MW)) – Barmer-II PS 400 kV Sc line on Dc tower# (Suitable to carry minimum 900 MW per circuit at nominal voltage)-Under Applicant Scope | 1 | 400 KV | Aug without ATS |  |  |  | Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 31-Mar-26 | 31-Mar-26 |  |  | 300 | N | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2030-09-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2030-12-30
2200000580 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 500 |  | 200 | 0 | 0 | 200 | NTPC | Granted | 200 | 0 | 200 | Barmer-II | Rajasthan | 2026-01-19 |  | Common Pooling station for Avaada Energy Private Limited Solar Power Projects (App. No. 2200000580 (200 MW) & 2200000636 (450MW) – Barmer-II PS 220 kV Dc line (Suitable to carry minimum 325 MW per circuit at nominal voltage)-Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA (Tentative) 1. Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 2. 400220kV, 6x500 MVA ICTs at Barmer-II PS 3. LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS 4. Barmer-II PS- Barmer-I PS 400kV Dc line (Quad) 5. Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation 6. Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) 7. Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor 8. LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss 9. ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 10. 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 26-Mar-26 | 26-Mar-26 |  |  | 200 | N | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 26-Mar-26 |  | 2026-03-26 | 2030-12-30
2200000583 | Main-Connectivity under GNA |  | RENEW VIKRAM SHAKTI PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 140 |  | 0 | 140 | 0 | 140 |  | Granted | 140 | 0 | 140 | Ananthapuram | Andhra Pradesh | 2025-12-17 | 2028-02-29 | •Generating Pooling Station of Ms Renew Vikram Shakti Pvt. Ltd. – Ananthapuram PS 220 kV Sc line on Dc tower# along with line bay at generation pooling station –under the scope of applicant. •1 no. 220 kV line bay at Ananthapuram PS for termination of above mentioned line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (augmentation other than ATS) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmis | Common Transmission system required for effectiveness of connectivityGNA (augmentation other than ATS) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh | 29-Feb-28 | 29-Feb-28 |  |  | 140 | 207 |  |  |  | 2026-03-31 | 2025-09-27 | 2026-10-31 |  | Not effective | 2028-02-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 140.00 ¦ Date: 2028-02-29 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 29-Feb-28 |  | 2028-02-29 | 2028-08-29
2200000584 | Main-Connectivity under GNA |  | UPC RENEWABLES INDIA MANAGEMENT PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 160 |  | 0 | 160 | 0 | 160 |  | Granted | 160 | 0 | 160 | Bijapur | Karnataka | 2025-04-01 | 2027-01-17 | •Generation Pooling Station of M/s UPC Renewables India Management Pvt. Ltd. – Bijapur PS 220 kV S/c line on D/c tower along with line bay at generation pooling station – under the scope of applicant •1 no. 220 kV line bay at Bijapur PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | 30-Sep-26 | 30-Sep-26 |  |  | 160 | 208 |  |  |  | 2027-01-16 | 2027-01-16 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 120.00 ¦ Date: 2027-01-17 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 40.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Sep-26 |  | 2026-09-30 | 2027-07-17
2200000586 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 252 | 0 | 0 | 252 | 0 | 252 |  | Granted | 252 | 0 | 252 | Bijapur | Karnataka | 2025-04-01 | 2027-04-30 | •Generation Pooling Station of M/s Sunsure Solarpark RJ One Pvt. Ltd. – Bijapur PS 220 kV S/c line along with line bay at generation pooling station – under the scope of applicant. •1 no. 220 kV line bay at Bijapur PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | 31-Dec-26 | 31-Dec-26 |  |  | 252 | 206 |  |  |  | 2027-01-16 | 2027-01-16 | 2027-03-31 |  | Not effective | 2027-04-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-04-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2027-05-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 50.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 4 ¦ MW: 102.00 ¦ Date: 2027-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2027-10-30
2200000594 | Main-Connectivity under GNA |  | GRT JEWELLERS (INDIA) PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 |  | 150 | 0 | 0 | 150 | SJVN | Granted | 150 | 0 | 150 | Tuticorin-II | Tamil Nadu | 2024-07-16 | 2026-05-04 | •Through dedicated connectivity transmission system granted to M/s GRT jewellers (India) Pvt. Ltd. for application no. 1200002293 i.e. GRT jewellers (India) Pvt. Ltd – Tuticorin-II (GIS) 230 kV S/c line – all arrangement under the scope of applicant | 0 | 230 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. • Augmentation of 1x500 MVA, 400/230 kV (6th) ICT at Tuticorin-II PS. Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Augmentation of transformation capacity at 400/230kV Tuticorin-II GIS PS in Tamil Nadu by 500 MVA, (6th) 400/230kV ICT | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. • Augmentation of 1x500 MVA, 400/230 kV (6th) ICT at Tuticorin-II PS. Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Augmentation of transformation capacity at 400/230kV Tuticorin-II GIS PS in Tamil Nadu by 500 MVA, (6th) 400/230kV ICT | 04-May-26 | 04-May-26 |  |  | 150 | 207 | 2026-06-28 |  |  |  | 2025-12-22 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 04-May-26 |  | 2026-05-04 | 2026-10-31
2200000602 | Main-Connectivity under GNA |  | ADANI GREEN ENERGY LIMITED | WR | Land Route | (x) Renewable Power Park developer | Hybrid | 65 MW (Solar 50MW Wind 35MW) | 0 | 50 | 35 | 0 | 85 |  | Granted | 65 | 0 | 65 | KPS-3 (Sec-II) | Gujarat | 2025-01-09 | 2029-12-12 | AGEL shall share the DTL & 40033 kV Switchyard (PSS-14) of AGEL’s Application no. 2200000953 (Hybrid 1530 MW) as given below • AGEL (PSS-14) – KPS3 (Sec-II) 400kV Dc line (with minimum capacity of 1965MW at nominal voltage) along with associated bays at generation end (under the scope of AGEL) • 2 nos. 400kV bays on Bus Section-II at KPS3 (under ISTS) | 0 | 400 KV | Aug without ATS |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmeda | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari(New) 765 kV Dc line Khavda Phase-IV • Creation of 765kV bus section-II at KPS3 (GIS) along with 765kV Bus Sectionaliser • Creation of 400kV bus section-II at KPS3 (GIS) along with 400kV Bus Sectionaliser • KPS3 (GIS) – Lakadia (AIS) 765 kV DC line • ±300MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400kV Bus section-2 • KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line • Establishment of 2x1500MVA, 765400kV & 2x500MVA, 400220kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) • Vadodara(GIS) –South Olpad(GIS) 765 kV DC line • LILO of Gandhar – Hazira 400kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • Ahmedabad – South Olpad(GIS) 765kV Dc line • Establishment of 4X1500 MVA 765400 kV & 2x500MVA 400220kV Boisar-II (GIS) • South Olpad(GIS) – Boisar-II(GIS) 765kV Dc line • LILO of Navsari(New) – Padghe(PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon(MH) 400kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of Babhaleswar – Padghe(M) 400kV Dc line at Boisar-II (Sec-I) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-I of Boisar-II and ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-II of Boisar-II • ±300 MVAr STATCOM with 3x125 MVAr MSC, 1x125 MVAr MSR at 400 kV level of Navsari(New)(PG) Ss with 1 No. of 400 kV bay (GIS) • Establishment of 2X1500 MVA 765400 kV & 3x500MVA 400220kV Pune-III (GIS) • Boisar-II – Pune- | 31-May-25 | 31-May-25 |  |  | 65 | 435M 434T & 438M 437T |  |  |  | 2026-08-30 | 2029-05-19 | 2029-05-19 |  | Not effective | 2029-12-12 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2029-12-12 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 35.00 ¦ Date: 2029-12-12 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2030-06-12
2200000603 | Main-Connectivity under GNA |  | ADANI GREEN ENERGY LIMITED | WR | Land Route | (x) Renewable Power Park developer | Wind | 75 | 0 | 0 | 75 | 0 | 75 |  | Granted | 75 | 0 | 75 | KPS-3 (Sec-II) | Gujarat | 2025-01-09 | 2029-12-12 | Ms AGEL shall share the DTL & 40033 kV Switchyard (PSS-13) granted to Ms AGEL for its 1250MW HPP against application no. 2200000476 as given above | 0 |  | Aug without ATS |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmeda | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari(New) 765 kV Dc line Khavda Phase-IV • Creation of 765kV bus section-II at KPS3 (GIS) along with 765kV Bus Sectionaliser • Creation of 400kV bus section-II at KPS3 (GIS) along with 400kV Bus Sectionaliser • KPS3 (GIS) – Lakadia (AIS) 765 kV DC line • ±300MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400kV Bus section-2 • KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line • Establishment of 2x1500MVA, 765400kV & 2x500MVA, 400220kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) • Vadodara(GIS) –South Olpad(GIS) 765 kV DC line • LILO of Gandhar – Hazira 400kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • Ahmedabad – South Olpad(GIS) 765kV Dc line • Establishment of 4X1500 MVA 765400 kV & 2x500MVA 400220kV Boisar-II (GIS) • South Olpad(GIS) – Boisar-II(GIS) 765kV Dc line • LILO of Navsari(New) – Padghe(PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon(MH) 400kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of Babhaleswar – Padghe(M) 400kV Dc line at Boisar-II (Sec-I) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-I of Boisar-II and ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-II of Boisar-II • ±300 MVAr STATCOM with 3x125 MVAr MSC, 1x125 MVAr MSR at 400 kV level of Navsari(New)(PG) Ss with 1 No. of 400 kV bay (GIS) • Establishment of 2X1500 MVA 765400 kV & 3x500MVA 400220kV Pune-III (GIS) • Boisar-II – Pune- | 31-May-25 | 31-May-25 |  |  | 75 | 432M & 431T |  |  |  | 2026-08-30 | 2029-05-19 | 2029-05-19 |  | Not effective | 2029-12-12 | Under Construction | Part Commissioned | 72.8 | ¦ Phase 1 ¦ MW: 41.60 ¦ Date: 2025-03-09 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 15.60 ¦ Date: 2025-03-28 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 15.60 ¦ Date: 2025-03-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 2.20 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2030-06-12
2200000610 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 200 | 0 | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Lakadiya | Gujarat | 2025-07-21 | 2026-11-19 | • SRIPL – Lakadia 220kV Sc line on Dc tower along with associated bays at generation end (under the scope of applicant). • 1 no. 220kV bay at ISTS end is already under approval under ISTS | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity a | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited Augmentation of transformation capacity at Lakadia PS by 4x500MVA, 400220kV ICTs (3rd to 6th) & 1x1500MVA 765400kV ICT (3rd) Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat un | 30-Jun-26 | 30-Jun-26 |  |  | 200 | 223 |  |  |  | 2026-08-14 | 2026-11-19 | 2027-10-31 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-05-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-10-31
2200000612 | Main-Connectivity under GNA |  | SPRNG WIND ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Raghanesda | Gujarat | 2026-01-05 | 2028-06-30 | • SWEPL – Raghanesda 400kV Sc line (on Dc tower) (refer Note-A) along with associated bays at generation end. • 1 no. 400kV line bay on ISTS end is under approval in ISTS | 1 |  | Aug without ATS |  |  | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc l | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV Dc line • LILO of Navsari (New) – | 30-Jun-28 | 30-Jun-28 |  |  | 200 | 451 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2028-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-28 |  | 2028-06-30 | 2028-12-30
2200000614 | Main-Connectivity under GNA |  | SPRNG OJAS PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Raghanesda | Gujarat | 2026-01-05 | 2028-12-31 | Ms SOPL shall share the dedicated Transmission Line proposed for Ms SWEPL (with appln. no. 2200000612) for its 200MW SPP as given below • SWEPL – Raghanesda 400kV Sc line (on Dc tower) along with associated bays at generation end. • 1 no. 400kV line bay on ISTS end is under approval in ISTS | 0 | 400 KV | Aug without ATS |  |  | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc l | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV Dc line • LILO of Navsari (New) – | 31-Dec-28 | 31-Dec-28 |  |  | 200 | 451 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2028-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-28 |  | 2028-12-31 | 2029-06-30
2200000618 | Main-Connectivity under GNA |  | MIGOS HYBREN PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 600 | 0 | 600 | 0 | 0 | 600 |  | Granted | 600 | 0 | 600 | Ramgarh | Rajasthan | 2025-07-06 |  | • Migos Hybren Private Limited Solar Power Project –– Ramgarh PS 220 kV Dc line (Suitable to carry minimum 300 MW per circuit at nominal voltage)-Under Applicant Scope • Implementation of 2 No. of 220 kV Bay at Ramgarh PS is under ISTS Scope | 2 | 220 KV | Aug without ATS |  |  | A. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part B1- Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 3x500 MVA, 400220 kV pooling station at Bhadla-3 along with 2x330 MVAr (765kV) Bus Reactor & 2x12 | A. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part B1- Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 3x500 MVA, 400220 kV pooling station at Bhadla-3 along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 2. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line B. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part C1 - Commissioned 1. Establishment of 2x1500 MVA, 765400kV & 2x500 MVA, 400220 kV pooling station at Ramgarh along with 2x240 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus reactor 2. Ramgarh PS – Bhadla-III PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Ramgarh end C. Additional Transmission system for evacuation of power from Bhadla-III PS as part of Rajasthan REZ Phase-III scheme (20 GW) 1. Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III PS D. Transmission system strengthening for interconnections of Bhadla-III & Bikaner-III complex 1. Bhadla-III – Bikaner-III 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end as well as associated 2 Nos. of 765kV line bay(s) at each at Bhadla-III & Bikaner-III end E. Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase III Part A3 1. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III–Bhadla-III 400kV Dc line F. Transmission system for evacuation of power from REZ in Rajasthan (20 GW) under Phase-III Part I 1. Establishment of 6000 MW, ± 800 kV Bhadla (HVDC) [LCC] terminal station (4x1500 MW) at a suitable location near Bhadla-III substation 2. Establishment of 6000 MW, ±800 kV Fatehpur (HVDC) [LCC] terminal station (4x1500 MW) at suitable location near Fatehpur (UP) 3. Bhadla-III – Bhadla (HVDC) 400 kV 2xDc line (Quad) along with the line bays at both substations 4. ±800 kV HVDC line (Hexa Lapwing) between Bhadla (HVDC) & Fatehpur (HVDC) (with Dedicated Metallic Return) 5. Augmentation of 5x1500 MVA, 765400 kV ICTs at Fatehpur (HVDC) along with 2x330 MVAr (765kV) bus reactor 6. LILO of both ckts of 765 kV Varanasi – Kanpur (GIS) Dc line at Fatehpur G. Augmentation at Bhadla-III, Ramgarh PS and Kanpur (PG) 1. Augmentation of 765400kV, 2x1500 MVA(3rd & 4th) ICTs at Ramgarh PS 2. Augmentation of 40 | 31-Dec-26 | 31-Dec-26 |  |  | 600 | 207,208 | [7 empty] | Not effective | 2029-07-20 |  | Not commissioned | 0 | [5 empty] | Not Submitted For Approval | 31-Dec-26 |  | 2026-12-31 | 2026-12-31
2200000625 | Main-Connectivity under GNA |  | LAYER HYBREN PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 140 (100- Solar; 40 Wind) |  | 100 | 40 | 0 | 140 |  | Granted | 140 | 0 | 140 | Davangere | Karnataka | 2025-07-18 | 2027-03-22 | • Generation Pooling Station of M/s Layer Hybren Pvt. Ltd. – Davanagere/ Chitradurga PS 220 kV S/c line along with line bay at generation pooling station – under the scope of applicant • 1 no. 220 kV line bay at Chitradurga/ Davangere PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for integration of Davangere / Chitradurga REZ | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for integration of Davangere / Chitradurga REZ | 31-Aug-26 | 31-Aug-26 |  |  | 140 | 202 |  |  |  | 2027-03-21 | 2027-03-21 | 2027-09-30 |  | Not effective | 2027-03-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 40.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2025 |  |  | 08/07/2026 | Pending with Level 2 | 31-Aug-26 |  | 2026-08-31 | 2027-09-30
2200000633 | Main-Connectivity under GNA |  | JINDAL POWER LIMITED | SR | Land Route | (xi) REGS with an installed capacity of 5 MW and above applying for grant of Connectivity to ISTS through the electrical system of a generating station already having Connectivity to ISTS | Solar | 52.6 |  | 52.6 | 0 | 0 | 52.6 |  | Granted | 52.6 | 0 | 52.6 | Nellore | Andhra Pradesh | 2024-11-06 | 2025-01-01 | Through electrical system of M/s Jindal Power Ltd. erstwhile Simhapuri Energy Limited (SEL), which is already connected with ISTS | 1 | 220 KV | Aug without ATS |  |  | · Augmentation of 400/220kV transformation capacity at 765/400/220kV Karera (near Datia) S/s (Sec-I) by 1x500MVA ICT (3rd) | · Augmentation of 400/220kV transformation capacity at 765/400/220kV Karera (near Datia) S/s (Sec-I) by 1x500MVA ICT (3rd) | 29-Jun-24 | 29-Jun-24 |  |  | 52.6 | 410 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 52.60 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 29-Jun-24 |  | 2024-06-29 | 2026-10-31
2200000634 | Main-Connectivity under GNA |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 600 | 0 | 600 | 0 | 0 | 600 |  | Granted | 600 | 0 | 600 | Bhuj | Gujarat | 2025-01-21 | 2026-11-19 | • INGEPL – Bhuj PS 220kV Dc line along with associated bays at generation end (under the scope of the applicant). • 2 nos. 220kV bays at Bhuj PS to be implemented under ISTS. | 2 | 220 KV | Aug without ATS |  |  | • Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th) • Banaskantha – Ahmedabad 765kV Dc line • Lakadia PS – Ahmedabad 765kV Dc line • Establishment of 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line | • Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th) • Banaskantha – Ahmedabad 765kV Dc line • Lakadia PS – Ahmedabad 765kV Dc line • Establishment of 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc Under Tendering • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs & 2x500 MVA 400220kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • Ahmedabad – South Olpad (GIS) 765kV Dc line • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad – Boisar-II 765kV Dc line • LILO of Navsari (New) – Padghe (PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon (MH) 400 kV Dc • LILO of Babhaleswar – Padghe (M) 400 kV Dc line at Boisar-II (Sec-I) • Establishment of 765400220kV Pune-III (GIS) Ss with 3x1500 MVA ICTs & 3x500MVA ICTs • Boisar-II – Pune-III 765kV Dc line • LILO of Narendra (New) – Pune (GIS) 765kV Dc line at Pune-III | 17-Jul-25 | 17-Jul-25 |  |  | 600 | 217 & 218 |  |  |  | 2027-03-31 | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 600.00 ¦ Date: 2026-11-19 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 17-Jul-25 |  | 2025-07-17 | 2027-10-30
2200000636 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 450 |  | 450 | 0 | 0 | 450 | SJVN | Granted | 450 | 0 | 450 | Barmer-II | Rajasthan | 2026-01-19 |  | Common Pooling station for Avaada Energy Private Limited Solar Power Projects (App. No. 2200000580 (200 MW) & 2200000636 (450MW) – Barmer-II PS 220 kV Dc line (Suitable to carry minimum 325 MW per circuit at nominal voltage)-Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  |  | 1. Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 2. 400220kV, 6x500 MVA ICTs at Barmer-II PS 3. LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS 4. Barmer-II PS- Barmer-I PS 400kV Dc line (Quad) 5. Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation 6. Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) 7. Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor 8. LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss 9. ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 10. 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 30-Sep-26 | 30-Sep-26 |  |  | 450 | N | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 450.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  |  | Pending with Level 2 | 30-Sep-26 |  | 2026-09-30 | 2030-12-30
2200000639 | Main-Connectivity under GNA |  | RDS SOLAR PARK PRIVATE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 350 | 0 | 300 | 50 | 0 | 350 |  | Granted | 350 | 0 | 350 | Lakadiya | Gujarat | 2025-06-24 | 2026-11-19 | Under the scope of Ms RDSSPPL 1. Establishment of RDSSPPL Solar PSS 2. Establishment of RDSSPPL Wind PSS 3. RDSSPPL Wind PSS to RDSSPPL Solar PSS 220kV Sc line on DC tower 4. RDSSPPL Solar PSS – Lakadia 220kV Sc line on Dc tower along with associated bays at generation end (under the scope of applicant). Note Ms AMNSIL (application no- 2200000324) shall utilize the Dc tower of 220kV Sc line (on Dc towers) of Ms RDSSPPL for stringing of second circuit from RDSSPPL Solar PSS (AP-02) to Lakadia ISTS PS. Under the scope of ISTS 1. 1 no. 220kV bay at ISTS end is under implementation under ISTS scheme “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” by Ms LBPTL. | 1 | 220 KV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA Under Approval • Augmentation of transformation capacity at Lakadia PS by 6x500MVA, 400220kV ICTs & 1x1500MVA 765400kV ICT (3rd) Under Implementation • Establishment of 2x500MV | Common Transmission System Augmentation for Connectivity under GNA Under Approval • Augmentation of transformation capacity at Lakadia PS by 6x500MVA, 400220kV ICTs & 1x1500MVA 765400kV ICT (3rd) Under Implementation • Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS • Lakadia – Ahmedabad 765kV Dc line • Establishment of 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari(New) 765 kV Dc Under Tendering • Establishment of 765400220kV South Olpad (GIS) Ss with 2 x 1500MVA ICTs & 2x500 MVA ICTs • Ahmedabad – South Olpad (GIS) 765kV Dc line • Establishment of 765400220kV Boisar-II (GIS) Ss with 4 x 1500MVA ICTs & 2x500 MVA ICTs • South Olpad – Boisar-II 765kV Dc line • LILO of Navsari (New) – Padghe (PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon (MH) 400 kV Dc • LILO of Babhaleswar – Padghe (M) 400 kV Dc line at Boisar-II (Sec-I) • Establishment of 765400220kV Pune-III (GIS) Ss with 3 x1500 MVA ICTs & 3x500MVA ICTs • Boisar-II – Pune-III 765kV Dc line • LILO of Narendra (New) – Pune (GIS) 765kV Dc line at Pune-III • LILO of Hinjewadi-Koyna 400 kV Sc line at Pune-III (GIS) Ss | 30-Jun-26 | 30-Jun-26 |  |  | 350 | 224 |  |  |  | 2026-08-14 | 2026-11-19 | 2027-10-31 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-08-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2027-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-10-31
2200000640 | Main-Connectivity under GNA |  | HERO SOLAR ENERGY PRIVATE LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | Total: 312 MW Solar: 132 MW Wind:180 MW |  | 132 | 180 | 25 | 337 | NHPC | Granted | 250 | 0 | 250 | Bidar | Karnataka | 2025-03-28 | 2027-03-31 | •Common Generation Pooling Station of M/s Hero Solar Energy Pvt. Ltd. for application no. 2200000640 (250 MW) and 2200000422 (300 MW) – Bidar PS 220 kV single circuit [through stringing of 2nd circuit on 220 kV D/c towers of DTL for application no. 2200000422] along with line bay at generation pooling station – under the scope of applicant •1 no. 220 kV line bay at Bidar PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | 31-Mar-27 | 31-Mar-27 |  |  | 250 | 204 | 2027-04-30 |  |  | 2026-06-30 | 2026-02-09 | 2026-10-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 180.00 ¦ Date: 2026-12-23 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 132.00 ¦ Date: 2026-12-23 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 25.00 ¦ Date: 2026-12-23 ¦ Status: Under Implementation ¦ Type: Standalone | 30.06.2026 | Yes |  |  | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2027-04-30
2200000641 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 200 | 0 | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Lakadiya | Gujarat | 2025-07-21 | 2027-03-31 | As confirmed by Ms SRIPL vide letter dated 07.05.2024, they shall share dedicated transmission system identified for its other 200MW Hybrid RE Project (Appl. No. 2200000610) as given below • SRIPL – Lakadia 220kV Sc line (on Dc Tower) along with associated bays at generation end (under the scope of applicant). • 1 no. 220kV bay at ISTS end is already under approval under ISTS | 0 | 220 KV | Aug without ATS |  |  | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capac | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited Augmentation of transformation capacity at Lakadia PS by 5x500MVA, 400220kV ICTs (3rd to 7th) & 1x1500MVA 765400kV ICT (3rd) Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujar | 30-Jun-26 | 30-Jun-26 |  |  | 200 | N |  |  |  | 2026-08-14 | 2026-11-19 | 2027-10-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-10-31
2200000644 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Sirohi | Rajasthan | 2025-05-27 | 2027-03-24 | Serentica Renewables India Private Limited Solar Power Project– Sirohi PS 220 kV S/c line on D/c tower# (suitable to carry minimum 300 MW at nominal voltage)-Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Augmentation of 5x500 MVA, 400/220kV ICTs at Sirohi PS Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Augmentation of 5x500 MVA, 400/220kV ICTs at Sirohi PS Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 30-Jun-26 | 30-Jun-26 |  |  | 300 | 207 |  |  |  | 2027-03-31 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-09-24
2200000646 | Main-Connectivity under GNA |  | ILLUMINATE HYBREN PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 296 | 0 | 296 | 0 | 0 | 296 | NTPC | Granted | 300 | 4 | 296 | Sirohi | Rajasthan | 2025-05-27 | 2027-03-24 | Illuminate Hybren Private Limited Solar Power Project– Sirohi PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage)-Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Establishment of 2x1500 MVA, 765400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Augmentation of 5x500 MVA, 400220kV ICTs at Sirohi PS Sirohi PS-Chittorgarh (PG) 400 kV Dc line al | Establishment of 2x1500 MVA, 765400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Augmentation of 5x500 MVA, 400220kV ICTs at Sirohi PS Sirohi PS-Chittorgarh (PG) 400 kV Dc line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta Dc line at Rishabdeo Ss Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line Establishment of 765400 kV (2x1500 MVA Kurawar Ss with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line LILO of Indore – Bhopal 765 kV Sc line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV Dc line at Astha Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line Sirohi – Mandsaur PS 765KV Dc line along with 240 MVAr switchable line reactor at Sirohi Ss end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV Dc line Mandsaur PS – Khandwa (New) 765kV Dc line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV Dc line | 30-Jun-26 | Phase 1 ¦ MW: 296.00 ¦ Date: 2026-06-30 |  |  | 296 | 208 |  |  |  | 2027-03-31 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-24 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 296.00 ¦ Date: 2026-06-30 | 296 | 2026-06-30 | 2027-06-30
2200000650 | Main-Connectivity under GNA |  | SPRNG VAYU KIRAN PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Raghanesda | Gujarat | 2026-01-02 | 2029-12-31 | Ms SVKPL shall share the dedicated Transmission Line proposed for Ms SWEPL (with appln. no. 2200000612) for its 200MW SPP as given below • SWEPL – Raghanesda 400kV Sc line (on Dc tower) along with associated bays at generation end. • 1 no. 400kV line bay on ISTS end is under implementation as part of Raghanesda PS (being implemented by Dineshchandra R. Agrawal Infracon Private Limited) | 0 | 400 KV | Aug without ATS |  |  | Under Implementation (SCOD progressively by 23.10.2027) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone Khavda RE Transmission Limited (a subsidiary of POWERGRID) • Banaskantha – Ahm | Under Implementation (SCOD progressively by 23.10.2027) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone Khavda RE Transmission Limited (a subsidiary of POWERGRID) • Banaskantha – Ahmedabad 765kV Dc line Khavda Phase-II Part C Scheme Khavda II-C Transmission Ltd. (a subsidiary of POWERGRID) • Establishment of 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line Khavda Phase-II Part D Scheme Torrent Power Grid Limited (TPGL) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc Transmission system for evacuation of 3GW RE power from Raghanesda Area of Gujarat-3GW under Phase-I Dineshchandra R. Agrawal Infracon Private Limited • Establishment of 4x1500MVA, 765400kV Ss near Raghanesda • Raghanesda (GIS) – Banaskantha (PG) 765kV Dc line Transmission System for Evacuation of Power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7 GW) Part B South Olpad Transmission Limited (a subsidiary of POWERGRID) • Establishment of 765400220kV South Olpad (GIS) Ss with 2 x 1500MVA ICTs & 2x500 MVA ICTs • Vadodara – South Olpad(GIS) 765kV Dc line • Ahmedabad – South Olpad(GIS) 765kV Dc line Transmission System for Evacuation of Power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7 GW) Part C Khavda IV C Power Transmission Limited (a subsidiary of Sterlite) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4 x 1500MVA ICTs & 2x500 MVA ICTs • South Olpad – Boisar-II 765kV Dc line • LILO of Navsari (New) – Padghe (PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon (MH) 400 kV Dc • LILO of Babhaleswar – Padghe (M) 400 kV Dc line at Boisar-II (Sec-I) Transmission System for Evacuation of Power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7 GW) Part D (expected by 19.11.2026) Pune-III Transmission Limited (a subsidiary of Adani) • Establishment of 765400220kV Pune-III (GIS) Ss with 3 x1500 MVA ICTs & 3x500MVA ICTs • Boisar-II – Pune-III 765kV Dc line • LILO of Narendra (New) – Pune (GIS) 765kV Dc line at Pune-III • LILO of Hinjewadi-Koyna 400 kV Sc line at Pune-III (GIS) Ss | 31-Dec-29 | 31-Dec-29 |  |  | 200 | 451 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2029-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-29 |  | 2029-12-31 | 2030-06-30
2200000651 | Main-Connectivity under GNA |  | SPRNG OJAS PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Raghanesda | Gujarat | 2026-01-05 | 2028-12-31 | Ms SOPL shall share the dedicated Transmission Line proposed for Ms SWEPL (with application no. 2200000612) for its 100MW SPP as given below • SWEPL - Raghanesda 400kV Sc line (on Dc tower) along with associated bay at generation end. • 1 no. 400kV line bay on ISTS end is under implementation as part of Raghanesda PS (being implemented by Dineshchandra R. Agrawal Infracon Private Limited) | 0 | 400 KV | Aug without ATS |  |  | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc l | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV Dc line • LILO of Navsari (New) – | 31-Dec-28 | 31-Dec-28 |  |  | 100 | 451 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2028-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2028-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-28 |  | 2028-12-31 | 2029-06-30
2200000657 | Main-Connectivity under GNA |  | TEPSOL GREEN ENERGY PRIVATE LIMITED | SR | Land Route | (x) Renewable Power Park developer | Hybrid | 200 (Wind- 160 & Solar-40) |  | 40 | 160 | 0 | 200 |  | Granted | 200 | 0 | 200 | Bijapur | Karnataka | 2025-12-17 | 2027-01-17 | •Generation Pooling Station of Ms Tepsol Green Energy Pvt. Ltd. – Bijapur PS 220 kV Sc line along with line bay at generation pooling station – under the scope of applicant •1 no. 220 kV line bay at Bijapur PS for termination of above mentioned line – under the scope of applicant | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for integration of Bijapur REZ • ISTS Network Expansion scheme in Western Region & Souther | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for integration of Bijapur REZ • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | 30-Jun-26 | 30-Jun-26 |  |  | 200 | 224 |  |  |  |  | 2027-01-16 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-07-17
2200000658 | Main-Connectivity under GNA |  | PURVAH GREEN POWER PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 99 | 0 | 0 | 99 | 0 | 99 |  | Granted | 99 | 0 | 99 | Bhuj | Gujarat | 2025-04-07 | 2026-11-19 | PGPPL – Bhuj PS 220kV Sc line (on Dc tower) along with associated line bays at both ends. | 1 | 400 KV | Aug without ATS |  |  | Under Implementation Transmission Scheme for providing connectivity to REGS at Bhuj PS (Part System) (POWERGRID) (SCOD 20102026) Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (10th) with associated ICT bays | Under Implementation Transmission Scheme for providing connectivity to REGS at Bhuj PS (Part System) (POWERGRID) (SCOD 20102026) Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (10th) with associated ICT bays Augmentation of transformation capacity at 400220kV Bhuj PS in Gujarat by 1x500MVA, 400220kV ICT (9th) (POWERGRID) (SCOD 02072025) Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd.- POWERGRID) (SCOD 21032025) Banaskantha – Ahmedabad 765kV Dc line along with associated bays Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin | 31-Mar-26 | 31-Mar-26 |  |  | 99 | 236 |  |  |  |  | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 99.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2027-10-30
2200000660 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 720(Solar:360 MW; Wind: 360) |  | 360 | 360 | 0 | 720 |  | Granted | 300 | 0 | 300 | Davangere | Karnataka | 2025-12-17 | 2027-03-22 | •Generation Pooling Station of Ms Serentica Renewables India Pvt. Ltd. – Davanagere Chitradurga PS 220 kV Sc line on Dc tower along with line bay at generation pooling station – under the scope of applicant •1 no. 220 kV line bay at Chitradurga Davangere PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmiss | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for integration of Davangere Chitradurga | 30-Jun-26 | 30-Jun-26 |  |  | 300 | 210 |  |  |  | 2027-03-21 | 2027-03-21 | 2027-09-30 |  | Not effective | 2027-03-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 150.00 ¦ Date: 2027-09-21 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-09-30
2200000673 | Main-Connectivity under GNA |  | PERCENTUM RENEWABLES PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 148 | 0 | 0 | 148 | 0 | 148 |  | Granted | 148 | 0 | 148 | Lakadiya | Gujarat | 2025-12-29 | 2026-11-19 | • PRPL – Lakadia 220kV Sc line (on Dc towers)# along with associated bay at generation end. • 1 no. 220kV bay on Sec-II at ISTS end is under implementation under ISTS scheme “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” by Ms LBPTL. | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity a | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited Augmentation of transformation capacity at Lakadia PS by 4x500MVA, 400220kV ICTs (3rd to 6th) & 1x1500MVA 765400kV ICT (3rd) Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat un | 50MW(S) 28.02.202650MW(S) 31.03.202650MW(W) 30.04.202650MW(W) 31.05.202650MW(W) 30.06.202650MW(W) 31.07.2026 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-02-28 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-03-31 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-04-30 Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-31 Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 6 ¦ MW: 50.00 ¦ Date: 2026-07-31 |  |  | 148 | 225 |  |  |  | 2026-08-14 | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 98.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-02-28 | 50 | 2026-02-28 | 2027-10-30
2200000673 | Main-Connectivity under GNA |  | PERCENTUM RENEWABLES PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 148 | 0 | 0 | 148 | 0 | 148 |  | Granted | 148 | 0 | 148 | Lakadiya | Gujarat | 2025-12-29 | 2026-11-19 | • PRPL – Lakadia 220kV Sc line (on Dc towers)# along with associated bay at generation end. • 1 no. 220kV bay on Sec-II at ISTS end is under implementation under ISTS scheme “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” by Ms LBPTL. | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity a | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited Augmentation of transformation capacity at Lakadia PS by 4x500MVA, 400220kV ICTs (3rd to 6th) & 1x1500MVA 765400kV ICT (3rd) Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat un | 50MW(S) 28.02.202650MW(S) 31.03.202650MW(W) 30.04.202650MW(W) 31.05.202650MW(W) 30.06.202650MW(W) 31.07.2026 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-02-28 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-03-31 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-04-30 Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-31 Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 6 ¦ MW: 50.00 ¦ Date: 2026-07-31 |  |  | 148 | 225 |  |  |  | 2026-08-14 | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 98.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 50.00 ¦ Date: 2026-03-31 | 50 | 2026-03-31 | 2027-10-30
2200000673 | Main-Connectivity under GNA |  | PERCENTUM RENEWABLES PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 148 | 0 | 0 | 148 | 0 | 148 |  | Granted | 148 | 0 | 148 | Lakadiya | Gujarat | 2025-12-29 | 2026-11-19 | • PRPL – Lakadia 220kV Sc line (on Dc towers)# along with associated bay at generation end. • 1 no. 220kV bay on Sec-II at ISTS end is under implementation under ISTS scheme “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” by Ms LBPTL. | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity a | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited Augmentation of transformation capacity at Lakadia PS by 4x500MVA, 400220kV ICTs (3rd to 6th) & 1x1500MVA 765400kV ICT (3rd) Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat un | 50MW(S) 28.02.202650MW(S) 31.03.202650MW(W) 30.04.202650MW(W) 31.05.202650MW(W) 30.06.202650MW(W) 31.07.2026 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-02-28 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-03-31 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-04-30 Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-31 Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 6 ¦ MW: 50.00 ¦ Date: 2026-07-31 |  |  | 148 | 225 |  |  |  | 2026-08-14 | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 98.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 3 ¦ MW: 50.00 ¦ Date: 2026-04-30 | 50 | 2026-04-30 | 2027-10-30
2200000673 | Main-Connectivity under GNA |  | PERCENTUM RENEWABLES PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 148 | 0 | 0 | 148 | 0 | 148 |  | Granted | 148 | 0 | 148 | Lakadiya | Gujarat | 2025-12-29 | 2026-11-19 | • PRPL – Lakadia 220kV Sc line (on Dc towers)# along with associated bay at generation end. • 1 no. 220kV bay on Sec-II at ISTS end is under implementation under ISTS scheme “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” by Ms LBPTL. | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity a | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited Augmentation of transformation capacity at Lakadia PS by 4x500MVA, 400220kV ICTs (3rd to 6th) & 1x1500MVA 765400kV ICT (3rd) Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat un | 50MW(S) 28.02.202650MW(S) 31.03.202650MW(W) 30.04.202650MW(W) 31.05.202650MW(W) 30.06.202650MW(W) 31.07.2026 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-02-28 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-03-31 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-04-30 Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-31 Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 6 ¦ MW: 50.00 ¦ Date: 2026-07-31 |  |  | 148 | 225 |  |  |  | 2026-08-14 | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 98.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-31 | 50 | 2026-05-31 | 2027-10-30
2200000673 | Main-Connectivity under GNA |  | PERCENTUM RENEWABLES PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 148 | 0 | 0 | 148 | 0 | 148 |  | Granted | 148 | 0 | 148 | Lakadiya | Gujarat | 2025-12-29 | 2026-11-19 | • PRPL – Lakadia 220kV Sc line (on Dc towers)# along with associated bay at generation end. • 1 no. 220kV bay on Sec-II at ISTS end is under implementation under ISTS scheme “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” by Ms LBPTL. | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity a | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited Augmentation of transformation capacity at Lakadia PS by 4x500MVA, 400220kV ICTs (3rd to 6th) & 1x1500MVA 765400kV ICT (3rd) Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat un | 50MW(S) 28.02.202650MW(S) 31.03.202650MW(W) 30.04.202650MW(W) 31.05.202650MW(W) 30.06.202650MW(W) 31.07.2026 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-02-28 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-03-31 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-04-30 Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-31 Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 6 ¦ MW: 50.00 ¦ Date: 2026-07-31 |  |  | 148 | 225 |  |  |  | 2026-08-14 | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 98.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-30 | 50 | 2026-06-30 | 2027-10-30
2200000673 | Main-Connectivity under GNA |  | PERCENTUM RENEWABLES PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 148 | 0 | 0 | 148 | 0 | 148 |  | Granted | 148 | 0 | 148 | Lakadiya | Gujarat | 2025-12-29 | 2026-11-19 | • PRPL – Lakadia 220kV Sc line (on Dc towers)# along with associated bay at generation end. • 1 no. 220kV bay on Sec-II at ISTS end is under implementation under ISTS scheme “Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” by Ms LBPTL. | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity a | Under Implementation Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part A” Establishment of 2x500MVA, 400220kV ICTs at Lakadia PS Augmentation of transformation capacity at 765400 kV Lakadia Ss (WRSS XXI(A) Transco Ltd.) in Gujarat Part B” Lakadia B Power Transmission Limited Augmentation of transformation capacity at Lakadia PS by 4x500MVA, 400220kV ICTs (3rd to 6th) & 1x1500MVA 765400kV ICT (3rd) Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat un | 50MW(S) 28.02.202650MW(S) 31.03.202650MW(W) 30.04.202650MW(W) 31.05.202650MW(W) 30.06.202650MW(W) 31.07.2026 | Phase 1 ¦ MW: 50.00 ¦ Date: 2026-02-28 Phase 2 ¦ MW: 50.00 ¦ Date: 2026-03-31 Phase 3 ¦ MW: 50.00 ¦ Date: 2026-04-30 Phase 4 ¦ MW: 50.00 ¦ Date: 2026-05-31 Phase 5 ¦ MW: 50.00 ¦ Date: 2026-06-30 Phase 6 ¦ MW: 50.00 ¦ Date: 2026-07-31 |  |  | 148 | 225 |  |  |  | 2026-08-14 | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 98.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 6 ¦ MW: 50.00 ¦ Date: 2026-07-31 | 50 | 2026-07-31 | 2027-10-30
2200000681 | Main-Connectivity under GNA |  | SPRNG URJA PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 1000 | 0 | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | Barmer-II | Rajasthan | 2026-01-19 |  | Sprng Urja Private Limited Renewable Power Park – Barmer-II PS 400 kV Sc line on Dc tower# (suitable to carry minimum 1000 MW at nominal voltage)-Under Applicant Scope | 1 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA at Barmer-II PS(Tentative) Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 400220kV, 6x500 MVA ICTs at Barmer-II PS LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 200MW30-06-2029200MW31-12-2029200MW30-06-2030200MW31-12-2030200MW30-06-2031 | Phase 1 ¦ MW: 200.00 ¦ Date: 2029-06-30 Phase 2 ¦ MW: 200.00 ¦ Date: 2029-12-31 Phase 3 ¦ MW: 200.00 ¦ Date: 2030-06-30 Phase 4 ¦ MW: 200.00 ¦ Date: 2030-12-31 Phase 5 ¦ MW: 200.00 ¦ Date: 2031-06-30 |  |  | 1000 | No | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2029-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 200.00 ¦ Date: 2030-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 4 ¦ MW: 200.00 ¦ Date: 2030-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 5 ¦ MW: 200.00 ¦ Date: 2031-06-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 200.00 ¦ Date: 2029-06-30 | 200 | 2029-06-30 | 2030-12-30
2200000681 | Main-Connectivity under GNA |  | SPRNG URJA PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 1000 | 0 | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | Barmer-II | Rajasthan | 2026-01-19 |  | Sprng Urja Private Limited Renewable Power Park – Barmer-II PS 400 kV Sc line on Dc tower# (suitable to carry minimum 1000 MW at nominal voltage)-Under Applicant Scope | 1 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA at Barmer-II PS(Tentative) Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 400220kV, 6x500 MVA ICTs at Barmer-II PS LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 200MW30-06-2029200MW31-12-2029200MW30-06-2030200MW31-12-2030200MW30-06-2031 | Phase 1 ¦ MW: 200.00 ¦ Date: 2029-06-30 Phase 2 ¦ MW: 200.00 ¦ Date: 2029-12-31 Phase 3 ¦ MW: 200.00 ¦ Date: 2030-06-30 Phase 4 ¦ MW: 200.00 ¦ Date: 2030-12-31 Phase 5 ¦ MW: 200.00 ¦ Date: 2031-06-30 |  |  | 1000 | No | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2029-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 200.00 ¦ Date: 2030-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 4 ¦ MW: 200.00 ¦ Date: 2030-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 5 ¦ MW: 200.00 ¦ Date: 2031-06-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 200.00 ¦ Date: 2029-12-31 | 200 | 2029-12-31 | 2030-12-30
2200000681 | Main-Connectivity under GNA |  | SPRNG URJA PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 1000 | 0 | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | Barmer-II | Rajasthan | 2026-01-19 |  | Sprng Urja Private Limited Renewable Power Park – Barmer-II PS 400 kV Sc line on Dc tower# (suitable to carry minimum 1000 MW at nominal voltage)-Under Applicant Scope | 1 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA at Barmer-II PS(Tentative) Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 400220kV, 6x500 MVA ICTs at Barmer-II PS LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 200MW30-06-2029200MW31-12-2029200MW30-06-2030200MW31-12-2030200MW30-06-2031 | Phase 1 ¦ MW: 200.00 ¦ Date: 2029-06-30 Phase 2 ¦ MW: 200.00 ¦ Date: 2029-12-31 Phase 3 ¦ MW: 200.00 ¦ Date: 2030-06-30 Phase 4 ¦ MW: 200.00 ¦ Date: 2030-12-31 Phase 5 ¦ MW: 200.00 ¦ Date: 2031-06-30 |  |  | 1000 | No | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2029-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 200.00 ¦ Date: 2030-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 4 ¦ MW: 200.00 ¦ Date: 2030-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 5 ¦ MW: 200.00 ¦ Date: 2031-06-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 3 ¦ MW: 200.00 ¦ Date: 2030-06-30 | 200 | 2030-06-30 | 2030-12-30
2200000681 | Main-Connectivity under GNA |  | SPRNG URJA PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 1000 | 0 | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | Barmer-II | Rajasthan | 2026-01-19 |  | Sprng Urja Private Limited Renewable Power Park – Barmer-II PS 400 kV Sc line on Dc tower# (suitable to carry minimum 1000 MW at nominal voltage)-Under Applicant Scope | 1 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA at Barmer-II PS(Tentative) Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 400220kV, 6x500 MVA ICTs at Barmer-II PS LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 200MW30-06-2029200MW31-12-2029200MW30-06-2030200MW31-12-2030200MW30-06-2031 | Phase 1 ¦ MW: 200.00 ¦ Date: 2029-06-30 Phase 2 ¦ MW: 200.00 ¦ Date: 2029-12-31 Phase 3 ¦ MW: 200.00 ¦ Date: 2030-06-30 Phase 4 ¦ MW: 200.00 ¦ Date: 2030-12-31 Phase 5 ¦ MW: 200.00 ¦ Date: 2031-06-30 |  |  | 1000 | No | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2029-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 200.00 ¦ Date: 2030-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 4 ¦ MW: 200.00 ¦ Date: 2030-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 5 ¦ MW: 200.00 ¦ Date: 2031-06-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 4 ¦ MW: 200.00 ¦ Date: 2030-12-31 | 200 | 2030-12-31 | 2031-06-30
2200000681 | Main-Connectivity under GNA |  | SPRNG URJA PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 1000 | 0 | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | Barmer-II | Rajasthan | 2026-01-19 |  | Sprng Urja Private Limited Renewable Power Park – Barmer-II PS 400 kV Sc line on Dc tower# (suitable to carry minimum 1000 MW at nominal voltage)-Under Applicant Scope | 1 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA at Barmer-II PS(Tentative) Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 400220kV, 6x500 MVA ICTs at Barmer-II PS LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 200MW30-06-2029200MW31-12-2029200MW30-06-2030200MW31-12-2030200MW30-06-2031 | Phase 1 ¦ MW: 200.00 ¦ Date: 2029-06-30 Phase 2 ¦ MW: 200.00 ¦ Date: 2029-12-31 Phase 3 ¦ MW: 200.00 ¦ Date: 2030-06-30 Phase 4 ¦ MW: 200.00 ¦ Date: 2030-12-31 Phase 5 ¦ MW: 200.00 ¦ Date: 2031-06-30 |  |  | 1000 | No | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2029-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 200.00 ¦ Date: 2030-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 4 ¦ MW: 200.00 ¦ Date: 2030-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 5 ¦ MW: 200.00 ¦ Date: 2031-06-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | Phase 5 ¦ MW: 200.00 ¦ Date: 2031-06-30 | 200 | 2031-06-30 | 2031-12-30
2200000687 | Main-Connectivity under GNA |  | EG SOLWIN RENEWABLES PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 | 0 | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Bijapur | Karnataka | 2025-04-01 | 2027-01-17 | •Through sharing of dedicated connectivity transmission system of granted to M/s Tepsol Green Energy Pvt. Ltd. [granted connectivity for 200 MW against application no. 2200000657] i.e. M/s Tepsol Green Energy Pvt. Ltd. – Bijapur PS 220 kV S/c line – all arrangement under the scope of applicant. [Sharing as request of applicant under Regulation 5.6 of GNA Regulations] | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | 31-Dec-26 | 31-Dec-26 |  |  | 100 | 224 |  |  |  |  | 2027-01-16 | 2027-03-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-01-17 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2027-07-17
2200000692 | Main-Connectivity under GNA |  | VISMAYA RENEWABLES INDIA PROJECT PRIVATELIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bijapur | Karnataka | 2025-04-01 | 2027-10-01 | • Generation Station of M/s Vismaya Renewables India Project Pvt Ltd. – Bijapur PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant •01 no. 220 kV line bay at Bijapur PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission Scheme for integration of Bijapur REZ in Karnataka, as per Annexure-II• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission Scheme for integration of Bijapur REZ in Karnataka, as per Annexure-II• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | 01-Apr-27 | 01-Apr-27 |  |  | 300 | 210 |  |  |  | 2027-01-16 | 2027-01-16 | 2027-03-31 |  | Not effective | 2027-10-01 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-10-01 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 01-Apr-27 |  | 2027-04-01 | 2028-04-01
2200000698 | Main-Connectivity under GNA |  | AMPLUS SUN BEAT PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 80 |  | 0 | 80 | 0 | 80 |  | Granted | 80 | 0 | 80 | Karur | Tamil Nadu | 2025-08-14 | 2026-12-31 | •Through sharing of dedicated connectivity transmission system granted to Ms First Energy Pvt. Ltd. for application no. 2200000441 (100 MW) i.e. Generation Pooling Station of Ms First Energy Pvt. Ltd. –Karur PS 230 kV Sc line – all arrangement under the scope of applicant. (As per request of applicant) | 0 | 230 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. • Transmission Scheme for evacuation of power from RE sources in Karur Tirpur wind Energy Zone ( | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. • Transmission Scheme for evacuation of power from RE sources in Karur Tirpur wind Energy Zone (Tamil Nadu) (1000 MW) under Phase-II | 31-May-26 | 31-May-26 |  |  | 80 | 203 |  |  |  |  | 2026-02-28 | 2027-01-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-01-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 30.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-May-26 |  | 2026-05-31 | 2027-06-30
2200000699 | Main-Connectivity under GNA |  | AMPLUS THETA ENERGY PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 65 |  | 0 | 65 | 0 | 65 |  | Granted | 65 | 0 | 65 | Karur | Tamil Nadu | 2025-08-14 | 2026-12-31 | •Through sharing of dedicated connectivity transmission system granted to Ms First Energy Pvt. Ltd. for application no. 2200000441 (100 MW) i.e. Generation Pooling Station of Ms First Energy Pvt. Ltd. –Karur PS 230 kV Sc line – all arrangement under the scope of applicant. (as per request of applicant) | 0 | 230 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. • Transmission Scheme for evacuation of power from RE sources in Karur Tirpur wind Energy Zone ( | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. • Transmission Scheme for evacuation of power from RE sources in Karur Tirpur wind Energy Zone (Tamil Nadu) (1000 MW) under Phase-II | 31-May-26 | 31-May-26 |  |  | 65 | 203 |  |  |  |  | 2026-02-28 | 2027-01-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-01-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 15.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-May-26 |  | 2026-05-31 | 2027-06-30
2200000700 | Main-Connectivity under GNA |  | FURIES SOLREN PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Davangere | Karnataka | 2025-05-16 | 2027-03-22 | • Generation Pooling Station of M/s Furies Solren Pvt. Ltd. – Davanagere/ Chitradurga PS 220 kV S/c line along with line bay at generation pooling station – under the scope of applicant • 1 no. 220 kV line bay at Davanagere/ Chitradurga PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for integration of Davanagere / Chitradurga | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for integration of Davanagere / Chitradurga | 30-Jun-26 | 30-Jun-26 |  |  | 300 | 204 |  |  |  |  | 2027-03-21 | 2027-09-30 |  | Not effective | 2027-03-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Solar | 22.12.2025 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-09-30
2200000701 | Main-Connectivity under GNA |  | ILLUMINATE HYBREN PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 215 | 85 | 0 | 300 |  | Granted | 300 | 0 | 300 | Davangere | Karnataka | 2025-05-16 | 2027-03-22 | • Generation Pooling Station of M/s Illuminate Hybren Pvt. Ltd. – Davanagere/ Chitradurga PS 220 kV S/c line along with line bay at generation pooling station – under the scope of applicant • 1 no. 220 kV line bay at Davanagere/ Chitradurga PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for integration of Davanagere / Chitradurga | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for integration of Davanagere / Chitradurga | 30-Sep-26 | 30-Sep-26 |  |  | 300 | 206 |  |  |  | 2027-03-21 | 2027-03-21 | 2027-09-30 |  | Not effective | 2027-03-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  |  | Pending with Level 2 | 30-Sep-26 |  | 2026-09-30 | 2027-09-30
2200000702 | Main-Connectivity under GNA |  | LAYER HYBREN PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 160 (110- Solar; 50 Wind) |  | 110 | 50 | 0 | 160 |  | Granted | 160 | 0 | 160 | Davangere | Karnataka | 2025-07-18 | 2027-03-22 | Through dedicated connectivity transmission system granted to M/s Layer Hybren Pvt. Ltd. for application no. 2200000625 (for 140 MW) i.e. M/s Layer Hybren Pvt. Ltd. – Davanagere/ Chitradurga PS 220 kV S/c line – all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission System for integration of Davangere / Chitradurga REZ | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission System for integration of Davangere / Chitradurga REZ | 30-Sep-26 | 30-Sep-26 |  |  | 160 | 202 |  |  |  | 2027-03-21 | 2027-03-21 | 2027-09-30 |  | Not effective | 2027-03-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 110.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 30-Sep-26 |  | 2026-09-30 | 2027-09-30
2200000708 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 48 |  | 0 | 48 | 0 | 48 |  | Granted | 48 | 0 | 48 | Bijapur | Karnataka | 2025-04-01 | 2027-12-31 | Through dedicated Connectivity transmission system grant of Connectivity to M/s Sunsure SolarPark Rj One Pvt. Ltd. for application no. 2200000586 (252 MW) [i.e. Generation Station of M/s Sunsure SolarPark Rj One Pvt. Ltd.– Bijapur PS 220 kV S/c line alongwith line bay at generation PS – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission Scheme for integration of Bijapur REZ in Karnataka, as per Annexure-II• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission Scheme for integration of Bijapur REZ in Karnataka, as per Annexure-II• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bijapur REZ in Karnataka | 31-Dec-27 | 31-Dec-27 |  |  | 48 | 206 |  |  |  | 2027-01-16 | 2027-01-16 | 2027-03-31 |  | Not effective | 2027-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 48.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2028-06-30
2200000709 | Main-Connectivity under GNA |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Neemuch | Madhya Pradesh | 2024-10-01 | 2026-01-31 | • ACME CSPL – Neemuch 220kV Sc line along with associated bay at generation end (under the scope of applicant). • 1 no. 220kV line bay at Neemuch Ss to be implemented under ISTS based on feedback of applicant. | 1 | 220 KV | Aug without ATS |  |  | Existing Transmission System | Existing Transmission System | 30-04-2025 | 30-04-2025 |  |  | 300 | 209 |  |  |  | 2026-10-31 |  |  |  | Not effective | 2026-10-31 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 05/08/2026 | Pending with Level 2 | 30-04-2025 |  | 2025-04-30 | 2026-10-31
2200000713 | Main-Connectivity under GNA |  | Gentari Renewables India Caster One Private Limited (Formerly known as AMPLUS CENEDUS SOLAR PRIVATE LIMITED) | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 350 |  | 0 | 380 | 0 | 380 |  | Granted | 350 | 0 | 350 | Ananthapuram | Andhra Pradesh | 2025-05-29 | 2027-03-28 | • Generating Pooling Station of M/s Gentari Renewables India Castor One Pvt. Ltd.– Ananthapuram PS 220 kV S/c line on D/c tower# along with line bays at generation pooling station – under the scope of applicant. • 1 no. 220 kV line bay at Ananthapuram PS for termination of above mentioned dedicated connectivity line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh Annexure-II • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission scheme for Solar Energy Zone in Ananthpuram (Ananthapur) (2500 MW) and Kurnool (1000 MW), Andhra Pradesh Annexure-II • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | 30-Sep-26 | 30-Sep-26 |  |  | 350 | 209 |  |  |  | 2026-03-31 | 2027-03-27 | 2027-06-30 |  | Not effective | 2027-03-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 350.00 ¦ Date: 2027-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Sep-26 |  | 2026-09-30 | 2027-09-28
2200000714 | Main-Connectivity under GNA |  | Gentari Renewables India Caster One Private Limited (Formerly known as AMPLUS CENEDUS SOLAR PRIVATE LIMITED) | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 350 |  | 0 | 350 | 0 | 350 |  | Granted | 350 | 0 | 350 | Davangere | Karnataka | 2025-05-16 | 2027-03-22 | •Generation Pooling Station of M/s Gentari Renewables India Castor One Pvt. Ltd. – Davanagere/ Chitradurga PS 220 kV S/c line on D/c tower along with line bay at generation pooling station – under the scope of applicant. •1 no. 220 kV line bay at Davanagere/ Chitradurga PS for termination of above mentioned line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission system for integration of Davanagere/ Chitradurga REZ | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission system for integration of Davanagere/ Chitradurga REZ | 30-Sep-26 | 30-Sep-26 |  |  | 350 | 214 |  |  |  | 2027-03-21 | 2027-03-21 | 2027-09-30 |  | Not effective | 2027-03-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 350.00 ¦ Date: 2027-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 30-Sep-26 |  | 2026-09-30 | 2027-09-30
2200000715 | Main-Connectivity under GNA |  | AMARESHA RENAWABLES INDIA PROJECT PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Barmer-II | Rajasthan | 2026-01-19 |  | Amaresha Renawables India Project Private Limited Renewable Power Park – Barmer-II PS 220 kV Sc line on Dc tower (suitable to carry minimum 300 MW at nominal voltage)-Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA at Barmer-II PS(Tentative) Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 400220kV, 6x500 MVA ICTs at Barmer-II PS LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 01-Apr-27 | 01-Apr-27 |  |  | 300 | [6 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2030-09-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 01-Apr-27 |  | 2027-04-01 | 2030-12-30
2200000718 | Main-Connectivity under GNA |  | JSW NEO ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 | SECI | Granted | 300 | 0 | 300 | Solapur Pool (Sec-I) | Maharashtra | 2024-10-11 | 2026-03-31 | • JSWNEL – Solapur PS 220kV Sc line (on Dc tower) along with associated bay at the generation end (Under the scope of the applicant). • 1 no. 220kV line bay at Solapur PS (Being implemented under ISTS as a part of the Pooling Station). | 1 | 220 KV | Aug without ATS |  |  | • Establishment of 4x500 MVA, 400220kV ICTs at Solapur PS • Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAA ACAL59 moose equivalent). | • Establishment of 4x500 MVA, 400220kV ICTs at Solapur PS • Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAA ACAL59 moose equivalent). | 31-Mar-26 | 31-Mar-26 |  |  | 300 | 203 |  |  |  | 2026-08-30 | 2026-03-20 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2026-10-30
2200000720 | Main-Connectivity under GNA |  | GANEKO ONE ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | Solar - 255 MW, Wind - 99 MW |  | 160 | 187 | 0 | 347 |  | Granted | 300 | 0 | 300 | Mandsaur (Sec-I) | Madhya Pradesh | 2024-11-11 | 2027-03-31 | • GOEPL – Mandsaur PS 220kV Sc line (on Dc tower) along with 220kV line bay at generation station (Under the scope of Ms GOEPL). • 1 no. 220kV line bay at Mandsaur PS shall be implemented under ISTS | 1 | 220 KV | Aug without ATS |  |  | • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur Pooling Station along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line • Establishment of 765400kV (2x1500MVA), 400220kV | • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur Pooling Station along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line | 31-Mar-27 | 31-Mar-27 |  |  | 300 | 206 |  |  |  | 2027-03-31 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 255.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 99.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Group Head | 31-Mar-27 |  | 2027-03-31 | 2027-06-30
2200000728 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 500 |  | 500 | 0 | 0 | 500 | NTPC | Granted | 500 | 0 | 500 | Neemuch | Madhya Pradesh | 2026-01-02 | 2027-09-29 | • AEPL – Neemuch PS 220kV D/c line (with min capacity of 335MW per ckt at nominal voltage) along with associated bay at the generation end (Under the scope of AEPL). • 2 no. 220kV line bays at Neemuch PS (being implemented under ISTS as part of Transmission system for Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II scheme). | 2 | 220 kV | Aug without ATS |  |  | Transmission system for Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II (Being implemented by: M/s Rajgarh Neemuch Power Transmission Limited (RNTL))(SCOD: 29.09.2027) • Creation of New 220kV Bus Section-II with augmentation of transformation capacity by 3x500MVA, 400/220kV ICTs (3rd, 4th & 5th) at Neemuch PS along with associated bays. • Establishment of 2x500MVA, 400/220kV Handiya S/s. • Neemuch PS – Pachora PS 400kV 400 kV D/c line (Quad ACSR/ AAAC/ AL59 Moose equivalent) along with associated line bays. • Pachora PS – Handiya (PG) 400kV 400 kV D/c line (Quad ACSR/ AAAC/ AL59 Moose equivalent) along with associated line bays. • LILO of Khandwa (PG) – Itarsi (PG) 400kV D/c (Twin Moose) line at Handiya S/s. | Transmission system for Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II (Being implemented by: M/s Rajgarh Neemuch Power Transmission Limited (RNTL))(SCOD: 29.09.2027) • Creation of New 220kV Bus Section-II with augmentation of transformation capacity by 3x500MVA, 400/220kV ICTs (3rd, 4th & 5th) at Neemuch PS along with associated bays. • Establishment of 2x500MVA, 400/220kV Handiya S/s. • Neemuch PS – Pachora PS 400kV 400 kV D/c line (Quad ACSR/ AAAC/ AL59 Moose equivalent) along with associated line bays. • Pachora PS – Handiya (PG) 400kV 400 kV D/c line (Quad ACSR/ AAAC/ AL59 Moose equivalent) along with associated line bays. • LILO of Khandwa (PG) – Itarsi (PG) 400kV D/c (Twin Moose) line at Handiya S/s. | 31-Jul-26 | 31-Jul-26 |  |  | 500 | No |  |  |  | 2027-09-29 | 2027-09-29 | 2027-09-29 |  | Not effective | 2027-09-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 500.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-09-29
2200000729 | Main-Connectivity under GNA |  | NLC INDIA LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 | SECI | Granted | 100 | 0 | 100 | Bhuj | Gujarat | 2025-06-06 | 2026-11-19 | NLCIL in present application shall share the DTL already granted to NLCIL for its SPP of 200MW against application no. 2200000386 as given below • NLCIL – Bhuj PS 220kV Sc line along with associated bay at Generating station end. • Bay at Bhuj PS is being implemented by NLCIL. | 0 | 220 KV | Aug without ATS |  |  | Under Implementation Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (10th) with associated ICT bays POWERGRID (SCOD 20.10.2026) Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th) | Under Implementation Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (10th) with associated ICT bays POWERGRID (SCOD 20.10.2026) Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th) POWERGRID (SCOD 01.07.2025) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (SCOD Matching with Khavda Ph-II Scheme) Khavda RE Transmission Limited (a subsidiary of POWERGRID) Banaskantha — Ahmedabad 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from pote | 07-Dec-24 | 07-Dec-24 |  |  | 100 | 222 |  |  |  |  | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2026-12-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 07-Dec-24 |  | 2024-12-07 | 2027-10-30
2200000733 | Main-Connectivity under GNA |  | INDOSOL SOLAR PRIVATE LIMITED | SR | Land Route | (x) Renewable Power Park developer | Solar | 800 | 0 | 800 | 0 | 0 | 800 |  | Granted | 800 | 0 | 800 | Kurnool-III | Andhra Pradesh | 2025-05-29 | 2027-03-28 | • Generating Pooling Station of M/s Indosol Solar Pvt. Ltd.– Kurnool-III PS 400 kV S/c line on D/c tower* along with line bays at generation end –under the scope of applicant. • 1 no. 400 kV line bay at Kurnool-III PS for termination of above mentioned dedicated connectivity line – under the scope of ISTS | 1 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | 500 MW 30.06.25300 MW31.03.26 | Phase 1 ¦ MW: 500.00 ¦ Date: 2025-06-30 Phase 2 ¦ MW: 300.00 ¦ Date: 2026-03-31 |  |  | 800 | 436(Main) & 435 (Tie) |  |  |  |  | 2027-03-27 | 2027-06-30 |  | Not effective | 2027-03-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 800.00 ¦ Date: 2027-03-28 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 500.00 ¦ Date: 2025-06-30 | 500 | 2025-06-30 | 2027-09-28
2200000733 | Main-Connectivity under GNA |  | INDOSOL SOLAR PRIVATE LIMITED | SR | Land Route | (x) Renewable Power Park developer | Solar | 800 | 0 | 800 | 0 | 0 | 800 |  | Granted | 800 | 0 | 800 | Kurnool-III | Andhra Pradesh | 2025-05-29 | 2027-03-28 | • Generating Pooling Station of M/s Indosol Solar Pvt. Ltd.– Kurnool-III PS 400 kV S/c line on D/c tower* along with line bays at generation end –under the scope of applicant. • 1 no. 400 kV line bay at Kurnool-III PS for termination of above mentioned dedicated connectivity line – under the scope of ISTS | 1 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | 500 MW 30.06.25300 MW31.03.26 | Phase 1 ¦ MW: 500.00 ¦ Date: 2025-06-30 Phase 2 ¦ MW: 300.00 ¦ Date: 2026-03-31 |  |  | 800 | 436(Main) & 435 (Tie) |  |  |  |  | 2027-03-27 | 2027-06-30 |  | Not effective | 2027-03-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 800.00 ¦ Date: 2027-03-28 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 300.00 ¦ Date: 2026-03-31 | 300 | 2026-03-31 | 2027-09-28
2200000734 | Main-Connectivity under GNA |  | INDOSOL SOLAR PRIVATE LIMITED | SR | Land Route | (x) Renewable Power Park developer | Solar | 900 |  | 900 | 0 | 0 | 900 |  | Granted | 900 | 0 | 900 | Kurnool-III | Andhra Pradesh | 2025-05-29 | 2027-04-01 | • Generating Pooling Station of M/s Indosol Solar Pvt. Ltd.– Kurnool-III PS 400 kV S/c line on D/c tower* along with line bays at generation end –under the scope of applicant. • 1 no. 400 kV line bay at Kurnool-III PS for termination of above mentioned dedicated connectivity line – under the scope of ISTS | 1 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | 31-Jul-26 | 31-Jul-26 |  |  | 900 | 442(Main) & 441 (Tie) |  |  |  |  | 2027-03-27 | 2027-06-30 |  | Not effective | 2027-04-01 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 900.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-10-01
2200000735 | Main-Connectivity under GNA |  | INDOSOL SOLAR PRIVATE LIMITED | SR | Land Route | (x) Renewable Power Park developer | Solar | 900 |  | 900 | 0 | 0 | 900 |  | Granted | 900 | 0 | 900 | Kurnool-III | Andhra Pradesh | 2025-05-29 | 2027-03-28 | •Generating Pooling Station of M/s Indosol Solar Pvt. Ltd.– Kurnool-III PS 400 kV S/c line on D/c tower along with line bays at generation end–under the scope of applicant. •1 no. 400 kV line bay at Kurnool-III PS for termination of above mentioned dedicated connectivity line – under the scope of ISTS. | 1 | 400 kV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | 31-Mar-27 | 31-Mar-27 |  |  | 900 | 439(Main) & 438 (Tie) |  |  |  |  | 2027-03-27 | 2027-06-30 |  | Not effective | 2027-03-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 900.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2027-09-30
2200000736 | Main-Connectivity under GNA |  | INDOSOL SOLAR PRIVATE LIMITED | SR | Land Route | (x) Renewable Power Park developer | Solar | 900 |  | 900 | 0 | 0 | 900 |  | Granted | 900 | 0 | 900 | Kurnool-III | Andhra Pradesh | 2025-05-29 | 2027-04-01 | • Generating Pooling Station of M/s Indosol Solar Pvt. Ltd.– Kurnool-III PS 400 kV S/c line on D/c tower along with line bays at generation end–under the scope of applicant. • 1 no. 400 kV line bay at Kurnool-III PS for termination of above mentioned dedicated connectivity line – under the scope of ISTS. | 1 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B, as per Annexure-II • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)/Solar Energy Zone (AP) (1500MW) - Part-A and Part-B, as per Annexure-II • Transmission system strengthening at Kurnool-III PS for integration of additional RE generation projects | 31-Mar-27 | 31-Mar-27 |  |  | 900 | 445(Main) & 444 (Tie) |  |  |  |  | 2027-03-27 | 2027-06-30 |  | Not effective | 2027-04-01 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 900.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2027-10-01
2200000743 | Main-Connectivity under GNA |  | IZHMA SOLAR PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Sirohi | Rajasthan | 2025-05-27 | 2028-03-31 | Izhma Solar Private Limited Solar Power Project – Sirohi PS 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage)# - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 400/220kV, 5x500 MVA ICTs at Sirohi PS Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 400/220kV, 5x500 MVA ICTs at Sirohi PS Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 31-Mar-28 | 31-Mar-28 |  |  | 200 | 212 |  |  |  | 2027-03-31 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-03-25 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-Mar-28 |  | 2028-03-31 | 2028-09-30
2200000747 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 180 |  | 0 | 180 | 0 | 180 | NTPC | Granted | 180 | 0 | 180 | Parli (New) | Maharashtra | 2026-01-05 | 2026-06-30 | TPREL – Parli (New) 400kV Sc line (on Dc tower) along with 400kV line bay at generation end (Under the scope of RPSPL) 1 no. 400kV line bay at Parli (New) Ss (under the scope of ISTS). | 1 | 400 KV |  |  |  | Nil | Nil | 30-Jun-26 | 30-Jun-26 |  |  | 180 | 409 | 2027-03-31 |  | PPA signed with NTPC on 11.04.2025 with SCOD of 24 months. Requested revised GNA start date 31.03.2027 |  |  |  |  | Not effective | 2026-08-25 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 180.00 ¦ Date: 2027-04-11 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-03-31
2200000752 | Main-Connectivity under GNA |  | ASNEN SOLAR PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Mandsaur (Sec-I) | Madhya Pradesh | 2024-11-11 | 2027-05-31 | • ASPL – Mandsaur PS 220kV Sc line (on Dc tower) along with 220kV line bay at generation station (Under the scope of Ms ASPL). • 1 no. 220kV line bay at Mandsaur PS shall be implemented under ISTS | 1 | 220 KV | Aug without ATS |  |  | • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur Pooling Station along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line • Establishment of 765400kV (2x1500MVA), 400220kV | • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur Pooling Station along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line | 31-May-27 | 31-May-27 |  |  | 200 | 204 |  |  |  | 2027-03-31 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-05-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-05-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-May-27 |  | 2027-05-31 | 2027-11-30
2200000754 | Main-Connectivity under GNA |  | SKADAR SOLAR PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Solapur Pool (Sec-I) | Maharashtra | 2024-10-11 | 2026-05-31 | • SSPL – Solapur PS 220kV Sc line (on Dc tower) along with associated bay at the generation end (Under the scope of the applicant). • 1 no. 220kV line bay at Solapur PS (Being implemented under ISTS as a part of the Pooling Station). | 1 | 220 KV | Aug without ATS |  |  | • Establishment of 4x500 MVA, 400220kV ICTs at Solapur PS • Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAA ACAL59 moose equivalent). | • Establishment of 4x500 MVA, 400220kV ICTs at Solapur PS • Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAA ACAL59 moose equivalent). | 31-May-26 | 31-May-26 |  |  | 200 | 204 |  |  |  | 2026-06-30 | 2026-03-20 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Solar | 08.07.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-May-26 |  | 2026-05-31 | 2026-11-30
2200000758 | Main-Connectivity under GNA |  | VAYUNA RENEWABLES INDIA PROJECT PRIVATE LIMITED | NR | Land BG Route | (x) Renewable Power Park developer | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Sirohi | Rajasthan | 2025-05-27 | 2027-04-01 | Vayuna Renewables India Project Private Limited RE Power Park – Sirohi PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage)# - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 400/220kV, 5x500 MVA ICTs at Sirohi PS Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor 400/220kV, 5x500 MVA ICTs at Sirohi PS Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 01-Apr-27 | 01-Apr-27 |  |  | 300 | 211 |  |  |  | 2027-03-31 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-04-01 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 01-Apr-27 |  | 2027-04-01 | 2027-10-01
2200000759 | Main-Connectivity under GNA |  | SAEL INDUSTRIES LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 0 | 300 | 0 | 300 | SECI | Granted | 300 | 0 | 300 | Bidar | Karnataka | 2025-03-03 | 2026-04-22 | • Generating Pooling Station of M/s Ampin Energy Utility Pvt. Ltd.- Bidar PS 220 kV S/c line on D/c tower# along with line bay at generation pooling station – under the scope of applicant. • 1 no. of 220 kV line bay at Bidar PS for termination of above mentioned dedicated Connectivity line - under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | 21-Jun-26 | 21-Jun-26 |  |  | 300 | 214 | 2027-06-30 |  | As per the PPA submitted vide mail dtd. 26.09.2025 | 2026-06-30 | 2026-02-09 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Group Head | 21-Jun-26 |  | 2026-06-21 | 2027-06-30
2200000762 | Main-Connectivity under GNA |  | AMPIN ENERGY UTILITY PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 185.4 (Solar-135; Wind 50.4) |  | 135 | 50.4 | 0 | 185.4 |  | Granted | 150 | 0 | 150 | Bidar | Karnataka | 2025-06-19 | 2027-12-31 | • Generating Pooling Station of Ms Ampin Energy Utility Pvt. Ltd.- Bidar PS 220 kV Sc line on Dc tower# along with line bay at generation pooling station – under the scope of applicant. • 1 no. of 220 kV line bay at Bidar PS for termination of above mentioned dedicated Connectivity line - under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • ISTS Network Expansion scheme in Weste | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | 31-Dec-27 | 31-Dec-27 |  |  | 150 | 216 |  |  |  | 2026-06-30 | 2026-02-09 | 2026-10-31 |  | Not effective | 2027-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.40 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 135.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2028-06-30
2200000763 | Main-Connectivity under GNA |  | AMPIN ENERGY UTILITY PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 185.4 (Solar-135; Wind 50.4) |  | 135 | 50.4 | 0 | 185.4 |  | Granted | 150 | 0 | 150 | Bidar | Karnataka | 2025-06-19 | 2027-12-31 | • Through dedicated connectivity transmission system granted to M/s Ampin Energy Utility Pvt. Ltd. for 150 MW (app. No. 2200000762) i.e. Generating station of M/s Ampin Energy Utility Pvt. Ltd. -Bidar PS 220 kV S/c line on D/c tower along with line bay at generation pooling station – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka | 31-Dec-27 | 31-Dec-27 |  |  | 150 | 216 |  |  |  | 2026-06-30 | 2026-02-09 | 2026-10-31 |  | Not effective | 2027-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.40 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 135.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2027-12-31
2200000778 | Main-Connectivity under GNA |  | RENEW SOLAR POWER PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 | SECI | Granted | 300 | 0 | 300 | Barmer-II | Rajasthan | 2026-01-19 |  | Renew Solar Power Private Limited Solar Power Project – Barmer-II PS 220 kV Sc line on Dc tower(Suitable to carry minimum 300 MW at nominal voltage)# - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  |  | Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 400220kV, 6x500 MVA ICTs at Barmer-II PS LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 31-Dec-26 | 31-Dec-26 |  |  | 300 | [6 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2030-09-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2030-12-30
2200000779 | Main-Connectivity under GNA |  | RENEW SOLAR POWER PRIVATE LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 | NTPC | Granted | 300 | 0 | 300 | Sirohi | Rajasthan | 2025-05-27 | 2027-06-30 | Common Pooling Station for Renew Solar Power Private Limited Solar Power Projects (App. No. 2200000551-400 MW & 2200000779 -300 MW) – Sirohi PS 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW at nominal voltage) - Under Applicant Scope | 0 | 400 KV | Aug without ATS |  |  | Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Establishment of 765 kV Mandsaur PS along with 2x330 MVAR (765 kV) Bus Reactors Mandsaur PS–Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of Indore – Bhopal 765 kV S/c line at Kurawar LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 30-Jun-27 | 30-Jun-27 |  |  | 300 | 412 |  |  |  | 2027-03-31 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-09-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-06-30
2200000780 | Main-Connectivity under GNA |  | RENEW SOLAR POWER PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 400 |  | 0 | 400 | 0 | 400 | NTPC | Granted | 400 | 0 | 400 | Ananthapuram-II | Andhra Pradesh | 2025-06-04 | 2027-06-30 | • Generation Pooling Station of M/s Gentari Renewables India Utilities 2 Pvt. Ltd. – Ananthapuram-II PS 220 kV S/c line on D/c towers [through stringing of both arms of 220 kV D/c towers and bunching both arms circuit at both end for termination of line in single bay] along with 220 kV line bay at generation Pooling Station end – under the scope of applicant • 1 no. 220 kV line bay at Ananthapuram-II PS for termination of DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Anantapur-II REZs (Phase-I) • Transmission system for integration of Davanagere/ Chitradurga REZ | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Anantapur-II REZs (Phase-I) • Transmission system for integration of Davanagere/ Chitradurga REZ | 30-Jun-27 | 30-Jun-27 |  |  | 400 | 2B1-02 |  |  |  | 2027-03-31 | 2027-03-31 | 2027-09-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2029-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-09-30
2200000783 | Main-Connectivity under GNA |  | OYSTER GREEN HYBRID ONE PRIVATE LIMITED | WR | Land BG Route | (vi) Captive generating plant | Wind | 99 |  | 0 | 99 | 0 | 99 |  | Granted | 99 | 0 | 99 | Bhuj | Gujarat | 2025-04-07 | 2026-11-19 | Ms OGH1PL shall share the DTL for Connectivity granted to Ms NVWEPL against application No. 2200000331) as given below • NVWEPL – Bhuj PS 220kV Dc line (high-capacity conductor enabling at least 500MW power transfer at nominal voltage) along with associated line bays at both ends. | 0 | 220 kV | Aug without ATS |  |  | Under Implementation • Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th) • Banaskantha – Ahmedabad 765kV Dc line • Lakadia PS – Ahmedabad 765kV Dc line • Establishment of 765400 kV Ahmedabad Ss • Ahmedabad – Navsar | Under Implementation • Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th) • Banaskantha – Ahmedabad 765kV Dc line • Lakadia PS – Ahmedabad 765kV Dc line • Establishment of 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc Under Tendering • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs & 2x500 MVA 400220kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • Ahmedabad – South Olpad (GIS) 765kV Dc line • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad – Boisar-II 765kV Dc line • LILO of Navsari (New) – Padghe (PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon (MH) 400 kV Dc • LILO of Babhaleswar – Padghe (M) 400 kV Dc line at Boisar-II (Sec-I) • Establishment of 765400220kV Pune-III (GIS) Ss with 3x1500 MVA ICTs & 3x500MVA ICTs • Boisar-II – Pune-III 765kV Dc line • LILO of Narendra (New) – Pune (GIS) 765kV Dc line at Pune-III | 01-Jun-25 | 01-Jun-25 |  |  | 99 | 205 & 208 |  |  |  |  | 2026-11-19 | 2027-10-30 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 52.80 ¦ Date: 2027-10-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 46.20 ¦ Date: 2027-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 01-Jun-25 |  | 2025-06-01 | 2027-10-30
2200000785 | Main-Connectivity under GNA |  | ADANI GREEN ENERGY LIMITED | WR | Land Route | (x) Renewable Power Park developer | Wind | 100 | 0 | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | KPS-3 (Sec-II) | Gujarat | 2025-01-09 | 2029-12-12 | AGEL shall share the DTL & 40033 kV Switchyard (PSS-14) of AGEL’s Application no. 2200000953 (Hybrid 1530 MW) as given below • AGEL (PSS-14) – KPS3 (Sec-II) 400kV Dc line (with minimum capacity of 1965MW at nominal voltage) along with associated bays at generation end (under the scope of AGEL) • 2 nos. 400kV bays on Bus Section-II at KPS3 (under ISTS) | 0 |  | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA Khavda Phase-I KPS1 – Bhuj 765kV Dc line KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park Establishment of 765400kV KPS2(GIS) Kha | Common Transmission System Augmentation for Connectivity under GNA Khavda Phase-I KPS1 – Bhuj 765kV Dc line KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park Establishment of 765400kV KPS2(GIS) Khavda Phase-II KPS2 – Lakadia 765kV Dc line Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss Lakadia – Ahmedabad 765kV Dc line Ahmedabad – Navsari (New) 765kV Dc line LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III Establishment of 765 kV Halvad switching station KPS2- Halvad 765 kV Dc line LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad Halvad – Vataman 765 kV Dc line Establishment of 765 kV switching station near Vataman LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station Vataman switching station – Navsari(New) 765 kV Dc line Khavda Phase-IV Creation of 765kV bus section-II at KPS3 (GIS) along with 765kV Bus Sectionaliser Creation of 400kV bus section-II at KPS3 (GIS) along with 400kV Bus Sectionaliser KPS3 (GIS) – Lakadia (AIS) 765 kV DC line ±300MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400kV Bus section-2 KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line Establishment of 2x1500MVA, 765400kV & 2x500MVA, 400220kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) Vadodara(GIS) –South Olpad(GIS) 765 kV DC line LILO of Gandhar – Hazira 400kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage Ahmedabad – South Olpad(GIS) 765kV Dc line Establishment of 4X1500 MVA 765400 kV & 2x500MVA 400220kV Boisar-II (GIS) South Olpad(GIS) – Boisar-II(GIS) 765kV Dc line LILO of Navsari(New) – Padghe(PG) 765kV Dc line at Boisar-II Boisar-II (Sec-II) – Velgaon(MH) 400kV Dc (Quad ACSRAAACAL59 moose equivalent) line LILO of Babhaleswar – Padghe(M) 400kV Dc line at Boisar-II (Sec-I) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-I of Boisar-II and ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-II of Boisar-II ±300 MVAr STATCOM with 3x125 MVAr MSC, 1x125 MVAr MSR at 400 kV level of Navsari(New)(PG | 31-Mar-25 | 31-Mar-25 |  |  | 100 | 435M 434T & 438M 437T |  |  |  | 2026-08-30 | 2029-05-19 | 2029-05-19 |  | Not effective | 2029-12-12 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2029-12-12 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2030-06-12
2200000786 | Main-Connectivity under GNA |  | ADANI GREEN ENERGY LIMITED | WR | Land Route | (x) Renewable Power Park developer | Wind | 195 | 0 | 0 | 195 | 0 | 195 |  | Granted | 195 | 0 | 195 | KPS-3 (Sec-II) | Gujarat | 2025-01-09 | 2029-12-12 | AGEL shall share the DTL & 40033 kV Switchyard (PSS-14) of AGEL’s Application no. 2200000953 (Hybrid 1530 MW) as given below • AGEL (PSS-14) – KPS3 (Sec-II) 400kV Dc line (with minimum capacity of 1965MW at nominal voltage) along with associated bays at generation end (under the scope of AGEL) • 2 nos. 400kV bays on Bus Section-II at KPS3 (under ISTS) | 0 | 400 KV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA Khavda Phase-I KPS1 – Bhuj 765kV Dc line KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park Establishment of 765400kV KPS2(GIS) Kha | Common Transmission System Augmentation for Connectivity under GNA Khavda Phase-I KPS1 – Bhuj 765kV Dc line KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park Establishment of 765400kV KPS2(GIS) Khavda Phase-II KPS2 – Lakadia 765kV Dc line Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss Lakadia – Ahmedabad 765kV Dc line Ahmedabad – Navsari (New) 765kV Dc line LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III Establishment of 765 kV Halvad switching station KPS2- Halvad 765 kV Dc line LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad Halvad – Vataman 765 kV Dc line Establishment of 765 kV switching station near Vataman LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station Vataman switching station – Navsari(New) 765 kV Dc line Khavda Phase-IV Creation of 765kV bus section-II at KPS3 (GIS) along with 765kV Bus Sectionaliser Creation of 400kV bus section-II at KPS3 (GIS) along with 400kV Bus Sectionaliser KPS3 (GIS) – Lakadia (AIS) 765 kV DC line ±300MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400kV Bus section-2 KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line Establishment of 2x1500MVA, 765400kV & 2x500MVA, 400220kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) Vadodara(GIS) –South Olpad(GIS) 765 kV DC line LILO of Gandhar – Hazira 400kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage Ahmedabad – South Olpad(GIS) 765kV Dc line Establishment of 4X1500 MVA 765400 kV & 2x500MVA 400220kV Boisar-II (GIS) South Olpad(GIS) – Boisar-II(GIS) 765kV Dc line LILO of Navsari(New) – Padghe(PG) 765kV Dc line at Boisar-II Boisar-II (Sec-II) – Velgaon(MH) 400kV Dc (Quad ACSRAAACAL59 moose equivalent) line LILO of Babhaleswar – Padghe(M) 400kV Dc line at Boisar-II (Sec-I) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-I of Boisar-II and ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-II of Boisar-II ±300 MVAr STATCOM with 3x125 MVAr MSC, 1x125 MVAr MSR at 400 kV level of Navsari(New)(PG | 31-Mar-25 | 31-Mar-25 |  |  | 195 | 435M 434T & 438M 437T |  |  |  | 2026-08-30 | 2029-05-19 | 2029-05-19 |  | Not effective | 2029-12-12 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 195.00 ¦ Date: 2029-12-12 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2030-06-12
2200000795 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 20 PRIVATE LIMITED | WR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | Wind - 66 MW, Solar - 18.75 MW, BESS - 12.56MW | 0 | 14.42 | 50.77 | 6.15 | 71.34 | NHPC | Granted | 50 | 0 | 50 | Solapur Pool (Sec-I) | Maharashtra | 2024-10-11 | 2026-06-30 | Ms SPI20PL shall share Dedicated Transmission System granted to Ms SPI7PL for its 50MW HPP against application no. 2200000213 as given below • SPI7PL – Solapur PS 220kV Sc line along with associated bay at generation end (under the scope of the applicant). • 1 no. 220kV line bay at Solapur PS is being implemented under ISTS as part of the pooling station. | 0 | 220 KV | Aug without ATS |  |  | Establishment of 400220kV, 4x500MVA ICTs at Solapur PS Solapur PS – Solapur (PG) 400kV Dc line (quad ACSRAAACAL59 moose equivalent) | Establishment of 400220kV, 4x500MVA ICTs at Solapur PS Solapur PS – Solapur (PG) 400kV Dc line (quad ACSRAAACAL59 moose equivalent) | 30-Jun-26 | 30-Jun-26 |  |  | 50 | 203 | 2026-12-18 |  | NHPC Ltd granted SCOD of generation project upto 18.12.2026 as per PPA | 2026-06-30 | 2026-03-20 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-12-18 ¦ Status: Under Implementation ¦ Type: | 08.07.2026 | Yes |  | 09/07/2026 | Not Submitted For Approval | 30-Jun-26 |  | 2026-06-30 | 2026-12-18
2200000798 | Main-Connectivity under GNA |  | ADYANT POWER PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 200 (SOLAR 101 MW WIND 99 MW) |  | 101 | 99 | 0 | 200 |  | Granted | 200 | 0 | 200 | Mandsaur (Sec-II) | Madhya Pradesh | 2025-03-13 | 2027-03-31 | • APPL – Mandsaur PS 220kV Sc line along with associated bay at the generation end (Under the scope of Ms APPL). • 1 no. 220kV line bay (on 220kV Bus Sec-II) at Mandsaur PS shall be implemented under ISTS | 1 | 220 KV | Aug without ATS |  |  | 1. Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2 5.5 GW) (JaisalmerBarmer Complex) Part C a. Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur Pooling Station along with 2x330MVAR (765kV) Bus Reactor & 2 | 1. Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2 5.5 GW) (JaisalmerBarmer Complex) Part C a. Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur Pooling Station along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. b. Mandsaur PS – Indore ((PG) 765 kV Dc Line 2. Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2 5.5 GW) (JaisalmerBarmer Complex) Part H1 a. Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. b. Mandsaur – Kurawar 765 kV Dc line c. LILO of Indore – Bhopal 765 kV Sc line at Kurawar d. Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line e. LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha f. Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line | 31-Mar-27 | 31-Mar-27 |  |  | 200 | 214 |  |  |  | 2027-03-31 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 101.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 99.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2027-09-30
2200000807 | Main-Connectivity under GNA |  | ADANI RENEWABLE ENERGY TWO LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 600 |  | 0 | 600 | 0 | 600 |  | Granted | 600 | 0 | 600 | Barmer-II | Rajasthan | 2026-01-19 |  | Common pooling station for Adani Renewable Energy Two Limited (App. No. 2200000807-600 MW &2200000809-595 MW) Wind Power Projects – Barmer-II PS 400 kV Sc line (high capacity) on Dc tower (Suitable to carry minimum 1195 MW at nominal voltage)# - Under Applicant Scope | 0 | 400 KV | Aug without ATS |  |  | Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(2 | Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 31-Mar-25 | 31-Mar-25 |  |  | 600 | No | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 600.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2030-12-30
2200000808 | Main-Connectivity under GNA |  | NLC INDIA LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 |  | 0 | 50 | 0 | 50 | SECI | Granted | 50 | 0 | 50 | Bhuj | Gujarat | 2025-06-06 | 2026-11-19 | NLCIL in present application shall share the DTL already granted to Nani Virani Wind Energy Pvt. Ltd. (NVWEPL) vide application no. 2200000331 [after transfer of 50MW connectivity from Ms Inox Green Energy Services Ltd. (IGESL; formerly Inox Wind Infrastructure Services Ltd. for its WPP against application no. 1200000559 to Ms Nani Virani Wind Energy Pvt. Ltd. (NVWEPL) vide CTU letter dated 08.02.2024] as given below • NVWEPL – Bhuj PS 220kV Dc line (high capacity conductor enabling at least 500MW power transfer at nominal voltage) along with associated line bays at both ends. | 0 | 220 KV | Aug without ATS |  |  | Under Implementation Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (10th) with associated ICT bays POWERGRID (SCOD 20.10.2026) Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th) | Under Implementation Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (10th) with associated ICT bays POWERGRID (SCOD 20.10.2026) Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th) POWERGRID (SCOD 01.07.2025) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (SCOD Matching with Khavda Ph-II Scheme) Khavda RE Transmission Limited (a subsidiary of POWERGRID) Banaskantha — Ahmedabad 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from pote | 07-Dec-24 | 07-Dec-24 |  |  | 50 | 205 & 208 |  |  |  |  | 2026-11-19 | 2027-10-31 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 26.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 24.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 07-Dec-24 |  | 2024-12-07 | 2027-10-31
2200000809 | Main-Connectivity under GNA |  | ADANI RENEWABLE ENERGY TWO LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 595 |  | 0 | 595 | 0 | 595 |  | Granted | 595 | 0 | 595 | Barmer-II | Rajasthan | 2026-01-19 |  | Common pooling station for Adani Renewable Energy Two Limited (App. No. 2200000807-600 MW &2200000809-595 MW) Wind Power Projects – Barmer-II PS 400 kV Sc line (high capacity) on Dc tower (Suitable to carry minimum 1195 MW at nominal voltage)# - Under Applicant Scope | 1 | 400 KV | Aug without ATS |  |  | Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(2 | Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 31-Mar-25 | 31-Mar-25 |  |  | 595 | No | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 595.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  |  | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2030-12-30
2200000810 | Main-Connectivity under GNA |  | ADANI RENEWABLE ENERGY HOLDING FOUR LIMITED | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 717 |  | 717 | 0 | 0 | 717 | SECI | Granted | 717 | 0 | 717 | Barmer-II | Rajasthan | 2026-01-19 |  | Adani Renewable Energy Holding Four Limited Solar Power Project – Barmer-II PS 400 kV Sc line on Dc tower# (Suitable to carry minimum 900 MW at nominal voltage) - Under Applicant Scope | 1 | 400 KV | Aug without ATS |  |  | Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(2 | Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 31-Mar-25 | 31-Mar-25 |  |  | 717 | [6 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 717.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Solar |  | Yes |  | 08/07/2026 | Pending with Group Head | 31-Mar-25 |  | 2025-03-31 | 2030-12-30
2200000812 | Main-Connectivity under GNA |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Merta-II | Rajasthan | 2025-05-26 | 2027-05-31 | • Common Pooling Station for Sembcorp Green Infra Private Limited Solar Power Projects (App. No. 2200000812300 MW & 2200000813300 MW)– Merta-II PS 220 kV Dc line (Suitable to carry minimum 300 MW per circuit at nominal voltage) along with associated bay at generation end – Under applicant scope • Implementation of 1 No. of 220kV Bay at Merta-II PS is under ISTS | 1 | 220 KV | Aug without ATS |  |  |  | a. Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-4 3.5 GW) Part A 1. Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror Ss (UP) 2. Dausa - Ghiror 765 kV Dc line along with 330MVAr switchable line reactor at Ghiror end and 240 MVAr switchable line reactor at Dausa end for each circuit of Dausa - Ghiror 765 kV Dc line 3. LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) Dc line at Ghiror Ss along with 240 MVAr switchable line reactor for each circuit at Ghiror Ss end of 765 kV Ghiror -Orai Dc line 4. LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 2xSc line at Ghiror along with 240 MVAr switchable line reactor at Ghiror end of 765 kV Ghiror -Fatehpur (PG) line 5. 400kV Ghiror-Firozabad (UPPTCL) Dc line (Quad) b. Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-4 3.5 GW) Part B 6. Establishment of 765400 kV, 2x1500 MVA & 5x500 MVA, 400220 kV Ss at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II Ss 7. Merta-II – Beawar 400 kV Dc line (Quad) 8. Merta-II – Dausa 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV Dc line c. Transmission system for evacuation of power from Rajasthan REZ Ph-V (Part-1 4 GW) [SirohiNagaur] Complex 9. Sirohi – Mandsaur PS 765KV Dc line along with 240 MVAr switchable line reactor at Sirohi Ss end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV Dc line 10. Mandsaur PS – Khandwa (New) 765kV Dc line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV Dc line | 31-May-27 | 31-May-27 |  |  | 300 | 201 |  |  |  | 2027-04-30 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-May-27 |  | 2027-05-31 | 2027-11-30
2200000813 | Main-Connectivity under GNA |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Merta-II | Rajasthan | 2025-05-26 | 2027-05-31 | SGIPL (App. No. 2200000813) shall share the Dc line on Dc tower for Connectivity granted to SGIPL for App. No. 2200000812 • Common Pooling Station for Sembcorp Green Infra Private Limited Solar Power Projects (App. No. 2200000812300 MW & 2200000813300 MW)– Merta-II PS 220 kV Dc line (Suitable to carry minimum 300 MW per circuit at nominal voltage) along with associated bay at generation end – Under applicant scope • Implementation of 1 No. of 220kV Bay at Merta-II PS is under ISTS | 1 | 220 KV | Aug without ATS |  |  |  | Establishment of 765400 kV, 2x1500 MVA & 5x500 MVA, 400220 kV Ss at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II Ss Merta-II – Beawar 400 kV Dc line (Quad) Merta-II – Dausa 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV Dc line line Establishment of 765400kV, 2x1500 MVA Ss at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror Ss (UP) Dausa - Ghiror 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV Dc line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) Dc line at Ghiror Ss along with 240 MVAr switchable line reactor for each circuit at Ghiror Ss end of 765 kV Ghiror -Orai Dc line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV Dc line at Ghiror along with 240 MVAr switchable line reactor at Ghiror Ss end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) Dc line (Quad) Sirohi – Mandsaur PS 765KV Dc line along with 240 MVAr switchable line reactor at Sirohi Ss end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV Dc line Mandsaur PS – Khandwa (New) 765kV Dc line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV Dc line | 31-May-27 | 31-May-27 |  |  | 300 | 202 |  |  |  | 2027-04-30 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-May-27 |  | 2027-05-31 | 2027-11-30
2200000817 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 334 (250 MW Solar + 84 MW Wind) |  | 250 | 84 | 0 | 334 | NTPC | Granted | 334 | 0 | 334 | Pachora (Sec-III) | Madhya Pradesh | 2026-01-07 | 2027-09-29 | • AEPL - Pachora PS 220 kV Sc line (on Dc tower) along with associated bay at generation end. (Under scope of applicant). • 1 no. 220 kV line bay on Bus Section-III at Pachora PS is being implemented under ISTS as part of Rajgarh Phase-III transmission scheme. | 1 | 220 KV | Aug without ATS |  |  | 1. Transmission System for Evacuation of Power from RE Projects in Rajgarh (1000MW) SEZ in Madhya Pradesh Phase- II (SCOD 14.02.2026) (Pachora Power Transmission Limited. -G R InfraProjects Ltd.) • 400220kV, 3x500MVA ICT augmentation (4th, 5th and 6th | 1. Transmission System for Evacuation of Power from RE Projects in Rajgarh (1000MW) SEZ in Madhya Pradesh Phase- II (SCOD 14.02.2026) (Pachora Power Transmission Limited. -G R InfraProjects Ltd.) • 400220kV, 3x500MVA ICT augmentation (4th, 5th and 6th) at Pachora PS. • Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) along with associated bays at both ends. 2. Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III and Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II(Part System) (SCOD 29.09.2027)( Ms Rajgarh Neemuch Power Transmission Limited -G R Infraprojects. Ltd.) • Creation of New 220kV Bus Section (3rd) with 220kV Bus Sectionaliser. • Augmentation of transformation capacity by 400220kV, 3x500 MVA ICTs (7th, 8th & 9th ) at Pachora PS to be terminated on 220kV Bus Section (3rd). • Pachora PS – Rajgarh (PG) 400 kV Dc line (Quad ACSR AAAC AL59 Moose equivalent) along with associated bays at both ends. • Installation of 1x125 MVAR, 420 kV bus reactor at Pachora PS (400kV Bus Section-II). | 31-Jul-26 | 31-Jul-26 |  |  | 334 |  |  |  |  | 2027-09-29 | 2027-09-29 | 2027-09-29 |  | Not effective | 2027-09-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 84.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-09-29
2200000818 | Main-Connectivity under GNA |  | JSW NEO ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 175 |  | 65 | 110 | 0 | 175 |  | Granted | 150 | 0 | 150 | Karur | Tamil Nadu | 2025-08-14 | 2025-12-31 | • Through dedicated connectivity transmission system of Ms JSW Neo Energy Ltd. for app. no. 1200003212 (for 150 MW) i.e. Generation Pooling Station of Ms JSW Neo Energy Ltd. – Karur PS 230 kV Sc line. – all arrangement under the scope of applicant | 0 | 230 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for evacuation of power from RE sources in Karur Tirpur wind Energy Zone (Tamil Nadu) (1000 | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for evacuation of power from RE sources in Karur Tirpur wind Energy Zone (Tamil Nadu) (1000 MW) under Phase-II | 31-May-25 | 31-May-25 |  |  | 150 | N |  |  |  |  | 2026-02-28 | 2027-01-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 95.70 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 54.30 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2027-01-31
2200000819 | Main-Connectivity under GNA |  | SPRNG VAYU VIDYUT PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 16.8 |  | 0 | 16.8 | 0 | 16.8 |  | Granted | 16.8 | 0 | 16.8 | Rajgarh (Sec-II) | Madhya Pradesh | 2024-11-20 | 2028-06-30 | SVVPL in present application shall share the DTL already identified to SVVPL in application no. 2200000022, which is detailed below: • SVVPL – Rajgarh (PG) 220kV S/c line along with associated bay at Generator end (Under the scope of applicant) • 220kV GIS line bay at Rajgarh 400/220kV (PG) S/s (on extended bus) for RE interconnection (under the scope of ISTS | 0 | 220 kV | Aug without ATS |  |  | 1. 1x500MVA, 400/220kV ICT (4th) at Rajgarh S/s (on the sectionalized 220kV bus) along with associated bays at both ends (400kV AIS & 220kV GIS) 2. 220kV bus extension (GIS) of Rajgarh (PG) 400/220 kV S/s along with 220kV Bus Coupler Bay for extended bus. 3. 220kV bus sectionaliser bay (GIS) between existing & extended 220 kV bus of Rajgarh S/s. | 1. 1x500MVA, 400/220kV ICT (4th) at Rajgarh S/s (on the sectionalized 220kV bus) along with associated bays at both ends (400kV AIS & 220kV GIS) 2. 220kV bus extension (GIS) of Rajgarh (PG) 400/220 kV S/s along with 220kV Bus Coupler Bay for extended bus. 3. 220kV bus sectionaliser bay (GIS) between existing & extended 220 kV bus of Rajgarh S/s. | 30-Jun-28 | 30-Jun-28 |  |  | 16.8 | 217 |  |  |  | 2024-12-05 | 2026-02-14 | 2026-12-31 |  | Not effective | 2028-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 16.80 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-28 |  | 2028-06-30 | 2028-12-30
2200000820 | Main-Connectivity under GNA |  | GREEN INFRA WIND ENERGY PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ananthapuram-II | Andhra Pradesh | 2025-06-04 | 2028-09-30 | • Generation Station of M/s Sembcorp Green Infra Pvt. Ltd. [erstwhile Green Infra Wind Energy Pvt. Ltd]– Anantapur-II PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Anantapur-II PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Anantapur-II (near Rayadurgam) REZs (Phase-1) • Transmission System for integration of Davanagere / Chitradurga | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Anantapur-II (near Rayadurgam) REZs (Phase-1) • Transmission System for integration of Davanagere / Chitradurga | 31-May-27 | Phase 1 ¦ MW: 300.00 ¦ Date: 2027-05-31 |  |  | 300 | 2B1-04 |  |  |  | 2027-03-31 | 2027-03-31 | 2027-09-30 |  | Not effective | 2028-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-09-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 300.00 ¦ Date: 2027-05-31 | 300 | 2027-05-31 | 2028-09-30
2200000823 | Main-Connectivity under GNA |  | BANYAN ENERGY PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Merta-II | Rajasthan | 2025-05-26 | 2027-03-24 | Banyan Energy Private Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage)# - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 30-Jun-26 | 30-Jun-26 |  |  | 300 | 204 |  |  |  | 2027-04-30 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-24 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-09-24
2200000824 | Main-Connectivity under GNA |  | SPRNG GREEN ENERGY 2 PRIVATE LIMITED | WR | Land BG Route | (x) Renewable Power Park developer | Solar | 600 | 0 | 600 | 0 | 0 | 600 |  | Granted | 600 | 0 | 600 | Mandsaur (Sec-I) | Madhya Pradesh | 2025-12-31 | 2029-12-31 | • SGE2PL – Mandsaur PS 400kV Sc line along with associated bay at the generation end (Under the scope of Ms SGE2PL). • 1 no. 400kV line bay at Mandsaur PS shall be implemented under ISTS as per request of applicant. | 1 | 400 KV | Aug without ATS |  |  | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x5 | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line | 200 MW 31.12.2029200 MW 31.12.2030200 MW 31.12.2031 | Phase 1 ¦ MW: 200.00 ¦ Date: 2029-12-31 Phase 2 ¦ MW: 200.00 ¦ Date: 2030-12-31 Phase 3 ¦ MW: 200.00 ¦ Date: 2031-12-31 |  |  | 600 | N |  |  |  | 2028-06-30 | 2026-10-15 | 2027-06-30 |  | Not effective | 2029-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2030-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 200.00 ¦ Date: 2031-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 200.00 ¦ Date: 2029-12-31 | 200 | 2029-12-31 | 2030-06-30
2200000824 | Main-Connectivity under GNA |  | SPRNG GREEN ENERGY 2 PRIVATE LIMITED | WR | Land BG Route | (x) Renewable Power Park developer | Solar | 600 | 0 | 600 | 0 | 0 | 600 |  | Granted | 600 | 0 | 600 | Mandsaur (Sec-I) | Madhya Pradesh | 2025-12-31 | 2029-12-31 | • SGE2PL – Mandsaur PS 400kV Sc line along with associated bay at the generation end (Under the scope of Ms SGE2PL). • 1 no. 400kV line bay at Mandsaur PS shall be implemented under ISTS as per request of applicant. | 1 | 400 KV | Aug without ATS |  |  | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x5 | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line | 200 MW 31.12.2029200 MW 31.12.2030200 MW 31.12.2031 | Phase 1 ¦ MW: 200.00 ¦ Date: 2029-12-31 Phase 2 ¦ MW: 200.00 ¦ Date: 2030-12-31 Phase 3 ¦ MW: 200.00 ¦ Date: 2031-12-31 |  |  | 600 | N |  |  |  | 2028-06-30 | 2026-10-15 | 2027-06-30 |  | Not effective | 2029-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2030-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 200.00 ¦ Date: 2031-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 200.00 ¦ Date: 2030-12-31 | 200 | 2030-12-31 | 2031-06-30
2200000824 | Main-Connectivity under GNA |  | SPRNG GREEN ENERGY 2 PRIVATE LIMITED | WR | Land BG Route | (x) Renewable Power Park developer | Solar | 600 | 0 | 600 | 0 | 0 | 600 |  | Granted | 600 | 0 | 600 | Mandsaur (Sec-I) | Madhya Pradesh | 2025-12-31 | 2029-12-31 | • SGE2PL – Mandsaur PS 400kV Sc line along with associated bay at the generation end (Under the scope of Ms SGE2PL). • 1 no. 400kV line bay at Mandsaur PS shall be implemented under ISTS as per request of applicant. | 1 | 400 KV | Aug without ATS |  |  | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x5 | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line | 200 MW 31.12.2029200 MW 31.12.2030200 MW 31.12.2031 | Phase 1 ¦ MW: 200.00 ¦ Date: 2029-12-31 Phase 2 ¦ MW: 200.00 ¦ Date: 2030-12-31 Phase 3 ¦ MW: 200.00 ¦ Date: 2031-12-31 |  |  | 600 | N |  |  |  | 2028-06-30 | 2026-10-15 | 2027-06-30 |  | Not effective | 2029-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2029-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2030-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 200.00 ¦ Date: 2031-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 3 ¦ MW: 200.00 ¦ Date: 2031-12-31 | 200 | 2031-12-31 | 2032-06-30
2200000825 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 76 |  | 0 | 76 | 0 | 76 | SECI | Granted | 76 | 0 | 76 | Bellary | Karnataka | 2025-06-19 | 2027-09-22 | • Generation Station of M/s NTPC Renewable Energy Ltd. – Bellary PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant • 01 no. 220 kV line bay at Bellary PS for above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | 16-Apr-26 | 16-Apr-26 |  |  | 76 |  |  |  |  | 2027-09-21 | 2027-09-21 | 2027-09-30 |  | Not effective | 2027-09-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 76.00 ¦ Date: 2027-09-22 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 | Yes |  |  | Pending with Level 2 | 16-Apr-26 |  | 2026-04-16 | 2027-09-30
2200000840 | Main-Connectivity under GNA |  | ACME Solar Holdings Limited | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Merta-II | Rajasthan | 2025-05-26 | 2027-03-31 | ACME Solar Holdings Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage)# - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 31-Mar-27 | 31-Mar-27 |  |  | 300 | 205 |  |  |  | 2027-04-30 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2027-09-30
2200000842 | Main-Connectivity under GNA |  | PURVAH GREEN POWER PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Merta-II | Rajasthan | 2025-05-26 | 2027-09-01 | Purvah Green Power Private Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage)# - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 31-May-27 | 31-May-27 |  |  | 300 | 213 |  |  |  | 2027-08-31 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-08-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-May-27 |  | 2027-05-31 | 2028-03-01
2200000843 | Main-Connectivity under GNA |  | SAEL INDUSTRIES LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 250 | 0 | 0 | 250 |  | Granted | 250 | 0 | 250 | Kurnool-IV | Andhra Pradesh | 2025-06-19 | 2027-03-25 | • Generation Station of M/s SAEL Industries Ltd. – Kurnool -IV PS 220 kV S/c line along with line bay at generation PS.- under the scope of applicant • 1 no. 220 kV line bay at Kurnool-IV PS for termination of above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV REZ- Phase-I | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV REZ- Phase-I | 31-Jul-26 | 31-Jul-26 |  |  | 250 | 230 |  |  |  | 2027-03-24 | 2027-03-24 | 2027-09-30 |  | Not effective | 2027-03-25 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-09-30
2200000844 | Main-Connectivity under GNA |  | SAEL INDUSTRIES LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Kurnool-IV | Andhra Pradesh | 2025-06-19 | 2027-03-25 | • Generation Station of M/s SAEL Industries Ltd. – Kurnool -IV PS 220 kV S/c line along with line bay at generation PS- under the scope of applicant. • 1 no. 220 kV line bay at Kurnool-IV PS for termination of above DTL – under the scope of ISTS. | 1 | 230 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV REZ- Phase-I | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV REZ- Phase-I | 31-Jul-26 | 31-Jul-26 |  |  | 300 | 234 |  |  |  |  | 2027-03-24 | 2027-09-30 |  | Not effective | 2027-03-25 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: | 22.12.2025 |  |  | 08/07/2026 | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-09-30
2200000848 | Main-Connectivity under GNA |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED | NR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Solar | 300 | 0 | 300 | 0 | 50 | 350 |  | Granted | 300 | 0 | 300 | Merta-II | Rajasthan | 2025-05-26 | 2027-03-31 | Hexa Climate Solutions Private Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage)# - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 100 MW 31.03.2027100 MW 30.09.2027100 MW 31.03.2028 | Phase 1 ¦ MW: 100.00 ¦ Date: 2027-03-31 Phase 2 ¦ MW: 100.00 ¦ Date: 2027-09-30 Phase 3 ¦ MW: 100.00 ¦ Date: 2028-03-31 |  |  | 300 | 215 |  |  |  | 2027-04-30 | 2026-12-30 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 1 ¦ MW: 100.00 ¦ Date: 2027-03-31 | 100 | 2027-03-31 | 2027-09-30
2200000848 | Main-Connectivity under GNA |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED | NR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Solar | 300 | 0 | 300 | 0 | 50 | 350 |  | Granted | 300 | 0 | 300 | Merta-II | Rajasthan | 2025-05-26 | 2027-03-31 | Hexa Climate Solutions Private Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage)# - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 100 MW 31.03.2027100 MW 30.09.2027100 MW 31.03.2028 | Phase 1 ¦ MW: 100.00 ¦ Date: 2027-03-31 Phase 2 ¦ MW: 100.00 ¦ Date: 2027-09-30 Phase 3 ¦ MW: 100.00 ¦ Date: 2028-03-31 |  |  | 300 | 215 |  |  |  | 2027-04-30 | 2026-12-30 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 2 ¦ MW: 100.00 ¦ Date: 2027-09-30 | 100 | 2027-09-30 | 2028-03-30
2200000848 | Main-Connectivity under GNA |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED | NR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Solar | 300 | 0 | 300 | 0 | 50 | 350 |  | Granted | 300 | 0 | 300 | Merta-II | Rajasthan | 2025-05-26 | 2027-03-31 | Hexa Climate Solutions Private Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower (suitable to carry minimum 300 MW at nominal voltage)# - Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 100 MW 31.03.2027100 MW 30.09.2027100 MW 31.03.2028 | Phase 1 ¦ MW: 100.00 ¦ Date: 2027-03-31 Phase 2 ¦ MW: 100.00 ¦ Date: 2027-09-30 Phase 3 ¦ MW: 100.00 ¦ Date: 2028-03-31 |  |  | 300 | 215 |  |  |  | 2027-04-30 | 2026-12-30 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | Phase 3 ¦ MW: 100.00 ¦ Date: 2028-03-31 | 100 | 2028-03-31 | 2028-09-30
2200000869 | Main-Connectivity under GNA |  | GANEKO THREE ENERGY PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 354 (Solar-255 MW, Wind-99 MW) |  | 255 | 99 | 0 | 354 |  | Granted | 300 | 0 | 300 | Ananthapuram-II | Andhra Pradesh | 2025-06-04 | 2027-12-31 | • Generation Station of Ms Ganeko Three Energy Pvt. Ltd – Anantapur-II PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Anantapur-II PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. • Transmission System for Integration of Anantapur-II REZs (Phase-I) as per Annexure-II. • Tran | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. • Transmission System for Integration of Anantapur-II REZs (Phase-I) as per Annexure-II. • Transmission System for integration of Davanagere Chitradurga as per Annexure-III. | 31-Mar-28 | 31-Mar-28 |  |  | 300 | 2B1-06 |  |  |  | 2027-12-31 | 2027-03-31 | 2027-09-30 |  | Not effective | 2027-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 120.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 180.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-28 |  | 2028-03-31 | 2028-09-30
2200000872 | Main-Connectivity under GNA |  | PURVAH GREEN POWER PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 349.8 |  | 0 | 349.8 | 0 | 349.8 |  | Granted | 349.8 | 0 | 349.8 | Ananthapuram-II | Andhra Pradesh | 2025-06-04 | 2027-04-01 | •Generating Pooling Station of Ms Purvah Green Power Pvt. Ltd.– Anantapur-II PS 220 kV Sc line on Dc tower# along with line bay at generation pooling station – under the scope of applicant. •1 no. of 220 kV line bay at Anantapur-II PS for termination of above mentioned dedicated Connectivity line - under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Anantapur-II REZs (Phase-I) • Transmission System for integration of Dav | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Anantapur-II REZs (Phase-I) • Transmission System for integration of Davanagere Chitradurga | 31-Mar-28 | 31-Mar-28 |  |  | 349.8 | 2B1-08 |  |  |  | 2027-03-31 | 2027-03-31 | 2027-09-30 |  | Not effective | 2027-04-01 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 349.80 ¦ Date: 2027-04-01 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-28 |  | 2028-03-31 | 2028-09-30
2200000876 | Main-Connectivity under GNA |  | JADE HYBREN PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 300(Solar-200 MW, Wind-100 MW) |  | 200 | 100 | 0 | 300 |  | Granted | 300 | 0 | 300 | Davangere | Karnataka | 2025-12-23 | 2027-09-25 | • Generation Pooling Station of Ms Jade Hybren Pvt. Ltd. – Davanagere Chitradurga PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Davanagere Chitradurga PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmiss | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for integration of Davanagere Chitradurga • Augmentation of 2x500 MVA, 400220 kV ICT at Davangere PS | 31-Dec-26 | 31-Dec-26 |  |  | 300 | 208 |  |  |  |  | 2027-09-24 | 2027-09-30 |  | Not effective | 2027-09-25 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-09-25 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2027-09-25 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2028-03-25
2200000879 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Merta-II | Rajasthan | 2025-05-26 | 2027-12-31 | Juniper Green Energy Private Limited Solar Power Project– Merta-II PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage)-Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | Establishment of 765/400 kV, 2x1500 MVA & 5x500 MVA, 400/220 kV S/s at suitable location near Merta (Merta-II Substation) along with 2x125 MVAr & 2x240 MVAr bus reactor at Merta-II S/s Merta-II – Beawar 400 kV D/c line (Quad) Merta-II – Dausa 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Merta-II – Dausa 765 kV D/c line Establishment of 765/400kV, 2x1500 MVA S/s at suitable location near Ghiror (Distt. Mainpuri) along with 2x125 MVAr & 2x240 MVAr bus reactor at Ghiror S/s (UP) Dausa - Ghiror 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end of Dausa - Ghiror 765 kV D/c line LILO of both ckt of 765 kV Aligarh (PG) – Orai (PG) D/c line at Ghiror S/s along with 240 MVAr switchable line reactor for each circuit at Ghiror S/s end of 765 kV Ghiror -Orai D/c line LILO of one ckt of 765kV Agra (PG) – Fatehpur (PG) 765kV D/c line at Ghiror along with 240 MVAr switchable line reactor at Ghiror S/s end of 765 kV Ghiror – Fatehpur line 400kV Ghiror-Firozabad (UPPTCL) D/c line (Quad) Sirohi – Mandsaur PS 765KV D/c line along with 240 MVAr switchable line reactor at Sirohi S/s end 330MVAr switchable line reactor at Mandsaur PS end for each circuit of Sirohi – Mandsaur PS 765KV D/c line Mandsaur PS – Khandwa (New) 765kV D/c line along with 240MVAr switchable line reactor for each circuit at each end of Mandsaur PS – Khandwa (New) 765kV D/c line | 31-Dec-27 | 31-Dec-27 |  |  | 300 | 216 |  |  |  | 2027-04-30 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2028-06-30
2200000881 | Main-Connectivity under GNA |  | PURVAH GREEN POWER PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 339.9 |  | 0 | 339.9 | 0 | 339.9 |  | Granted | 339.9 | 0 | 339.9 | Ananthapuram-II | Andhra Pradesh | 2025-06-04 | 2027-04-01 | •Generating Pooling Station of Ms Purvah Green Power Pvt. Ltd.– Anantapur-II PS 220 kV Sc line on Dc tower# along with line bay at generation pooling station – under the scope of applicant. •1 no. of 220 kV line bay at Anantapur-II PS for termination of above mentioned dedicated Connectivity line - under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmiss | Common Transmission system required for effectiveness of connectivityGNA (Augmentation other than ATS) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Anantapur-II (near Rayadurgam) REZs (Phase-1) • Transmission System for integration of Davanagere Chitradurga | 31-Mar-28 | 31-Mar-28 |  |  | 339.9 | 2B1-10 |  |  |  | 2027-03-31 | 2027-03-31 | 2027-09-30 |  | Not effective | 2027-04-01 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 339.90 ¦ Date: 2027-04-01 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-28 |  | 2028-03-31 | 2028-03-31
2200000883 | Main-Connectivity under GNA |  | PURVAH GREEN POWER PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 297 |  | 0 | 297 | 0 | 297 |  | Granted | 297 | 0 | 297 | Pachora (Sec-III) | Madhya Pradesh | 2026-01-07 | 2027-09-29 | • PGPPL – Pachora PS 220kV Sc line (on Dc Towers)# along with 220kV line bay at generation station (Under the scope of Ms PGPPL). • 1 no. 220kV line bay on Bus Section-III at Pachora PS shall be implemented under ISTS as a part of “Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III and Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II”. | 1 | 220 KV | Aug without ATS |  |  | 1. Transmission System for Evacuation of Power from RE Projects in Rajgarh (1000MW) SEZ in Madhya Pradesh Phase- II (SCOD 14.02.2026) (Pachora Power Transmission Limited. -G R InfraProjects Ltd.) 400220kV, 3x500MVA ICT augmentation (4th, 5th and | 1. Transmission System for Evacuation of Power from RE Projects in Rajgarh (1000MW) SEZ in Madhya Pradesh Phase- II (SCOD 14.02.2026) (Pachora Power Transmission Limited. -G R InfraProjects Ltd.) 400220kV, 3x500MVA ICT augmentation (4th, 5th and 6th) at Pachora PS. Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) along with associated bays at both ends. 2. Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III and Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II(Part System) (SCOD 29.09.2027)( Ms Rajgarh Neemuch Power Transmission Limited -G R Infraprojects. Ltd.) Creation of New 220kV Bus Section (3rd) with 220kV Bus Sectionaliser. Augmentation of transformation capacity by 400220kV, 3x500 MVA ICTs (7th, 8th & 9th ) at Pachora PS to be terminated on 220kV Bus Section (3rd). Pachora PS – Rajgarh (PG) 400 kV Dc line (Quad ACSR AAAC AL59 Moose equivalent) along with associated bays at both ends. Installation of 1x125 MVAR, 420 kV bus reactor at Pachora PS (400kV Bus Section-II). | 31-May-27 | 31-May-27 |  |  | 297 | N |  |  |  | 2027-09-29 | 2027-09-29 | 2027-09-29 |  | Not effective | 2027-09-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 297.00 ¦ Date: 2027-09-29 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-May-27 |  | 2027-05-31 | 2028-03-29
2200000892 | Main-Connectivity under GNA |  | AMPIN ENERGY UTILITY PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 185.4 (Solar-135; Wind 50.4) |  | 135 | 50.4 | 0 | 185.4 | NTPC | Granted | 150 | 0 | 150 | Bidar | Karnataka | 2025-12-23 | 2027-12-31 | • Generation Pooling Station of M/s Ampin Energy Utility Pvt. Ltd. – Bidar PS 220 kV S/c line along with line bay at generation pooling station – under the scope of applicant • 1 no. 220 kV line bay at Bidar PS for termination of above mentioned line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • Augmentation of 1x500 MVA, 400/220 kV 6th ICT at Bidar PS | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • Augmentation of 1x500 MVA, 400/220 kV 6th ICT at Bidar PS | 31-Dec-27 | 31-Dec-27 |  |  | 150 | 218 |  |  |  |  | 2027-02-28 | 2027-06-30 |  | Not effective | 2027-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.40 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 135.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2027-12-31
2200000893 | Main-Connectivity under GNA |  | AMPIN Energy C&I Thirteen Private Limited (Formerly known as AMP ENERGY C&I THIRTEEN PRIVATE LIMITED) | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 68.9 (Solar-50; Wind 18.9) |  | 50 | 18.9 | 0 | 68.9 |  | Granted | 50 | 0 | 50 | Bidar | Karnataka | 2025-12-23 | 2027-12-31 | Through dedicated connectivity transmission system agreed for app. no. 2200000892 i.e. Generating station of M/s Ampin Energy Utility Pvt. Ltd. – Bidar PS 220 kV S/c line - all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • Augmentation of 1x500 MVA, 400/220 kV 6th ICT at Bidar PS | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • Augmentation of 1x500 MVA, 400/220 kV 6th ICT at Bidar PS | 31-Mar-27 | 31-Mar-27 |  |  | 50 | 218 |  |  |  |  | 2027-02-28 | 2027-06-30 |  | Not effective | 2027-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-06-30
2200000899 | Main-Connectivity under GNA |  | BHOJRAJ RENEWABLES ENERGY PRIVATE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 | 0 | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Mandsaur (Sec-II) | Madhya Pradesh | 2024-11-26 | 2026-12-31 | BREPL – Mandsaur 220kV Sc line (on Dc Towers) along with associated bay at the generation end (Under the scope of BREPL). 1 no. 220kV line bay (on 220kV Bus Sec-II) at Mandsaur PS (being implemented under ISTS as part of PS). | 1 | 220 KV | Aug without ATS |  |  | 1. Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C Establishment of 3x1500 MVA, 765400 kV & 5x500MVA, 400220kV Mandsaur Pooling Station (along with associated bays) Mandsaur P | 1. Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C Establishment of 3x1500 MVA, 765400 kV & 5x500MVA, 400220kV Mandsaur Pooling Station (along with associated bays) Mandsaur PS – Indore ((PG) 765 kV Dc Line 2. Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 Establishment of 765400 kV (2x1500 MVA), 400220 kV (2x500 MVA) & 220132 kV (3x200 MVA) Kurawar Ss Mandsaur – Kurawar 765 kV Dc line along with LILO of Indore – Bhopal 765 kV Sc line at Kurawar Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line. | 31-Dec-27 | 31-Dec-27 |  |  | 300 | 218 |  |  |  | 2027-03-31 | 2026-10-15 | 2027-06-30 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2028-06-30
2200000906 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 500 |  | 500 | 0 | 0 | 500 |  | Granted | 500 | 0 | 500 | Barmer-II | Rajasthan | 2026-01-19 |  | Common Pooling station for NTPC Renewable Energy Ltd. Solar Power Projects (2200000567(300MW) & 22000000906-500 MW) – Barmer-II PS 400 kV Sc line on Dc tower (Suitable to carry minimum 900 MW at nominal voltage)-Under Applicant Scope | 0 | 400 KV | Aug without ATS |  |  |  | 1. Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 2. LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS 3. Barmer-II PS- Barmer-I PS 400kV Dc line (Quad) 4. Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation 5. Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) 6. Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor 7. LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss 8. ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 9. 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 30-Oct-26 | 30-Oct-26 |  |  | 500 | Not allocated | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 500.00 ¦ Date: 2030-09-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Oct-26 |  | 2026-10-30 | 2030-12-30
2200000919 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 400 |  | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Kurnool-IV | Andhra Pradesh | 2025-06-19 | 2027-03-25 | • Generation Station of M/s Tata Power Renewable Energy Ltd.– Kurnool -IV PS 220 kV S/c line on D/c tower [through stringing of both arms of D/c tower and bunching them at both ends to form single circuit] along with line bay at generation PS- under the scope of applicant. • 1 no. 220 kV line bay at Kurnool-IV PS for termination of above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV REZ- Phase-I | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV REZ- Phase-I | 31-Jul-26 | 31-Jul-26 |  |  | 400 | 236 |  |  |  | 2027-03-24 | 2027-03-24 | 2027-09-30 |  | Not effective | 2027-03-25 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-09-30
2200000920 | Main-Connectivity under GNA |  | ZENATARIS RENEWABLE ENERGY PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 62.7 |  | 0 | 62.7 | 0 | 62.7 |  | Granted | 62.7 | 0 | 62.7 | Hiriyur | Karnataka | 2025-01-07 | 2025-12-31 | Through dedicated connectivity transmission system of M/s Zenataris Renewable Energy Pvt. Ltd. granted for application no. 0251100011 i.e M/s Zenataris Renewable Energy Pvt. Ltd. –Hiriyur 220 kV S/c line- all arrangement under the scope of ISTS | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure | 30-Jun-25 | 30-Jun-25 |  |  | 62.7 | 216 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 62.70 ¦ Date: 2026-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-25 |  | 2025-06-30 | 2026-10-31
2200000923 | Main-Connectivity under GNA |  | WAFT ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Pachora (Sec-III) | Madhya Pradesh | 2026-01-06 | 2027-09-29 | WEPL shall share the DTL of 297MW REGS of Ms Purvah Green Power Pvt Ltd. (appl. No. 2200000883) • PGPPL – Pachora PS 220kV Sc line along with 220kV line bay at generation station (Under the scope of Ms PGPPL). • 1 no. 220kV line bay on Bus Section-III at Pachora PS shall be implemented under ISTS as a part of Rajgarh Phase-III transmission scheme. | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III (Being implemented by Ms Rajgarh Neemuch Power Transmission Limited (a subsidiary of GR Infra)) (SCOD 29.09.2027) • Creation of New 220kV | Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III (Being implemented by Ms Rajgarh Neemuch Power Transmission Limited (a subsidiary of GR Infra)) (SCOD 29.09.2027) • Creation of New 220kV Bus Section (3rd) with 220kV Bus Sectionaliser. • Augmentation of transformation capacity by 400220kV, 3x500 MVA ICTs (7th, 8th & 9th ) at Pachora PS terminated on 220kV Bus Section (3rd). • Pachora PS – Rajgarh (PG) 400 kV Dc line (Quad ACSR AAAC AL59 Moose equivalent) along with associated bays at both ends Transmission System for Evacuation of Power from RE Projects in Rajgarh 1000MW SEZ in Madhya Pradesh Phase- II (Being implemented by Pachora Power Transmission Limited. (a subsidiary of GR Infra)) (SCOD 14.02.2026) • 400220kV, 3x500MVA ICT augmentation (4th, 5th and 6th) at Pachora PS. • Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) along with associated bays at both ends. | 30-Jun-26 | 30-Jun-26 |  |  | 100 | N |  |  |  | 2027-09-29 | 2027-09-29 | 2027-09-29 |  | Not effective | 2027-09-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-09-29 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2028-03-29
2200000924 | Main-Connectivity under GNA |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 | 0 | 150 | 0 | 0 | 150 | NTPC | Granted | 150 | 0 | 150 | Mandsaur (Sec-II) | Madhya Pradesh | 2024-11-26 | 2026-12-31 | ACSPL – Mandsaur 220kV Sc line (on Dc towers) along with associated bay at the generation end (Under the scope of ACSPL). 1 no. 220kV line bay (on 220kV Bus Sec-II) at Mandsaur PS (being implemented under ISTS as part of PS). | 1 | 220 KV | Aug without ATS |  |  | 1. Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C Establishment of 3x1500 MVA, 765400 kV & 5x500MVA, 400220kV Mandsaur Pooling Station (along with associated bays) Mandsaur PS | 1. Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C Establishment of 3x1500 MVA, 765400 kV & 5x500MVA, 400220kV Mandsaur Pooling Station (along with associated bays) Mandsaur PS – Indore ((PG) 765 kV Dc Line 2. Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 Establishment of 765400 kV (2x1500 MVA), 400220 kV (2x500 MVA) & 220132 kV (3x200 MVA) Kurawar Ss Mandsaur – Kurawar 765 kV Dc line along with LILO of Indore – Bhopal 765 kV Sc line at Kurawar Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line. | 25-Sep-26 | 25-Sep-26 |  |  | 150 | 216 |  |  |  | 2027-03-31 | 2026-10-15 | 2027-06-30 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 25-Sep-26 |  | 2026-09-25 | 2027-06-30
2200000931 | Main-Connectivity under GNA |  | GENTARI RENEWABLES INDIA CASTOR ONE PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 230 |  | 0 | 230 | 0 | 230 |  | Granted | 230 | 0 | 230 | Kurnool-IV | Andhra Pradesh | 2025-06-19 | 2027-03-25 | • Generating Pooling Station of M/s Gentari Renewables India Castor One Pvt. Ltd.- Kurnool-IV PS 220 kV S/c line on D/c tower# along with line bay at generation pooling station – under the scope of applicant. • 1 no. of 220 kV line bay at Kurnool-IV PS for termination of above mentioned dedicated Connectivity line - under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV REZ- Phase-I | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV REZ- Phase-I | 30-Sep-26 | 30-Sep-26 |  |  | 230 | 238 |  |  |  | 2027-03-24 | 2027-03-24 | 2027-09-30 |  | Not effective | 2027-03-25 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 230.00 ¦ Date: 2027-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 30-Sep-26 |  | 2026-09-30 | 2027-09-30
2200000932 | Main-Connectivity under GNA |  | JSW NEO ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 325 |  | 0 | 325 | 0 | 325 | SECI | Granted | 325 | 0 | 325 | Davangere | Karnataka | 2025-12-30 | 2027-09-25 | • Generation Station of Ms JSW Neo Energy Ltd. – Davanagere Chitradurga PS 220 kV Sc line on Dc tower along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Davanagere Chitradurga PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for integration of Davanagere Chitradurga • Augmentation of 2x500 MVA, 400220 kV ICT (7th & | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for integration of Davanagere Chitradurga • Augmentation of 2x500 MVA, 400220 kV ICT (7th & 8th) at Davangere PS | 12-Jun-26 | 12-Jun-26 |  |  | 325 | [5 empty] | 2027-09-24 | 2027-09-30 |  | Not effective | 2027-09-25 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 325.00 ¦ Date: 2027-09-20 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 12-Jun-26 |  | 2026-06-12 | 2027-09-30
2200000938 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 500 |  | 470 | 0 | 0 | 470 |  | Granted | 470 | 0 | 470 | Neemuch | Madhya Pradesh | 2026-01-02 | 2027-09-29 | • AEPL – Neemuch PS 220kV D/c line (with min capacity of 335MW per ckt at nominal voltage) along with associated bay at the generation end (Under the scope of AEPL). • 2 no. 220kV line bays at Neemuch PS (being implemented under ISTS as part of Transmission system for Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II scheme). | 2 | 220 kV | Aug without ATS |  |  | Transmission system for Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II (Being implemented by: M/s Rajgarh Neemuch Power Transmission Limited (RNTL))(SCOD: 29.09.2027) • Creation of New 220kV Bus Section-II with augmentation of transformation capacity by 3x500MVA, 400/220kV ICTs (3rd , 4th & 5th) at Neemuch PS along with associated bays. • Establishment of 2x500MVA, 400/220kV Handiya S/s. Neemuch PS – Pachora PS 400kV 400 kV D/c line (Quad ACSR/ AAAC/ AL59 Moose equivalent) along with associated line bays. • Pachora PS – Handiya (PG) 400kV 400 kV D/c line (Quad ACSR/ AAAC/ AL59 Moose equivalent) along with associated line bays. • LILO of Khandwa (PG) – Itarsi (PG) 400kV D/c (Twin Moose) line at Handiya S/s. | Transmission system for Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II (Being implemented by: M/s Rajgarh Neemuch Power Transmission Limited (RNTL))(SCOD: 29.09.2027) • Creation of New 220kV Bus Section-II with augmentation of transformation capacity by 3x500MVA, 400/220kV ICTs (3rd , 4th & 5th) at Neemuch PS along with associated bays. • Establishment of 2x500MVA, 400/220kV Handiya S/s. Neemuch PS – Pachora PS 400kV 400 kV D/c line (Quad ACSR/ AAAC/ AL59 Moose equivalent) along with associated line bays. • Pachora PS – Handiya (PG) 400kV 400 kV D/c line (Quad ACSR/ AAAC/ AL59 Moose equivalent) along with associated line bays. • LILO of Khandwa (PG) – Itarsi (PG) 400kV D/c (Twin Moose) line at Handiya S/s. | 31-Mar-27 | 31-Mar-27 |  |  | 470 |  |  |  |  | 2027-09-29 | 2027-09-29 | 2027-09-29 |  | Not effective | 2027-09-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 470.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-03-29
2200000948 | Main-Connectivity under GNA |  | SAEL INDUSTRIES LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 | SECI | Granted | 300 | 0 | 300 | Tumkur-II | Karnataka | 2025-03-19 | 2026-09-04 | • Generation Station of M/s SAEL Industries Ltd. – Tumkur-II PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Tumkur-II PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Tumkur-II REZ in Karnataka, as per Annexure | Common Transmission system required for effectiveness of connectivity/GNA (Augmentation other than ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission Scheme for integration of Tumkur-II REZ in Karnataka, as per Annexure | 15-Aug-26 | 15-Aug-26 |  |  | 300 | 203 | 2027-06-30 |  | As per the PPA submitted by applicant vide email dtd 02.03.2026 | 2026-09-02 | 2026-09-02 | 2026-11-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 15-Aug-26 |  | 2026-08-15 | 2027-06-30
2200000953 | Main-Connectivity under GNA |  | ADANI GREEN ENERGY LIMITED | WR | Land Route | (x) Renewable Power Park developer | Hybrid | 1530 MW (Solar1400 MW & Wind130 MW) | 0 | 1400 | 130 | 0 | 1530 |  | Granted | 1530 | 0 | 1530 | KPS-3 (Sec-II) | Gujarat | 2025-01-09 | 2029-05-19 | • AGEL (PSS-14) – KPS3 (Sec-II) 400kV Dc line (with minimum capacity of 1965MW at nominal voltage) along with associated bays at generation end (under the scope of AGEL) • 2 nos. 400kV bays on Bus Section-II at KPS3 (under ISTS) | 2 | 400 KV | Aug without ATS |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmeda | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line • KPS1 – KPS2 765kV Dc line Establishment of KPS2 in Khavda RE Park • Establishment of 765400kV KPS2(GIS) Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari(New) 765 kV Dc line Khavda Phase-IV • Creation of 765kV bus section-II at KPS3 (GIS) along with 765kV Bus Sectionaliser • Creation of 400kV bus section-II at KPS3 (GIS) along with 400kV Bus Sectionaliser • KPS3 (GIS) – Lakadia (AIS) 765 kV DC line • ±300MVAr STATCOM with 1x125 MVAr MSC, 2x125 MVAr MSR at KPS3 400kV Bus section-2 • KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line • Establishment of 2x1500MVA, 765400kV & 2x500MVA, 400220kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) • Vadodara(GIS) –South Olpad(GIS) 765 kV DC line • LILO of Gandhar – Hazira 400kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • Ahmedabad – South Olpad(GIS) 765kV Dc line • Establishment of 4X1500 MVA 765400 kV & 2x500MVA 400220kV Boisar-II (GIS) • South Olpad(GIS) – Boisar-II(GIS) 765kV Dc line • LILO of Navsari(New) – Padghe(PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon(MH) 400kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of Babhaleswar – Padghe(M) 400kV Dc line at Boisar-II (Sec-I) using twin HTLS conductor with minimum capacity of 1700MVA per ckt at nominal voltage • ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-I of Boisar-II and ±200MVAr STATCOM with 2x125 MVAr MSC, 1x125 MVAr MSR at 400 kV bus section-II of Boisar-II • ±300 MVAr STATCOM with 3x125 MVAr MSC, 1x125 MVAr MSR at 400 kV level of Navsari(New)(PG) Ss with 1 No. of 400 kV bay (GIS) • Establishment of 2X1500 MVA 765400 kV & 3x500MVA 400220kV Pune-III (GIS) • Boisar-II – Pune- | 15-Jun-25 | 15-Jun-25 |  |  | 1530 | 435M 434T & 438M 437T |  |  |  | 2026-08-30 | 2029-05-19 | 2029-05-19 |  | Not effective | 2029-12-12 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 1400.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 130.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 02-04-2026 |  |  | 02/04/2026 | Not Submitted For Approval | 15-Jun-25 |  | 2025-06-15 | 2029-11-19
2200000954 | Main-Connectivity under GNA |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 250 |  | 250 | 0 | 0 | 250 |  | Granted | 250 | 0 | 250 | Barmer-II | Rajasthan | 2026-01-19 |  | Common Pooling station for Vismaya Five Renewables Pvt. Ltd. Solar Power Projects (App. No. 2200000954- 250 MW & App. No. 2200001285-50MW) – Barmer-II PS 220 kV Sc line on Dc tower# (suitable to carry minimum 300 MW at nominal voltage) -Under Applicant Scope | 1 | 220 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA (Tentative) 1. Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 2. 400220kV, 6x500 MVA ICTs at Barmer-II PS 3. LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS 4. Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) 5. Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation 6. Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) 7. Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor 8. LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss 9. ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 10. 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 31-Oct-30 | 31-Oct-30 |  |  | 250 |  | 2026-12-31 |  |  |  |  | 2030-12-30 |  | Not effective | 2030-10-31 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2030-10-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Oct-30 |  | 2030-10-31 | 2031-04-30
2200000956 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 240 |  | 240 | 0 | 0 | 240 | SECI | Granted | 240 | 0 | 240 | Pachora (Sec-III) | Madhya Pradesh | 2026-01-06 | 2027-09-29 | • AEPL – Pachora PS 220kV Sc line (on Dc tower) along with 220kV line bay at generation station (Under the scope of Ms AEPL). • 1 no. 220kV line bay on Bus Section-III at Pachora PS is being implemented under ISTS as a part of Rajgarh Phase-III transmission scheme. | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III (Being implemented by Ms Rajgarh Neemuch Power Transmission Limited (a subsidiary of GR Infra)) (SCOD 29.09.2027) • Creation of New 220kV | Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III (Being implemented by Ms Rajgarh Neemuch Power Transmission Limited (a subsidiary of GR Infra)) (SCOD 29.09.2027) • Creation of New 220kV Bus Section (3rd) with 220kV Bus Sectionaliser. • Augmentation of transformation capacity by 400220kV, 3x500 MVA ICTs (7th, 8th & 9th ) at Pachora PS terminated on 220kV Bus Section (3rd). • Pachora PS – Rajgarh (PG) 400 kV Dc line (Quad ACSR AAAC AL59 Moose equivalent) along with associated bays at both ends Transmission System for Evacuation of Power from RE Projects in Rajgarh 1000MW SEZ in Madhya Pradesh Phase- II (Being implemented by Pachora Power Transmission Limited. (a subsidiary of GR Infra)) (SCOD 14.02.2026) • 400220kV, 3x500MVA ICT augmentation (4th, 5th and 6th) at Pachora PS. • Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) along with associated bays at both ends. | 30-Sep-26 | 30-Sep-26 |  |  | 240 |  |  |  |  | 2027-09-29 | 2027-09-29 | 2027-09-29 |  | Not effective | 2027-09-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 240.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Sep-26 |  | 2026-09-30 | 2027-09-29
2200000967 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 82.5 |  | 0 | 82.5 | 0 | 82.5 |  | Granted | 82.5 | 0 | 82.5 | Karur | Tamil Nadu | 2026-06-17 | 2026-10-31 | • Through dedicated connectivity transmission system [230 kV Sc line on Dc tower] allocated to Ms TATA Power Renewable Energy Ltd. for application no. 2200000242 [198 MW] & subsequently sharing with application no. 2200000448 [93.6 MW] and stringing of 2nd arms of 230 kV Dc towers of the dedicated connectivity line and bunching both arms circuits at both ends to form single circuit line for termination in same bay allocated for application no. 2200000242] – all arrangement under the scope of applicant. | 0 | 230 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 2x500 MVA, 400230kV ICT (3rd and 4th) at Karur PS. | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 2x500 MVA, 400230kV ICT (3rd and 4th) at Karur PS. | 30-Jun-26 | 30-Jun-26 |  |  | 82.5 | 207 |  |  |  |  | 2027-01-31 |  |  | Not effective | 2026-10-31 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-04-30
2200000973 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Barmer-II | Rajasthan | 2026-01-19 |  | Common Pooling station for NTPC Renewable Energy Ltd. Solar Power Projects 2200000567(300MW), 22000000906 (500 MW) & 2200000973(100 MW)) – Barmer-II PS 400 kV Sc line on Dc tower# (Suitable to carry minimum 900 MW per circuit at nominal voltage)-Under Applicant Scope | 0 | 400 KV | Aug without ATS |  |  |  | Transmission system for Connectivity under GNA (Tentative) 1. Establishment of 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 2. LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS 3. Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) 4. 4. Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation 5. 5. Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) 6. Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor 7. LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss 8. ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 9. 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 31-Mar-27 | 31-Mar-27 |  |  | 100 | N | [5 empty] | 2030-12-30 |  | Not effective | 2030-09-30 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2030-09-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2030-12-30
2200000976 | Main-Connectivity under GNA |  | ADYANT ENERSOL PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 84 MW (60 MW Solar + 24 MW Wind) |  | 60 | 24 | 0 | 84 | SECI | Granted | 84 | 0 | 84 | Mandsaur (Sec-I) | Madhya Pradesh | 2025-08-14 | 2027-03-24 | AdEPL – Mandsaur PS 220kV Sc line (on Dc towers#) along with associated bay at the generation end (Under the scope of Ms AdEPL). 01 no. 220kV line bay (on 220kV Bus Sec-I) at Mandsaur PS is being implemented under ISTS. | 1 | 220 KV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2 5.5 GW) (JaisalmerBarmer Complex) Part C Establishment of 3x1500MVA, 765400kV & 5x500MVA, 40022 | Common Transmission System Augmentation for Connectivity under GNA Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2 5.5 GW) (JaisalmerBarmer Complex) Part C Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur Pooling Station along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. Mandsaur PS – Indore ((PG) 765 kV Dc Line Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV (Part-2 5.5 GW) (JaisalmerBarmer Complex) Part H1 Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. Mandsaur – Kurawar 765 kV Dc line LILO of Indore – Bhopal 765 kV Sc line at Kurawar Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line Transmission system for evacuation of power from Rajasthan REZ Ph-V (Part-1 4 GW) [SirohiNagaur] Complex Mandsaur PS – Khandwa (New) 765 kV Dc line | 31-Jul-26 | 31-Jul-26 |  |  | 84 | 208 |  |  |  | 2027-03-31 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-03-24 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 60.00 ¦ Date: 2027-03-24 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 24.00 ¦ Date: 2027-03-24 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-06-30
2200000981 | Main-Connectivity under GNA |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED | WR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Wind | 75.6 | 0 | 0 | 75.6 | 0 | 75.6 |  | Granted | 75.6 | 0 | 75.6 | Bhuj | Gujarat | 2025-06-06 | 2026-11-19 | Ms HCSPL shall share the dedicated transmission system already granted to Ms Avikiran Solar India Pvt. Ltd. (ASIPL) for its WPP of 168MW against application no. 1200001423 • Avikiran Solar India Pvt. Ltd. – Bhuj PS 220kV Sc line (with minimum capacity of 300 MW) along with associated bays at Bhuj PS & generation switchyard. (under the scope of Ms ASIPL). | 0 | 220 kV | Aug without ATS |  |  | Under PlanningApproval  Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (10th) with associated ICT bays* *Note POWERGRID vide e-mail dated 06.06.2024 & 12.06.2024 has informed that 400kV ICT Bay will be AIS (in dia. of bus | Under PlanningApproval  Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (10th) with associated ICT bays* *Note POWERGRID vide e-mail dated 06.06.2024 & 12.06.2024 has informed that 400kV ICT Bay will be AIS (in dia. of bus reactor) and 220kV ICT bay will be HybridMTS with connection of ICT with 220kV bay possible only through EHV Cables GIB. Under Implementation  Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th)  Khavda RE Zone • Banaskantha – Ahmedabad 765kV Dc line  Khavda Ph-II Part-B • Lakadia PS – Ahmedabad 765kV Dc line  Khavda Ph-II Part-C • Ahmedabad – Navsari (New) 765 kV Dc line • Establishment of 765400 kV Ahmedabad Ss  Khavda Ph-II Part-D • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line  Khavda Ph-III Part-A • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad  Khavda Ph-III Part-B • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc  Khavda Ph-IV B • Establishment of 765400220kV South Olpad (GIS) Ss • Vadodara – South Olpad(GIS) 765kV Dc line • Ahmedabad – South Olpad(GIS) 765kV Dc line  Khavda Ph-IV C • Establishment of 765400220kV Boisar-II (GIS) Ss • South Olpad – Boisar-II 765kV Dc line • LILO of Navsari (New) – Padghe (PG) 765kV Dc line at Boisar-II • Boisar-II (Sec-II) – Velgaon (MH) 400 kV Dc • LILO of Babhaleswar – Padghe (M) 400 kV Dc line at Boisar-II (Sec-I) Under Tendering  Khavda Ph-IV D (LOI issued on 21.10.2024) • Establishment of 765400220kV Pune-III (GIS) Ss. • Boisar-II – Pune-III 765kV Dc line • LILO of Narendra (New) – Pune (GIS) 765kV Dc line at Pune-III | 30-Jun-26 | 30-Jun-26 |  |  | 75.6 | 232 |  |  |  |  | 2026-11-19 | 2027-10-31 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 75.60 ¦ Date: 2026-11-19 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-10-31
2200000982 | Main-Connectivity under GNA |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED | SR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Wind | 200 MW (Wind - 200, BESS - 50) |  | 0 | 200 | 50 | 250 |  | Granted | 200 | 0 | 200 | Davangere | Karnataka | 2026-06-09 | 2028-06-30 | •Generation Station of Ms Hexa Climate Solutions Pvt. Ltd. – Davangere Chitradurga PS 220 kV Sc line on Dc tower along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Davangere PS for termination of above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission system strengthening at Davan | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission system strengthening at Davanagere for integration of RE generation | 30-Jun-28 | 30-Jun-28 |  |  | 200 | N | [5 empty] | 2027-09-30 |  | Not effective | 2028-06-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Standalone |  |  |  |  | Pending with Level 2 | 30-Jun-28 |  | 2028-06-30 | 2028-12-30
2200000988 | Main-Connectivity under GNA |  | RENEW SOLAR POWER PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Raghanesda | Gujarat | 2026-01-05 | 2027-11-30 | RSPPL shall share the DTL for Connectivity granted to Ms RSPPL for its 300MW SPP against application No. 2200000993 as given below • RSPPL – Raghanesda PS 400kV Sc line (on Dc tower) alongwith 400kV line bay at generation end (Under the scope of RPSPL). • 1 no. 400kV line bay at Raghanesda PS (being implemented under ISTS as part of Raghanesda 3GW scheme). | 0 | 400 KV | Aug without ATS |  |  | Under Implementation (under ISTS) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) Banaskantha – Ahmedabad 765kV Dc | Under Implementation (under ISTS) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) Banaskantha – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs South Olpad (GIS) – Boisar-II 765 | 30-Nov-27 | 30-Nov-27 |  |  | 300 | 453 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2027-11-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-11-30 ¦ Status: Under Implementation ¦ Type: Solar | Under impl |  |  |  | Pending with Level 2 | 30-Nov-27 |  | 2027-11-30 | 2028-05-30
2200000989 | Main-Connectivity under GNA |  | RENEW SOLAR POWER PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Raghanesda | Gujarat | 2026-01-05 | 2028-02-29 | RSPPL shall share the DTL for Connectivity granted to Ms RSPPL for its 300MW SPP against application No. 2200000993 as given below • RSPPL – Raghanesda PS 400kV Sc line (on Dc tower) alongwith 400kV line bay at generation end (Under the scope of RPSPL). • 1 no. 400kV line bay at Raghanesda PS (being implemented under ISTS as part of Raghanesda 3GW scheme). | 0 | 400 KV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA Under Implementation (under ISTS) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission | Common Transmission System Augmentation for Connectivity under GNA Under Implementation (under ISTS) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) Banaskantha – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) Establishment of 765400220kV Boisar-II (GIS) Ss | 29-Feb-28 | 29-Feb-28 |  |  | 100 | 453 |  |  |  |  | 2027-10-23 | 2027-10-23 |  | Not effective | 2028-02-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2028-02-29 ¦ Status: Under Implementation ¦ Type: Solar | 09-07-2026 |  |  | 09/07/2026 | Pending with Level 2 | 29-Feb-28 |  | 2028-02-29 | 2028-08-29
2200000992 | Main-Connectivity under GNA |  | RENEW SOLAR POWER PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Raghanesda | Gujarat | 2026-01-05 | 2028-02-29 | RSPPL shall share the DTL for Connectivity granted to Ms RSPPL for its 300MW REGS against appl. no. 2200000993. • RSPPL – Raghanesda PS 400kV Sc line (on Dc tower) along with 400kV line bay at generation end (Under the scope of RPSPL). • 1 no. 400kV line bay at Raghanesda PS (being implemented under ISTS as part of “Transmission System for evacuation of RE power from Raghanesda area of Gujarat – 3GW under phase-I”.). | 0 | 400 KV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Lt | Common Transmission System Augmentation for Connectivity under GNA A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • S | 29-Feb-28 | 29-Feb-28 |  |  | 100 | 453 |  |  |  |  | 2027-10-23 | 2027-10-23 |  | Not effective | 2028-02-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2028-02-29 ¦ Status: Under Implementation ¦ Type: Solar | 01-04-2026 |  |  | 08/07/2026 | Pending with Level 2 | 29-Feb-28 |  | 2028-02-29 | 2028-08-29
2200000993 | Main-Connectivity under GNA |  | RENEW SOLAR POWER PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Raghanesda | Gujarat | 2026-01-05 | 2027-10-23 | • RSPPL – Raghanesda PS 400kV Sc line (on Dc tower) alongwith 400kV line bay at generation end (Under the scope of RPSPL). • 1 no. 400kV line bay at Raghanesda PS (being implemented under ISTS as part of Raghanesda 3GW scheme). | 1 | 400 KV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Lt | Common Transmission System Augmentation for Connectivity under GNA A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • S | 30-Sep-27 | 30-Sep-27 |  |  | 300 | 453 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2027-10-23 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-10-23 ¦ Status: Under Implementation ¦ Type: Solar | 01-04-2026 |  |  | 01/04/2026 | Not Submitted For Approval | 30-Sep-27 |  | 2027-09-30 | 2028-04-23
2200000995 | Main-Connectivity under GNA |  | OYSTER GREEN HYBRID THREE PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 140(Solar 100 MWWind 40 MW) | 0 | 100 | 40 | 0 | 140 |  | Granted | 140 | 0 | 140 | Pachora (Sec-III) | Madhya Pradesh | 2026-01-06 | 2027-09-29 | • OGH3PL – Pachora PS 220kV Sc line (on Dc towers) along with associated bay at generation end (Under scope of Ms OGH3PL). • 1 no. 220kV line bay at Pachora PS is being implemented under ISTS as a part of Rajgarh Ph-III Scheme. | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III (Being implemented by Ms Rajgarh Neemuch Power Transmission Limited (a subsidiary of GR Infra)) (SCOD 29.09.2027) • Creation of New 220kV | Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III (Being implemented by Ms Rajgarh Neemuch Power Transmission Limited (a subsidiary of GR Infra)) (SCOD 29.09.2027) • Creation of New 220kV Bus Section (3rd) with 220kV Bus Sectionaliser. • Augmentation of transformation capacity by 400220kV, 3x500 MVA ICTs (7th, 8th & 9th ) at Pachora PS terminated on 220kV Bus Section (3rd). • Pachora PS – Rajgarh (PG) 400 kV Dc line (Quad ACSR AAAC AL59 Moose equivalent) along with associated bays at both ends Transmission System for Evacuation of Power from RE Projects in Rajgarh 1000MW SEZ in Madhya Pradesh Phase- II (Being implemented by Pachora Power Transmission Limited. (a subsidiary of GR Infra)) (SCOD 14.02.2026) • 400220kV, 3x500MVA ICT augmentation (4th, 5th and 6th) at Pachora PS. • Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) along with associated bays at both ends. | 30-Jun-26 | 30-Jun-26 |  |  | 140 |  |  |  |  | 2027-09-29 | 2027-09-29 | 2027-09-29 |  | Not effective | 2027-09-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-09-29 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 40.00 ¦ Date: 2027-09-29 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2028-03-29
2200000999 | Main-Connectivity under GNA |  | ORION HYBREN PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 300 MW (100 MW Wind, 200 MW Solar) |  | 200 | 100 | 0 | 300 |  | Granted | 300 | 0 | 300 | Tumkur-II | Karnataka | 2025-07-18 | 2027-05-31 | • Generation Station of M/s Orion Hybren Pvt. Ltd. – Tumkur-II PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Tumkur-II PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Tumkur-II REZ in Karnataka | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Tumkur-II REZ in Karnataka | 31-May-27 | 31-May-27 |  |  | 300 | 207 |  |  |  | 2026-09-02 | 2026-09-02 | 2026-11-30 |  | Not effective | 2027-05-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-05-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2027-05-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 31-May-27 |  | 2027-05-31 | 2027-11-30
2200001001 | Main-Connectivity under GNA |  | PULSE HYBREN PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bidar | Karnataka | 2025-06-04 | 2027-06-01 | • Generation Pooling S/s of M/s Pulse Hybren Pvt. Ltd. – Bidar PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Bidar PS for termination of above mentioned line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka as pe Annexure-II. • Augmentation of 3x500 MVA, 400/220 kV (6th- 8th) ICTs and 1x1500 MVA, 765/400kV ICT (4th) at Bidar PS. | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka as pe Annexure-II. • Augmentation of 3x500 MVA, 400/220 kV (6th- 8th) ICTs and 1x1500 MVA, 765/400kV ICT (4th) at Bidar PS. | 31-May-27 | 31-May-27 |  |  | 300 | 220 |  |  |  | 2027-05-31 | 2027-02-28 | 2027-06-30 |  | Not effective | 2027-06-01 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-05-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-May-27 |  | 2027-05-31 | 2027-12-01
2200001002 | Main-Connectivity under GNA |  | QUEST HYBREN PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bidar | Karnataka | 2025-06-04 | 2027-07-01 | •Generation Pooling S/s of M/s Quest Hybren Pvt. Ltd. – Bidar PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Bidar PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • Augmentation of 3x500 MVA, 400/220 kV (6th- 8th) ICTs and 1x1500 MVA, 765/400kV ICT (4th) at Bidar PS. | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • Augmentation of 3x500 MVA, 400/220 kV (6th- 8th) ICTs and 1x1500 MVA, 765/400kV ICT (4th) at Bidar PS. | 30-Jun-27 | 30-Jun-27 |  |  | 300 | 222 |  |  |  | 2027-06-30 | 2027-02-28 | 2027-06-30 |  | Not effective | 2027-07-01 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2028-01-01
2200001003 | Main-Connectivity under GNA |  | ACME Solar Holdings Limited | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 500 |  | 500 | 0 | 0 | 500 |  | Granted | 500 | 0 | 500 | Ananthapuram-II | Andhra Pradesh | 2026-01-12 | 2027-10-18 | • Generation Station of Ms Acme Solar Holdings Ltd. [erstwhile Ms Acme Solar Holdings Pvt. Ltd.] – Anantapur-II PS 400 kV Sc line on Dc tower along with line bay at generation PS – under the scope of applicant. • 1 no. 400 kV line bay at Anantapur-II PS for termination of above mentioned line – under the scope of ISTS | 1 | 400 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Anantapur-II REZs (Phase-1) •Transmission System for integration of Dava | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Anantapur-II REZs (Phase-1) •Transmission System for integration of Davanagere Chitradurga | 25-Jun-26 | 25-Jun-26 |  |  | 500 |  |  |  |  | 2027-10-17 | 2027-03-31 | 2027-09-30 |  | Not effective | 2027-10-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 500.00 ¦ Date: 2028-04-18 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 25-Jun-26 |  | 2026-06-25 | 2028-04-18
2200001008 | Main-Connectivity under GNA |  | GANEKO TWO ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 354 MW(Solar 255Wind 99) | 0 | 167 | 180 | 0 | 347 |  | Granted | 300 | 0 | 300 | Solapur Pool (Sec-I) | Maharashtra | 2024-12-09 | 2026-12-31 | • G2EPL – Solapur PS 220kV Sc line (on Dc tower) along with associated bay at the generation end (Under the scope of G2EPL). • 1 no. 220kV line bay on 220kV Bus Sec-I of Solapur PS (to be implemented under ISTS). | 1 | 220 KV | Aug without ATS |  |  | • Establishment of 4x500 MVA, 400220kV ICTs at Solapur PS • Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAAACAL59 moose equivalent). | • Establishment of 4x500 MVA, 400220kV ICTs at Solapur PS • Solapur PS – Solapur (PG) 400 kV Dc line (Quad ACSRAAACAL59 moose equivalent). | 30-Sep-27 | 30-Sep-27 |  |  | 300 | 208 |  |  |  | 2026-06-30 | 2026-03-20 | 2026-06-30 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 167.00 ¦ Date: 2027-03-20 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 180.00 ¦ Date: 2027-03-20 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Sep-27 |  | 2027-09-30 | 2028-03-30
2200001012 | Main-Connectivity under GNA |  | SAEL INDUSTRIES LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Tumkur-II | Karnataka | 2025-03-19 | 2026-09-30 | •Generation Station of M/s SAEL Industries Ltd. –Tumkur-II PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant •01 no. 220 kV line bay at Tumkur-II PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission Scheme for integration of Tumkur-II REZ in Karnataka, as per Annexure-II | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission Scheme for integration of Tumkur-II REZ in Karnataka, as per Annexure-II | 15-Nov-26 | 15-Nov-26 |  |  | 300 | 205 |  |  |  | 2026-09-02 | 2026-09-02 | 2026-11-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 15-Nov-26 |  | 2026-11-15 | 2026-11-30
2200001014 | Main-Connectivity under GNA |  | JSW NEO ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 | SJVN | Granted | 200 | 0 | 200 | Raghanesda | Gujarat | 2026-01-02 | 2027-10-23 | • JSWNEL – Raghanesda PS 400kV Sc line (on Dc tower) along 400kV line bay at generation end (Under the scope of JSWNEL). • 1 no. 400kV line bay on ISTS end is under implementation as part of Raghanesda PS (being implemented by Dineshchandra R. Agrawal Infracon Private Limited) | 1 | 400 KV | Aug without ATS |  |  | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc l | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV Dc line • LILO of Navsari (New) – Padghe (PG) | 31-Jul-26 | 31-Jul-26 |  |  | 200 | 454 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2027-10-23 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-10-23 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-10-23
2200001015 | Main-Connectivity under GNA |  | JSW NEO ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 | SJVN | Granted | 100 | 0 | 100 | Davangere | Karnataka | 2025-12-30 | 2027-09-25 | Generation Pooling Station of Ms JSW Neo Energy Ltd. – Davanagere Chitradurga PS 220 kV Sc line (through stringing of 2nd arm of Dc tower of dedicated connectivity transmission line agreed granted for application no. 2200000932) along with line bay at generation PS – under the scope of applicant. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission system for integration of Davanagere Chitradurga REZ, as per Annexure-II • Augmen | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission system for integration of Davanagere Chitradurga REZ, as per Annexure-II • Augmentation of 4x500 MVA, 400220 kV ICT (5th - 8th) at Davangere PS | 31-Jul-26 | 31-Jul-26 |  |  | 100 | [5 empty] | 2027-09-24 | 2027-09-30 |  | Not effective | 2027-09-25 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-09-20 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-09-30
2200001017 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Tumkur-II | Karnataka | 2025-03-19 | 2028-03-31 | •Generation Station of Ms Sunsure Solarpark Rj One Pvt. Ltd. –Tumkur-II PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant •01 no. 220 kV line bay at Tumkur-II PS for above DTL – under the scope of Applicant. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission Scheme for integration of Tumkur-II REZ in Karnataka, as per Annexure-II | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission Scheme for integration of Tumkur-II REZ in Karnataka, as per Annexure-II | 31-Mar-28 | 31-Mar-28 |  |  | 300 | 211 |  |  |  | 2026-09-02 | 2026-09-02 | 2026-11-30 |  | Not effective | 2028-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 150.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-28 |  | 2028-03-31 | 2028-09-30
2200001018 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 350 | 0 | 350 | 0 | 0 | 350 |  | Granted | 350 | 0 | 350 | Raghanesda | Gujarat | 2026-01-02 | 2028-03-31 | • SSRJ1PL – Raghanesda PS 220kV Sc line (on Dc Tower) along 220kV line bay at generation end (Under the scope of applicant). • 1 no. 220kV line bay at Raghanesda PS being implemented under ISTS as a part of “Transmission System for evacuation of RE power from Raghanesda area of Gujarat - 3GW under Phase-I” (by Dineshchandra R. Agrawal Infracon Private Limited) | 1 | 220 KV | Aug without ATS |  |  | Under Implementation (under ISTS) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) Banaskantha – Ahmedabad 765kV Dc | Under Implementation (under ISTS) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) Banaskantha – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) Lakadia PS – Ahmedabad 765kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) Establishment of 3x1500MVA 765400 kV Ahmedabad Ss Ahmedabad – Navsari (New) 765 kV Dc line Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) Establishment of 765 kV Halvad switching station LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) 765 kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. Vadodara – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs South Olpad (GIS) – Boisar-II 765 | 31-Mar-27 | 31-Mar-27 |  |  | 350 | 221 |  |  |  | 2028-03-31 | 2027-10-23 | 2027-10-23 |  | Not effective | 2028-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 350.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-09-30
2200001019 | Main-Connectivity under GNA |  | JSW NEO ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 | SECI | Granted | 100 | 0 | 100 | Davangere | Karnataka | 2025-12-30 | 2027-09-25 | Through dedicated connectivity transmission system granted for Ms JSW Neo Energy Ltd. for app. no. 2200001015 i.e. Generation Pooling Station of Ms JSW Neo Energy Ltd. – Davanagere Chitradurga PS 220 kV Sc line (through stringing of 2nd arm of Dc tower of dedicated connectivity transmission line agreed granted for application no. 2200000932) – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission system for integration of Davanagere Chitradurga REZ, as per Annexure-II • Augmen | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission system for integration of Davanagere Chitradurga REZ, as per Annexure-II • Augmentation of 4x500 MVA, 400220 kV ICT (5th - 8th) at Davangere PS | 31-Jul-26 | 31-Jul-26 |  |  | 100 | to be finalized |  |  |  |  | 2027-09-24 | 2027-09-30 |  | Not effective | 2027-09-25 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-09-25 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-09-30
2200001020 | Main-Connectivity under GNA |  | JSW NEO ENERGY LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 | SECI | Granted | 200 | 0 | 200 | Raghanesda | Gujarat | 2026-01-02 | 2027-10-23 | JSWNEL shall share the DTL for Connectivity granted to Ms JSWNEL for its 200MW SPP against application No. 2200001014 as given below • JSWNEL – Raghanesda PS 400kV Sc line (on Dc tower) along 400kV line bay at generation end (Under the scope of JSWNEL). • 1 no. 400kV line bay on ISTS end is under implementation as part of Raghanesda PS (being implemented by Dineshchandra R. Agrawal Infracon Private Limited) | 0 | 400 KV | Aug without ATS |  |  | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc l | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV Dc line • LILO of Navsari (New) – Padghe (PG) 7 | 31-Jul-26 | 31-Jul-26 |  |  | 200 | 454 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2027-10-23 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-10-23 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-10-23
2200001028 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 20 PRIVATE LIMITED | WR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | 84.75 MW(Wind - 66 MW, Solar - 18.75 MW) | 0 | 4.33 | 15.23 | 1.85 | 21.41 | NHPC | Granted | 15 | 0 | 15 | Solapur Pool (Sec-I) | Maharashtra | 2025-07-01 | 2026-06-30 | Ms SPI20PL shall share the DTL of Ms Solarcraft Power India 7 Pvt. Ltd. (SPI7PL) for its 50MW WPP against application no. 2200000213 as given below • SPI7PL – Solapur PS 220kV Sc line on Dc Tower along with associated bay at generation station (Under the scope of Ms SPI7PL). • 1 no. 220kV line bay at Solapur PS shall be implemented under ISTS. | 0 | 220 KV | Aug without ATS |  |  | Under Implementation (under ISTS) Transmission System for Evacuation of Power from RE Projects in Solapur (1500MW) SEZ in Maharashtra (Solapur Transmission Ltd. – TPL) (SCOD20-Mar-2026) Establishment of 400220kV, 4x500MVA ICTs at Solapu | Under Implementation (under ISTS) Transmission System for Evacuation of Power from RE Projects in Solapur (1500MW) SEZ in Maharashtra (Solapur Transmission Ltd. – TPL) (SCOD20-Mar-2026) Establishment of 400220kV, 4x500MVA ICTs at Solapur PS along with 2x125MVAR, 420kV Bus Reactors. Solapur PS – Solapur (PG) 400kV Dc line (Quad ACSRAAACAL59 moose equivalent) 2 nos. of 400kV line bays at Solapur (PG) Ss for termination of Solapur PS- Solapur (PG) 400kV Dc line | 30-Jun-26 | 30-Jun-26 |  |  | 15 | 202 | 2026-12-17 |  | As per PPA signed between SPI20PL & NHPC, the SCOD of generation project is 17.12.2026 | 2026-06-30 | 2026-03-20 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 15.00 ¦ Date: 2026-12-18 ¦ Status: Under Implementation ¦ Type: | 08-07-2026 | Yes |  | 09/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2026-12-17
2200001035 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 80 | 0 | 0 | 80 | 0 | 80 | SECI | Granted | 80 | 0 | 80 | Dhule (Sec-I) | Maharashtra | 2024-12-09 | 2026-12-31 | Ms AEPL shall share the DTL granted to Ms AEPL for its 50MW WPP against application no. 2200000081, as given below AEPL – Dhule PS (Sec-I) 220kV Sc line along with associated bay at AEPL end (Under scope of Ms AEPL). 1 no. 220kV bay at Dhule PS (Sec-I) is under implementation as a part of pooling station. | 0 | 220 KV | Aug without ATS |  |  | • Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAAC AL59 Moose equivalent (60 km) | • Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAAC AL59 Moose equivalent (60 km) | 31-Dec-26 | 31-Dec-26 |  |  | 80 |  |  |  |  | 2026-10-30 | 2026-02-09 | 2026-10-30 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 80.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2026-12-31
2200001036 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 160 | 0 | 0 | 160 | 0 | 160 | SJVN | Granted | 160 | 0 | 160 | Dhule (Sec-I) | Maharashtra | 2024-12-09 | 2026-12-31 | Ms AEPL shall share the DTL granted to Ms AEPL for its 50MW WPP against application no. 2200000081, as given below • AEPL – Dhule PS (Sec-I) 220kV Sc line along with associated bay at AEPL end (Under scope of Ms AEPL). • 1 no. 220kV bay at Dhule PS (Sec-I) is under implementation as a part of pooling station. | 0 | 220 KV | Aug without ATS |  |  | • Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAAC AL59 Moose equivalent (60 km) | • Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAAC AL59 Moose equivalent (60 km) | 31-Dec-26 | 31-Dec-26 |  |  | 160 | 203 |  |  |  | 2026-10-30 | 2026-02-02 | 2026-10-30 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 160.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2026-12-31
2200001037 | Main-Connectivity under GNA |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED | WR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | Solar- 135 MW Wind - 160 MW BESS - 40 | 0 | 135 | 160 | 40 | 335 |  | Granted | 200 | 0 | 200 | Mandsaur (Sec-I) | Madhya Pradesh | 2026-01-02 | 2028-06-30 | • HCSPL – Mandsaur PS 220kV Sc line along with associated bay at the generation end (Under the scope of Ms HCSPL). • 1 no. 220kV line bay (on 220kV Bus Sec-I) at Mandsaur PS shall be implemented under ISTS (as per request of applicant). | 1 | 220 KV | Aug without ATS |  |  | Under Implementation 1) Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & | Under Implementation 1) Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line 2) Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line 3) Rajasthan REZ Ph-V (Part-1 4 GW) [SirohiNagaur] Complex (SCOD 24.03.2027) (Rajasthan V Power Transmission Limited – POWERGRID) • Mandsaur PS – Khandwa (New) 765 kV Dc line. | 30-Jun-28 | 30-Jun-28 |  |  | 200 |  |  |  |  | 2028-06-30 | 2027-03-24 | 2027-06-30 |  | Not effective | 2028-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 135.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 160.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 40.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Standalone | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-28 |  | 2028-06-30 | 2028-06-30
2200001043 | Main-Connectivity under GNA |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED | SR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Wind | 200 MW (Wind-200, BESS - 40) | 0 | 0 | 200 | 50 | 250 |  | Granted | 200 | 0 | 200 | Ananthapuram-II | Andhra Pradesh | 2026-01-12 | 2028-06-30 | •Generation Station of Ms Hexa Climate Solutions Pvt. Ltd – Anantapur-II PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant •1 no. 220 kV line bay at Anantapur-II PS for termination of above mentioned line – under the scope of applicant | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission System for Integration of Anantapur-II REZs (Phase-1) as per Annexure-II •Transmiss | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission System for Integration of Anantapur-II REZs (Phase-1) as per Annexure-II •Transmission System for integration of Davanagere Chitradurga as per Annexure-III | 30-Jun-28 | 30-Jun-28 |  |  | 200 | 207 |  |  |  |  | 2027-03-31 | 2027-09-30 |  | Not effective | 2028-06-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Standalone | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-28 |  | 2028-06-30 | 2028-12-30
2200001047 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 16 PRIVATE LIMITED | WR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | 247.4 MW(Wind - 191.4 MW, Solar - 56 MW) |  | 10.59 | 36.21 | 17.22 | 64.02 | SJVN | Granted | 35 | 0 | 35 | Solapur Pool (Sec-I) | Maharashtra | 2025-07-01 | 2026-04-01 | Ms SPI16PL shall share the DTL of Ms Solarcraft Power India 7 Pvt. Ltd. (SPI7PL) for its 50MW WPP against application no. 2200000213 as given below • SPI7PL – Solapur PS 220kV Sc line on Dc Towera along with associated bay at generation station (Under the scope of Ms SPI7PL). • 1 no. 220kV line bay at Solapur PS shall be implemented under ISTS. | 0 | 220 KV | Aug without ATS |  |  | Under Implementation (under ISTS) Transmission System for Evacuation of Power from RE Projects in Solapur (1500MW) SEZ in Maharashtra (Solapur Transmission Ltd. – TPL) (SCOD20-Mar-2026) Establishment of 400220kV, 4x500MVA ICTs at Solapu | Under Implementation (under ISTS) Transmission System for Evacuation of Power from RE Projects in Solapur (1500MW) SEZ in Maharashtra (Solapur Transmission Ltd. – TPL) (SCOD20-Mar-2026) Establishment of 400220kV, 4x500MVA ICTs at Solapur PS along with 2x125MVAR, 420kV Bus Reactors. Solapur PS – Solapur (PG) 400kV Dc line (Quad ACSRAAACAL59 moose equivalent) 2 nos. of 400kV line bays at Solapur (PG) Ss for termination of Solapur PS- Solapur (PG) 400kV Dc line | 1-Apr-26 | 1-Apr-26 |  |  | 35 | 202 | 2026-07-30 |  | PPA was signed between SPI16Pl & SJVN dated 13.05.2024, so SCOD of the project is 24 months from effective date i.e. 13.05.2026. SJVN vide letter dtd. 20.01.2026 provided further extension till 30.07.2026. | 2026-08-30 | 2026-03-20 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 56.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 191.40 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 91.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Standalone | 08-07-2026 | Yes |  | 21/07/2026 | Pending with Level 2 | 1-Apr-26 |  | 2026-04-01 | 2026-10-30
2200001048 | Main-Connectivity under GNA |  | RENEW SOLAR POWER PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 | 0 | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Raghanesda | Gujarat | 2026-01-05 | 2028-01-31 | RSPPL shall share the DTL for Connectivity granted to Ms RSPPL for its 300MW REGS against appl. no. 2200000993. • RSPPL – Raghanesda PS 400kV Sc line (on Dc tower) along with 400kV line bay at generation end (Under the scope of RPSPL). • 1 no. 400kV line bay at Raghanesda PS (being implemented under ISTS as part of “Transmission System for evacuation of RE power from Raghanesda area of Gujarat – 3GW under phase-I”.). | 0 | 400 kV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA A. Under Implementation (under ISTS): 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD: 21/03/2025): • Banaskantha – Ahmedabad 765kV D/c line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD: 21/03/2025): • Lakadia PS – Ahmedabad 765kV D/c line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD: 21/03/2025): • Establishment of 3x1500MVA 765/400 kV Ahmedabad S/s • Ahmedabad – Navsari (New) 765 kV D/c line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD: 21/03/2025): • LILO of Pirana (PG) – Pirana (T) 400kV D/c line at Ahmedabad S/s along with reconductoring of Pirana (PG) – Pirana (T) 400kV D/c line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD: 26/12/2025): • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV D/c at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD: 26/12/2025): • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV D/c line • LILO of Lakadia – Vadodara 765 kV D/c line at Vataman • Vataman switching station – Navsari (New) 765 kV D/c line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD: 15/10/2026): • Establishment of 765/400/220kV South Olpad (GIS) S/s with 2x1500MVA 765/400kV ICTs. • Vadodara – South Olpad (GIS) 765kV D/c line • LILO of Gandhar – Hazira 400 kV D/c line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV D/c line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD: 15/10/2026): • Establishment of 765/400/220kV Boisar-II (GIS) S/s with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV D/c line • LILO of Navsari (New) – Padghe (PG) 765kV D/c line at Boisar-II • Boisar-II (Sec-II) – Velgaon (MH) 400 kV D/c • LILO of Babhaleswar – Padghe (M) 400 kV D/c line at Boisar-II (Sec-I) 9. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-D (part system) (Pune Transmission Ltd. – AESL) (SCOD: 19/11/2026): • Establishment of 765/400/220kV Pune-III (GIS) S/s with 2x1500 MVA ICTs & 3x500MVA ICTs • Boisar-II – Pune-III 765kV D/c line • LILO of Narendra (New) – Pune (GIS) 765kV D/c line at Pune-III • LILO of Hinjewadi – Koyna 400kV S/c line at Pune III (GIS) S/s 10. Transmission System for evacuation of RE power from Raghanesda area of Gujarat - 3GW under Phase-I (Part System) (Dineshchandra R. Agrawal Infracon Private Limited) (SCOD: 23-Oct-27): • Establishment of 4x1500 MVA, 765/400 kV Substation near Raghanesda (GIS) with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor • Raghanesda (GIS) – Banaskantha (PG) 765 kV D/c line • 2 Nos. 765 kV line bays at Banaskantha (PG) S/s | Common Transmission System Augmentation for Connectivity under GNA A. Under Implementation (under ISTS): 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD: 21/03/2025): • Banaskantha – Ahmedabad 765kV D/c line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD: 21/03/2025): • Lakadia PS – Ahmedabad 765kV D/c line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD: 21/03/2025): • Establishment of 3x1500MVA 765/400 kV Ahmedabad S/s • Ahmedabad – Navsari (New) 765 kV D/c line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD: 21/03/2025): • LILO of Pirana (PG) – Pirana (T) 400kV D/c line at Ahmedabad S/s along with reconductoring of Pirana (PG) – Pirana (T) 400kV D/c line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD: 26/12/2025): • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV D/c at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD: 26/12/2025): • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV D/c line • LILO of Lakadia – Vadodara 765 kV D/c line at Vataman • Vataman switching station – Navsari (New) 765 kV D/c line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD: 15/10/2026): • Establishment of 765/400/220kV South Olpad (GIS) S/s with 2x1500MVA 765/400kV ICTs. • Vadodara – South Olpad (GIS) 765kV D/c line • LILO of Gandhar – Hazira 400 kV D/c line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV D/c line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD: 15/10/2026): • Establishment of 765/400/220kV Boisar-II (GIS) S/s with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV D/c line • LILO of Navsari (New) – Padghe (PG) 765kV D/c line at Boisar-II • Boisar-II (Sec-II) – Velgaon (MH) 400 kV D/c • LILO of Babhaleswar – Padghe (M) 400 kV D/c line at Boisar-II (Sec-I) 9. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-D (part system) (Pune Transmission Ltd. – AESL) (SCOD: 19/11/2026): • Establishment of 765/400/220kV Pune-III (GIS) S/s with 2x1500 MVA ICTs & 3x500MVA ICTs • Boisar-II – Pune-III 765kV D/c line • LILO of Narendra (New) – Pune (GIS) 765kV D/c line at Pune-III • LILO of Hinjewadi – Koyna 400kV S/c line at Pune III (GIS) S/s 10. Transmission System for evacuation of RE power from Raghanesda area of Gujarat - 3GW under Phase-I (Part System) (Dineshchandra R. Agrawal Infracon Private Limited) (SCOD: 23-Oct-27): • Establishment of 4x1500 MVA, 765/400 kV Substation near Raghanesda (GIS) with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420 kV bus reactor • Raghanesda (GIS) – Banaskantha (PG) 765 kV D/c line • 2 Nos. 765 kV line bays at Banaskantha (PG) S/s | 31-Jan-28 | 31-Jan-28 |  |  | 200 | 453 |  |  |  |  | 2027-10-23 | 2027-10-23 |  | Not effective | 2028-01-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-01-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Jan-28 |  | 2028-01-31 | 2028-07-31
2200001061 | Main-Connectivity under GNA |  | JAGALURU SOLAR POWER PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Tumkur-II | Karnataka | 2025-03-19 | 2027-03-31 | •Generation Station of M/s Jagaluru Solar Power Pvt. Ltd. –Tumkur-II PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant •01 no. 220 kV line bay at Tumkur-II PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission Scheme for integration of Tumkur-II REZ in Karnataka, as per Annexure-II | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I •Transmission Scheme for integration of Tumkur-II REZ in Karnataka, as per Annexure-II | 31-Dec-27 | 31-Dec-27 |  |  | 300 | 209 |  |  |  | 2026-09-02 | 2026-09-02 | 2026-11-30 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08.07.2026 |  |  |  | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2028-06-30
2200001064 | Main-Connectivity under GNA |  | ACME SOLAR HOLDINGS LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 400 |  | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Raghanesda | Gujarat | 2026-01-05 | 2027-10-23 | • ASHL – Raghanesda PS 400kV Sc line (on Dc towers) along with associated 400kV line bay at generation end (Under the scope of ASHL). • 1 no. 400kV line bay at Raghanesda PS being implemented under ISTS as a part of “Transmission System for evacuation of RE power from Raghanesda area of Gujarat - 3GW under Phase-I ” (by Dineshchandra R. Agrawal Infracon Private Limited). • 1 no. 400kV line bay at Raghanesda PS (being implemented under ISTS as part of “Transmission System for evacuation of RE power from Raghanesda area of Gujarat – 3GW under phase-I”.). | 1 |  | Aug without ATS |  |  | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21.03.2025) • Banaskantha – Ahmedabad 765kV Dc | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21.03.2025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21.03.2025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21.03.2025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21.03.2025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26.12.2025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26.12.2025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15.10.2026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15.10.2026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV Dc line • LILO of Navsari (New) | 31-Dec-26 | 31-Dec-26 |  |  | 400 | 456 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2027-10-23 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2028-04-20 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2028-04-23
2200001065 | Main-Connectivity under GNA |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 |  | 150 | 0 | 0 | 150 |  | Granted | 150 | 0 | 150 | Fatehgarh-II | Rajasthan | 2025-05-05 | 2027-03-24 |  | 0 | 400 KV | Aug without ATS |  |  |  |  | 31-Oct-26 | 31-Oct-26 |  |  | 150 | 438(Main),437(Tie) |  |  |  |  | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Oct-26 |  | 2026-10-31 | 2027-09-24
2200001070 | Main-Connectivity under GNA |  | CONTINUUM POWER TRADING (TN) PRIVATE LIMITED | WR | Land BG Route | (xi) REGS with an installed capacity of 5 MW and above applying for grant of Connectivity to ISTS through the electrical system of a generating station already having Connectivity to ISTS | Wind | 36 |  | 0 | 36 | 0 | 36 |  | Granted | 36 | 0 | 36 | Bhuj | Gujarat | 2025-08-14 | 2026-11-19 | CPTPL shall share the DTL granted to Ms NVWEPL vide application no. 2200000331 [for transfer of 50MW connectivity from Ms Inox Green Energy Services Ltd. (IGESL) for its WPP against application no. 1200000559 (LTA) to Ms Nani Virani Wind Energy Pvt. Ltd. (NVWEPL) vide CTU letter dated 08.02.2024] NVWEPL – Bhuj PS 220kV Dc line (high-capacity conductor enabling at least 711MW power transfer at nominal voltage) along with associated line bays at both ends. | 0 | 220 kV | Aug without ATS |  |  | Under Implementation (SCOD progressively by 19.11.2026) • Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (10th) with associated ICT bays • Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th) | Under Implementation (SCOD progressively by 19.11.2026) • Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (10th) with associated ICT bays • Augmentation of Transformation capacity at Bhuj PS by 1x500MVA, 400220kV ICT (9th) Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone • Banaskantha – Ahmedabad 765kV Dc line Khavda Phase-II (Parts B to D) • Lakadia PS – Ahmedabad 765kV Dc line • Establishment of 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line Khavda Phase-III • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc | 31-Mar-25 | 31-Mar-25 |  |  | 36 | 205 & 208 |  |  |  |  | 2026-11-19 | 2027-10-31 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 36.00 ¦ Date: 2026-11-19 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2027-10-31
2200001072 | Main-Connectivity under GNA |  | HERO SOLAR ENERGY PRIVATE LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Solar | 250 |  | 250 | 0 | 125 | 375 | SECI | Granted | 250 | 0 | 250 | Bidar | Karnataka | 2025-06-04 | 2027-02-19 | • Generation Station of M/s Hero Solar Energy Pvt. Ltd – Bidar PS 220 kV S/c line on D/c tower# along with line bay at generation PS – under the scope of applicant. • 01 no. 220 kV line bay at Bidar PS for above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • Augmentation of 3x500 MVA, 400/220 kV (6th- 8th) ICTs and 1x1500 MVA, 765/400kV ICT (4th) at Bidar PS. | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for Solar Energy Zone in Bidar (2500 MW), Karnataka • Augmentation of 3x500 MVA, 400/220 kV (6th- 8th) ICTs and 1x1500 MVA, 765/400kV ICT (4th) at Bidar PS. | 31-Oct-26 | 31-Oct-26 |  |  | 250 | 206 | 2026-12-29 |  | Hero Solar representative informed that vide SECI letter, revised SCD is 60 days subsequent to the readiness of delivery point and power evacuation infrastructure and/or start date of connectivity. | 2027-06-30 | 2027-02-28 | 2027-06-30 |  | Not effective | 2027-02-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 31-Oct-26 |  | 2026-10-31 | 2027-06-30
2200001074 | Main-Connectivity under GNA |  | JSW NEO ENERGY LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Solar | 500 |  | 500 | 0 | 0 | 500 | SECI | Granted | 500 | 0 | 500 | Ananthapuram-II | Andhra Pradesh | 2026-01-12 | 2027-10-18 | • Generation Station of Ms JSW Neo Energy Ltd.– Anantapur-II PS 400 kV Sc line along with line bay at generation PS – under the scope of applicant. • 1 no. 400 kV line bay at Anantapur-II PS for termination of above mentioned line – under the scope of ISTS | 1 | 400 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission System for Integration of Anan | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) | 31-Aug-26 | 31-Aug-26 |  |  | 500 | [5 empty] | 2027-03-31 | 2027-09-30 |  | Not effective | 2027-10-18 |  |  | 0 | ¦ Phase 1 ¦ MW: 500.00 ¦ Date: 2027-10-15 ¦ Status: Under Implementation ¦ Type: Solar | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Aug-26 |  | 2026-08-31 | 2027-10-18
2200001075 | Main-Connectivity under GNA |  | EG ARKA SOLAR PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Tumkur-II | Karnataka | 2026-06-12 | 2029-05-30 | •Generation Pooling Station of Ms EG Arka Solar Pvt. Ltd. – Tumkur-II PS 220 kV Sc line on Dc tower* along with line bay at generation pooling station – under the scope of applicant. •1 no. 220 kV terminal line bay at Tumkur-II PS for termination of above dedicated connectivity line – under the scope of applicant. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line •Transmission scheme for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line •Transmission scheme for integration of Tumkur-II REZ in Karnataka •Transmission system strengthening at Tumkur-II for integration of additional RE potential (2.7 GW) | 31-Dec-26 | 31-Dec-26 |  |  | 100 | [5 empty] | 2027-10-17 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2029-11-30
2200001077 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 432 (Wind-232 MW, Solar-200 MW) |  | 200 | 232 | 0 | 432 |  | Granted | 300 | 0 | 300 | Ananthapuram-II | Andhra Pradesh | 2026-01-12 | 2027-10-18 | • Generation Station of Ms Serentica Renewables India Pvt Ltd – Anantapur-II PS 220 kV Sc line on Dc tower along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Anantapur-II PS for termination of above mentioned line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission System for Integration of Anan | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) | 31-Dec-26 | 31-Dec-26 |  |  | 300 |  | 2027-10-17 |  |  |  | 2027-03-31 | 2027-10-17 |  | Not effective | 2027-10-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 232.00 ¦ Date: 2027-10-18 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2027-10-18 ¦ Status: Under Implementation ¦ Type: Solar | 08.07.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2028-04-18
2200001082 | Main-Connectivity under GNA |  | ACME SOLAR HOLDINGS LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Solar | 350 |  | 350 | 0 | 175 | 525 | SECI | Granted | 350 | 0 | 350 | Pavagada | Karnataka | 2025-06-12 | 2027-01-01 | • Generating Pooling Station of M/s Acme Solar Holdings Ltd.– Tumkur (Pavagada) PS 220 kV S/c line on D/c tower# along with line bays at generation pooling station – under the scope of applicant. • 1 no. of 220 kV line bay at Tumkur (Pavagada) PS - under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 2x500 MVA, 400/ 220 kV (9th & 10th) ICTs at Tumkur (Pavagada) PS | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 2x500 MVA, 400/ 220 kV (9th & 10th) ICTs at Tumkur (Pavagada) PS | 31-Dec-26 | 31-Dec-26 |  |  | 350 | 232 | 2027-06-30 |  | Acme representative informed that vide SECI letter, for 150MW PPA revised Scheduled commencement of Power supply date is 60 days subsequent to the Actual start /operationalization date and PPA for 200MW is signed, SCSD is 30.06.2027 |  | 2026-05-20 | 2026-12-31 |  | Not effective | 2027-01-01 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2027-03-01 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 75.00 ¦ Date: 2027-03-01 ¦ Status: Under Implementation ¦ Type: Standalone ¦ Phase 4 ¦ MW: 100.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Standalone | 30.06.2026 | Yes |  | 21/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2027-06-30
2200001083 | Main-Connectivity under GNA |  | ADANI WIND ENERGY KUTCHH THREE LIMITED | WR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Navinal | Gujarat | 2026-01-05 | 2027-08-04 | • AWEK3L – Navinal (Mundra) S/s (GIS) 220kV S/c line (on D/c or M/c towers) along with associated bay at generation end (Under the scope of applicant). • 220kV bay at ISTS S/s end is being implemented under ISTS by Navinal Transmission Ltd. (A subsidiary of Adani Energy Solutions Limited). | 1 | 220 kV | Aug with ATS | Transmission System for providing connectivity to RE applicant(s) at Navinal (Mundra)(GIS): • Creation of 220 kV switchyard (Bus Sec-I) at Navinal (Mundra) S/s (GIS) along with installation of 1x500MVA, 400/220 kV ICT at Navinal (Mundra) S/s (GIS). | 2027-08-04 | Network Expansion Scheme in Navinal (Mundra) area of Gujarat for drawal of power in the area 1. Establishment of 4x1500MVA, 765/400 kV Navinal (Mundra) S/s (GIS). 2. LILO of Bhuj-II – Lakadia 765 kV D/c line at Navinal (Mundra) (GIS) S/s. Under Implementation by M/s Navinal Transmission Limited (NTL) (A subsidiary of Adani Energy Solutions Limited). | Network Expansion Scheme in Navinal (Mundra) area of Gujarat for drawal of power in the area 1. Establishment of 4x1500MVA, 765/400 kV Navinal (Mundra) S/s (GIS). 2. LILO of Bhuj-II – Lakadia 765 kV D/c line at Navinal (Mundra) (GIS) S/s. Under Implementation by M/s Navinal Transmission Limited (NTL) (A subsidiary of Adani Energy Solutions Limited). | 30-May-25 | 30-May-25 |  |  | 300 |  |  |  |  | 2027-08-04 | 2027-08-04 | 2027-08-04 |  | Not effective | 2027-08-04 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-08-04 ¦ Status: Under Implementation ¦ Type: Wind | 01-04-2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-May-25 |  | 2025-05-30 | 2028-02-04
2200001090 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 150 |  | 0 | 150 | 0 | 150 |  | Granted | 150 | 0 | 150 | kallam | Maharashtra | 2025-04-07 | 2025-10-05 | SRIPL – Kallam PS 220kV line along with associated bays at generation end as detailed below 220kV Sc line on (Dc towers#) from SRIPL PSS of 150MW REGS to Common point of 220 kV line from Ms Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) PSS (of 350MW REGS) to Kallam PS (under the scope of SRIPL). 220 kV Sc line from common point to Kallam PS shall be strung on the Dc & Mc towers being implemented by Ms Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) for its earlier 350 MW REGS with application nos. 231400004 (210MW), 331400007 (140MW). 1 no. 220kV Bay No. 210 at Kallam PS end implemented under ISTS. | 1 | 220 KV | Aug without ATS |  |  | • LILO of both circuits of Parli(M) – Karjat(M) Lonikand-II(M) 400kV Dc line (twin moose) at Kallam PS. | • LILO of both circuits of Parli(M) – Karjat(M) Lonikand-II(M) 400kV Dc line (twin moose) at Kallam PS. | 31-May-25 | 31-May-25 |  |  | 150 | 210 |  |  |  | 2025-01-04 | 2025-10-05 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 60.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 90.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2026-10-30
2200001098 | Main-Connectivity under GNA |  | LAMBENT ENERGY (EIGHT) PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 354 (Solar-255 MW, Wind-99 MW) |  | 255 | 99 | 0 | 354 |  | Granted | 300 | 0 | 300 | Bidar | Karnataka | 2026-07-06 |  | •Generation Station of Ms Lambent Energy (Eight) Pvt. Ltd – Bidar PS 220 kV Sc line on Dc tower# along with line bay at generation PS – under the scope of applicant •01 no. 220 kV line bay at Bidar PS for termination of above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for Solar Energy Zone in Bidar (2500 MW) in Karnataka •Augmentation of 3x500 MVA, 400220 kV ( | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for Solar Energy Zone in Bidar (2500 MW) in Karnataka •Augmentation of 3x500 MVA, 400220 kV (6th - 8th) ICTs and 1x1500 MVA, 765400kV ICT (4th) at Bidar PS | 31-Dec-27 | 31-Dec-27 |  |  | 300 | N | [7 empty] | Not effective | 2027-02-19 |  | Not commissioned | 0 | [5 empty] | Not Submitted For Approval | 31-Dec-27 |  | 2027-12-31 | 2028-06-30
2200001099 | Main-Connectivity under GNA |  | PRATAPATI ENERGY (SEVEN) PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 354 (Solar-255 MW, Wind-99MW) |  | 255 | 99 | 0 | 354 |  | Granted | 300 | 0 | 300 | Kurnool-IV | Andhra Pradesh | 2026-03-02 | 2027-12-31 | • Generation Station of Ms Pratapati Energy (Seven) Pvt. Ltd –Kurnool-IV PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant • 01 no. 220 kV line bay at Kurnool-IV PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV REZ- Phase-I | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV REZ- Phase-I | 31-Dec-27 | 31-Dec-27 |  |  | 300 | 240 | [5 empty] | 2027-09-30 |  | Not effective | 2027-12-31 | Under Construction |  | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2028-06-30
2200001102 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 345 |  | 0 | 345 | 0 | 345 | REMCL | Granted | 345 | 0 | 345 | Bellary | Karnataka | 2025-06-19 | 2027-09-22 | • Generation Station of M/s NTPC Renewable Energy Ltd. – Bellary PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant. • 01 no. 220 kV line bay at Bellary PS for above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka. • Transmission system for integration of Davanagere/ Chitradurga REZ• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka. • Transmission system for integration of Davanagere/ Chitradurga REZ• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | 14-Aug-26 | 14-Aug-26 |  |  | 345 |  |  |  |  | 2027-09-21 | 2027-09-21 | 2027-09-30 |  | Not effective | 2027-09-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 345.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 14-Aug-26 |  | 2026-08-14 | 2027-09-30
2200001103 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 55 |  | 0 | 55 | 0 | 55 | REMCL | Granted | 55 | 0 | 55 | Bellary | Karnataka | 2025-06-19 | 2027-09-22 | • Through dedicated Connectivity transmission system grant of Connectivity to M/s NTPC Renewable Energy Ltd. (application no. 2200000825 [i.e. Generation Station of M/s NTPC Renewable Energy Ltd. – Bellary PS 220 kV S/c line along with line bay at generation PS – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | 14-Aug-26 | 14-Aug-26 |  |  | 55 |  |  |  |  | 2027-09-21 | 2027-09-21 | 2027-09-30 |  | Not effective | 2027-09-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 55.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 14-Aug-26 |  | 2026-08-14 | 2027-09-30
2200001107 | Main-Connectivity under GNA |  | AZURE POWER SIXTY THREE PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Raghanesda | Gujarat | 2026-01-05 | 2027-10-23 | • AP63PL – Raghanesda PS 220kV Sc line along with associated 220kV line bay at generation end (Under the scope of entity). • 1 no. 220kV line bay at Raghanesda PS being implemented under ISTS as a part of “Transmission System for evacuation of RE power from Raghanesda area of Gujarat - 3GW under Phase-I ” (by Dineshchandra R. Agrawal Infracon Private Limited) | 1 | 220 KV | Aug without ATS |  |  | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21.03.2025) • Banaskantha – Ahmedabad 765kV Dc | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21.03.2025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21.03.2025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21.03.2025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21.03.2025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26.12.2025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26.12.2025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15.10.2026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15.10.2026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV Dc line • LILO of Navsari (New) | 30-Sep-27 | 30-Sep-27 |  |  | 300 | 223 |  |  |  | 2027-09-30 | 2027-10-23 | 2027-10-23 |  | Not effective | 2027-10-23 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-10-23 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Sep-27 |  | 2027-09-30 | 2028-04-23
2200001112 | Main-Connectivity under GNA |  | DIYOS FOUR RENEWABLES PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Tumkur-II | Karnataka | 2026-06-12 | 2029-05-30 | • Generation Pooling Station of Ms Diyos Four Renewables Pvt. Ltd. –Tumkur-II PS 220 kV Sc line on Dc tower* along with line bay at generation pooling station – under the scope of applicant. • 1 no. 220 kV terminal line bay at Tumkur-II PS for termination of above dedicated connectivity line –under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for integration of Tumkur-II REZ in Karnataka •Transmission system strengthening at Tumkur-II for integration of additional RE potential (2.7 GW) | 30-Sep-27 | 30-Sep-27 |  |  | 300 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Solar | 08.07.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Sep-27 |  | 2027-09-30 | 2029-11-30
2200001113 | Main-Connectivity under GNA |  | GENTARI RENEWABLES INDIA UTILITIES 2 PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 400 |  | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Bellary | Karnataka | 2025-06-19 | 2027-09-22 | • Generation Pooling Station of M/s Gentari Renewables India Utilities 2 Pvt. Ltd. – Bellary PS 220 kV S/c line on D/c towers [through stringing of both arms of 220 kV D/c towers and bunching both arms circuit at both end for termination of line in single bay] along with 220 kV line bay at generation Pooling Station end – under the scope of applicant • 1 no. 220 kV line bay at Bellary PS for termination of DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | 31-Dec-26 | 31-Dec-26 |  |  | 400 |  |  |  | Gentari renewables representative informed that PPA not signed yet |  | 2027-09-21 | 2027-09-30 |  | Not effective | 2027-09-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: | 22.12.2025 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2028-03-22
2200001114 | Main-Connectivity under GNA |  | GENTARI RENEWABLES INDIA UTILITIES 2 PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 132 |  | 0 | 132 | 0 | 132 |  | Granted | 132 | 0 | 132 | Bellary | Karnataka | 2025-06-19 | 2027-09-22 | • Through sharing of dedicated connectivity transmission system of M/s NTPC Renewable Energy Ltd. [granted for app. no. 2200000825 for 76 MW] i.e. Generation Station of M/s NTPC Renewable Energy Ltd. – Bellary PS 220 kV S/c line – all arrangement under the scope of applicant. •Note: M/s NTPC Renewable Energy Ltd. (app no. 2200000825) has already been sharing dedicated transmission system with M/s NTPC Renewable Energy Ltd. (app. no. 2200001103 for 55 MW). | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | 31-Dec-26 | 31-Dec-26 |  |  | 132 |  |  |  | Gentari renewables representative informed that PPA not signed yet | 2027-09-21 | 2027-09-21 | 2027-09-30 |  | Not effective | 2027-09-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 132.00 ¦ Date: 2027-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2028-03-22
2200001115 | Main-Connectivity under GNA |  | JSW RENEW ENERGY TWELVE LIMITED | SR | Land BG Route | (xi) REGS with an installed capacity of 5 MW and above applying for grant of Connectivity to ISTS through the electrical system of a generating station already having Connectivity to ISTS | Hybrid | 175 (Solar-65 MW, Wind-110 MW) | 0 | 65 | 110 | 0 | 175 |  | Granted | 140 | 0 | 140 | Tuticorin-II | Tamil Nadu | 2025-08-25 | 2025-12-23 | • Through dedicated connectivity transmission system of Ms JSW Renew Energy Ltd. (for app. no. 1200002869) granted connectivity at Tuticorin-II PS – all arrangement under the scope of applicant. | 0 | 230 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. • Augmentation of 1x500 MVA, 400230 kV (6th) ICT at Tuticorin-II PS. | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. • Augmentation of 1x500 MVA, 400230 kV (6th) ICT at Tuticorin-II PS. | 01-Mar-25 | 01-Mar-25 |  |  | 140 | 215 & 216 |  |  |  |  | 2025-12-22 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 52.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 56.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 55.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  |  | Pending with Level 2 | 01-Mar-25 |  | 2025-03-01 | 2026-10-31
2200001119 | Main-Connectivity under GNA |  | EG SOLAR POWER VENTURES PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Tumkur-II | Karnataka | 2026-06-12 | 2029-05-30 | •Through Sharing of dedicated connectivity transmission system agreed for Ms EG Arka Solar Pvt. Ltd. For app. No. 2200001075 i.e. Generation Pooling Station of Ms EG Solar Power Ventures Pvt. Ltd. – Tumkur-II PS 220 kV Sc line on Dc tower – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for integration of Tumkur-II REZ in Karnataka •Transmission system strengthening at Tumkur-II for integration of additional RE potential (2.7 GW) | 31-Dec-26 | 31-Dec-26 |  |  | 100 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2029-11-30
2200001120 | Main-Connectivity under GNA |  | JSW GREEN ENERGY ONE LIMITED | SR | Land BG Route | (xi) REGS with an installed capacity of 5 MW and above applying for grant of Connectivity to ISTS through the electrical system of a generating station already having Connectivity to ISTS | Solar | 50 |  | 40 | 0 | 0 | 40 |  | Granted | 40 | 0 | 40 | Tuticorin-II | Tamil Nadu | 2025-08-25 | 2025-12-23 | • Through sharing of dedicated connectivity transmission system of Ms Mytrah Vayu (Sabarmati) Pvt. Ltd. granted connectivity at Tuticorin-II PS. – all arrangement under the scope of applicant. | 0 | 230 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. • Augmentation of 1x500 MVA, 400230 kV (6th) ICT at Tuticorin-II PS. | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. • Augmentation of 1x500 MVA, 400230 kV (6th) ICT at Tuticorin-II PS. | 31-May-25 | 31-May-25 |  |  | 40 | 222 &223 |  |  |  |  | 2025-09-21 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 40.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-May-25 |  | 2025-05-31 | 2026-10-31
2200001124 | Main-Connectivity under GNA |  | NCL INDUSTRIES LTD | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 220 (Solar-120 MW, Wind 100 MW) |  | 120 | 100 | 0 | 220 |  | Granted | 130 | 0 | 130 | Tuticorin-II | Tamil Nadu | 2026-02-26 | 2028-02-18 | • Generation Pooling station of Ms NCL Industries Ltd. – Tuticorin-II 230 kV Sc line on Dc tower along with line bay at generation end - under the scope of applicant • 1 no. 230 kV terminal line bay at ISTS end (Tuticorin-II PS) for termination of above DTL – under the scope of ISTS. | 1 | 230 KV | Aug with ATS | Augmentation of 1x500 MVA, 400230 kV ICT (7th) at Tuticorin-II GIS PS |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-Mar-27 | 31-Mar-27 |  |  | 130 | 219 |  |  |  |  | 2026-10-31 | 2026-10-31 |  | Not effective | 2028-02-18 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 120.00 ¦ Date: 2028-02-18 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2028-02-18 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-08-18
2200001128 | Main-Connectivity under GNA |  | ADITYA BIRLA RENEWABLES LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 100 | 0 | 50 | 50 | 0 | 100 |  | Granted | 100 | 0 | 100 | Fatehgarh-III (Sec-II) | Rajasthan | 2026-01-19 | 2028-06-30 | (i). Through sharing of dedicated transmission of Ms Green Infra Clean Solar Farms Limited Solar Power Project – Barmer-II PS 220 kV Sc line on Dc tower (Suitable to carry minimum 300 MW per circuit at nominal voltage) (ii). Infrastructure required for sharing dedicated transmission system - under the scope of Ms Aditya Birla Renewables Limited | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA (Tentative) Establishment of 6x500 MVA, 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor LILO of both ckts of 400kV Fatehgarh-IV PS – Bar | Transmission system for Connectivity under GNA (Tentative) Establishment of 6x500 MVA, 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420kV bus reactor LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 15-Jun-26 | 15-Jun-26 |  |  | 100 | 449 |  |  |  |  | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2028-06-15 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 15-Jun-26 |  | 2026-06-15 | 2028-12-30
2200001138 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA 11 PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 | SECI | Granted | 100 | 0 | 100 | Bellary | Karnataka | 2025-06-19 | 2027-09-22 | • Generation Pooling Station of M/s Serentica Renewables India 11 Pvt. Ltd. – Bellary PS 220 kV S/c line on D/c tower* along with 220 kV line bay at generation Pooling Station end – under the scope of applicant. • 1 no. 220 kV line bay at ISTS end for termination of DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | 31-Mar-27 | 31-Mar-27 |  |  | 100 |  |  |  |  | 2027-09-21 | 2027-09-21 | 2027-09-30 |  | Not effective | 2027-09-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2027-06-15 ¦ Status: Under Implementation ¦ Type: | 16.03.2026 | Yes |  |  | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2027-09-30
2200001140 | Main-Connectivity under GNA |  | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 | NHPC | Granted | 300 | 0 | 300 | Bellary | Karnataka | 2025-06-19 | 2027-09-22 | • Generation Pooling Station of M/s Acme Cleantech Solutions Pvt. Ltd. – Bellary PS 220 kV S/c line on D/c* along with 220 kV line bay at generation Pooling Station end – under the scope of applicant. • 1 no. 220 kV line bay at ISTS end for termination of DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ• ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission Scheme for integration of Bellary REZ in Karnataka • Transmission system for integration of Davanagere/ Chitradurga REZ | 31-Dec-26 | 31-Dec-26 |  |  | 300 |  |  |  |  | 2027-09-21 | 2027-09-21 | 2027-09-30 |  | Not effective | 2027-09-22 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-10-22 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 | Yes |  |  | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2027-09-30
2200001143 | Main-Connectivity under GNA |  | AMPIN ENERGY UTILITY PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 185.4 (Solar-135 MW, Wind-50.4 MW) |  | 135 | 50.4 | 0 | 185.4 | SECI | Granted | 150 | 0 | 150 | Tumkur-II | Karnataka | 2026-06-12 | 2029-05-30 | • Through sharing of dedicated connectivity transmission system granted for Ms Ampin Energy C&I Fourteen Pvt. Ltd. for application no. 2200001144 i.e. Generation Pooling Station of Ms Ampin Energy C&I Fourteen Pvt. Ltd. – Tumkur-II PS 220 kV Sc line – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for integration of Tumkur-II REZ in Karnataka •Transmission system strengthening at Tumkur-II for integration of additional RE potential (2.7 GW) | 31-Dec-27 | 31-Dec-27 |  |  | 150 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 135.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 50.40 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2029-05-30
2200001144 | Main-Connectivity under GNA |  | AMPIN Energy C&I Fourteen Private Limited (Formerly known as AMP ENERGY C&I FOURTEEN PRIVATE LIMITED) | SR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Solar | 50 |  | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Tumkur-II | Karnataka | 2026-06-12 | 2029-05-30 | •Generation Pooling Station of Ms Ampin Energy C&I Fourteen Pvt. Ltd. – Tumkur-II PS 220 kV Sc line on Dc tower along with line bay at generation pooling station – under the scope of applicant. •1 no. 220 kV terminal line bay at Tumkur-II PS for termination of above dedicated line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for integration of Tumkur-II REZ in Karnataka •Transmission system strengthening at Tumkur-II for integration of additional RE potential (2.7 GW) | 30-Jun-27 | 30-Jun-27 |  |  | 50 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 25.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Standalone | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2029-11-30
2200001146 | Main-Connectivity under GNA |  | AMPIN Energy C&I Twenty- Eight Private Limited (Formerly knwon as AMP ENERGY C&I TWENTY EIGHT PRIVATE LIMITED) | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 60.9 (Solar-40 MW, Wind-18.9 MW) |  | 42 | 18.9 | 0 | 60.9 |  | Granted | 50 | 0 | 50 | Tumkur-II | Karnataka | 2026-06-12 | 2029-05-30 | •Through sharing of dedicated connectivity transmission system agreed for Ms Ampin Energy C&I Fourteen Pvt. Ltd. for application no. 2200001144 i.e. Generation Pooling Station of Ms Ampin Energy C&I Fourteen Pvt. Ltd. – Tumkur-II PS 220 kV Sc line on Dc tower – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for integration of Tumkur-II REZ in Karnataka •Transmission system strengthening at Tumkur-II for integration of additional RE potential (2.7 GW) | 30-Jun-27 | 30-Jun-27 |  |  | 50 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 42.00 ¦ Date: 2029-05-29 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 18.90 ¦ Date: 2029-05-29 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2029-11-30
2200001147 | Main-Connectivity under GNA |  | AMPIN Energy C&I Twenty- Nine Private Limited (Formerly knwon asAMP ENERGY C&I TWENTY NINE PRIVATE LIMITED) | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 63.4 (Solar-35 MW, Wind-28.4 MW) |  | 35 | 28.4 | 0 | 63.4 |  | Granted | 50 | 0 | 50 | Tumkur-II | Karnataka | 2026-06-12 | 2029-05-30 | •Through sharing of dedicated connectivity transmission system granted for Ms Ampin Energy C&I Fourteen Pvt. Ltd. for application no. 2200001144 i.e. Generation Pooling Station of Ms Ampin Energy C&I Fourteen Pvt. Ltd. – Tumkur-II PS 220 kV Sc line on Dc tower – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission scheme for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission scheme for integration of Tumkur-II REZ in Karnataka • Transmission system strengthening at Tumkur-II for integration of additional RE potential (2.7 GW) | 30-Jun-27 | 30-Jun-27 |  |  | 50 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 35.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 28.40 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2029-11-30
2200001148 | Main-Connectivity under GNA |  | JSW RENEW ENERGY THIRTEEN LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Solapur | Maharashtra | 2025-05-19 | 2026-03-31 | Ms JSWRE13L shall share the DTL of Ms RGESL against application no. 231400007 as given below • Establishment of 33400kV Pooling Sub-Station PSS4 (under the scope of applicant(RGESL)) • RGESL PSS 4 – Solapur (PG) 400kV Sc line (on Dc tower) (with HTLS conductor with minimum capacity of 2100MW at nominal voltage) along with associated bays at both ends (under the scope of applicant(RGESL)) | 0 | 400 KV | Existing |  |  |  |  | 31-Mar-26 | 31-Mar-26 | 300 | 2026-03-31 |  | 433 | [7 empty] | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-26 |  | 2026-03-31 | 2026-09-30
2200001150 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Dhule (Sec-I) | Maharashtra | 2025-08-28 | 2027-06-30 | • AEPL – Dhule PS (Sec-I) 220kV Sc line (which shall be strung on the Dc and Mc towers* being implemented with earlier 50MW application no. 2200000081 of Ms AEPL at Dhule PS) along with associated bay at generation end (Under scope of AEPL). • 1 no. 220kV line bay at Dhule PS is being implemented under ISTS as a part of the Dhule Pooling Station by Ms Dhule Power | 1 |  | Aug without ATS |  |  | • Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAAC AL59 Moose equivalent (60 km) | • Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAAC AL59 Moose equivalent (60 km) | 30-Jun-27 | 30-Jun-27 |  |  | 200 | 204 |  |  |  | 2026-10-30 | 2026-02-09 | 2026-10-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-12-30 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-12-30
2200001152 | Main-Connectivity under GNA |  | ESSAR RENEWABLES LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 | SJVN | Granted | 300 | 0 | 300 | Tumkur-II | Karnataka | 2026-06-12 | 2029-05-30 | • Generation Pooling Station of Ms Essar Renewables Limited – Tumkur-II PS 220 kV Sc line on Dc along with line bay at generation pooling station – under the scope of applicant. • 1 no. 220 kV terminal line bay at Tumkur II PS for termination of above dedicated line –under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission scheme | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission scheme for integration of Tumkur-II REZ in Karnataka • Transmission system strengthening at Tumkur-II for integration of additional RE potential (2.7 GW) | 31-Oct-26 | 31-Oct-26 |  |  | 300 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2029-05-29 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Oct-26 |  | 2026-10-31 | 2029-05-30
2200001158 | Main-Connectivity under GNA |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED | WR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Solar | 1000 | 0 | 700 | 0 | 350 | 1050 |  | Granted | 700 | 0 | 700 | Solapur | Maharashtra | 2025-08-28 | 2026-03-31 | Ms WFEPL shall share the DTL granted to Ms RGESL against application no. 231400007 as given below • Establishment of 33400kV Pooling Sub-Station PSS4 (under the scope of applicant(RGESL)) • RGESL PSS 4 – Solapur (PG) 400kV Sc line (on Dc tower) (with HTLS conductor with minimum capacity of 2100MW at nominal voltage) along with associated bays at both ends (under the scope of applicant(RGESL)) | 0 | 400 KV | Existing |  |  | Existing Transmission System | Existing Transmission System | 300 MW 31.03.2026300 MW 30.09.2026400 MW 31.03.2027 | Phase 1 ¦ MW: 300.00 ¦ Date: 2026-03-31 Phase 2 ¦ MW: 300.00 ¦ Date: 2026-09-30 Phase 3 ¦ MW: 400.00 ¦ Date: 2027-03-31 | 700 | 2026-03-31 |  | 433 | [7 empty] | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 700.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 300.00 ¦ Date: 2026-03-31 | 300 | 2026-03-31 | 2026-09-30
2200001158 | Main-Connectivity under GNA |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED | WR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Solar | 1000 | 0 | 700 | 0 | 350 | 1050 |  | Granted | 700 | 0 | 700 | Solapur | Maharashtra | 2025-08-28 | 2026-03-31 | Ms WFEPL shall share the DTL granted to Ms RGESL against application no. 231400007 as given below • Establishment of 33400kV Pooling Sub-Station PSS4 (under the scope of applicant(RGESL)) • RGESL PSS 4 – Solapur (PG) 400kV Sc line (on Dc tower) (with HTLS conductor with minimum capacity of 2100MW at nominal voltage) along with associated bays at both ends (under the scope of applicant(RGESL)) | 0 | 400 KV | Existing |  |  | Existing Transmission System | Existing Transmission System | 300 MW 31.03.2026300 MW 30.09.2026400 MW 31.03.2027 | Phase 1 ¦ MW: 300.00 ¦ Date: 2026-03-31 Phase 2 ¦ MW: 300.00 ¦ Date: 2026-09-30 Phase 3 ¦ MW: 400.00 ¦ Date: 2027-03-31 | 700 | 2026-03-31 |  | 433 | [7 empty] | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 700.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 300.00 ¦ Date: 2026-09-30 | 300 | 2026-09-30 | 2027-03-30
2200001158 | Main-Connectivity under GNA |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED | WR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Solar | 1000 | 0 | 700 | 0 | 350 | 1050 |  | Granted | 700 | 0 | 700 | Solapur | Maharashtra | 2025-08-28 | 2026-03-31 | Ms WFEPL shall share the DTL granted to Ms RGESL against application no. 231400007 as given below • Establishment of 33400kV Pooling Sub-Station PSS4 (under the scope of applicant(RGESL)) • RGESL PSS 4 – Solapur (PG) 400kV Sc line (on Dc tower) (with HTLS conductor with minimum capacity of 2100MW at nominal voltage) along with associated bays at both ends (under the scope of applicant(RGESL)) | 0 | 400 KV | Existing |  |  | Existing Transmission System | Existing Transmission System | 300 MW 31.03.2026300 MW 30.09.2026400 MW 31.03.2027 | Phase 1 ¦ MW: 300.00 ¦ Date: 2026-03-31 Phase 2 ¦ MW: 300.00 ¦ Date: 2026-09-30 Phase 3 ¦ MW: 400.00 ¦ Date: 2027-03-31 | 700 | 2026-03-31 |  | 433 | [7 empty] | Effective |  |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 700.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 3 ¦ MW: 400.00 ¦ Date: 2027-03-31 | 400 | 2027-03-31 | 2027-09-30
2200001160 | Main-Connectivity under GNA |  | SPRNG WIND ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 164 MW Hybrid (NTPC LOA: 70 MW Solar + 24 MW Wind and SJVN LOA: 70 MW Wind) |  | 100 | 0 | 0 | 100 | NTPC | Granted | 100 | 0 | 100 | Raghanesda | Gujarat | 2026-01-05 | 2028-12-31 | SWEPL may share the DTL granted to Ms SWEPL against application no. 2200000612 as given below • SWEPL - Raghanesda 400kV Sc line (on Dc tower) along with associated bays at generation end. • 1 no. 400kV line bay on ISTS end (under the scope of ISTS) | 0 | 400 KV | Aug without ATS |  |  | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc l | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV Dc line • LILO of Navsari (New) – | 31-Jul-26 | 31-Jul-26 |  |  | 100 | 451 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2028-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2028-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2029-06-30
2200001161 | Main-Connectivity under GNA |  | SPRNG VAYU KIRAN PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 | 0 | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Raghanesda | Gujarat | 2026-01-05 | 2030-06-30 | SVKPL may share the DTL granted to Ms SWEPL against application no. 2200000612 as given below • SWEPL - Raghanesda 400kV Sc line (on Dc tower) along with associated bays at generation end. • 1 no. 400kV line bay on ITS end (under the scope of ISTS) | 0 | 400 KV | Aug without ATS |  |  | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc l | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV Dc line • LILO of Navsari (New) – | 100 MW 30062030100 MW 31122030 | Phase 1 ¦ MW: 100.00 ¦ Date: 2030-06-30 Phase 2 ¦ MW: 100.00 ¦ Date: 2030-12-31 |  |  | 200 | 451 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2030-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2030-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2030-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 29-07-2026 |  |  | 29/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 100.00 ¦ Date: 2030-06-30 | 100 | 2030-06-30 | 2030-12-30
2200001161 | Main-Connectivity under GNA |  | SPRNG VAYU KIRAN PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 | 0 | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Raghanesda | Gujarat | 2026-01-05 | 2030-06-30 | SVKPL may share the DTL granted to Ms SWEPL against application no. 2200000612 as given below • SWEPL - Raghanesda 400kV Sc line (on Dc tower) along with associated bays at generation end. • 1 no. 400kV line bay on ITS end (under the scope of ISTS) | 0 | 400 KV | Aug without ATS |  |  | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc l | A. Under Implementation (under ISTS) 1. Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (Khavda RE Transmission Ltd. - POWERGRID) (SCOD 21032025) • Banaskantha – Ahmedabad 765kV Dc line 2. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-B (Khavda II-B Transmission Ltd. - POWERGRID) (SCOD 21032025) • Lakadia PS – Ahmedabad 765kV Dc line 3. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-C (Khavda II-C Transmission Ltd. - POWERGRID) (SCOD 21032025) • Establishment of 3x1500MVA 765400 kV Ahmedabad Ss • Ahmedabad – Navsari (New) 765 kV Dc line 4. Transmission Scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase-II, Part-D (TPGL) (SCOD 21032025) • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss along with reconductoring of Pirana (PG) – Pirana (T) 400kV Dc line 5. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) • Establishment of 765 kV Halvad switching station • LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad 6. Transmission Scheme for evacuation of additional 7 GW of RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) • Establishment of 765 kV switching station near Vataman • Halvad – Vataman 765 kV Dc line • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman • Vataman switching station – Navsari (New) 765 kV Dc line 7. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) • Establishment of 765400220kV South Olpad (GIS) Ss with 2x1500MVA 765400kV ICTs. • Vadodara – South Olpad (GIS) 765kV Dc line • LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 2100 MVA per ckt at nominal voltage • Ahmedabad – South Olpad (GIS) 765kV Dc line 8. Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (part system) (Khavda IV C Power Transmission Ltd. – SG38L) (SCOD 15102026) • Establishment of 765400220kV Boisar-II (GIS) Ss with 4x1500MVA ICTs & 2x500MVA ICTs • South Olpad (GIS) – Boisar-II 765kV Dc line • LILO of Navsari (New) – | 100 MW 30062030100 MW 31122030 | Phase 1 ¦ MW: 100.00 ¦ Date: 2030-06-30 Phase 2 ¦ MW: 100.00 ¦ Date: 2030-12-31 |  |  | 200 | 451 |  |  |  | 2027-10-23 | 2027-10-23 | 2027-10-23 |  | Not effective | 2030-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2030-06-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2030-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 29-07-2026 |  |  | 29/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 100.00 ¦ Date: 2030-12-31 | 100 | 2030-12-31 | 2031-06-30
2200001165 | Main-Connectivity under GNA |  | EG SUN ENERGY PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Tumkur-II | Karnataka | 2026-06-12 | 2029-05-30 | •Through Sharing of dedicated connectivity transmission system of Ms EG Arka Solar Pvt. Ltd. for app. no. 2200001075 i.e. Generation Pooling Station of Ms EG Arka Solar Private Limited – Tumkur-II PS 220 kV Sc line on Dc – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for integration of Tumkur-II REZ in Karnataka •Transmission system strengthening at Tumkur-II for integration of additional RE potential (2.7 GW) | 31-Dec-26 | 31-Dec-26 |  |  | 100 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2029-11-30
2200001170 | Main-Connectivity under GNA |  | ACME SOLAR HOLDINGS LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 | SJVN | Granted | 300 | 0 | 300 | Tumkur-II | Karnataka | 2026-06-12 | 2029-05-30 | • Generation Pooling Station of Ms Acme Solar Holdings Limited – Tumkur-II PS 220 kV Sc line on Dc tower* along with line bay at generation pooling station – under the scope of applicant. • 1 no. 220 kV terminal line bay at Tumkur II PS for termination of above dedicated connectivity line –under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for integration of Tumkur-II REZ in Karnataka •Transmission system strengthening at Tumkur-II for integration of additional RE potential (2.7 GW) | 31-Dec-26 | 31-Dec-26 |  |  | 300 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2029-05-31 ¦ Status: Under Implementation ¦ Type: Solar | 08.07.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2029-05-30
2200001172 | Main-Connectivity under GNA |  | HANUR SOLAR POWER PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Tumkur-II | Karnataka | 2026-06-12 | 2029-05-30 | • Generation Pooling Station of Ms Hanur Solar Power Private Limited – Tumkur-II PS 220 kV Sc line along with line bay at generation pooling station – under the scope of applicant. • 1 no. 220 kV terminal line bay at Tumkur II PS for termination of above dedicated connectivity line –under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission scheme for integration of Tumkur-II REZ in Karnataka •Transmission system strengthening at Tumkur-II for integration of additional RE potential (2.7 GW) | 30-Sep-27 | 30-Sep-27 |  |  | 300 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2029-05-29 ¦ Status: Under Implementation ¦ Type: Solar | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Sep-27 |  | 2027-09-30 | 2029-11-30
2200001192 | Main-Connectivity under GNA |  | WAAREE RENEWABLE TECHNOLOGIES LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Mandsaur (Sec-II) | Madhya Pradesh | 2025-12-31 | 2027-03-24 | • WRTL – Mandsaur 220kV Sc line (on Dc tower) along with associated bay at the generation end (Under the scope of WRTL) • 1 no. 220kV line bay (on 220kV Bus Sec-II) at Mandsaur PS is being implemented under ISTS as part of Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur Ss for RE Interconnection scheme. | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x5 | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line Rajasthan REZ Ph-V (Part-1 4 GW) [SirohiNagaur] Complex (SCOD 24.03.2027) (Rajasthan V Power Transmission Limited – POWERGRID) • Mandsaur PS – Khandwa (New) 765 kV Dc line Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur Ss for RE Interconnection (SCOD 24.03.2027) (Mandsaur I RE Transmission Limited - Ms Power Grid Corporation of India Limited) (Part System) • Augmentation of Transformation capacity by 1x500MVA, 400220kV ICT (6th) (Terminated on 400kV Bus Section-I & 220kV Bus Section-II) | 30-Jun-26 | 30-Jun-26 |  |  | 300 |  |  |  |  | 2027-03-24 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-03-24 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-24 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-26 |  | 2026-06-30 | 2027-09-24
2200001201 | Main-Connectivity under GNA |  | ACME SOLAR HOLDINGS LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bellary | Karnataka | 2026-07-14 | 2028-02-13 | •Generation Pooling Station of Ms Acme Solar Holdings Limited - Bellary PS 220 kV Sc line on Dc tower along with implementation of 220 kV line bay at generation pooling station end - under the scope of applicant. •1 no. 220 kV terminal line bay at Bellary PS for termination of above DTL - under the scope of ISTS. [under implementation as part of ”Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ”] | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka • Transmission sy | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka • Transmission system strengthening at Davanagere for integration of RE generation •Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765 kV Dc line. | 31-Dec-26 | 31-Dec-26 |  |  | 300 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-02-13 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2028-08-13
2200001214 | Main-Connectivity under GNA |  | ADYANT ENERSOL PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 164 MW Hybrid (NTPC LOA: 70 MW Solar + 24 MW Wind and SJVN LOA: 70 MW Wind) |  | 70 | 94 | 0 | 164 | NTPC | Granted | 164 | 0 | 164 | Mandsaur (Sec-I) | Madhya Pradesh | 2026-01-02 | 2027-03-24 | Ms AdEPL shall share the DTL granted to AdEPL for its 84MW HPP against appln. No. 2200000976 as given below • AdEPL – Mandsaur PS 220kV Sc line along with associated bay at the generation end (Under the scope of Ms AdEPL). • 01 no. 220kV line bay (on 220kV Bus Sec-I) at Mandsaur PS is being implemented under ISTS. | 0 | 220 KV | Aug without ATS |  |  | Under Implementation 1) Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & | Under Implementation 1) Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line 2) Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line 3) Rajasthan REZ Ph-V (Part-1 4 GW) [SirohiNagaur] Complex (SCOD 24.03.2027) (Rajasthan V Power Transmission Limited – POWERGRID) • Mandsaur PS – Khandwa (New) 765 kV Dc line 4) Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur Ss for RE Interconnection (part system) (SCOD 24.03.2027) (Mandsaur I RE Transmission Limited - POWERGRID) • Creation of New 400kV & 765kV Bus Sections- II through Sectionaliser arrangement at Mandsaur PS. • Augmentation of Transformation capacity by 1x1500MVA, 765400kV ICT (4th) (Terminated at 400kV & 765kV Bus Section-II) at Mandsaur PS. • Augmentation of Transformation capacity by 1x500MVA, 400220kV ICT (6th) (Terminated on 400kV Bus Section-I & 220kV Bus Section-II) at Mandsaur PS. | 31-Jul-26 | 31-Jul-26 |  |  | 164 | [5 empty] | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 70.00 ¦ Date: 2027-03-24 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 94.00 ¦ Date: 2027-03-24 ¦ Status: ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2027-06-30
2200001229 | Main-Connectivity under GNA |  | TEQ GREEN POWER XIX PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 300 (Solar-200 MW, Wind-100 MW) | 0 | 200 | 100 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bellary | Karnataka | 2026-07-14 | 2028-12-30 | • Generation Pooling Station of Ms TEQ Green Power XIX Private Limited - Bellary PS 220 kV Sc line on Dc tower along with implementation of 220 kV line bay at generation pooling station end - under the scope of applicant. • 1 no. 220 kV terminal line bay at Bellary PS for termination of above DTL - under the scope of ISTS. [under implementation as part of ”Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW)”] | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka •Transmission syst | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka •Transmission system strengthening at Davanagere for integration of RE generation •Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765 kV Dc line. | 150 MW 31.12.28150 MW 31.03.29 | Phase 1 ¦ MW: 150.00 ¦ Date: 2028-12-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2029-03-31 |  |  | 300 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-12-30 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 150.00 ¦ Date: 2028-12-31 | 150 | 2028-12-31 | 2029-06-30
2200001229 | Main-Connectivity under GNA |  | TEQ GREEN POWER XIX PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 300 (Solar-200 MW, Wind-100 MW) | 0 | 200 | 100 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bellary | Karnataka | 2026-07-14 | 2028-12-30 | • Generation Pooling Station of Ms TEQ Green Power XIX Private Limited - Bellary PS 220 kV Sc line on Dc tower along with implementation of 220 kV line bay at generation pooling station end - under the scope of applicant. • 1 no. 220 kV terminal line bay at Bellary PS for termination of above DTL - under the scope of ISTS. [under implementation as part of ”Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW)”] | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka •Transmission syst | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka •Transmission system strengthening at Davanagere for integration of RE generation •Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765 kV Dc line. | 150 MW 31.12.28150 MW 31.03.29 | Phase 1 ¦ MW: 150.00 ¦ Date: 2028-12-31 Phase 2 ¦ MW: 150.00 ¦ Date: 2029-03-31 |  |  | 300 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-12-30 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 150.00 ¦ Date: 2029-03-31 | 150 | 2029-03-31 | 2029-09-30
2200001233 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bellary | Karnataka | 2026-07-14 | 2028-02-13 | • Generation Pooling Station of Ms NTPC Renewable Energy Limited - Bellary PS 220 kV Sc line on Dc Tower* along with implementation of 220 kV line bay at generation pooling station end - under the scope of applicant. • 1 no. 220 kV terminal line bay at Bellary PS for terminal of above DTL - under the scope of ISTS.[under implementation as part of ”Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW)”] | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka •Transmission sy | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka •Transmission system strengthening at Davanagere for integration of RE generation •Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765 kV Dc line. | 30-Mar-27 | 30-Mar-27 |  |  | 300 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-02-13 |  |  | 0 |  | 30.06.2028 |  |  | 21/07/2026 | Pending with Level 2 | 30-Mar-27 |  | 2027-03-30 | 2028-08-13
2200001234 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 92 | 0 | 92 | Bellary | Karnataka | 2026-07-14 | 2028-02-13 | •Through dedicated connectivity transmission system of Ms NTPC Renewable Energy Limited for app. no. 2200000825 i.e. Generation Pooling Station of Ms NTPC Renewable Energy Limited – Bellary PS 220 kV Sc line on Dc tower – all arrangement - under the scope of applicant. [terminal line bay at ISTS end is under implementation as part of ”Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ”]] | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka • Part of trans | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka • Part of transmission system strengthening at Davanagere for integration of RE generation • Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765 kV Dc line. | 30-Mar-27 | 30-Mar-27 |  |  | 92 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-02-13 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Mar-27 |  | 2027-03-30 | 2028-08-13
2200001237 | Main-Connectivity under GNA |  | KYROS HYBREN PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bellary | Karnataka | 2026-07-14 | 2028-02-13 | • Generation Pooling Station of Ms Kyros Hybren Private Limited - Bellary PS 220 kV Sc line on Dc tower along with implementation of 220 kV line bay at generation pooling station end - under the scope of applicant. • 1 no. 220 kV terminal line bay at Bellary PS for termination of above DTL - under the scope of ISTS. [under implementation as part of ”Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW)”] | 1 | 220 KV | Aug without ATS |  |  |  |  | 30-Jun-27 | 30-Jun-27 |  |  | 300 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-02-13 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2028-08-13
2200001239 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Davangere | Karnataka | 2025-12-23 | 2028-01-31 | • Generation Pooling Station of Ms NTPC Renewable Energy Limited. – Devengere PS 400 kV Sc line along with 400 kV line bay at generation Pooling Station end – under the scope of applicant. • 1 no. 400 kV line bay at ISTS end for termination of DTL – under the scope of ISTS. | 1 | 400 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission system strengthening at Davanag | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission system strengthening at Davanagere for integration of RE generation | 30-Mar-27 | 30-Mar-27 |  |  | 300 | [5 empty] | 2027-09-24 | 2027-09-30 |  | Not effective | 2028-01-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 30-Mar-27 |  | 2027-03-30 | 2028-07-31
2200001240 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 82 | 0 | 82 |  | Granted | 82 | 0 | 82 | Davangere | Karnataka | 2025-12-23 | 2028-01-31 | •Through dedicated connectivity transmission system of Ms NTPC Renewable Energy Ltd. for app. no. 1200001239 i.e. Generation Station of Ms NTPC Renewable Energy Ltd. – Davangere PS 400 kV Sc line - all arrangement under the scope of applicant. | 0 | 400 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanager | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanagere for integration of RE generation | 30-Mar-27 | 30-Mar-27 |  |  | 82 | [5 empty] | 2027-09-24 | 2027-09-30 |  | Not effective | 2028-01-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 82.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Mar-27 |  | 2027-03-30 | 2028-07-31
2200001244 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | WR | Land Route | (vi) Captive generating plant | Wind | 111.8 | 0 | 0 | 10.8 | 0 | 10.8 |  | Granted | 10.8 | 0 | 10.8 | kallam | Maharashtra | 2025-04-07 | 2025-10-05 | Ms TPREL shall share the DTL of Ms TSPPL for its 66MW WPP against application no. 1670224223993 as given below • TSPPL – Kallam PS 400kV Sc line along with associated bay at generation station (under the scope of Ms TSPPL). • 1 no.400kV line bay at Kallam PS (under the scope of ISTS). | 0 | 400 KV | Aug without ATS |  |  | • LILO of both circuits of Parli (M) – Karjat (M) Lonikand II(M) 400kV Dc line (twin moose) at Kallam PS. | • LILO of both circuits of Parli (M) – Karjat (M) Lonikand II(M) 400kV Dc line (twin moose) at Kallam PS. | 31-Mar-25 | 31-Mar-25 |  |  | 10.8 | 421 |  |  |  | 2025-03-31 | 2025-10-05 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 10.80 ¦ Date: 2026-08-01 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-25 |  | 2025-03-31 | 2026-10-31
2200001256 | Main-Connectivity under GNA |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 468 |  | 0 | 468 | 0 | 468 |  | Granted | 468 | 0 | 468 | Davangere | Karnataka | 2025-12-23 | 2028-01-31 | • Through dedicated connectivity transmission system of Ms NTPC Renewable Energy Ltd for app. no. 1200001239 i.e. Generation Station of Ms NTPC Renewable Energy Ltd – Davangere PS 400 kV Sc line - all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | 1.ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region 2. Transmission system for integration of Davanagere Chitradurga REZ 3. Transmission system strengthening at | 1.ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region 2. Transmission system for integration of Davanagere Chitradurga REZ 3. Transmission system strengthening at Davanagere for integration of RE generation | 10-Apr-26 | 10-Apr-26 |  |  | 468 | [5 empty] | 2027-09-24 | 2027-09-30 |  | Not effective | 2028-01-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 468.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 10-Apr-26 |  | 2026-04-10 | 2028-07-31
2200001258 | Main-Connectivity under GNA |  | PURVAH RENEWABLE POWER PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bellary | Karnataka | 2026-07-14 | 2028-09-01 | • Generation Pooling Station of Ms Purvah Renewable Power Private Limited – Bellary PS 220 kV Sc line on Dc tower* along with line bay at generation pooling station - under the scope of applicant. • 1 no. 220 kV terminal line bay at Bellary PS for terminal of above dedicated connectivity line - under the scope of ISTS.[under implementation as part of ”Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW)”] | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka •Transmission sy | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka •Transmission system strengthening at Davanagere for integration of RE generation • Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765 kV Dc line. | 01-Sep-28 | 01-Sep-28 |  |  | 300 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-09-01 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 01-Sep-28 |  | 2028-09-01 | 2029-03-01
2200001263 | Main-Connectivity under GNA |  | PURVAH GREEN POWER PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Bellary | Karnataka | 2026-07-14 | 2028-09-01 | • Generation Pooling Station of Ms Purvah Green Power Private Limited – Bellary PS 220 kV Sc line on Dc tower* along with line bay at generation pooling station - under the scope of applicant. • 1 no. 220 kV terminal line bay at Bellary PS for terminal of above dedicated connectivity line - under the scope of ISTS.[under implementation as part of ”Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW)”] | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka •Transmission sy | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission Scheme for integration of Davanagere Chitradurga REZ and Bellary REZ in Karnataka •Transmission system strengthening at Davanagere for integration of RE generation •Transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765 kV Dc line. | 01-Sep-28 | 01-Sep-28 |  |  | 300 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-09-01 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 01-Sep-28 |  | 2028-09-01 | 2029-03-01
2200001276 | Main-Connectivity under GNA |  | JUNIPER GREEN GEM PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Dhule (Sec-I) | Maharashtra | 2025-05-19 | 2028-06-30 | • JGGPL – Dhule PS (Sec-I) 220kV Sc (on Dc tower) line along with associated bays at generation end (Under scope of JGGPL). • 1 no. 220kV line bay at Dhule PS is being implemented under ISTS as a part of the Pooling Station. | 1 | 220 KV | Aug without ATS |  |  | • Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAAC AL59 Moose equivalent (60 km) | • Establishment of 4x500 MVA, 400220 kV Pooling Station near Dhule. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAAC AL59 Moose equivalent (60 km) | 30-Jun-28 | 30-Jun-28 |  |  | 100 | 206 |  |  |  | 2026-06-30 | 2026-02-09 | 2026-10-30 |  | Not effective | 2028-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-28 |  | 2028-06-30 | 2028-12-30
2200001279 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Mandsaur (Sec-II) | Madhya Pradesh | 2025-12-31 | 2027-06-30 | NTPC REL shall share the DTL proposed for NTPC REL for its 300MW SPP against application no. 2200001301 as given below • NTPC REL-Mandsaur 400kV Sc line along with associated bays at the Generating end (Under the scope of Ms NTPCREL). • 01 no. 400kV line bay (on 4000kV Bus Sec-II) at Mandsaur PS shall be implemented under ISTS as per request of applicant. | 0 | 400 kV | Aug without ATS |  |  | Under Implementation: Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-2:5.5 GW) (Jaisalmer/Barmer Complex): Part C (SCOD: 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765/400kV & 5x500MVA, 400/220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV D/c Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-2:5.5 GW) (Jaisalmer/Barmer Complex): Part H1 (SCOD: 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765/400kV (2x1500MVA), 400/220kV (2x500MVA) & 220/132 kV (3x200 MVA) Kurawar S/s along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV D/c line • LILO of Indore – Bhopal 765 kV S/c line at Kurawar • Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D/ c line at Astha • Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Rajasthan REZ Ph-V (Part-1: 4 GW) [Sirohi/Nagaur] Complex (SCOD: 24.03.2027) (Rajasthan V Power Transmission Limited – POWERGRID) • Mandsaur PS – Khandwa (New) 765 kV D/c line Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur S/s for RE Interconnection (SCOD: 24.03.2027) (Mandsaur I RE Transmission Limited - M/s Power Grid Corporation of India Limited) • Creation of New 400kV & 765kV Bus Sections through Sectionaliser arrangement • Augmentation of Transformation capacity by 1x1500MVA, 765/400kV ICT (4th) (Terminated at 400kV & 765kV Bus Section-II) | Under Implementation: Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-2:5.5 GW) (Jaisalmer/Barmer Complex): Part C (SCOD: 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765/400kV & 5x500MVA, 400/220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV D/c Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-2:5.5 GW) (Jaisalmer/Barmer Complex): Part H1 (SCOD: 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765/400kV (2x1500MVA), 400/220kV (2x500MVA) & 220/132 kV (3x200 MVA) Kurawar S/s along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV D/c line • LILO of Indore – Bhopal 765 kV S/c line at Kurawar • Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D/ c line at Astha • Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line Rajasthan REZ Ph-V (Part-1: 4 GW) [Sirohi/Nagaur] Complex (SCOD: 24.03.2027) (Rajasthan V Power Transmission Limited – POWERGRID) • Mandsaur PS – Khandwa (New) 765 kV D/c line Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur S/s for RE Interconnection (SCOD: 24.03.2027) (Mandsaur I RE Transmission Limited - M/s Power Grid Corporation of India Limited) • Creation of New 400kV & 765kV Bus Sections through Sectionaliser arrangement • Augmentation of Transformation capacity by 1x1500MVA, 765/400kV ICT (4th) (Terminated at 400kV & 765kV Bus Section-II) | 30-Jun-27 | 30-Jun-27 |  |  | 300 | 433 |  |  |  | 2028-06-30 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2028-06-30
2200001280 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Mandsaur (Sec-II) | Madhya Pradesh | 2026-01-01 | 2027-06-30 | NTPC REL shall share the DTL proposed for NTPC REL for its 300MW SPP against application no. 2200001301 as given below • NTPC REL-Mandsaur 400kV Sc line along with associated bays at the Generating end (Under the scope of Ms NTPCREL). • 01 no. 400kV line bay (on 4000kV Bus Sec-II) at Mandsaur PS shall be implemented under ISTS as per request of applicant. | 0 | 400 KV | Aug without ATS |  |  | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x5 | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line Rajasthan REZ Ph-V (Part-1 4 GW) [SirohiNagaur] Complex (SCOD 24.03.2027) (Rajasthan V Power Transmission Limited – POWERGRID) • Mandsaur PS – Khandwa (New) 765 kV Dc line Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur Ss for RE Interconnection (SCOD 24.03.2027) (Mandsaur I RE Transmission Limited - Ms Power Grid Corporation of India Limited) • Creation of New 400kV & 765kV Bus Sections through Sectionaliser arrangement • Augmentation of Transformation capacity by 1x1500MVA, 765400kV ICT (4th) (Terminated at 400kV & 765kV Bus Section-II) Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Asht | 30-Jun-27 | 30-Jun-27 |  |  | 300 |  |  |  |  | 2027-03-31 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-12-30
2200001285 | Main-Connectivity under GNA |  | VISMAYA FIVE RENEWABLES PRIVATE LIMITED | NR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 |  | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Barmer-II | Rajasthan | 2026-01-19 |  | Common Pooling station for Vismaya Five Renewables Private Limited Solar Power Projects (App. No. 2200000954- 250 MW & App. No. 2200001285-50MW) – Barmer-II PS 220 kV Sc line on Dc tower (suitable to carry minimum 300 MW at nominal voltage) -Under Applicant Scope | 0 | 220 KV | Aug without ATS |  |  |  | 1. Establishment of 6x500 MVA, 400220kV Pooling Station at suitable location near Barmer (Barmer-II PS) along with 2x125 MVAr bus reactor 2. LILO of both ckts of 400kV Fatehgarh-IV PS – Barmer-I PS at Barmer-II PS 3. Barmer-II PS- Barmer-I PS 400kV Dc line (Quad)(20km) 4. Establishment of 6000 MW, ± 800 kV Barmer-II (HVDC) terminal station (4x1500 MW) at a suitable location near Barmer-II substation 5. Establishment of 6000 MW, ± 800 kV South Kalamb Ss (HVDC) terminal station (4x1500 MW) at a suitable location near South of Kalamb (WR) 6. Establishment 2x1500 MVA, 765400kV Substation near South of Kalamb with 2x330 MVAR, 765 kV bus reactor and 2x125 MVAR, 420kV bus reactor 7. LILO of Pune-III – Boisar-II 765kV Dc line at South Kalamb with associated bays at South Kalamb Ss 8. ±800 kV HVDC line between Barmer-II (HVDC) & South Kalamb (HVDC) (with Dedicated Metallic Return) 9. 2x[]300(-)150MVAr Synchronous condenser at 220kV level of Barmer-II PS | 31-Dec-30 | 31-Dec-30 |  |  | 50 | [6 empty] | 2030-12-30 |  | Not effective | 2030-12-31 | Under Bidding | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2030-12-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-30 |  | 2030-12-31 | 2031-06-30
2200001289 | Main-Connectivity under GNA |  | ACME SOLAR HOLDINGS LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Mandsaur (Sec-II) | Madhya Pradesh | 2026-01-01 | 2027-03-24 | ASHL shall share the DTL granted to ACSPL for its 150MW SPP against Appl. No. 2200000924 as given below • ACSPL – Mandsaur 220kV Sc line (on Dc towers) along with associated bay at the generation end (Under the scope of ACSPL). • 1 no. 220kV line bay (on 220kV Bus Sec-II) at Mandsaur PS (being implemented under ISTS as part of PS) | 0 | 220 KV | Aug without ATS |  |  | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x5 | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line Rajasthan REZ Ph-V (Part-1 4 GW) [SirohiNagaur] Complex (SCOD 24.03.2027) (Rajasthan V Power Transmission Limited – POWERGRID) • Mandsaur PS – Khandwa (New) 765 kV Dc line Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur Ss for RE Interconnection (SCOD 24.03.2027) (Mandsaur I RE Transmission Limited - Ms Power Grid Corporation of India Limited) • Creation of New 400kV & 765kV Bus Sections through Sectionaliser arrangement • Augmentation of Transformation capacity by 1x1500MVA, 765400kV ICT (4th) (Terminated at 400kV & 765kV Bus Section-II) • Augmentation of Transformation capacity by 1x500MVA, 400220kV ICT (6th) (Terminated on 400kV Bus Section-I & 220kV Bus Section-II) | 31-Dec-26 | 31-Dec-26 |  |  | 200 | 216 |  |  |  | 2027-03-24 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-03-24 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-09-15 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Dec-26 |  | 2026-12-31 | 2027-09-24
2200001294 | Main-Connectivity under GNA |  | HERO SOLAR ENERGY PRIVATE LIMITED | SR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | Solar: 220 MW Wind: 52.8 MW BESS: 5 MW |  | 220 | 52.8 | 5 | 277.8 |  | Granted | 270 | 0 | 270 | Ananthapuram-II | Andhra Pradesh | 2026-01-12 | 2027-10-18 | • Generation Station of Ms Hero Solar Energy Pvt. Ltd. – Ananthapuram-II PS 220 kV Sc line on Dc tower* along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Ananthapuram-II PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission System for Integration of Anan | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Part of Transmission System for Anantapur-II REZ – (Phase-II) | 31-May-27 | 31-May-27 |  |  | 270 |  |  |  |  | 2027-10-17 | 2027-10-17 | 2027-10-17 |  | Not effective | 2027-10-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 220.00 ¦ Date: 2027-10-18 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 52.80 ¦ Date: 2027-10-18 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 5.00 ¦ Date: 2027-10-18 ¦ Status: Under Implementation ¦ Type: Standalone | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-May-27 |  | 2027-05-31 | 2028-04-18
2200001301 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Mandsaur (Sec-II) | Madhya Pradesh | 2025-12-31 | 2027-03-31 | • NTPC REL-Mandsaur 400kV Sc line along with associated bays at the generation end (Under the scope of Ms NTPC REL). • 1 no. 400kV line bay (on Bus Section-II) at Mandsaur PS is being implemented under ISTS under “Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur Ss for RE Interconnection scheme” | 1 | 400 KV | Aug without ATS |  |  | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x5 | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line Rajasthan REZ Ph-V (Part-1 4 GW) [SirohiNagaur] Complex (SCOD 24.03.2027) (Rajasthan V Power Transmission Limited – POWERGRID) • Mandsaur PS – Khandwa (New) 765 kV Dc line Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur Ss for RE Interconnection (SCOD 24.03.2027) (Mandsaur I RE Transmission Limited - Ms Power Grid Corporation of India Limited) • Creation of New 400kV & 765kV Bus Sections through Sectionaliser arrangement • Augmentation of Transformation capacity by 1x1500MVA, 765400kV ICT (4th) (Terminated at 400kV & 765kV Bus Section-II) | 30-Mar-27 | 30-Mar-27 |  |  | 300 |  |  |  |  | 2027-03-31 | 2027-03-24 | 2027-06-30 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Mar-27 |  | 2027-03-30 | 2027-09-30
2200001303 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ananthapuram-II | Andhra Pradesh | 2026-01-12 | 2028-04-18 | • Generation Station of M/s NTPC Renewable Energy Ltd.– Ananthapuram-II PS 400 kV S/c line along with line bay at generation PS – under the scope of applicant • 1 no. 400 kV line bay at Ananthapuram-II PS for above DTL – under the scope of ISTS. | 1 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Transmission System for Anantapur-II REZ – (Phase-II) | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Transmission System for Anantapur-II REZ – (Phase-II) | 31-Mar-27 | 31-Mar-27 |  |  | 300 |  |  |  |  | 2027-10-17 | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-04-18 ¦ Status: Under Implementation ¦ Type: Solar | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-10-18
2200001304 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ananthapuram-II | Andhra Pradesh | 2026-01-12 | 2028-04-18 | • Through sharing of dedicated connectivity transmission system of M/s NTPC Renewable Energy Ltd. Granted for application no. 2200001303 i.e Generation Station of M/s NTPC Renewable Energy Ltd. – Ananthapuram-II PS 400 kV S/c line along with line-all arrangement under the scope of applicant | 0 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Transmission System for Anantapur-II REZ – (Phase-II) | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Transmission System for Anantapur-II REZ – (Phase-II) | 31-Mar-27 | 31-Mar-27 |  |  | 300 |  |  |  |  | 2027-10-17 | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-04-18 ¦ Status: Under Implementation ¦ Type: Solar | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-10-18
2200001318 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ananthapuram-II | Andhra Pradesh | 2026-01-13 | 2028-04-18 | • Generation Station of M/s NTPC Renewable Energy Ltd.– Ananthapuram-II PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Ananthapuram-II PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Transmission System for Anantapur-II REZ – (Phase-II) | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Transmission System for Anantapur-II REZ – (Phase-II) | 30-Jun-27 | 30-Jun-27 |  |  | 300 |  |  |  |  | 2028-04-17 | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-04-18 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  |  | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2028-10-18
2200001319 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ananthapuram-II | Andhra Pradesh | 2026-01-13 | 2028-04-18 | •Through dedicated connectivity transmission system of M/s NTPC Renewable Energy Ltd. Granted for application no. 2200001303 i.e Generation Station of M/s NTPC Renewable Energy Ltd. – Ananthapuram-II PS 400 kV S/c line along with line-all arrangement under the scope of applicant | 1 | 400 kV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Transmission System for Anantapur-II REZ – (Phase-II) | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Transmission System for Anantapur-II REZ – (Phase-II) | 31-Mar-27 | 31-Mar-27 |  |  | 300 | [5 empty] | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-04-18 ¦ Status: Under Implementation ¦ Type: Solar | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-10-18
2200001321 | Main-Connectivity under GNA |  | TEQ GREEN POWER XX PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Pavagada | Karnataka | 2025-12-24 | 2027-03-16 | • Generation Station of M/s TEQ Green Power XX Pvt. Ltd.– Tumkur (Pavagada) PS 220 kV S/c line on D/c tower* along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Tumkur (Pavagada) PS for above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 2x500 MVA, 400/220 kV (9th-10th) ICT at Tumkur (Pavagada) PS | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 2x500 MVA, 400/220 kV (9th-10th) ICT at Tumkur (Pavagada) PS | 150 MW 30.03.27150 MW 30.06.27 | Phase 1 ¦ MW: 150.00 ¦ Date: 2027-03-30 Phase 2 ¦ MW: 150.00 ¦ Date: 2027-06-30 |  |  | 300 | 233 |  |  |  |  | 2026-05-20 | 2026-12-31 |  | Not effective | 2027-03-16 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-15 ¦ Status: Under Implementation ¦ Type: | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 150.00 ¦ Date: 2027-03-30 | 150 | 2027-03-30 | 2027-09-30
2200001321 | Main-Connectivity under GNA |  | TEQ GREEN POWER XX PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Pavagada | Karnataka | 2025-12-24 | 2027-03-16 | • Generation Station of M/s TEQ Green Power XX Pvt. Ltd.– Tumkur (Pavagada) PS 220 kV S/c line on D/c tower* along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Tumkur (Pavagada) PS for above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 2x500 MVA, 400/220 kV (9th-10th) ICT at Tumkur (Pavagada) PS | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 2x500 MVA, 400/220 kV (9th-10th) ICT at Tumkur (Pavagada) PS | 150 MW 30.03.27150 MW 30.06.27 | Phase 1 ¦ MW: 150.00 ¦ Date: 2027-03-30 Phase 2 ¦ MW: 150.00 ¦ Date: 2027-06-30 |  |  | 300 | 233 |  |  |  |  | 2026-05-20 | 2026-12-31 |  | Not effective | 2027-03-16 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-15 ¦ Status: Under Implementation ¦ Type: | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 150.00 ¦ Date: 2027-06-30 | 150 | 2027-06-30 | 2027-12-30
2200001325 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 47 | 0 | 47 | 0 | 0 | 47 |  | Granted | 47 | 0 | 47 | Pachora (Sec-III) | Madhya Pradesh | 2026-01-07 | 2027-09-29 | Ms AEPL shall share the DTL along with associated bay proposed for AEPL for its 240MW SPP against application no. 2200000956. • AEPL – Pachora PS 220kV Sc line (on Dc tower) along with 220kV line bay at generation station (Under the scope of Ms AEPL). • 1 no. 220kV line bay on Bus Section-III at Pachora PS is being implemented under ISTS as a part of Rajgarh Phase-III transmission scheme. | 0 | 220 KV | Aug without ATS |  |  | 1. Transmission System for Evacuation of Power from RE Projects in Rajgarh (1000MW) SEZ in Madhya Pradesh Phase- II (SCOD 14.02.2026) (Pachora Power Transmission Limited. -G R InfraProjects Ltd.) • 400220kV, 3x500MVA ICT augmentation (4th, 5th and 6th | 1. Transmission System for Evacuation of Power from RE Projects in Rajgarh (1000MW) SEZ in Madhya Pradesh Phase- II (SCOD 14.02.2026) (Pachora Power Transmission Limited. -G R InfraProjects Ltd.) • 400220kV, 3x500MVA ICT augmentation (4th, 5th and 6th) at Pachora PS. • Pachora PS – Ujjain (MPPTCL) 400 kV Dc line (Quad ACSRAAACAL59 Moose equivalent) along with associated bays at both ends. 2. Transmission system for Evacuation of Power from RE Projects in Rajgarh (1500 MW) SEZ in Madhya Pradesh-Phase III and Evacuation of Power from RE Projects in Neemuch (1000 MW) SEZ in Madhya Pradesh-Phase II(Part System) (SCOD 29.09.2027)( Ms Rajgarh Neemuch Power Transmission Limited -G R Infraprojects. Ltd.) • Creation of New 220kV Bus Section (3rd) with 220kV Bus Sectionaliser. • Augmentation of transformation capacity by 400220kV, 3x500 MVA ICTs (7th, 8th & 9th ) at Pachora PS to be terminated on 220kV Bus Section (3rd). • Pachora PS – Rajgarh (PG) 400 kV Dc line (Quad ACSR AAAC AL59 Moose equivalent) along with associated bays at both ends. • Installation of 1x125 MVAR, 420 kV bus reactor at Pachora PS (400kV Bus Section-II). | 30-Jun-27 | 30-Jun-27 |  |  | 47 |  |  |  |  | 2027-09-29 | 2027-09-29 | 2027-09-29 |  | Not effective | 2027-09-29 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 47.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2028-03-29
2200001341 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ananthapuram-II | Andhra Pradesh | 2026-01-12 | 2028-04-18 | • Generation Station of M/s NTPC Renewable Energy Ltd.– Ananthapuram-II PS 220 kV S/c line along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Ananthapuram-II PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Transmission System for Anantapur-II REZ – (Phase-II) | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere/ Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Transmission System for Anantapur-II REZ – (Phase-II) | 31-Mar-27 | 31-Mar-27 |  |  | 300 |  |  |  |  | 2028-04-17 | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-12-13 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-10-18
2200001356 | Main-Connectivity under GNA |  | Jindal Green Private Limited (Formerly known as JSP GREEN PRIVATE LIMITED) | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 350 |  | 0 | 350 | 0 | 350 |  | Granted | 350 | 0 | 350 | Mandsaur (Sec-III) | Madhya Pradesh | 2026-01-07 | 2027-06-15 | • JSPGPL -Mandsaur 220kV Sc line on Dc tower along with associated bays at the generation end (Under the scope of Ms JSPGPL). • 1 no. 220kV line bay at Mandsaur PS (220kV New Bus Section-3) is being implemented under ISTS by Mandsaur I RE Transmission Limited. | 1 | 220 KV | Aug without ATS |  |  | Under Implementation 1) Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & | Under Implementation 1) Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line 2) Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line 3) Rajasthan REZ Ph-V (Part-1 4 GW) [SirohiNagaur] Complex (SCOD 24.03.2027) (Rajasthan V Power Transmission Limited – POWERGRID) • Mandsaur PS – Khandwa (New) 765 kV Dc line 4) Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur Ss for RE Interconnection (part system) (SCOD 15.06.2027) (Mandsaur I RE Transmission Limited - POWERGRID) • Creation of New 400kV & 765kV Bus Sections-II through Sectionaliser arrangement at Mandsaur PS. • Augmentation of Transformation capacity by 1x1500MVA, 765400kV ICT (4th) (Terminated at 400kV & 765kV Bus Section-II) at Mandsaur PS. • Creation of New 220kV Bus Section-3 with Sectionaliser arrangement at Mandsaur PS. • Augmentation of Transformation capacity by 1x500MVA, 400220kV ICT (6th) (Terminated on 400kV Bus Section-I & 220kV Bus Section-II) and 1x500MVA, 400220kV ICT (7th) (Terminated on 400kV Bus Section-II & 220kV Bus Section-III) at Mandsaur PS. | 15-Jun-27 | 15-Jun-27 |  |  | 350 |  |  |  |  | 2027-06-15 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-15 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 350.00 ¦ Date: 2027-05-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 15-Jun-27 |  | 2027-06-15 | 2027-12-15
2200001362 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Kurnool-IV | Andhra Pradesh | 2026-03-19 | 2028-05-30 | • Generation Station of Ms NTPC Renewable Energy Ltd.– Kurnool-IV PS 400 kV Sc line along with line bay at generation PS – under the scope of applicant • 1 no. 400 kV line bay at Kurnool-IV PS for above DTL – under the scope of ISTS. | 1 | 400 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Part of Transmission System for Integration of Ku | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Part of Transmission System for Integration of Kurnool-IV PS (Phase-II) | 30-Jun-27 | 30-Jun-27 |  |  | 300 | [5 empty] | 2028-05-29 | 2028-05-29 |  | Not effective | 2028-05-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2028-11-30
2200001363 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 600 |  | 600 | 0 | 0 | 600 |  | Granted | 600 | 0 | 600 | Kurnool-IV | Andhra Pradesh | 2026-03-19 | 2028-05-30 | •Through dedicated connectivity transmission system proposed for Ms NTPC Renewable Energy Limited for application no. 2200001362 i.e. Generation Station of Ms NTPC Renewable Energy Ltd. – Kurnool-IV PS 400 kV Sc line – all arrangement under the scope of applicant | 0 | 400 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Part of Transmission System for Integration of Kur | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Part of Transmission System for Integration of Kurnool-IV PS (Phase-II) | 30-Jun-27 | 30-Jun-27 |  |  | 600 | [5 empty] | 2028-05-29 | 2028-05-29 |  | Not effective | 2028-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2028-11-30
2200001364 | Main-Connectivity under GNA |  | ESSAR RENEWABLES LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 | NHPC | Granted | 300 | 0 | 300 | Kurnool-IV | Andhra Pradesh | 2026-03-19 | 2028-05-30 | •Generation Station of Ms Essar Renewables Ltd.– Kurnool-IV PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant •1 no. 220 kV line bay at Kurnool-IV PS for above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Part of Transmission System for Integration of Kur | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Part of Transmission System for Integration of Kurnool-IV PS (Phase-II) | 09-Feb-27 | 09-Feb-27 |  |  | 300 | 242 |  |  |  |  | 2028-05-29 | 2028-05-29 |  | Not effective | 2028-05-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-03-29 ¦ Status: Under Implementation ¦ Type: Solar | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 09-Feb-27 |  | 2027-02-09 | 2028-05-30
2200001383 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Kurnool-IV | Andhra Pradesh | 2026-03-19 | 2028-05-30 | • Generation Station of Ms NTPC Renewable Energy Ltd.– Kurnool-IV PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Kurnool-IV PS for above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Part of Transmission System for Integration of Ku | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Part of Transmission System for Integration of Kurnool-IV PS (Phase-II) | 30-Jun-27 | 30-Jun-27 |  |  | 300 | [5 empty] | 2028-05-29 | 2028-05-29 |  | Not effective | 2028-05-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2028-11-30
2200001384 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Kurnool-IV | Andhra Pradesh | 2026-03-19 | 2028-05-30 | • Generation Station of Ms NTPC Renewable Energy Ltd.– Kurnool-IV PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Kurnool-IV PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Part of Transmission System for Integration of Ku | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Part of Transmission System for Integration of Kurnool-IV PS (Phase-II) | 30-Jun-27 | 30-Jun-27 |  |  | 300 | [6 empty] | 2028-05-29 |  | Not effective | 2028-05-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2028-11-30
2200001416 | Main-Connectivity under GNA |  | HERO SOLAR ENERGY PRIVATE LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | Solar: 130 MW Wind: 151.8 MW BESS: 30 MW |  | 130 | 151.8 | 30 | 311.8 | SJVN | Granted | 270 | 0 | 270 | Ananthapuram-II | Andhra Pradesh | 2026-01-12 | 2028-04-18 | • Generation Station of Ms Hero Solar Energy Pvt. Ltd. – Ananthapuram-II PS 220 kV Sc line on Dc tower* along with line bay at generation PS – under the scope of applicant • 1 no. 220 kV line bay at Ananthapuram-II PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission System for Integration of Anan | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission System for Integration of Ananthapuram-II REZs (Phase-I) • Transmission System for Anantapur-II REZ – (Phase-II) | 30-Apr-27 | 30-Apr-27 |  |  | 270 |  |  |  |  | 2028-04-17 | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 130.00 ¦ Date: 2028-04-18 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 151.80 ¦ Date: 2028-04-18 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 3 ¦ MW: 30.00 ¦ Date: 2028-04-18 ¦ Status: Under Implementation ¦ Type: Standalone | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 30-Apr-27 |  | 2027-04-30 | 2028-04-18
2200001421 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 350 |  | 0 | 350 | 0 | 350 | SJVN | Granted | 350 | 0 | 350 | Ishanagar | Madhya Pradesh | 2026-01-01 | 2027-06-30 | • AEPL – Ishanagar 400kV Sc line (on Dc tower) along with associated bays at the generation end (Under the scope of Ms AEPL). • 1 no. 400kV line bay at Ishanagar PS is to be implemented under ISTS by Ms IPTL. | 1 | 400 KV | Aug without ATS |  |  | Under Implementation (ISTS) Western Region Expansion Scheme XXXIII (WRES - XXXIII) Part C” project by Ms IndiGrid 1 Ltd. and IndiGrid 2 Ltd. (Consortium) • Establishment of 2x1500 MVA, 765400 kV and 2x500 MVA, 400220kV Ishanagar (New) Ss. • LILO of one | Under Implementation (ISTS) Western Region Expansion Scheme XXXIII (WRES - XXXIII) Part C” project by Ms IndiGrid 1 Ltd. and IndiGrid 2 Ltd. (Consortium) • Establishment of 2x1500 MVA, 765400 kV and 2x500 MVA, 400220kV Ishanagar (New) Ss. • LILO of one ckt of Jabalpur - Orai 765kV Dc line at Ishanagar (New) Ss. Under Implementation (ISTS) Western Region Expansion Scheme XXXIII (WRES - XXXIII) Part C” project by Ms IndiGrid 1 Ltd. and IndiGrid 2 Ltd. (Consortium) • Establishment of 2x1500 MVA, 765400 kV and 2x500 MVA, 400220kV Ishanagar (New) Ss. • LILO of one ckt of Jabalpur - Orai 765kV Dc line at Ishanagar (New) Ss. | 30-Jun-27 | 30-Jun-27 |  |  | 350 | 410M & 411T |  |  |  | 2027-06-30 | 2026-02-09 | 2026-08-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 350.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 | Yes |  |  | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-06-30
2200001431 | Main-Connectivity under GNA |  | TEQ GREEN POWER XXII PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 250 (200 MW Wind, 50 MW Solar) | 0 | 50 | 200 | 0 | 250 |  | Granted | 250 | 0 | 250 | Mandsaur (Sec-III) | Madhya Pradesh | 2026-01-01 | 2028-03-30 | • TGP XXIIPL -Mandsaur 220kV Sc line (on Dc tower) along with associated bays at the generation end (Under the scope of Ms TGP22PL). • 1 no. 220kV line bay at Mandsaur PS (220kV New Bus Section-3) is being implemented under ISTS. | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x5 | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line Rajasthan REZ Ph-V (Part-1 4 GW) [SirohiNagaur] Complex (SCOD 24.03.2027) (Rajasthan V Power Transmission Limited – POWERGRID) • Mandsaur PS – Khandwa (New) 765 kV Dc line Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur Ss for RE Interconnection (SCOD 15.06.2027) (Mandsaur I RE Transmission Limited - Ms Power Grid Corporation of India Limited) • Creation of New 400kV & 765kV Bus Sections through Sectionaliser arrangement • Augmentation of Transformation capacity by 1x1500MVA, 765400kV ICT (4th) (Terminated at 400kV & 765kV Bus Section-II) • Creation of New 220kV Bus Section-3 with Sectionaliser arrangement at Mandsaur PS. • Augmentation of Transformation capacity by 1x500MVA, 400220kV ICT (6th) (Terminated on 400kV Bus Section-I & 220kV Bus Section-II) and 1x500MVA, 400220kV ICT (7th) (Terminated on 400kV Bus Section-II & 220kV Bus Section-III) at Mandsaur PS. | 200 MW 31.03.2028, 50 MW 31.10.2028 | Phase 1 ¦ MW: 200.00 ¦ Date: 2028-03-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2028-10-31 |  |  | 250 |  |  |  |  | 2028-03-30 | 2026-10-15 | 2027-06-15 |  | Not effective | 2028-03-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-03-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2028-03-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | Phase 1 ¦ MW: 200.00 ¦ Date: 2028-03-31 | 200 | 2028-03-31 | 2028-09-30
2200001431 | Main-Connectivity under GNA |  | TEQ GREEN POWER XXII PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 250 (200 MW Wind, 50 MW Solar) | 0 | 50 | 200 | 0 | 250 |  | Granted | 250 | 0 | 250 | Mandsaur (Sec-III) | Madhya Pradesh | 2026-01-01 | 2028-03-30 | • TGP XXIIPL -Mandsaur 220kV Sc line (on Dc tower) along with associated bays at the generation end (Under the scope of Ms TGP22PL). • 1 no. 220kV line bay at Mandsaur PS (220kV New Bus Section-3) is being implemented under ISTS. | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x5 | Under Implementation Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part C (SCOD 19.08.2026) (Rajasthan IV C Power Transmission Ltd. – POWERGRID) • Establishment of 3x1500MVA, 765400kV & 5x500MVA, 400220kV Mandsaur PS along with 2x330MVAR (765kV) Bus Reactor & 2x125MVAR, 420kV Bus Reactor. • Mandsaur PS – Indore ((PG) 765 kV Dc Line Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-25.5 GW) (JaisalmerBarmer Complex) Part H1 (SCOD 15.10.2026) (Rajasthan IV H1 Power Transmission Ltd. – POWERGRID) • Establishment of 765400kV (2x1500MVA), 400220kV (2x500MVA) & 220132 kV (3x200 MVA) Kurawar Ss along with 2x330 MVAR 765kV bus reactor and 1x125MVAR, 420kV bus reactor. • Mandsaur – Kurawar 765 kV Dc line • LILO of Indore – Bhopal 765 kV Sc line at Kurawar • Kurawar – Ashtha 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line • LILO of one circuit of Indore – Itarsi 400 kV D c line at Astha • Shujalpur – Kurawar 400 kV Dc (Quad ACSRAAACAL59 moose equivalent) line Rajasthan REZ Ph-V (Part-1 4 GW) [SirohiNagaur] Complex (SCOD 24.03.2027) (Rajasthan V Power Transmission Limited – POWERGRID) • Mandsaur PS – Khandwa (New) 765 kV Dc line Augmentation of Transformation Capacity and Implementation of line bays at Mandsaur Ss for RE Interconnection (SCOD 15.06.2027) (Mandsaur I RE Transmission Limited - Ms Power Grid Corporation of India Limited) • Creation of New 400kV & 765kV Bus Sections through Sectionaliser arrangement • Augmentation of Transformation capacity by 1x1500MVA, 765400kV ICT (4th) (Terminated at 400kV & 765kV Bus Section-II) • Creation of New 220kV Bus Section-3 with Sectionaliser arrangement at Mandsaur PS. • Augmentation of Transformation capacity by 1x500MVA, 400220kV ICT (6th) (Terminated on 400kV Bus Section-I & 220kV Bus Section-II) and 1x500MVA, 400220kV ICT (7th) (Terminated on 400kV Bus Section-II & 220kV Bus Section-III) at Mandsaur PS. | 200 MW 31.03.2028, 50 MW 31.10.2028 | Phase 1 ¦ MW: 200.00 ¦ Date: 2028-03-31 Phase 2 ¦ MW: 50.00 ¦ Date: 2028-10-31 |  |  | 250 |  |  |  |  | 2028-03-30 | 2026-10-15 | 2027-06-15 |  | Not effective | 2028-03-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-03-30 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2028-03-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | Phase 2 ¦ MW: 50.00 ¦ Date: 2028-10-31 | 50 | 2028-10-31 | 2029-04-30
2200001463 | Main-Connectivity under GNA |  | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 | NHPC | Granted | 300 | 0 | 300 | Ishanagar | Madhya Pradesh | 2025-12-31 | 2027-06-30 | AEPL shall share the DTL proposed for its other WPP (2200001421 at Ishanagr) as given below • AEPL – Ishanagar 400kV Sc line along with associated bays at the generation end (Under the scope of Ms AEPL). •1 no. 400kV line bay at Ishanagar PS is being implemented under ISTS by Ms Ishanagar Power Transmission Ltd. (IPTL) (Subsidiary of Indigrid 2 Pvt Ltd.) | 0 | 400 KV | Aug without ATS |  |  | Under Implementation (ISTS) Western Region Expansion Scheme XXXIII (WRES - XXXIII) Part C” project by Ms IndiGrid 1 Ltd. and IndiGrid 2 Ltd. (Consortium) • Establishment of 2x1500 MVA, 765400 kV and 2x500 MVA, 400220kV Ishanagar (New) Ss. • LILO of one | Under Implementation (ISTS) Western Region Expansion Scheme XXXIII (WRES - XXXIII) Part C” project by Ms IndiGrid 1 Ltd. and IndiGrid 2 Ltd. (Consortium) • Establishment of 2x1500 MVA, 765400 kV and 2x500 MVA, 400220kV Ishanagar (New) Ss. • LILO of one ckt of Jabalpur - Orai 765kV Dc line at Ishanagar (New) Ss. | 30-Jun-27 | 30-Jun-27 |  |  | 300 | 410M & 411T |  |  |  | 2027-06-30 | 2026-02-09 | 2026-08-31 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 | No |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-06-30
2200001482 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Kurnool-IV | Andhra Pradesh | 2026-03-19 | 2028-05-30 | • Generation Station of Ms Tata Power Renewable Energy Ltd – Kurnool-IV PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Kurnool-IV PS for termination of above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool- | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 31-Mar-27 | 31-Mar-27 |  |  | 300 | [5 empty] | 2028-05-29 | 2028-05-29 |  | Not effective | 2028-05-30 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-11-30
2200001484 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 400 |  | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Ananthapuram-II | Andhra Pradesh | 2026-01-13 | 2028-04-18 | • Generation Station of Ms Tata Power Renewable Energy Ltd – Anantapur-II PS 220 kV Sc line on Dc tower* [through stringing of both arms of Dc towers and bunching both arms at each end to form single circuit for terminating in one bay] along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Anantapur-II PS for termination of above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ •Transmission System for Integration o | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ •Transmission System for Integration of Anantapur-II REZs (Phase-I) Transmission System for Anantapur-II REZ - Phase-II details as per Annexure-IV | 31-Mar-27 | 31-Mar-27 |  |  | 400 |  |  |  |  | 2028-04-17 | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2028-04-18 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-10-18
2200001502 | Main-Connectivity under GNA |  | SINDHARI SOLAR POWER PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ananthapuram-II | Andhra Pradesh | 2026-06-30 | 2028-04-18 | •Generation Station of Ms Sindhari Solar Power Private Limited – Anantapur-II PS 220 kV Sc line on Dc tower along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Anantapur-II PS for termination of above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission system for integration of Davanagere Chitradurga REZ •Transmission System for Integration of Anantap | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission system for integration of Davanagere Chitradurga REZ •Transmission System for Integration of Anantapur-II REZs (Phase-I) details as per Annexure-III •Transmission System for Anantapur-II REZ - Phase-II | 31-Dec-27 | 31-Dec-27 |  |  | 300 | [5 empty] | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2028-10-18
2200001514 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Dhule (Sec-II) | Maharashtra | 2026-01-02 | 2027-06-30 | • NTPC REL – Dhule PS 220kV Sc line (on Dc tower) along with associated bay at the generation end (under the scope of applicant). • 1 No. 220kV bay (Sec-II) at Dhule PS end is being implemented under ISTS as part of Pooling Station by Ms Dhule Power Transmission Limited (subsidiary of IndiGrid 2 Pvt Ltd.) | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Transmission scheme for evacuation of power from Dhule 2 GW REZ (SCOD09.02.2026) (Ms Dhule Power Transmission Limited) • Establishment of 4x500 MVA, 400220 kV Pooling Station at Dhule PS. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line | Under Implementation Transmission scheme for evacuation of power from Dhule 2 GW REZ (SCOD09.02.2026) (Ms Dhule Power Transmission Limited) • Establishment of 4x500 MVA, 400220 kV Pooling Station at Dhule PS. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAACAL59 Moose equivalent (60 km). | 30-Jun-27 | 30-Jun-27 |  |  | 300 | 217 |  |  |  | 2026-10-30 | 2026-02-09 | 2026-10-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-12-30
2200001515 | Main-Connectivity under GNA |  | ESSAR RENEWABLES LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 175 | 0 | 0 | 175 | 0 | 175 | NHPC | Granted | 175 | 0 | 175 | Ananthapuram-II | Andhra Pradesh | 2026-01-13 | 2028-04-18 | • Generation Station of Ms Essar Renewables Ltd. – Anantapur-II PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Anantapur-II PS for termination of above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission System for Integration of Anan | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission system for integration of Davanagere Chitradurga REZ • Transmission System for Integration of Anantapur-II REZs (Phase-I) • Transmission System for Integration of Anantapur-II REZs (Phase-II) | 8-Apr-27 | 8-Apr-27 |  | 2028-04-18 | 175 |  |  |  |  | 2028-04-17 | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 175.00 ¦ Date: 2028-04-15 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 8-Apr-27 |  | 2027-04-08 | 2028-04-18
2200001519 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Dhule (Sec-II) | Maharashtra | 2026-01-02 | 2027-06-30 | NTPC REL – Dhule PS 220kV Sc line (on Dc tower) along with associated bay at the generation end (under the scope of applicant). • 1 No. 220kV bay (Sec-II) at Dhule PS end is being implemented under ISTS as part of Pooling Station by Ms Dhule Power Transmission Limited (subsidiary of IndiGrid 2 Pvt Ltd.) | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Transmission scheme for evacuation of power from Dhule 2 GW REZ (SCOD09.02.2026) (Ms Dhule Power Transmission Limited) • Establishment of 4x500 MVA, 400220 kV Pooling Station at Dhule PS. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line | Under Implementation Transmission scheme for evacuation of power from Dhule 2 GW REZ (SCOD09.02.2026) (Ms Dhule Power Transmission Limited) • Establishment of 4x500 MVA, 400220 kV Pooling Station at Dhule PS. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAACAL59 Moose equivalent (60 km). | 30-Jun-27 | 30-Jun-27 |  |  | 300 | 213 |  |  |  | 2026-10-30 | 2026-02-09 | 2026-10-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2027-12-30
2200001524 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ananthapuram-III | Andhra Pradesh | 2026-07-14 |  | • Generation Station of Ms Tata Power Renewable Energy Limited – Ananthapuram-III PS 220 kV Sc line on Dc tower along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Ananthapuram-III PS for above DTL – under the scope of ISTS.[under implementation as part of “Transmission System for Integration of Anantapur-III REZ (Phase-I)”] | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Krishnagiri REZ Phase-I •Transmission System for Integration of Anantapur-III REZ (Phase-I) | 31-Mar-27 | 31-Mar-27 |  |  | 300 | [8 empty] | Not effective | 2029-08-01 | [8 empty] | Not Submitted For Approval | 31-Mar-27 |  | 2027-03-31 | 2027-09-30
2200001535 | Main-Connectivity under GNA |  | JUNIPER GREEN GEM PRIVATE LIMITED | WR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Dhule (Sec-I) | Maharashtra | 2026-01-05 | 2028-06-30 | JGGPL shall share the DTL agreed for grant of connectivity to its other SPP of 100MW at Dhule PS (2200001276) as given below • JGGPL – Dhule PS (Sec-I) 220kV Sc (on Dc tower) line along with associated bays at generation end (Under scope of JGGPL). • 1 no. 220kV line bay at Dhule PS is being implemented under ISTS as a part of the Pooling Station by Ms Dhule Power Transmission Limited (subsidiary of IndiGrid 2 Pvt Ltd.) | 0 | 220 KV | Aug without ATS |  |  | Under Implementation Transmission scheme for evacuation of power from Dhule 2 GW REZ (SCOD09.02.2026) (Ms Dhule Power Transmission Limited) • Establishment of 4x500 MVA, 400220 kV Pooling Station at Dhule PS. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line | Under Implementation Transmission scheme for evacuation of power from Dhule 2 GW REZ (SCOD09.02.2026) (Ms Dhule Power Transmission Limited) • Establishment of 4x500 MVA, 400220 kV Pooling Station at Dhule PS. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAACAL59 Moose equivalent (60 km). | 30-Jun-28 | 30-Jun-28 |  |  | 200 |  |  |  |  | 2026-10-30 | 2026-02-09 | 2026-10-30 |  | Not effective | 2028-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-06-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-28 |  | 2028-06-30 | 2028-12-30
2200001540 | Main-Connectivity under GNA |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 1000(Wind- 334 MW, Solar- 666 MW) | 0 | 666 | 334 | 0 | 1000 |  | Granted | 465 | 0 | 465 | Ananthapuram-II | Andhra Pradesh | 2026-06-30 | 2028-04-18 | • Generation Station of Ms Waaree Forever Energies Pvt. Ltd. – Ananthapuram-II PS 220 kV Dc line along with line bay at generation PS –under the scope of applicant. • 2 nos. 220 kV line bay at Ananthapuram-II PS for termination of above DTL – under the scope of ISTS. | 2 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthing between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthing between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission System for Integration of Anantapur-II REZs (Phase-I) •Transmission System for Anantapur-II REZ - Phase-II | 300MW 31-03-2027; 300MW 30-09-2027;400MW 31-12-2027; | Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 Phase 2 ¦ MW: 300.00 ¦ Date: 2027-09-30 Phase 3 ¦ MW: 400.00 ¦ Date: 2027-12-31 |  |  | 465 | [5 empty] | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 | 300 | 2027-03-31 | 2028-10-18
2200001540 | Main-Connectivity under GNA |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 1000(Wind- 334 MW, Solar- 666 MW) | 0 | 666 | 334 | 0 | 1000 |  | Granted | 465 | 0 | 465 | Ananthapuram-II | Andhra Pradesh | 2026-06-30 | 2028-04-18 | • Generation Station of Ms Waaree Forever Energies Pvt. Ltd. – Ananthapuram-II PS 220 kV Dc line along with line bay at generation PS –under the scope of applicant. • 2 nos. 220 kV line bay at Ananthapuram-II PS for termination of above DTL – under the scope of ISTS. | 2 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthing between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthing between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission System for Integration of Anantapur-II REZs (Phase-I) •Transmission System for Anantapur-II REZ - Phase-II | 300MW 31-03-2027; 300MW 30-09-2027;400MW 31-12-2027; | Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 Phase 2 ¦ MW: 300.00 ¦ Date: 2027-09-30 Phase 3 ¦ MW: 400.00 ¦ Date: 2027-12-31 |  |  | 465 | [5 empty] | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 300.00 ¦ Date: 2027-09-30 | 300 | 2027-09-30 | 2028-10-18
2200001540 | Main-Connectivity under GNA |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 1000(Wind- 334 MW, Solar- 666 MW) | 0 | 666 | 334 | 0 | 1000 |  | Granted | 465 | 0 | 465 | Ananthapuram-II | Andhra Pradesh | 2026-06-30 | 2028-04-18 | • Generation Station of Ms Waaree Forever Energies Pvt. Ltd. – Ananthapuram-II PS 220 kV Dc line along with line bay at generation PS –under the scope of applicant. • 2 nos. 220 kV line bay at Ananthapuram-II PS for termination of above DTL – under the scope of ISTS. | 2 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthing between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthing between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission System for Integration of Anantapur-II REZs (Phase-I) •Transmission System for Anantapur-II REZ - Phase-II | 300MW 31-03-2027; 300MW 30-09-2027;400MW 31-12-2027; | Phase 1 ¦ MW: 300.00 ¦ Date: 2027-03-31 Phase 2 ¦ MW: 300.00 ¦ Date: 2027-09-30 Phase 3 ¦ MW: 400.00 ¦ Date: 2027-12-31 |  |  | 465 | [5 empty] | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | Phase 3 ¦ MW: 400.00 ¦ Date: 2027-12-31 | 400 | 2027-12-31 | 2028-10-18
2200001544 | Main-Connectivity under GNA |  | ESSAR RENEWABLES LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Solar | 360 |  | 360 | 0 | 220 | 580 | NHPC | Granted | 360 | 0 | 360 | Kurnool-IV | Andhra Pradesh | 2026-03-19 | 2028-05-30 | • Generation Station of Ms ESSAR Renewables Limited – Kurnool-IV PS 220 kV Sc line on Dc tower* [stringing of both arms of Dc tower and bunching at both ends to integrate the line in single 220 kV line bay at both ends] along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Kurnool-IV PS for termination of above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool- | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV PS (Phase-I), • Transmission System for Integration of Kurnool-IV PS (Phase-II) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 8-Apr-27 | 8-Apr-27 |  |  | 360 | [6 empty] | 2028-05-29 |  | Not effective | 2028-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 360.00 ¦ Date: 2028-03-29 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 220.00 ¦ Date: 2028-03-29 ¦ Status: Under Implementation ¦ Type: Standalone | 08.07.2026 |  |  |  | Pending with Level 2 | 8-Apr-27 |  | 2027-04-08 | 2028-05-30
2200001584 | Main-Connectivity under GNA |  | ADYANT ENERSOL PRIVATE LIMITED | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 94 MW (70 MW Solar + 24 MW Wind) |  | 70 | 24 | 0 | 94 | SJVN | Granted | 94 | 0 | 94 | Dhule (Sec-I) | Maharashtra | 2026-01-02 | 2027-05-04 | • AdEPL - Dhule PS 220kV Sc line along with associated bay at the generation end (under the scope of applicant). • 1 No. 220kV bay (on Sec-I) at Dhule PS end (to be taken up under ISTS) | 1 | 220 KV | Aug without ATS |  |  | Under Implementation Transmission scheme for evacuation of power from Dhule 2 GW REZ (SCOD09.02.2026) (Ms Dhule Power Transmission Limited) • Establishment of 4x500 MVA, 400220 kV Pooling Station at Dhule PS. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line | Under Implementation Transmission scheme for evacuation of power from Dhule 2 GW REZ (SCOD09.02.2026) (Ms Dhule Power Transmission Limited) • Establishment of 4x500 MVA, 400220 kV Pooling Station at Dhule PS. • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAACAL59 Moose equivalent (60 km). | 31-Mar-27 | 31-Mar-27 |  |  | 94 |  |  |  |  | 2027-05-04 | 2026-02-09 | 2026-10-30 |  | Not effective | 2027-05-04 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 70.00 ¦ Date: 2027-05-04 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 24.00 ¦ Date: 2027-05-04 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2027-05-04
2200001588 | Main-Connectivity under GNA |  | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 400 (Solar- 200; Wind- 200) |  | 200 | 200 | 0 | 400 |  | Granted | 300 | 0 | 300 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2028-05-30 | •Generation Station of Ms Serentica Renewables India Private Limited – Kurnool-IV PS 220 kV Sc on Dc Tower line along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV terminal line bay at Kurnool-IV PS for above DTL –under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Trans | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for Integration of Kurnool-IV PS (Phase-I) as per Annexure-II •Part of Transmission System for Integration of Kurnool-IV PS (Phase-II) as per Annexure-III | 30-Jun-27 | 30-Jun-27 |  |  | 300 | [6 empty] | 2028-05-29 |  | Not effective | 2028-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2028-05-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 200.00 ¦ Date: 2028-05-30 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2028-11-30
2200001621 | Main-Connectivity under GNA |  | SAEL INDUSTRIES LIMITED | WR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Solar | 150 (Solar: 150, BESS: 75) |  | 150 | 0 | 75 | 225 |  | Granted | 150 | 0 | 150 | Dhule (Sec-I) | Maharashtra | 2026-01-02 | 2027-05-04 | Ms SIL shall share the DTL identified for AdEPL (2200001584; 94MW Hybrid REGS) as given below • AdEPL - Dhule PS 220kV Sc line along with associated bay at the generation end (under the scope of applicant). • 1 No. 220kV bay (on Sec-I) at Dhule PS end (under ISTS). [220kV bay is being implemented as part of Dhule PS by Dhule Power Transmission Limited (subsidiary of IndiGrid 2 Pvt Ltd.) vide CTU OM dated 04.11.2025 with schedule of 18 Months from award] | 0 | 220 KV | Aug without ATS |  |  | Under Implementation Transmission scheme for evacuation of power from Dhule 2 GW REZ (SCOD09.02.2026) (Ms Dhule Power Transmission Limited ) • Establishment of 4x500 MVA, 400220 kV Pooling Station at Dhule PS • Dhule PS – Dhule (BDTCL) 400 kV Dc Line | Under Implementation Transmission scheme for evacuation of power from Dhule 2 GW REZ (SCOD09.02.2026) (Ms Dhule Power Transmission Limited ) • Establishment of 4x500 MVA, 400220 kV Pooling Station at Dhule PS • Dhule PS – Dhule (BDTCL) 400 kV Dc Line (Quad ACSRAAACAL59 Moose equivalent (60 km) | 30-May-27 | 30-May-27 |  |  | 150 |  |  |  |  | 2027-05-04 | 2026-02-09 | 2026-10-30 |  | Not effective | 2027-05-04 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2028-05-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 75.00 ¦ Date: 2028-05-30 ¦ Status: Under Implementation ¦ Type: Standalone | 08-07-2026 |  |  | 08/07/2026 | Not Submitted For Approval | 30-May-27 |  | 2027-05-30 | 2027-11-30
2200001626 | Main-Connectivity under GNA |  | BHALKI SOLAR POWER PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2029-05-30 | •Generation Station of Ms Bhalki Solar Power Private Limited – Kurnool-IV PS 220 kV Sc line on Dc tower along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Kurnool-IV PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission System | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 31-Mar-28 | 31-Mar-28 |  |  | 300 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Solar | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-28 |  | 2028-03-31 | 2029-11-30
2200001644 | Main-Connectivity under GNA |  | EG ELECTRICIA ENERGY PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2029-05-30 | •Generation Station of Ms EG Electricia Energy Pvt. Ltd – Kurnool-IV PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant . 1 no. 220 kV line bay at Kurnool - IV PS for above DTL – under the scope of applicant | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission System f | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 31-Dec-27 | 31-Dec-27 |  |  | 100 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2029-11-30
2200001665 | Main-Connectivity under GNA |  | ABC CT RE PARK (04) PRIVATE LIMITED | SR | Land BG Route | (x) Renewable Power Park developer | Wind | 250 |  | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Kurnool-IV | Andhra Pradesh | 2026-03-19 | 2029-05-30 | • Generation Station of Ms ABC CT RE Park (04) Private Limited – Kurnool-IV PS 220 kV Sc line on Dc tower* along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Kurnool-IV PS for termination of above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Transmission System for Integration of Kurnool-IV PS (Phase-I • Transmission System for Integration of Kurnool- | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 30-Sep-28 | 30-Sep-28 |  |  | 250 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2029-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Sep-28 |  | 2028-09-30 | 2029-11-30
2200001666 | Main-Connectivity under GNA |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 500 | 0 | 0 | 500 | 0 | 500 |  | Granted | 500 | 0 | 500 | Kurnool-IV | Andhra Pradesh | 2026-03-19 | 2029-05-30 | • Generation Station of Ms Waaree Forever Energies Private Limited – Kurnool-IV PS 400 kV Sc line along with line bay at generation PS – under the scope of applicant. • 1 no. 400 kV line bay at Kurnool - IV PS for above DTL – under the scope of ISTS. | 1 | 400 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-I | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 300 MW 31-Mar-28,200 MW 31-Dec-28 | Phase 1 ¦ MW: 300.00 ¦ Date: 2028-03-31 Phase 2 ¦ MW: 200.00 ¦ Date: 2028-12-31 |  |  | 500 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 500.00 ¦ Date: 2029-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 1 ¦ MW: 300.00 ¦ Date: 2028-03-31 | 300 | 2028-03-31 | 2029-11-30
2200001666 | Main-Connectivity under GNA |  | WAAREE FOREVER ENERGIES PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 500 | 0 | 0 | 500 | 0 | 500 |  | Granted | 500 | 0 | 500 | Kurnool-IV | Andhra Pradesh | 2026-03-19 | 2029-05-30 | • Generation Station of Ms Waaree Forever Energies Private Limited – Kurnool-IV PS 400 kV Sc line along with line bay at generation PS – under the scope of applicant. • 1 no. 400 kV line bay at Kurnool - IV PS for above DTL – under the scope of ISTS. | 1 | 400 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-I | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 300 MW 31-Mar-28,200 MW 31-Dec-28 | Phase 1 ¦ MW: 300.00 ¦ Date: 2028-03-31 Phase 2 ¦ MW: 200.00 ¦ Date: 2028-12-31 |  |  | 500 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 500.00 ¦ Date: 2029-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | Phase 2 ¦ MW: 200.00 ¦ Date: 2028-12-31 | 200 | 2028-12-31 | 2029-11-30
2200001674 | Main-Connectivity under GNA |  | KENGERI SOLAR POWER PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2029-05-30 | •Generation Station of Ms Kengeri Solar Power Private Limited – Kurnool-IV PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Kurnool-IV PS for above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar – Parli 765 kV Dc line | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar – Parli 765 kV Dc line •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 31-Mar-28 | 31-Mar-28 |  |  | 300 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind |  |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-28 |  | 2028-03-31 | 2029-11-30
2200001675 | Main-Connectivity under GNA |  | ABC CT RE PARK (05) PRIVATE LIMITED | SR | Land BG Route | (x) Renewable Power Park developer | Wind | 250 |  | 0 | 250 | 0 | 250 |  | Granted | 250 | 0 | 250 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2029-05-30 | •Generation Station of Ms ABC CT RE Park (05) Pvt. Ltd. – Kurnool-IV PS 220 kV Sc on Dc tower* along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV terminal line bay at Kurnool-IV PS for above DTL –under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 30-Sep-28 | 30-Sep-28 |  |  | 250 | [5 empty] | 2029-05-25 | 2029-05-25 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Sep-28 |  | 2028-09-30 | 2029-11-30
2200001676 | Main-Connectivity under GNA |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 |  | 0 | 200 | 0 | 200 |  | Granted | 200 | 0 | 200 | Ananthapuram-II | Andhra Pradesh | 2026-06-30 | 2028-04-18 | • Generation Station of Ms Indianoil NTPC Green Energy Private Limited – Ananthapuram-II PS 220 kV Sc line on Dc tower* along with line bay at generation PS –under the scope of applicant. • 1 no. 220 kV line bay at Ananthapuram-II PS for termination of above DTL – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthing between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. • Transmission system for | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthing between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. • Transmission system for integration of Davanagere Chitradurga REZ • Transmission System for Integration of Anantapur-II REZs (Phase-I) •Transmission System for Anantapur-II REZ - Phase-II | 31-Mar-27 | 31-Mar-27 |  |  | 200 | [5 empty] | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-10-18
2200001686 | Main-Connectivity under GNA |  | RELIANCE NU SUNTECH PRIVATE LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Solar | 930 MW: Solar 465 MW: BESS |  | 930 | 0 | 465 | 1395 | NTPC | Granted | 930 | 0 | 930 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2029-05-30 | • Generation Station of Ms Reliance Nu Suntech Pvt. Ltd. – Kurnool-IV PS 400 kV Sc line along with line bay at generation PS – under the scope of applicant. •1 no. 400 kV line bay at Kurnool-IV PS for above DTL – under the scope of ISTS | 1 | 400 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission System | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 31-Dec-27 | 31-Dec-27 |  |  | 930 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 930.00 ¦ Date: 2029-07-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 465.00 ¦ Date: 2029-07-30 ¦ Status: Under Implementation ¦ Type: Standalone |  | Yes |  |  | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2029-05-30
2200001697 | Main-Connectivity under GNA |  | EG ENERGIA SUPPLY PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2029-05-30 | •Through sharing of dedicated connectivity transmission system of Ms EG Electricia Energy Pvt. Ltd. for app. no. 2200001644 i.e. Generation Station of Ms EG Electricia Energy Pvt. Ltd – Kurnool-IV PS 220 kV Sc line – all arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System fo | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 31-Dec-27 | 31-Dec-27 |  |  | 100 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind |  |  |  |  | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2029-11-30
2200001716 | Main-Connectivity under GNA |  | REFEX GREEN POWER LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 | NTPC | Granted | 100 | 0 | 100 | NP Kunta | Andhra Pradesh | 2026-07-01 | 2027-10-18 | •Generation Pooling Station of Ms Refex Power Ltd. – N P Kunta 220 kV Sc line on Dc tower along with line bay at generation pooling station – under the scope of applicant. •1 no. 220 kV terminal line bay at N P Kunta for termination of above dedicated connectivity line –under the scope of Applicant. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Inter-Regional strengthening between SR Grid and WR Grid i.e. Bidar – Parli 765 kV Dc line. •Augmentation of tra | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Inter-Regional strengthening between SR Grid and WR Grid i.e. Bidar – Parli 765 kV Dc line. •Augmentation of transformation capacity by 1x500 MVA, 400220 kV ICT (5th) at NP Kunta. | 23-Dec-26 | 23-Dec-26 |  |  | 100 | [5 empty] | 2027-10-17 | 2027-10-17 |  | Not effective | 2027-10-18 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 23-Dec-26 |  | 2026-12-23 | 2027-10-18
2200001737 | Main-Connectivity under GNA |  | ENFINITY GLOBAL SUNSOURCE PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 100 |  | 0 | 100 | 0 | 100 |  | Granted | 100 | 0 | 100 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2029-05-30 | • Through sharing of dedicated connectivity transmission system of Ms EG Electricia Energy Pvt. Ltd. for app. no. 2200001644 i.e. Generation Station of Ms EG Electricia Energy Pvt. Ltd. – Kurnool-IV PS 220 kV Sc line – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission System | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. • Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 31-Dec-27 | 31-Dec-27 |  |  | 100 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind |  |  |  | 08/07/2026 | Pending with Group Head | 31-Dec-27 |  | 2027-12-31 | 2029-11-30
2200001739 | Main-Connectivity under GNA |  | SOLAR ENERGY CORPORATION OF INDIA LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 |  | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Pavagada | Karnataka | 2025-12-24 | 2027-09-03 | • Through dedicated connectivity transmission system of Ms SECI for app. no. 1200003590 i.e. Generation Station of Ms Solar Energy Corporation of India Ltd. – Pavagada (Tumkur) PS 220 kV Sc line on Dc tower* - all arrangement under the scope of applicant. • SECI has already granted connectivity for 100 MW (app. no. 2200000057) through dedicated connectivity transmission system of app. no. 1200003590. | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 8th – 10th 400220 kV ICTs at Pavagada PS. | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Augmentation of 8th – 10th 400220 kV ICTs at Pavagada PS. | 03-Sep-27 | 03-Sep-27 |  |  | 50 | 218 |  |  |  |  | 2026-05-20 | 2026-12-31 |  | Not effective | 2027-09-03 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-09-03 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 03-Sep-27 |  | 2027-09-03 | 2028-03-03
2200001743 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 400 |  | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Ananthapuram-III | Andhra Pradesh | 2026-07-14 |  | •Generation Station of Ms Sunsure Solarpark RJ One Private Limited – Anantapur-III PS 220 kV line [though stringing of both arms of 220 kV Dc towers and bunching the both arms circuit at both ends to terminate in the single 220 kV bay] along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Anantapur-III PS for above DTL – under the scope of ISTS.[under implementation as part of “Transmission System for Integration of Anantapur-III REZ (Phase-I)”] | 1 | 220 KV | Aug without ATS |  |  | ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Krishnagiri REZ Phase-I •Transmission System for Integration of Anantapur-III REZ (Phase-I) | 31-Dec-28 | 31-Dec-28 |  |  | 400 | [8 empty] | Not effective | 2029-08-01 | [8 empty] | Not Submitted For Approval | 31-Dec-28 |  | 2028-12-31 | 2029-06-30
2200001744 | Main-Connectivity under GNA |  | SUNSURE SOLARPARK RJ ONE PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 400 |  | 400 | 0 | 0 | 400 |  | Granted | 400 | 0 | 400 | Ananthapuram-III | Andhra Pradesh | 2026-07-14 |  | • Generation Station of Ms Sunsure Solarpark RJ One Private Limited –Anantapur-III PS 220 kV Sc line on Dc tower* [with stringing of both Dc tower and bunching of both circuits at both ends to form Sc line] along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Ananthapuram -III PS for above DTL – under the scope of ISTS.[under implementation as part of “Transmission System for Integration of Anantapur-III REZ (Phase-I)”] | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Krishnagiri REZ Phase-I •Transmission System for Integration of Anantapur-III REZ (Phase-I) | 31-Dec-29 | 31-Dec-29 |  |  | 400 | [8 empty] | Not effective | 2029-12-31 | [8 empty] | Not Submitted For Approval | 31-Dec-29 |  | 2029-12-31 | 2030-06-30
2200001749 | Main-Connectivity under GNA |  | SOLARCRAFT POWER INDIA 4 PRIVATE LIMITED | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 |  | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Bhadla-III | Rajasthan | 2026-03-27 |  |  | 0 | 220 KV | [5 empty] | 01-Sep-28 | 01-Sep-28 |  |  | 50 | 222 | [5 empty] | 2029-07-20 |  | Not effective | 2029-07-20 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2028-09-01 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 01-Sep-28 |  | 2028-09-01 | 2029-07-20
2200001757 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Davangere | Karnataka | 2025-12-23 | 2028-12-31 | • Generation Station of Ms Juniper Green Energy Pvt. Ltd – Davanger PS 220 kV Sc line along with line bays at generation end – under the scope of applicant. • 1 no. 220 kV terminal line bay at Davangere PS for termination of above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission system for integration of Davanagere Chitradurga REZ, as per Annexure-II • Trans | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I • Transmission system for integration of Davanagere Chitradurga REZ, as per Annexure-II • Transmission system strenghtening at Davanagere for integration of RE generation | 31-Dec-28 | 31-Dec-28 |  |  | 300 | [5 empty] | 2027-09-24 | 2027-09-30 |  | Not effective | 2028-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Dec-28 |  | 2028-12-31 | 2029-06-30
2200001796 | Main-Connectivity under GNA |  | NTPC RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ananthapuram-II | Andhra Pradesh | 2026-06-30 | 2028-04-18 | • Generation Pooling Station of Ms NTPC Renewable Energy Ltd. – Ananthapuram-II PS 220 kV Sc line on Dc tower* along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Ananthapuram-II PS for termination of above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission System for Integration of Anantapur-III REZs (Phase-I) •Transmission System for Integration of Kurno | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission System for Integration of Anantapur-II REZs (Phase-I) •Transmission System for Anantapur-II REZ - Phase-II | 30-Jun-27 | 30-Jun-27 |  |  | 300 | [5 empty] | 2028-04-17 | 2028-04-17 |  | Not effective | 2028-04-18 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-27 |  | 2027-06-30 | 2028-10-18
2200001803 | Main-Connectivity under GNA |  | JIRE GREEN ENERGY PROJECT ONE LIMITED | SR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | 450 (Solar - 150MW, Wind - 300MW & BESS-150MW) |  | 150 | 300 | 150 | 600 |  | Granted | 300 | 0 | 300 | Davangere | Karnataka | 2026-07-01 | 2028-12-20 | •Generation Pooling Station of Ms JIRE Green Energy Project One Limited – Davangere PS 220 kV Sc line along with line bay at generation pooling station – under the scope of applicant. •1 no. 220 kV terminal line bay at Davangere PS for termination of above Dedicated connectivity line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanager | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanagere for integration of RE generation •Part of transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Augmentation of 1x500 MVA, 400220 kV ICT (9th) at Davangere PS | 30-Dec-27 | 30-Dec-27 | [8 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-12-20 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Dec-27 |  | 2027-12-30 | 2029-06-20
2200001808 | Main-Connectivity under GNA |  | ADYANT ENERSOL PRIVATE LIMITED | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 163 |  | 0 | 163 | 0 | 163 | NTPC and SJVN | Granted | 163 | 0 | 163 | Davangere | Karnataka | 2025-12-30 | 2028-01-31 | •Generation Pooling Station of Ms Adyant Enersol Pvt. Ltd. – Davangere PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Davangere PS for termination of above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanagere | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanagere for integration of RE generation •Inter-Regional strengthening between SR Grid and WR Grid i.e. Bidar – Parli 765 kV Dc line. | 31-Mar-27 | 31-Mar-27 |  |  | 163 | [5 empty] | 2027-10-17 | 2027-10-17 |  | Not effective | 2028-01-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 112.00 ¦ Date: 2027-12-11 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 51.00 ¦ Date: 2028-01-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-Mar-27 |  | 2027-03-31 | 2028-01-31
2200001915 | Main-Connectivity under GNA |  | KONCHA SOLAR POWER PRIVATE LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ananthapuram-III | Andhra Pradesh | 2026-07-14 |  | •Generation Station of Ms Koncha Solar Power Private Limited – Anantapur-III PS 220 kV Sc line along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Anantapur-III PS for above DTL – under the scope of ISTS.[under implementation as part of “Transmission System for Integration of Anantapur-III REZ (Phase-I)”] | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Krishnagiri REZ Phase-I •Transmission System for Integration of Anantapur-III REZ (Phase-I) | 31-Dec-28 | 31-Dec-28 |  |  | 300 | [8 empty] | Not effective | 2029-08-01 | [8 empty] | Not Submitted For Approval | 31-Dec-28 |  | 2028-12-31 | 2029-06-30
2200001923 | Main-Connectivity under GNA |  | TERRA CLEAN LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | Total-300MW Solar-100MW Wind-200MW |  | 100 | 200 | 0 | 300 |  | Granted | 300 | 0 | 300 | Davangere | Karnataka | 2026-06-09 | 2028-02-13 | •Generation Station of Ms Tera Clean Ltd. – Davangere PS 220 kV Sc line on Dc tower along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV terminal line bay at Davangere PS for termination of above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanager | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanagere for integration of RE generation •Part of transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line | 31-Dec-27 | 31-Dec-27 |  |  | 300 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-02-13 |  |  | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2028-02-13 ¦ Status: Under Implementation ¦ Type: Solar | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-Dec-27 |  | 2027-12-31 | 2028-08-13
2200001956 | Main-Connectivity under GNA |  | JUNIPER GREEN ENERGY LIMITED (formerly known as JUNIPER GREEN ENERGY PRIVATE LIMITED) | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | Solar- 50 MW |  | 50 | 0 | 0 | 50 |  | Granted | 50 | 0 | 50 | Davangere | Karnataka | 2025-12-23 | 2028-12-31 | •Through dedicated Connectivity transmission system of Ms Juniper Green Energy Pvt. Ltd. for app. no. 2200001757 for 300 MW i.e. Generation Pooling Station of Ms Juniper Green Energy Pvt. Ltd – Davangere PS 220 kV Sc line – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanagere | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanagere for integration of RE generation •Inter-Regional strengthening between SR Grid and WR Grid i.e. Bidar – Parli 765 kV Dc line. | 31-Dec-28 | 31-Dec-28 |  |  | 50 | [5 empty] | 2027-10-17 | 2027-10-17 |  | Not effective | 2028-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2028-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  |  | Pending with Level 2 | 31-Dec-28 |  | 2028-12-31 | 2029-06-30
2200001962 | Main-Connectivity under GNA |  | JINDAL GREEN PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 350 |  | 0 | 350 | 0 | 350 |  | Granted | 350 | 0 | 350 | Ananthapuram-III | Andhra Pradesh | 2026-07-14 |  | •Generation Station of Ms Jindal Green Private Limited – Anantapur-III PS 220 kV Sc line on Dc tower* along with line bay at generation PS – under the scope of applicant. •1 no. 220 kV line bay at Anantapur-III PS for above DTL – under the scope of ISTS.[under implementation as part of “Transmission System for Integration of Anantapur-III REZ (Phase-I)”] | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Krishnagiri REZ Phase-I •Transmission System for Integration of Anantapur-III REZ (Phase-I) | 31-Dec-27 | 31-Dec-27 |  |  | 350 | [8 empty] | Not effective | 2029-08-01 | [8 empty] | Not Submitted For Approval | 31-Dec-27 |  | 2027-12-31 | 2028-06-30
2200001987 | Main-Connectivity under GNA |  | BBMB | NR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 10 | 0 | 10 | 0 | 0 | 10 |  | Granted | 10 | 0 | 10 | Bhiwani(BBMB) | Haryana | 2025-09-01 | 2025-09-03 |  | 1 | 132 KV | [5 empty] | 31-Jul-25 | 31-Jul-25 | 10 | 2025-09-03 | [9 empty] | Effective |  |  | Part Commissioned | 8.8 | ¦ Phase 1 ¦ MW: 8.80 ¦ Date: 2026-03-11 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 1.20 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  | COD Updated | 08/07/2026 | Pending with Level 2 | 31-Jul-25 |  | 2025-07-31 | 2026-03-03
2200001994 | Main-Connectivity under GNA |  | RAJASTHAN BESS PRIVATE LIMITED | NR | Land Route | (vii) Standalone ESS | Standalone ESS | 250 |  | 0 | 0 | 250 | 250 |  | Granted | 250 | 0 | 250 | Bhadla-III | Rajasthan | 2025-09-03 | 2027-02-25 |  | 1 | 220 KV | [5 empty] | 23-Jun-26 | 23-Jun-26 |  |  | 250 | 233 |  |  |  | 2027-02-25 |  | 2026-11-30 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 23-Jun-26 |  | 2026-06-23 | 2027-08-25
2200001996 | Main-Connectivity under GNA |  | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Tuticorin-II | Tamil Nadu | 2026-02-26 | 2028-02-18 | • Generation Pooling station of Ms Indianoil NTPC Green Energy Private Limited – Tuticorin-II 230 kV Sc line along with line bay at generation end - under the scope of applicant • 1 no. 230 kV terminal line bay at ISTS end for termination of above DTL – under the scope of ISTS | 1 | 230 KV | Aug with ATS | Augmentation of 1x500 MVA, 400230 kV ICT (7th) at Tuticorin-II GIS | 2028-02-17 | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-Jul-26 | 31-Jul-26 |  |  | 200 | [5 empty] | 2024-07-16 | 2026-10-31 |  | Not effective | 2028-02-18 | Under Construction |  | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-10-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  |  | Pending with Level 2 | 31-Jul-26 |  | 2026-07-31 | 2028-08-18
2200002046 | Main-Connectivity under GNA |  | CLEAN MAX TADOBA PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 271.8 |  | 151.8 | 120 | 0 | 271.8 |  | Granted | 150 | 0 | 150 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2029-05-30 | • Generation Station of Ms Clean Max Tadoba Pvt. Ltd. – Kurnool-IV PS 220 kV Sc line on Dc tower* along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Kurnool-IV PS for above DTL –under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 28-Dec-28 | 28-Dec-28 |  |  | 150 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-04-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 151.80 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 120.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind |  |  |  |  | Pending with Level 2 | 28-Dec-28 |  | 2028-12-28 | 2029-11-30
2200002048 | Main-Connectivity under GNA |  | CLEAN MAX DRACO PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 97.8 |  | 52.8 | 45 | 0 | 97.8 |  | Granted | 50 | 0 | 50 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2029-05-30 | • Through sharing of dedicated connectivity transmission system agreed for grant for Ms Clean Max Tadoba Pvt. Ltd. for app. no. 2200002046 i.e. Generation Station of Ms Clean Max Tadoba Pvt. Ltd. – Kurnool-IV PS 220 kV Sc line on Dc Tower– all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 29-Dec-28 | 29-Dec-28 |  |  | 50 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 52.80 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 45.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind |  |  |  | 08/07/2026 | Pending with Level 2 | 29-Dec-28 |  | 2028-12-29 | 2029-11-30
2200002049 | Main-Connectivity under GNA |  | H.G. BANASKANTHA BESS PRIVATE LIMITED | WR | Land Route | (vii) Standalone ESS | Standalone ESS | 185 |  | 0 | 0 | 185 | 185 |  | Granted | 217.64 | 0 | 217.64 | Radhanesda | Gujarat | 2026-02-04 | 2027-03-24 | HGBBPL shall share the dedicated transmission system proposed for Kinurja S1 Private Limited (KS1PL) (appl. no. 2200002108) as given below. • KS1PL – Banaskantha (Radhanesda) PS (GIS) 220kV Sc line along with associated bays at the generation end (under the scope of Ms KS1PL). • 1 no. 220kV line bay at Banaskantha (Radhanesda) PS (GIS) is presently under implementation by POWERGRID as per CTU OM dated 05.12.2025. | 1 | 220 KV | Existing |  |  |  |  | 1-Dec-26 | 1-Dec-26 |  |  | 217.64 | 210 | 2027-03-24 |  |  | 2027-03-24 |  |  |  | Not effective | 2027-03-24 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 185.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Standalone | 08-07-2026 |  |  |  | Pending with Level 2 | 1-Dec-26 |  | 2026-12-01 | 2027-09-24
2200002050 | Main-Connectivity under GNA |  | TORRENT GREEN ENERGY PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 450 |  | 150 | 300 | 0 | 450 |  | Granted | 300 | 0 | 300 | Ananthapuram-III | Andhra Pradesh | 2026-07-14 |  | •Generation Station of Ms Torrent Green Energy Pvt. Ltd – Anantapur-III PS 220 kV Sc line on Dc tower* along with line bay at generation PS end – under the scope of applicant •1 no. 220 kV line bay at Anantapuram-III PS for above DTL – under the scope of ISTS.[under implementation as part of “Transmission System for Integration of Anantapur-III REZ (Phase-I)”] | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Krishnagiri REZ Phase-I •Transmission System for Integration of Anantapur-III REZ (Phase-I) | 31-Dec-27 | 31-Dec-27 |  |  | 300 | [8 empty] | Not effective | 2029-08-01 | [8 empty] | Not Submitted For Approval | 31-Dec-27 |  | 2027-12-31 | 2028-06-30
2200002057 | Main-Connectivity under GNA |  | HEXA CLIMATE SOLUTIONS PRIVATE LIMITED | SR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | 150 |  | 50 | 100 | 50 | 200 |  | Granted | 100 | 0 | 100 | Davangere | Karnataka | 2026-07-01 | 2028-12-20 | •Through dedicated Connectivity transmission system of Ms Hexa Climate for app. no. 200000982 i.e. Generation Station of Ms Hexa Climate Solutions Pvt. Ltd. –DavanagereChitradurga PS 220 kV Sc line – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanage | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanagere for integration of RE generation •Part of transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Augmentation of 1x500 MVA, 400220 kV ICT (9th) at Davangere PS | 30-Jun-28 | 30-Jun-28 |  |  | 100 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-12-19 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-Jun-28 |  | 2028-06-30 | 2029-06-20
2200002077 | Main-Connectivity under GNA |  | TERRA CLEAN LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Ananthapuram-III | Andhra Pradesh | 2026-07-14 |  | • Generation Station of Ms Terra Clean Ltd.– Anantapuram-III PS 220 kV Sc line along with line bay at generation PS end – under the scope of applicant. • 1 no. 220 kV line bay at Anantapur-III PS for above DTL – under the scope of ISTS.[under implementation as part of “Transmission System for Integration of Anantapur-III REZ (Phase-I)”] | 1 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission System for Integration of Anantapur-III REZs (Phase-I) •Transmission System for Integration of Kurno | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Krishnagiri REZ Phase-I •Transmission System for Integration of Anantapur-III REZ (Phase-I) | 31-Dec-28 | 31-Dec-28 |  |  | 300 | [8 empty] | Not effective | 2029-08-01 | [8 empty] | Not Submitted For Approval | 31-Dec-28 |  | 2028-12-31 | 2029-06-30
2200002078 | Main-Connectivity under GNA |  | TERRA CLEAN LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 350 |  | 250 | 100 | 0 | 350 |  | Granted | 350 | 0 | 350 | Krishnagiri | Andhra Pradesh | 2026-07-07 | 2029-07-15 | • Generation Station of Ms Terra Clean Limited – Krishnagiri PS 220 kV Sc line on Dc tower* along with line bay at generation PS end – under the scope of applicant. • 1 no. 220 kV line bay at Krishnagiri PS for above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. • Transmission system f | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Krishnagiri REZ Phase-I. | 31-Dec-28 | 31-Dec-28 |  |  | 350 | [8 empty] | Not effective | 2029-07-15 |  |  | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2029-07-15 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2029-07-15 ¦ Status: Under Implementation ¦ Type: Wind |  |  |  | 27/07/2026 | Pending with Level 2 | 31-Dec-28 |  | 2028-12-31 | 2030-01-15
2200002107 | Main-Connectivity under GNA |  | CLEAN MAX SOLSTICE PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 179 |  | 99 | 80 | 0 | 179 |  | Granted | 100 | 0 | 100 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2029-05-30 | • Through sharing of dedicated connectivity transmission system agreed for grant for Ms Clean Max Tadoba Pvt. Ltd. for app. no. 2200002046 i.e. Generation Station of Ms Clean Max Tadoba Pvt. Ltd. – Kurnool-IV PS 220 kV Sc line on Dc Tower– all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 31-Dec-28 | 31-Dec-28 |  |  | 100 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 99.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 80.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind |  |  |  |  | Pending with Level 2 | 31-Dec-28 |  | 2028-12-31 | 2029-11-30
2200002108 | Main-Connectivity under GNA |  | KINURJA S1 PRIVATE LIMITED | WR | Land Route | (vii) Standalone ESS | Standalone ESS | 65 |  | 0 | 0 | 65 | 65 |  | Granted | 65 | 0 | 65 | Radhanesda | Gujarat | 2026-02-04 | 2027-03-24 | • KS1PL – Banaskantha (Radhanesda) PS (GIS) 220kV Sc line along with associated bays at the generation end (under the scope of Ms KS1PL). • 1 no. 220kV line bay at Banaskantha (Radhanesda) (GIS) PS is presently under implementation by POWERGRID as per CTU OM dated 05.12.2025. | 1 | 220 KV | Existing |  |  |  |  | 23-Dec-26 | 23-Dec-26 |  |  | 65 | 210 | [7 empty] | Not effective | 2027-03-24 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 65.00 ¦ Date: 2027-03-24 ¦ Status: Under Implementation ¦ Type: Standalone | 09-07-2026 |  |  | 09/07/2026 | Pending with Level 2 | 23-Dec-26 |  | 2026-12-23 | 2027-09-24
2200002177 | Main-Connectivity under GNA |  | Adyant Enersol Private Limited | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 24 | 0 | 0 | 24 | 0 | 24 |  | Granted | 24 |  | 24 | Davangere | Karnataka | 2026-07-01 | 2028-12-20 | Through dedicated Connectivity transmission system of Ms Adyant Enersol Pvt. Ltd. for app. no. 200001808 i.e. Generation Station of Ms Adyant Enersol Pvt. Ltd. –DavanagereChitradurga PS 220 kV Sc line – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. Transmission system for integration of Davanagere Chitradurga REZ as per Annexure-II Transmissi | ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. Transmission system for integration of Davanagere Chitradurga REZ as per Annexure-II Transmission system strengthening at Davanagere for integration of RE generation as per Annexure-III Part of transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) as per Annexure-IV Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. Augmentation of 1x500 MVA, 400220 kV ICT (9th) at Davangere PS | 30-june-2027 | 30-june-2027 |  |  | 24 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-12-20 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-june-2027 |  | 2027-06-30 | 2029-06-20
2200002211 | Main-Connectivity under GNA |  | CLEAN MAX TAHOE PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 97.8 |  | 52.8 | 45 | 0 | 97.8 |  | Granted | 50 | 0 | 50 | Kurnool-IV | Andhra Pradesh | 2026-06-12 | 2029-05-30 | • Through sharing of dedicated connectivity transmission system granted to Ms Clean Max Tadoba Pvt. Ltd. granted for grant towards app. no. 2200002046 i.e. Generation Station of Ms Clean Max Tadoba Pvt. Ltd.-Kurnool-IV PS 220 kV Sc line on Dc tower – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Transmission System for Integration of Kurnool-IV PS (Phase-I) •Transmission System for Integration of Kurnool-IV PS (Phase-II) | 30-Dec-28 | 30-Dec-28 |  |  | 50 | [5 empty] | 2029-05-29 | 2029-05-29 |  | Not effective | 2029-05-30 |  |  | 0 | ¦ Phase 1 ¦ MW: 52.80 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 45.00 ¦ Date: 2029-05-30 ¦ Status: Under Implementation ¦ Type: Wind |  |  |  | 08/07/2026 | Pending with Level 2 | 30-Dec-28 |  | 2028-12-30 | 2029-11-30
2200002277 | Main-Connectivity under GNA |  | SOLAR ENERGY CORPORATION OF INDIA LIMITED | SR | Land BG Route | (vii) Standalone ESS | Standalone ESS | 600 |  | 0 | 0 | 600 | 600 |  | Granted | 600 | 0 | 600 | Kurnool-III | Andhra Pradesh | 2026-07-01 | 2027-01-31 | • Generation Pooling Station of Ms Solar Energy Corporation of India Ltd. – Kurnool-III PS 220 kV Dc line along with line bay at generation PS – under the scope of applicant. • 2 no. 220 kV terminal line bay at Kurnool-III for termination of above dedicated connectivity line – under the scope of ISTS. | 2 | 220 KV | Aug without ATS |  |  | •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)Solar Energy Zone (AP) (1500MW)-Part-A and Part-B | •Transmission Scheme Transmission scheme for evacuation of power from RE sources in Kurnool Wind Energy Zone (3000MW)Solar Energy Zone (AP) (1500MW)-Part-A and Part-B | 31-Jan-27 | 31-Jan-27 |  |  | 600 | 219 & 221 | [7 empty] | Not effective | 2027-01-31 | [8 empty] | Not Submitted For Approval | 31-Jan-27 |  | 2027-01-31 | 2027-07-31
2200002314 | Main-Connectivity under GNA |  | TATA POWER RENEWABLE ENERGY LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Krishnagiri | Andhra Pradesh | 2026-07-07 | 2029-07-15 | • Generation Station of Ms Tata Power Renewable Energy Limited – Krishnagiri PS 220 kV Sc line on Dc tower* along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Krishnagiri PS for above DTL – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. • Transmission system | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Krishnagiri REZ Phase-I | 31-Mar-28 | 31-Mar-28 |  |  | 300 | [8 empty] | Not effective | 2029-07-15 | [8 empty] | Not Submitted For Approval | 31-Mar-28 |  | 2028-03-31 | 2030-01-15
2200002439 | Main-Connectivity under GNA |  | SOLAR ENERGY CORPORATION OF INDIA LIMITED | SR | Land Route | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 88 | 0 | 88 | Davangere | Karnataka | 2026-07-01 | 2028-12-20 | •Through sharing of dedicated Connectivity transmission system of Ms Adyant Enersol Pvt. Ltd. for app. no. 200001808 i.e. Generation Station of Ms Adyant Enersol Pvt. Ltd. –DavanagereChitradurga PS 220 kV Sc line – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanager | •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region. •Transmission system for integration of Davanagere Chitradurga REZ •Transmission system strengthening at Davanagere for integration of RE generation •Part of transmission system strengthening for integration of additional RE potential at Davangere (0.25 GW) and Bellary (2.75 GW) •Inter-Regional Strengthening between SR Grid and WR Grid i.e Bidar-Parli 765 kV Dc line. •Augmentation of 1x500 MVA, 400220 kV ICT (9th) at Davangere PS | 2027-12-31 | 2027-12-31 |  |  | 88 | [5 empty] | 2028-02-12 | 2028-02-12 |  | Not effective | 2028-12-20 |  |  | 0 |  | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 2027-12-31 |  | 2027-12-31 | 2029-06-20
2200002499 | Main-Connectivity under GNA |  | SVR SUN PRIVATE LIMITED | SR | Land BG Route | (iii) Generating station(s), including REGS(s), with ESS | Solar |  |  | 300 | 0 | 150 | 450 |  | Granted | 300 |  | 300 | Krishnagiri | Andhra Pradesh | 2026-07-15 |  | • Generation Station of Ms SVR Sun Private Limited – Krishnagiri PS 220 kV Sc line on Dc tower* along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Krishnagiri PS for above DTL – under the scope of ISTS. [under implementation as part of “Transmission system for integration of Krishnagiri REZ Phase-I”] | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system fo | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Krishnagiri REZ Phase-I | 31-10-2028 | 31-10-2028 |  |  | 300 | [8 empty] | Not effective | 2029-08-01 | [8 empty] | Unknown Status | 31-10-2028 |  | 2028-10-31 | 2029-04-30
2200002536 | Main-Connectivity under GNA |  | SAEL INDUSTRIES LIMITED | SR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Solar |  |  | 300 | 0 | 150 | 450 | SECI | Granted | 300 |  | 300 | Krishnagiri | Andhra Pradesh | 2026-07-14 |  | • Generation Station of Ms SAEL Industries Limited – Krishnagiri PS 220 kV Sc line on Dc tower* along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Krishnagiri PS for above DTL – under the scope of ISTS.[To be implemented as part of “Transmission system for integration of Krishnagiri REZ Phase-I”]. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. • Transmission system | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. • Transmission system for integration of Krishnagiri REZ Phase-I | 31-03-2028 | 31-03-2028 |  |  | 300 | [8 empty] | Not effective | 2029-08-01 | [8 empty] | Unknown Status | 31-03-2028 |  | 2028-03-31 | 2028-03-31
2200002568 | Main-Connectivity under GNA |  | AMPLUS KEMET SOLAR PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 |  | 0 | 200 | 0 | 200 |  | Granted | 200 |  | 200 | Krishnagiri | Andhra Pradesh | 2026-07-14 |  | • Generation Station of Ms Amplus Kemet Solar Private Limited – Krishnagiri PS 220 kV Sc line on Dc tower along with line bay at generation PS – under the scope of applicant. • 1 no. 220 kV line bay at Krishnagiri PS for above DTL – under the scope of ISTS. [To be implemented as part of “Transmission system for integration of Krishnagiri REZ Phase-I”]. | 1 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region •Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. •Transmission system for integration of Krishnagiri REZ Phase-I | 31-Dec-29 | 31-Dec-29 |  |  | 200 | [8 empty] | Not effective | 2029-12-31 | [8 empty] | Not Submitted For Approval | 31-Dec-29 |  | 2029-12-31 | 2030-06-30
2200002569 | Main-Connectivity under GNA |  | AMPLUS BEAT ENERGY PRIVATE LIMITED | SR | Land BG Route | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 |  | 0 | 200 | 0 | 200 |  | Granted | 200 |  | 200 | Krishnagiri | Andhra Pradesh | 2026-07-14 |  | •Through sharing of dedicated connectivity transmission system of Ms Amplus Kemet Solar Pvt. Ltd. granted for app. no. 2200002568 i.e. Generation Station of Ms Amplus Karmet Solar Pvt. Ltd. – Krishnagiri PS 220 kV Sc line on Dc tower* [along with stringing of 2nd circuit arm of Dc towers of above mentioned 220 kV line and bunching of both circuits at both ends to form Sc linefor termination in single 220 kV bay at both ends] along with line bay at generation PS – under the scope of applicant.[To be implemented as part of “Transmission system for integration of Krishnagiri REZ Phase-I”]. | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. • Transmission system f | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region • Inter-Regional Strengthening between SR Grid and WR Grid i.e. Bidar-Parli 765kV Dc line. • Transmission system for integration of Krishnagiri REZ Phase-I | 31-Dec-29 | 31-Dec-29 |  |  | 200 | [8 empty] | Not effective | 2029-12-31 | [8 empty] | Not Submitted For Approval | 31-Dec-29 |  | 2029-12-31 | 2030-06-30
2200002655 | Non-Solar Hour Access as per Regulation 5.11(a) |  | SARJAN REALITIES PRIVATE LIMITED | WR | Land Route | (x) Renewable Power Park developer | Standalone ESS | 1060 |  |  |  | 1060 | 1060 |  | Granted | 1060 |  | 1060 | KPS-3 (Sec-II) | Gujarat | 2026-08-05 | 2028-03-31 | SRPL (PSS-11) – KPS3 (GIS) (Bus Section-II) 400kV Sc line (on Dc towers) along with associated line bay at generation end (under the scope of applicant) 400kV line bay at KPS3 (Sec-II) end is being implemented under ISTS under “Transmission System for Evacuation of Power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7 GW) Part A” scheme by Khavda IV A Power Transmission Limited (a subsidiary of AESL) | 1 | 400 KV | Aug without ATS |  |  | Common Transmission System Augmentation Under Implementation (under ISTS) Transmission system for evacuation of additional 7 GW RE Power from Khavda RE Park under Phase III Part A (Ms Halvad Transmission Ltd. – AESL) (SCOD 26122025) (An | Common Transmission System Augmentation Under Implementation (under ISTS) Transmission system for evacuation of additional 7 GW RE Power from Khavda RE Park under Phase III Part A (Ms Halvad Transmission Ltd. – AESL) (SCOD 26122025) (Ant. COD Dec’26) Establishment of 765 kV Halvad switching station KPS2 (GIS) - Halvad 765 kV Dc line LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission system for evacuation of additional 7 GW RE Power from Khavda RE Park under Phase-III, Part-B (Ms Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) (Ant. COD Dec’26) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) (GIS) 765 kV Dc line Transmission System for Evacuation of Power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7 GW) Part A (Ms Khavda IV A Transmission Ltd.-AESL) (SCOD 30082026) Creation of 765 kV Bus section-II at KPS3 (GIS) with 3x1500 MVA, 765400 kV ICTs at Bus Section-II along with 765 kV Bus Sectionaliser. Creation of 400 kV Bus Section-II at KPS3 (GIS) along with 400 kV Bus Sectionaliser. KPS3 (GIS) – Lakadia (AIS) 765 kV DC line KPS1 (GIS)– Bhuj PS 765 kV 2nd DC line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-B (Ms South Olpad Transmission Ltd. – POWERGRID) (SCOD 15102026) Establishment of 2x1500 MVA, 765400 kV & 2x500 MVA, 400220 kV GIS Ss at a suitable location South of Olpad (between Olpad and Ichhapore) Vadodara(GIS) – South Olpad (GIS) 765kV Dc line LILO of Gandhar – Hazira 400 kV Dc line at South Olpad (GIS) using twin HTLS conductor with minimum capacity of 1700 MVA per ckt at nominal voltage Ahmedabad – South Olpad (GIS) 765kV Dc line Transmission System for evacuation of power from potential renewable energy zone in Khavda area of Gujarat under Phase-IV (7GW), Part-C (Ms Khavda IV C Power Transmission Ltd. – SGL38) (SCOD 15102026) Establishment of 4x1500 MVA, 765400 kV & 2x500 MVA, 400220kV Boisar-II (GIS) Ss South Olpad (GIS) – Boisar-II(GIS) 765kV Dc line LILO of Navsari (New) – Padghe (PG) 765kV Dc line at Boisar-II Boisar-II (Sec-II) – Velgaon (MH) 400 kV Dc LILO of Babhaleswar – Padghe (M) 400 kV Dc line at Boisar-II (Sec-I) Transmission System for evacuation of power fr | 2028-03-31 | 2028-03-31 |  |  | 1060 | [8 empty] | Not effective | 2028-03-31 | [8 empty] | Unknown Status | 2028-03-31 |  | 2028-03-31 | 2028-09-30
2200002656 | Non-Solar Hour Access as per Regulation 5.11(a) |  | SARJAN REALITIES PRIVATE LIMITED | WR | Land Route | (x) Renewable Power Park developer | Standalone ESS | 950 |  |  |  | 950 | 950 |  | Granted | 950 |  | 950 | KPS-3 (Sec-I) | Gujarat | 2026-08-05 | 2028-03-31 | SRPL (PSS-12) – KPS3 (GIS) (Bus Section-I) 400kV Sc line (on Dc towers) along with associated line bay at generation end (under the scope of applicant) 1 No. 400kV Bay at KPS3 (GIS) (Bus Section-I) is under implementation under ISTS (as per CTUIL O.M. dated 04.11.2025) | 1 | 400 KV | Aug without ATS |  |  | Transmission system for evacuation of additional 7 GW RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) (Ant. COD Dec-26) Establishment of 765 kV Halvad switching station KPS2 ( | Transmission system for evacuation of additional 7 GW RE Power from Khavda RE Park under Phase III Part A (Part System) (Halvad Transmission Ltd. – AESL) (SCOD 26122025) (Ant. COD Dec-26) Establishment of 765 kV Halvad switching station KPS2 (GIS) - Halvad 765 kV Dc line LILO of Lakadia – Ahmedabad 765 kV Dc at Halvad Transmission system for evacuation of additional 7 GW RE Power from Khavda RE Park under Phase-III, Part-B (Vataman Transmission Ltd. – POWERGRID) (SCOD 26122025) (Ant. COD Dec-26) Establishment of 765 kV switching station near Vataman Halvad – Vataman 765 kV Dc line LILO of Lakadia – Vadodara 765 kV Dc line at Vataman Vataman switching station – Navsari (New) (GIS) 765 kV Dc line | 2028-03-31 | 2028-03-31 |  |  | 950 | [8 empty] | Not effective | 2028-03-31 | [8 empty] | Unknown Status | 2028-03-31 |  | 2028-03-31 | 2028-09-30
2200002662 | Main-Connectivity under GNA |  | NTPC LIMITED | ER | Land Route | (xii) Standalone ESS with an installed capacity of 5 MW and above applying for grant of Connectivity to ISTS through the electrical system of a generating station already having Connectivity to ISTS | Standalone ESS | 200 |  |  |  | 200 | 200 |  | Granted | 200 |  | 200 | Barh | Bihar | 2026-05-12 | 2027-08-31 | NTPC Barh generation is connected to ISTS at 400kV bus at generation switchyard of NTPC Ltd. The instant BESS shall be connected at the existing 132kV bus in the generation switchyard having 400132kV, 3x200MVA ICTs. | 0 |  | Existing |  |  |  |  | 2027-08-31 | 2027-08-31 |  |  | 200 | [8 empty] | Not effective | 2027-08-31 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-08-31 ¦ Status: Under Implementation ¦ Type: Standalone | 23-06-2026 |  |  |  | Pending with Level 2 | 2027-08-31 |  | 2027-08-31 | 2028-02-29
2200002958 | Main-Connectivity under GNA |  | NTPC LIMITED | ER | Land Route | (xii) Standalone ESS with an installed capacity of 5 MW and above applying for grant of Connectivity to ISTS through the electrical system of a generating station already having Connectivity to ISTS | Standalone ESS | 200 |  |  |  | 200 | 200 |  | Granted | 200 |  | 200 | Nabinagar-II | Bihar | 2026-05-12 | 2027-08-31 | NTPC Nabinagar generation is connected to ISTS at 400kV bus at generation switchyard of NTPC Ltd. The instant BESS shall be connected at the existing 132kV bus in the generation switchyard having 400132kV, 2x200MVA ICTs. | 0 |  | Existing |  |  |  |  | 2027-08-31 | 2027-08-31 |  |  | 200 | [8 empty] | Not effective | 2027-08-31 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-08-31 ¦ Status: Under Implementation ¦ Type: Standalone | 23-06-2026 |  |  |  | Pending with Level 2 | 2027-08-31 |  | 2027-08-31 | 2028-02-29
9100000037 | Deemed GNA to gen | LTA app no. 1200003577 | Tunga Renewables Energy Pvt. Ltd. Connectivity Appl No.- 1200003577 | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 189.84 |  | 0 | 189.84 | 0 | 189.84 |  | Granted | 189.84 | 0 | 189.84 | Koppal | Karnataka | 2023-09-21 | 2024-07-16 | Testing data | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Souther | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 30-06-2023 | 30-06-2023 |  |  | 189.84 | 205 | 2022-09-05 |  | Tunga Renewable Energy Pvt Ltd. representative informed that Revised SCoD is 05.09.2022 & Petition is under CERC to extend the SCoD matching with ISTS transmission system. With reference to the Petition No 339/MP/2022 i.e., Tunga Renewable Energy Private Limited (TREPL) v. Solar Energy Corporation of India Limited & Ors., wherein CTU has been subsequently impleaded as a party vide CERC direction in RoP dated 15.11.2022. In the said Petition, TREPL has contended that there was delay in grant of connectivity and/or LTA to the ISTS network by CTU. It was clarified by the CTU that there was no delay in grant of Connectivity and/or LTA which were granted in the regular course as per the applications made and the availability of transmission system. |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 |  | 16.03.2026 |  |  | 03/07/2026 | Pending with Level 2 | 30-06-2023 |  | 2023-06-30 | 2026-10-31
9100000038 | Deemed GNA to gen | 1200003530 LTA app no. 0451100005 | Project Ten Renewable Power Pvt. Ltd. ( Connectivity Appl No.-1200003530) | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 150 |  | 0 | 150 | 0 | 150 |  | Granted | 150 | 0 | 150 | Koppal | Karnataka | 2023-09-21 | 2024-07-16 |  | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 05-06-2023 | 05-06-2023 |  |  | 150 | 215 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 05-06-2023 |  | 2023-06-05 | 2026-10-31
9100000041 | Deemed GNA to gen | Connectivity Appl No.- 1200003497; LTA app no. 451100008 (120 MW) & Connectivity Appl No.- 1200003534 ; LTA app no 0451100003 (50 MW) | Azure Power India Pvt. Ltd. | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 170 |  | 0 | 170 | 0 | 170 |  | Granted | 170 | 50 | 120 | Gadag | Karnataka | 2023-09-21 | 2024-12-31 |  | 1 | 220 KV |  |  |  | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Weste | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 30-06-2023 | 30-06-2023 |  |  | 120 | 201 | 2025-07-26 |  | Azure Power representative informed that SECI vide Letter dtd. 26.07.2023 has revised the SCD of project as 26.07.2025. Azure Power vide Email informed that Azure has filed the company has preferred to file an appeal before the Hon’ble Appellate Tribunal for Electricity (APTEL) vide DFR No. 226/2024, filed on 2nd May 2024, andadmitted under Appeal No. APL-330/2024. The proceedings are currently pending adjudication before the Hon’ble Tribunal. It was informed to the grantee that transmission charges shall be applicable for the delay period in commissioning for generation project as per the CERC Regulations. |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 |  | 16.03.2026 |  | Not provided the status. Azure Power vide Email informed that Azure has filed the company has preferred to file an appeal before the Hon’ble Appellate Tribunal for Electricity (APTEL) vide DFR No. 226/2024, filed on 2nd May 2024, and admitte | 03/07/2026 | Pending with Level 2 | 30-06-2023 |  | 2023-06-30 | 2026-10-31
9100000042 | Deemed GNA to gen | LTA app no. 451100007 | Green Infra Wind Connectivity Appl No.- 0451100007 | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 178.5 |  | 0 | 178.5 | 0 | 178.5 |  | Granted | 178.5 | 0 | 178.5 | Gadag | Karnataka | 2023-09-21 | 2024-07-16 |  | 1 | 220 KV |  |  |  | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Weste | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 20-06-2023 | 20-06-2023 | 54.6 | 2025-12-27 |  | 202 | 2025-07-26 |  | SGIPL representative informed that SECI vide letter dated 14.06.2024 has revised PPA SCoD as 26.07.2025. Representative of M/s Green Infra Wind Energy Ltd. informed that their DTL is being constructed by M/s Vena Energy Vidyuth Pvt Ltd (VEVPL) and its status shall be as given by M/s VEVPL for Connectivity- 1200002872. |  | 2024-07-16 | 2026-10-31 |  | Effective | 2026-10-31 | Under Construction | Part Commissioned | 54.6 | ¦ Phase 1 ¦ MW: 54.60 ¦ Date: 2025-01-17 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 14.70 ¦ Date: 2026-03-25 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 29.40 ¦ Date: 2026-05-13 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 25.02 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 5 ¦ MW: 25.20 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 20-06-2023 |  | 2023-06-20 | 2025-12-27
9100000042 | Deemed GNA to gen | LTA app no. 451100007 | Green Infra Wind Connectivity Appl No.- 0451100007 | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 178.5 |  | 0 | 178.5 | 0 | 178.5 |  | Granted | 178.5 | 0 | 178.5 | Gadag | Karnataka | 2023-09-21 | 2024-07-16 |  | 1 | 220 KV |  |  |  | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Weste | Common Transmission system required for effectiveness of connectivityGNA (System strengthening without ATS) • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 20-06-2023 | 20-06-2023 |  |  | 123.9 | 202 | 2025-07-26 |  | SGIPL representative informed that SECI vide letter dated 14.06.2024 has revised PPA SCoD as 26.07.2025. Representative of M/s Green Infra Wind Energy Ltd. informed that their DTL is being constructed by M/s Vena Energy Vidyuth Pvt Ltd (VEVPL) and its status shall be as given by M/s VEVPL for Connectivity- 1200002872. |  | 2024-07-16 | 2026-10-31 |  | Not Effective | 2026-10-31 | Under Construction | Part Commissioned | 54.6 | ¦ Phase 1 ¦ MW: 54.60 ¦ Date: 2025-01-17 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 14.70 ¦ Date: 2026-03-25 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 29.40 ¦ Date: 2026-05-13 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 25.02 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 5 ¦ MW: 25.20 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 20-06-2023 |  | 2023-06-20 | 2026-10-31
9100000043 | Deemed GNA to gen | LTA app no. 451100009 | ReNew Naveen Urja Pvt. Ltd | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 297.5 | 0 | 297.5 |  | Granted | 297.5 | 0 | 297.5 | Gadag | Karnataka | 2023-09-21 | 2024-07-16 |  | 1 | 220 KV |  |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-07-2023 | 31-07-2023 |  |  | 297.5 | 213 | 2025-07-26 |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 297.50 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  |  | Pending with Level 2 | 31-07-2023 |  | 2023-07-31 | 2026-10-31
9100000045 | Deemed GNA to gen | LTA app no. 1200003533 (170 MW) Connectivity Appl No.-1200002868 | JSW Renew Energy Connectivity Appl No.-1200002868 | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 170 |  | 0 | 170 | 0 | 170 |  | Granted | 170 | 0 | 170 | Karur | Tamil Nadu | 2023-09-21 | 2024-07-16 |  | 1 | 230 KV |  |  |  | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. • Transmission Scheme for evacuation of power from RE sources in Karur/ Tirpur wind Energy Zone (Tamil Nadu) (1000 MW) under Phase-I | • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region as per Annexure-I. • Transmission Scheme for evacuation of power from RE sources in Karur/ Tirpur wind Energy Zone (Tamil Nadu) (1000 MW) under Phase-I | 31-10-2022 | 31-10-2022 |  |  | 170 | 206 | [5 empty] | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 170.00 ¦ Date: 2026-04-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 02/04/2026 | Pending with Level 2 | 31-10-2022 |  | 2022-10-31 | 2026-10-31
9100000047 | Deemed GNA to gen | LTA app no. 451100004 | Project Ten Renewable Power Pvt. Ltd. | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Pavagada | Karnataka | 2023-09-21 | 2024-07-16 |  | 1 | 220 KV |  |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 05-06-2023 | 05-06-2023 |  |  | 300 | 221 | 2024-09-14 |  | Representative of Project Ten Renewables Power Pvt. Ltd. informed that revised SCoD as per SECI bid is 14.09.2024. They also informed that time extension has been sought from SECI, response awaited. SECI extension letter to be submitted. It was informed to the grantee that transmission charges shall be applicable for the delay period in commissioning for generation project as per the CERC Regulations. |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-08-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 05-06-2023 |  | 2023-06-05 | 2026-10-31
9100000050 | Deemed GNA to gen | LTA app no.1200003664 | Greenko AP01 IREP Pvt. Ltd (Connectivity Appl No.- 1200002672) | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 900 |  | 1500 | 0 | 0 | 1950 |  | Granted | 900 | 0 | 900 | Kurnool (new) | Andhra Pradesh | 2023-09-21 | 2024-07-16 |  | 1 | 400 KV |  |  |  | Common Transmission System for Connectivity – under ISTS • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission System for Connectivity – under ISTS • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 04-02-2022 | 04-02-2022 |  |  | 900 | 409 |  |  |  |  | 2024-07-16 | 2026-06-30 |  | Not effective | 2026-10-31 | Under Construction |  | 0 |  | 03-02-2026 |  |  | 03/02/2026 | Not Submitted For Approval | 04-02-2022 |  | 2022-02-04 | 2026-06-30
9100000052 | Deemed GNA to gen | 1200000326 | ReNew Power Ltd. (formerly Renew Power Ventures Pvt. Ltd.) (RPL-Bhuvad) | WR |  | (i) Generating station(s), including REGS(s), without ESS | Wind | 350 |  | 0 | 350 | 0 | 350 |  | Granted | 350 | 0 | 350 | Bhachau | Gujarat | 2023-09-22 | 2023-10-01 |  | 2 | 220 kV | [5 empty] | 15-12-2017 | 15-12-2017 | 350 | 2019-05-01 |  | 212 & 213 | [7 empty] | Effective |  | Commissioned | Part Commissioned | 230.1 | ¦ Phase 1 ¦ MW: 126.00 ¦ Date: 2019-05-17 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 58.50 ¦ Date: 2019-09-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 27.60 ¦ Date: 2020-09-01 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 18.00 ¦ Date: 2021-02-06 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 5 ¦ MW: 119.90 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 15-12-2017 |  | 2017-12-15
9100000143 | Deemed GNA to gen | 1200003241 | Renew Solar Power Pvt. Ltd. (RSPPL) Connectivity: 1200003241 (300MW); LTA: 1200003270 (300MW); | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | kallam | Maharashtra | 2023-09-22 | 2024-08-10 |  | 1 | 220 kV | [5 empty] | 30-10-2022 | 30-10-2022 | 300 | 2024-08-10 |  | 206 | 2026-04-11 | 2026-10-09 | SECI wide letter dated 22.03.2023 has provided extension till 10.02.2026 and maximum permissible till 10.08.2026 |  |  |  | 2024-02-14 | Effective |  | Commissioned | Part Commissioned | 138.6 | ¦ Phase 1 ¦ MW: 59.40 ¦ Date: 2025-09-05 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 36.30 ¦ Date: 2025-10-12 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 19.80 ¦ Date: 2025-11-08 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 13.20 ¦ Date: 2026-01-02 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 5 ¦ MW: 9.90 ¦ Date: 2026-02-15 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 6 ¦ MW: 161.40 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 | Yes |  | 27/07/2026 | Pending with Level 2 | 30-10-2022 |  | 2022-10-30 | 2026-10-09
9100000145 | Deemed GNA to gen | 1200002678 | Adani Renewable Energy Holding Four Ltd. (Erstwhile Adani Green Energy Four Ltd.) | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 917 |  | 917 | 0 | 0 | 917 |  | Granted | 917 | 0 | 917 | KPS-1 (Sec-I) | Gujarat | 2023-09-22 | 2026-10-01 |  | 1 |  |  |  |  | 500 Khavda Ph-I 417 Khavda Ph-II | 500 Khavda Ph-I 417 Khavda Ph-II | 30-12-2022 | 30-12-2022 | 500 | 2024-02-25 |  | 401 | 2026-01-12 | 2027-01-12 | AREHFL representative vide email dtd. 05-07-2024 informed that Revised SCoD as per SECI LoA for 500MW+1083MW+ 417MW are as follows: 500MW: 250MW- 19.03.2025 but allowed till 19.03.2026 250MW: 05.11.2026 417MW: 167MW: 05.11.2026 250MW: 05.11.2026 |  | 2025-12-26 |  | 2026-02-24 | Effective | 2026-10-01 | Commissioned | Part Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-01-23 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2026-03-13 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 50.00 ¦ Date: 2026-03-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 50.00 ¦ Date: 2026-04-20 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 87.73 ¦ Date: 2024-12-13 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 12.38 ¦ Date: 2025-02-27 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 7 ¦ MW: 67.00 ¦ Date: 2025-02-24 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 8 ¦ MW: 250.00 ¦ Date: 2027-02-07 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 9 ¦ MW: 250.00 ¦ Date: 2027-03-07 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 30-12-2022 |  | 2022-12-30 | 2027-01-12
9100000145 | Deemed GNA to gen | 1200002678 | Adani Renewable Energy Holding Four Ltd. (Erstwhile Adani Green Energy Four Ltd.) | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 917 |  | 917 | 0 | 0 | 917 |  | Granted | 917 | 0 | 917 | KPS-1 (Sec-I) | Gujarat | 2023-09-22 | 2026-10-01 |  | 1 |  |  |  |  | 500 Khavda Ph-I 417 Khavda Ph-II | 500 Khavda Ph-I 417 Khavda Ph-II | 30-12-2022 | 30-12-2022 |  |  | 417 | 401 | 2026-01-12 | 2027-01-12 | AREHFL representative vide email dtd. 05-07-2024 informed that Revised SCoD as per SECI LoA for 500MW+1083MW+ 417MW are as follows: 500MW: 250MW- 19.03.2025 but allowed till 19.03.2026 250MW: 05.11.2026 417MW: 167MW: 05.11.2026 250MW: 05.11.2026 |  | 2025-12-26 |  | 2026-02-24 | Not Effective | 2026-10-01 | Commissioned | Part Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-01-23 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 100.00 ¦ Date: 2026-03-13 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 50.00 ¦ Date: 2026-03-19 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 50.00 ¦ Date: 2026-04-20 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 87.73 ¦ Date: 2024-12-13 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 12.38 ¦ Date: 2025-02-27 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 7 ¦ MW: 67.00 ¦ Date: 2025-02-24 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 8 ¦ MW: 250.00 ¦ Date: 2027-02-07 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 9 ¦ MW: 250.00 ¦ Date: 2027-03-07 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 30-12-2022 |  | 2022-12-30 | 2027-01-12
9100000149 | Deemed GNA to gen | 1200003170 | Rewa Ultra Mega Solar Ltd. (Neemuch Solar Park) Connectivity: 1200003170 (500MW); LTA: 1200003189 (500MW); | WR | L&FC | (x) Renewable Power Park developer | Solar | 100 |  | 500 | 0 | 0 | 500 |  | Granted | 500 | 0 | 500 | Neemuch | Madhya Pradesh | 2023-11-20 | 2024-05-06 |  | 2 | 220 kV | [5 empty] | 30-11-2022 | 30-11-2022 | 500 | 2024-05-06 |  | 205 & 206 |  |  |  | 2024-02-24 | 2024-02-24 |  | 2024-04-24 | Effective |  | Commissioned | Part Commissioned | 330 | ¦ Phase 1 ¦ MW: 330.00 ¦ Date: 2024-11-26 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 118.80 ¦ Date: 2026-07-28 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 51.20 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 28-07-2026 |  |  | 28/07/2026 | Pending with Level 2 | 30-11-2022 |  | 2022-11-30 | 2024-11-06
9100000155 | Deemed GNA to gen | 230700003 | NTPC Renewable Energy Limited Connectivity: 230700003; LTA: 430700003 (300+150MW); | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 150 |  | 0 | 150 | 0 | 150 |  | Granted | 150 | 0 | 150 | Bhuj | Gujarat | 2023-09-22 | 2024-02-28 |  | 0 |  | Existing |  |  |  |  | 30-04-2023 | 30-04-2023 | 150 | 2024-02-28 |  | 205 & 208 | 2026-12-31 |  | NTPC REL representative vide email dtd. 14.10.2025 informed that Revised SCoD as per REIA letter dated 14.10.2025 is 31.12.2025 SECI wide letter dated 31.12.2025 informed that extension in revised SCOD is 30.06.2026. |  |  |  |  | Effective |  | Commissioned | Part Commissioned | 146 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2023-11-05 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 90.00 ¦ Date: 2025-04-09 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 6.00 ¦ Date: 2025-07-31 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 4.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 | Yes |  | 21/07/2026 | Pending with Level 2 | 30-04-2023 |  | 2023-04-30 | 2026-12-31
9100000157 | Deemed GNA to gen | 230700005 | Gujarat State Electricity Corporation Limited Connectivity: 230700005; LTA: 430000002; | WR | L&FC | (x) Renewable Power Park developer | Solar | 1000 |  | 1000 | 0 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | KPS-2 (Sec-I) | Gujarat | 2023-09-22 | 2025-01-31 |  | 1 |  |  |  |  | Khavda Ph-II | Khavda Ph-II | 29-02-2024 | 29-02-2024 |  |  | 1000 | 416 |  |  |  | 2026-06-30 | 2025-03-21 |  | 2026-02-24 | Not effective | 2026-08-25 | Commissioned | Part Commissioned | 400 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2026-01-21 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 64.00 ¦ Date: 2026-08-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 36.00 ¦ Date: 2026-08-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 4 ¦ MW: 300.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 5 ¦ MW: 200.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 29-02-2024 |  | 2024-02-29 | 2026-06-30
9100000159 | Deemed GNA to gen | 230700007 | Adani Green Energy Limited Connectivity: 230700007; LTA: 430700008 (1000MW); | WR | L&A | (x) Renewable Power Park developer | Hybrid | 1166.4 |  | 800 | 200 | 0 | 1000 |  | Granted | 1000 | 0 | 1000 | KPS-1 (Sec-II) | Gujarat | 2023-09-22 | 2025-03-31 |  | 1 |  |  |  |  | Khavda Ph-II | Khavda Ph-II | 31-12-2024 | 31-12-2024 | 1000 | 2026-03-08 |  | 421 |  |  |  |  | 2025-03-21 |  | 2026-04-02 | Effective |  | Commissioned | Part Commissioned | 750 | ¦ Phase 1 ¦ MW: 52.00 ¦ Date: 2025-03-31 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 98.80 ¦ Date: 2025-03-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 26.00 ¦ Date: 2025-05-14 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 31.20 ¦ Date: 2025-06-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 5 ¦ MW: 51.60 ¦ Date: 2025-09-05 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 77.70 ¦ Date: 2025-12-26 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 7 ¦ MW: 52.00 ¦ Date: 2025-03-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 8 ¦ MW: 102.90 ¦ Date: 2025-03-28 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 9 ¦ MW: 77.40 ¦ Date: 2025-03-30 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 10 ¦ MW: 51.60 ¦ Date: 2025-05-11 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 11 ¦ MW: 25.00 ¦ Date: 2026-05-29 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 12 ¦ MW: 77.70 ¦ Date: 2026-05-25 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 13 ¦ MW: 26.10 ¦ Date: 2026-05-29 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 14 ¦ MW: 265.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2026-03-08
9100000161 | Deemed GNA to gen | 230700009 | Adani Green Energy LimitedConnectivity 230700009;LTA 430700010 (1050MW); | WR | L&A | (x) Renewable Power Park developer | Hybrid | 1111.60 | 0 | 810 | 301.6 | 0 | 1111.6 |  | Granted | 1050 | 0 | 1050 | KPS-3 (Sec-I) | Gujarat | 2023-09-22 | 2025-05-31 |  | 1 |  |  |  |  | Khavda Ph-II | Khavda Ph-II | 31-05-2025 | 31-05-2025 | 1050 | 2026-03-08 |  | 409 |  |  |  |  | 2025-03-21 | 2026-02-15 |  | Effective |  | Commissioned | Part Commissioned | 1061.6 | ¦ Phase 1 ¦ MW: 25.00 ¦ Date: 2025-07-31 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 15.60 ¦ Date: 2025-07-28 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 26.00 ¦ Date: 2025-07-28 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 35.00 ¦ Date: 2025-07-31 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 46.80 ¦ Date: 2026-03-18 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 6 ¦ MW: 5.20 ¦ Date: 2026-03-18 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 7 ¦ MW: 10.40 ¦ Date: 2026-03-28 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 8 ¦ MW: 52.00 ¦ Date: 2025-08-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 9 ¦ MW: 72.80 ¦ Date: 2025-09-04 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 10 ¦ MW: 5.20 ¦ Date: 2025-11-12 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 11 ¦ MW: 50.00 ¦ Date: 2025-09-30 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 12 ¦ MW: 50.00 ¦ Date: 2026-01-09 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 13 ¦ MW: 31.20 ¦ Date: 2025-09-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 14 ¦ MW: 31.20 ¦ Date: 2025-11-13 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 15 ¦ MW: 5.20 ¦ Date: 2026-02-11 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 16 ¦ MW: 75.00 ¦ Date: 2025-12-03 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 17 ¦ MW: 50.00 ¦ Date: 2026-02-10 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 18 ¦ MW: 75.00 ¦ Date: 2026-03-13 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 19 ¦ MW: 25.00 ¦ Date: 2026-03-24 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 20 ¦ MW: 75.00 ¦ Date: 2026-03-24 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 21 ¦ MW: 50.00 ¦ Date: 2026-03-24 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 22 ¦ MW: 50.00 ¦ Date: 2026-03-30 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 23 ¦ MW: 100.00 ¦ Date: 2026-05-08 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 24 ¦ MW: 50.00 ¦ Date: 2026-05-08 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 25 ¦ MW: 50.00 ¦ Date: 2026-05-29 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 26 ¦ MW: 50.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-05-2025 |  | 2025-05-31 | 2026-03-08
9100000391 | Deemed GNA to gen | St-II:1200002635(600 MW) LTA:1200002789(600 MW) | Adani Renewable Energy Holding Seventeen Private Limited | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 600 |  | 600 | 0 | 0 | 600 |  | Granted | 600 | 0 | 600 | Fatehgarh-III (Sec-I) | Rajasthan | 2023-09-25 | 2023-10-01 |  | 2 | 220 KV | [5 empty] | 01-03-2022 | 01-03-2022 | 600 | 2025-01-22 |  | 206,208 | 2026-03-31 | 2026-09-30 | Maximum delay permitted by REIA from PPA letter with NHPC 320MW: 30.09.2026 & 280MW:30.12.2026 |  |  | 2024-12-19 | 2024-12-19 | Effective |  | Commissioned | Part Commissioned | 251 | ¦ Phase 1 ¦ MW: 251.00 ¦ Date: 2026-03-25 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 69.00 ¦ Date: 2026-08-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 280.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 | Yes |  | 06/08/2026 | Pending with Level 2 | 01-03-2022 |  | 2022-03-01 | 2026-09-30
9100000416 | Deemed GNA to gen | St-II: 1200002401 (500 MW) LTA:1200003586 (267 MW) | Azure Power India Private Limited | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 267 |  | 267 | 0 | 0 | 267 |  | Granted | 267 | 200 | 67 | Bhadla-II | Rajasthan | 2023-09-25 | 2024-09-28 | Azure Power India Private Limited Power Plant Bhadla-ll PS 400kV SIC line (to be clubbed with Appl. No. 1200002403) (suitable to carry min 1000 MW power at nominal voltage) along with associated bay at generation end under scope of applicant. 400kV Bay at Bhadla-ll PS shall be under the scope of ISTS. | 1 | 400 KV | [5 empty] | 30-09-2021 | 30-09-2021 | 67 | 2026-01-18 |  | 412(Main),411(Tie) | 2027-11-04 |  | 50 MW: 04.11.2027, 17 MW: 16.07.2028 & Remaining 200 MW PPA yet to be signed | 2024-07-07 | 2024-09-30 | 2026-01-14 | 2026-01-14 | Effective |  | Commissioned | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 67.00 ¦ Date: 2028-09-30 ¦ Status: Under Implementation ¦ Type: |  |  | 200 MW Revoked |  | Pending with Level 2 | 30-09-2021 |  | 2021-09-30 | 2027-11-04
9100000417 | Deemed GNA to gen | St-II: 1200002401 (500 MW) (233 out of 500 MW) 1200002403(500 MW) (100 out of 500 MW) LTA:1200003587 (333 MW) | Azure Power India Private Limited | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 333 |  | 333 | 0 | 0 | 333 |  | Granted | 333 | 0 | 333 | Bhadla-II | Rajasthan | 2023-09-25 | 2024-09-28 | Azure Power India Private Limited Power Plant Bhadla-ll PS 400kV SIC line (to be clubbed with Appl. No. 1200002403) (suitable to carry min 1000 MW power at nominal voltage) along with associated bay at generation end under scope of applicant. 400kV Bay at Bhadla-ll PS shall be under the scope of ISTS. | 0 | 400 KV | [5 empty] | 30-09-2021 | 30-09-2021 | 333 | 2026-01-18 |  | 412(Main),411(Tie) | 2028-07-16 |  | PPA signed dated 03.02.2026 | 2024-07-07 | 2023-11-10 | 2026-01-14 | 2026-01-14 | Effective |  | Commissioned | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 333.00 ¦ Date: 2028-09-30 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 30-09-2021 |  | 2021-09-30 | 2028-07-16
9100000419 | Deemed GNA to gen | St-II: 1200002432(500 MW) LTA:1200003689 (500 MW) | Adani Renewable Energy Holding Four Ltd. | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 500 |  | 500 | 0 | 0 | 500 |  | Granted | 500 | 0 | 500 | Ramgarh | Rajasthan | 2023-09-25 | 2025-10-26 |  | 1 | 400 KV | [5 empty] | 01-07-2022 | 01-07-2022 |  |  | 500 | 404(Main),405(Tie) |  |  |  |  | 2025-02-01 | 2027-03-31 |  | Not effective | 2026-12-31 | Under Construction | Part Commissioned | 137.5 | ¦ Phase 1 ¦ MW: 137.50 ¦ Date: 2026-03-30 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 362.50 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar |  | Yes |  | 08/07/2026 | Pending with Level 2 | 01-07-2022 |  | 2022-07-01 | 2027-03-31
9100000424 | Deemed GNA to gen | St-II:1200003813 (100 MW) LTA:1200003879 (100 MW) | ReNew Dinkar Jyoti Private Limited | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-01-11 | 2025-09-20 |  | 0 | 400 kV | [5 empty] | 20-09-2023 | 20-09-2023 |  |  | 100 | 423 | 2025-01-31 | 2025-07-31 | 31.01.2025 Or 30 days subsequent to the readiness of power evacuation infrastructure/operationalization of LTA/GNA at Fatehgarh-III, whichever is earlier | 2026-02-10 | 2025-02-01 | 2026-11-30 |  | Not effective | 2026-11-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: | 08.07.2026 |  | Bay Charged on 10-02-2026 | 08/07/2026 | Pending with Level 2 | 20-09-2023 |  | 2023-09-20 | 2026-11-30
9100000429 | Deemed GNA to gen | St-II:1200002688 (300 MW) LTA:1200003947 (300 MW) | Eden Renewable Bercy Private Limited | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-II | Rajasthan | 2023-09-25 | 2024-09-28 |  | 1 | 220 KV | [5 empty] | 13-04-2022 | 13-04-2022 | 300 | 2026-01-18 |  | A202 | 2027-04-08 |  | As per SECI Letter dated 11.02.2026 | 2024-08-12 | 2023-11-30 | 2026-01-14 | 2026-01-14 | Effective |  | Commissioned | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-04-08 ¦ Status: Under Implementation ¦ Type: | 08-07-2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 13-04-2022 |  | 2022-04-13 | 2027-04-08
9100000437 | Deemed GNA to gen | St-II Connectivity: 1200000287 LTA: 1200000293,1200000337, 1200002949,1200003348 | Adani Renewable Energy Park Rajasthan Ltd | NR |  | (x) Renewable Power Park developer | Hybrid | 704 |  | 600 | 510 | 0 | 1110 |  | Granted | 704 | 0 | 704 | Fatehgarh | Rajasthan | 2023-09-25 | 2023-10-01 |  | 0 | 400 KV | [5 empty] | 30-06-2017 | 30-06-2017 | 704 | 2021-08-01 | [8 empty] | 2021-08-01 | Effective |  | Commissioned | Part Commissioned | 700 | ¦ Phase 1 ¦ MW: 700.00 ¦ Date: 2022-10-01 ¦ Status: COD Declared ¦ Type: ¦ Phase 2 ¦ MW: 4.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Hybrid | 08-07-2026 |  |  |  | Pending with Level 2 | 30-06-2017 |  | 2017-06-30
9200000013 | Conn under 37.1_37.2_37.6 | 0451100011 | Serentica Renewables India Pvt. Ltd | SR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 132 |  | 56 | 24 | 0 | 80 |  | Granted | 80 | 0 | 80 | Gadag | Karnataka | 2024-04-04 | 2024-10-01 | Through dedicated connectivity Tr. System granted to M/s Serentica Renewables India Pvt. Ltd. at Gadag PS for application no. 1200003761. | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 01-07-2024 | 01-07-2024 |  |  | 80 | 216 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Part Commissioned | 0 | ¦ Phase 2 ¦ MW: 11.25 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 12.36 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 5 ¦ MW: 19.90 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 01-07-2024 |  | 2024-07-01 | 2026-10-31
9200000016 | Conn under 37.1_37.2_37.6 | 0451100010 | Serentica Renewables India Pvt. Ltd | SR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 165 |  | 70 | 30 | 0 | 100 |  | Granted | 100 | 0 | 100 | Gadag | Karnataka | 2024-04-04 | 2024-10-01 | • Through dedicated connectivity tr. System granted to M/s Serentica Renewables India Pvt. Ltd. at Gadag PS for application no. 1200003761. | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 01-07-2024 | 01-07-2024 |  |  | 100 | 216 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Part Commissioned | 41.47 | ¦ Phase 2 ¦ MW: 20.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 9.51 ¦ Date: 2025-10-31 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 24.87 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 01-07-2024 |  | 2024-07-01 | 2026-10-31
9200000017 | Conn under 37.1_37.2_37.6 | 1200003849 | Tunga Renewable Energy Pvt. Ltd. | SR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 45.07 |  | 0 | 45.07 | 0 | 45.07 |  | Granted | 45.07 | 0 | 45.07 | Koppal | Karnataka | 2024-03-08 | 2025-06-30 | • Through dedicated transmission system granted to M/s Tunga Renewable Energy Pvt Ltd. at Koppal PS for application no. 1200003392 | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 30-06-2024 | 30-06-2024 |  |  | 45.07 | 205 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 45.07 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: | 22.12.2025 |  |  | 06/05/2026 | Pending with Level 2 | 30-06-2024 |  | 2024-06-30 | 2026-10-31
9200000018 | Conn under 37.1_37.2_37.6 | 1200003392 | Tunga Renewable Energy Pvt. Ltd. | SR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 115 |  | 0 | 115 | 0 | 115 |  | Granted | 115 | 0 | 115 | Koppal | Karnataka | 2024-03-08 | 2025-06-30 | • M/s Tunga Renewable Energy Pvt Ltd – Koppal PS 220kV S/c line on D/c tower along with 220kV bay at generation end • 220kV line bay at Koppal PS end for termination of above dedicated line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 30-06-2023 | 30-06-2023 |  |  | 115 | 205 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 115.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 06/05/2026 | Pending with Level 2 | 30-06-2023 |  | 2023-06-30 | 2026-10-31
9200000021 | Conn under 37.1_37.2_37.6 | 0451100013 | Serentica Renewable India 1 Pvt. | SR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 133.3333333 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Koppal | Karnataka | 2024-01-25 | 2024-09-30 | • Through dedicated transmission system granted to M/s Serentica Renewables India 1 Pvt. Ltd. at Koppal PS for application no. 1200003822 | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 01-07-2024 | 01-07-2024 |  |  | 100 | [5 empty] | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Part Commissioned | 106.25 | ¦ Phase 1 ¦ MW: 63.07 ¦ Date: 2025-08-01 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 2.20 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 01-07-2024 |  | 2024-07-01 | 2026-10-31
9200000022 | Conn under 37.1_37.2_37.6 | 0451100012 | Serentica Renewable India 1 Pvt. | SR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 133.3333333 |  | 100 | 0 | 0 | 100 |  | Granted | 100 | 0 | 100 | Koppal | Karnataka | 2024-01-25 | 2024-07-16 | • Through dedicated transmission system granted to M/s Serentica Renewables India 1 Pvt. Ltd. at Koppal PS for application no. 1200003822 | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 07-01-2024 | 07-01-2024 |  |  | 100 | [5 empty] | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Part Commissioned | 106.25 | ¦ Phase 1 ¦ MW: 63.07 ¦ Date: 2025-08-01 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 2.20 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 07-01-2024 |  | 2024-01-07 | 2026-10-31
9200000024 | Conn under 37.1_37.2_37.6 | 1200003815 | Ircon Renewable Power Ltd. | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 500 |  | 500 | 0 | 0 | 500 |  | Granted | 500 | 0 | 500 | Pavagada | Karnataka | 2024-05-13 | 2025-08-17 | Generating Pooling Station at switchyard of Ms Ircon Renewable Power Ltd. at Tumkur, Karnataka – Pavagada PS 220kV Sc line including terminal bay at generation pooling station - under the scope of grantee. 02 no. 220 kV bays at Pavagada (Tumkur) PS for termination of dedicated connectivity line - under the scope of applicant. | 2 | 220 KV | Aug without ATS |  |  | Common Transmission System for Connectivity – under ISTS • Augmentation of 1X500 MVA, 400220kV Pavagada (Tumkur) PS i.e. 7th ICT at Pavagada (Tumkur) PS • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power duri | Common Transmission System for Connectivity – under ISTS • Augmentation of 1X500 MVA, 400220kV Pavagada (Tumkur) PS i.e. 7th ICT at Pavagada (Tumkur) PS • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 30-01-2024 | 30-01-2024 | 400 | 2025-12-27 |  | 222 & 223 |  |  |  |  | 2025-08-16 | 2026-10-31 |  | Effective | 2026-10-31 | Under Construction | Part Commissioned | 400 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2024-10-11 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2024-12-10 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 50.00 ¦ Date: 2025-03-05 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 75.00 ¦ Date: 2025-04-29 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 75.00 ¦ Date: 2025-07-29 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 100.00 ¦ Date: 2025-09-12 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 7 ¦ MW: 75.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 8 ¦ MW: 25.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 30-01-2024 |  | 2024-01-30 | 2025-12-27
9200000024 | Conn under 37.1_37.2_37.6 | 1200003815 | Ircon Renewable Power Ltd. | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 500 |  | 500 | 0 | 0 | 500 |  | Granted | 500 | 0 | 500 | Pavagada | Karnataka | 2024-05-13 | 2025-08-17 | Generating Pooling Station at switchyard of Ms Ircon Renewable Power Ltd. at Tumkur, Karnataka – Pavagada PS 220kV Sc line including terminal bay at generation pooling station - under the scope of grantee. 02 no. 220 kV bays at Pavagada (Tumkur) PS for termination of dedicated connectivity line - under the scope of applicant. | 2 | 220 KV | Aug without ATS |  |  | Common Transmission System for Connectivity – under ISTS • Augmentation of 1X500 MVA, 400220kV Pavagada (Tumkur) PS i.e. 7th ICT at Pavagada (Tumkur) PS • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power duri | Common Transmission System for Connectivity – under ISTS • Augmentation of 1X500 MVA, 400220kV Pavagada (Tumkur) PS i.e. 7th ICT at Pavagada (Tumkur) PS • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 30-01-2024 | 30-01-2024 |  |  | 100 | 222 & 223 |  |  |  |  | 2025-08-16 | 2026-10-31 |  | Not Effective | 2026-10-31 | Under Construction | Part Commissioned | 400 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2024-10-11 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2024-12-10 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 50.00 ¦ Date: 2025-03-05 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 75.00 ¦ Date: 2025-04-29 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 75.00 ¦ Date: 2025-07-29 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 100.00 ¦ Date: 2025-09-12 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 7 ¦ MW: 75.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 8 ¦ MW: 25.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 | Yes |  | 08/07/2026 | Pending with Level 2 | 30-01-2024 |  | 2024-01-30 | 2026-10-31
9200000025 | Conn under 37.1_37.2_37.6 | 1200003590 | Solar Energy Corporation of India Ltd. | SR | L&A | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 |  | Granted | 200 | 0 | 200 | Pavagada | Karnataka | 2024-05-13 | 2025-06-23 | •Generating Pooling Station of M/s Solar Energy Corporation of India Ltd. (Ramagiri)– Pavagada (Tumkur) PS 220 kV 220 kV S/c line on D/c tower# along with line bay at generation pooling station – under the scope of applicant. •1 no. of 220 kV line bay at Pavagada (Tumkur) PS for termination of above mentioned dedicated Connectivity line - under the scope of applicant. | 1 | 220 KV | Aug without ATS |  |  | •Augmentation of 1x500 MVA 400/220 kV Pavagada (Tumkur) PS i.e. 6th ICT at Pavagada (Tumkur) PS •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | •Augmentation of 1x500 MVA 400/220 kV Pavagada (Tumkur) PS i.e. 6th ICT at Pavagada (Tumkur) PS •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-12-2024 | 31-12-2024 |  |  | 200 | 221 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-07-15 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  |  | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2026-10-31
9200000026 | Conn under 37.1_37.2_37.6 | 0251100003 | Sembcorp Green Infra Private Limited (Formerly known as Green Infra Wind Energy Limited) | SR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 70 |  | 0 | 70 | 0 | 70 |  | Granted | 70 | 0 | 70 | Gadag | Karnataka | 2024-03-08 | 2025-05-31 | • Generating Pooling Station of M/s Green Infra Wind Energy Ltd. –Gadag PS 220kV S/c line on D/c tower including terminal bays at generating pooling station - under the scope of applicant. • 220 kV bay at Gadag PS end for termination of dedicated line - under the scope of ISTS | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-12-2024 | 31-12-2024 |  |  | 70 | [5 empty] | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 70.00 ¦ Date: 2027-01-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2026-10-31
9200000027 | Conn under 37.1_37.2_37.6 | 0351100002 | Sembcorp Green Infra Private Limited (Formerly known as Green Infra Wind Energy Limited) | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 50 |  | 0 | 50 | 0 | 50 |  | Granted | 50 | 0 | 50 | Gadag | Karnataka | 2024-03-08 | 2024-09-30 | Through dedicated connectivity tr. System granted to M/s Green Infra Wind Energy Ltd. at Gadag PS for application no. 0251100003 | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-01-2024 | 31-01-2024 |  |  | 50 |  | 2026-08-31 |  | SGIPL representative informed that they have signed PPA with Central Railway on 31.03.2023 for 50 MW. SGIPL representative informed that SCD is revised as 31.08.2026 |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 25.20 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 25.20 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 | Yes |  |  | Pending with Level 2 | 31-01-2024 |  | 2024-01-31 | 2026-10-31
9200000028 | Conn under 37.1_37.2_37.6 | SW5958957243-M029_D001_A007-1670310631002 | Sembcorp Green Infra Private Limited (Formerly known as Green Infra Wind Energy Limited) | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 1.5 |  | 0 | 1.5 | 0 | 1.5 |  | Granted | 1.5 | 0 | 1.5 | Gadag | Karnataka | 2024-03-08 | 2024-07-16 | Through dedicated connectivity tr. System granted to M/s Green Infra Wind Energy Ltd. at Gadag PS for application no. 0251100003 | 0 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 20-06-2023 | 20-06-2023 |  |  | 1.5 | [5 empty] | 2025-12-26 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 1.50 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 | Yes |  | 06/05/2026 | Pending with Level 2 | 20-06-2023 |  | 2023-06-20 | 2026-10-31
9200000029 | Conn under 37.1_37.2_37.6 | 0251100005 | TP Saurya Ltd.$ | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Koppal | Karnataka | 2024-08-08 | 2025-01-11 | •Generation Pooling Station of Ms TP Saurya Ltd. – Koppal PS 220 kV Sc line including 220 kV terminal bays at generation pooling station – under the scope of applicant. •01 nos. of 220 kV line bays at Koppal PS for termination of above mentioned dedicated Connectivity line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission System for Connectivity – under ISTS •Transmission scheme for evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplu | Common Transmission System for Connectivity – under ISTS •Transmission scheme for evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-10-2024 | 31-10-2024 | 141 | 2025-12-27 |  | 203 | 2026-12-29 |  | SECI vide letter dated 20.05.2024 has extended the SCD of the project upto 24.02.2026 or ‘Actual date of connectivity+60days’ whichever is later. |  | 2024-07-16 | 2026-10-31 |  | Effective | 2026-10-31 | Under Construction | Part Commissioned | 0 | ¦ Phase 1 ¦ MW: 130.77 ¦ Date: 2026-01-06 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 61.52 ¦ Date: 2026-02-03 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 46.15 ¦ Date: 2026-04-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 61.70 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  |  | Pending with Level 2 | 31-10-2024 |  | 2024-10-31 | 2026-12-29
9200000029 | Conn under 37.1_37.2_37.6 | 0251100005 | TP Saurya Ltd.$ | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Koppal | Karnataka | 2024-08-08 | 2025-01-11 | •Generation Pooling Station of Ms TP Saurya Ltd. – Koppal PS 220 kV Sc line including 220 kV terminal bays at generation pooling station – under the scope of applicant. •01 nos. of 220 kV line bays at Koppal PS for termination of above mentioned dedicated Connectivity line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission System for Connectivity – under ISTS •Transmission scheme for evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplu | Common Transmission System for Connectivity – under ISTS •Transmission scheme for evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka) (2500MW) •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-10-2024 | 31-10-2024 |  |  | 159 | 203 | 2026-12-29 |  | SECI vide letter dated 20.05.2024 has extended the SCD of the project upto 24.02.2026 or ‘Actual date of connectivity+60days’ whichever is later. |  | 2024-07-16 | 2026-10-31 |  | Not Effective | 2026-10-31 | Under Construction | Part Commissioned | 0 | ¦ Phase 1 ¦ MW: 130.77 ¦ Date: 2026-01-06 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 61.52 ¦ Date: 2026-02-03 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 46.15 ¦ Date: 2026-04-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 61.70 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  |  | Pending with Level 2 | 31-10-2024 |  | 2024-10-31 | 2026-12-29
9200000030 | Conn under 37.1_37.2_37.6 | 0251100010 | Sembcorp Green Infra Private Limited (Formerly known as Green Infra Wind Energy Limited) | SR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 0 | 300 | 0 | 300 |  | Granted | 300 | 0 | 300 | Gadag-II | Karnataka | 2024-09-13 | 2025-12-27 | • Generation Pooling Station of M/s Green Infra Wind Energy Ltd. –Gadag-II PS 220 kV S/c line including 220 kV line bay at generation pooling station – under the scope of grantee. • 01 nos. of 220 kV line bays at Gadag-II PS for termination of above dedicated Connectivity line – under the scope of ISTS. | 1 | 220 KV | Aug without ATS |  |  | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (PhaseA) in Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS): • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (PhaseA) in Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 01-04-2025 | 01-04-2025 |  |  | 300 | 204 |  |  |  | 2026-06-30 | 2025-12-26 | 2026-10-31 |  | Not effective | 2027-01-17 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 01-04-2025 |  | 2025-04-01 | 2026-10-31
9200000032 | Conn under 37.1_37.2_37.6 | 0251100021 | Tata Power Renewable Energy Ltd. | SR | L&A | (i) Generating station(s), including REGS(s), without ESS | Wind | 300 |  | 300 | 0 | 0 | 300 |  | Granted | 300 | 0 | 300 | Koppal-II | Karnataka | 2025-02-28 | 2025-12-27 | • Generation Pooling Station of M/s Tata Power Renewables Energy Ltd. –Koppal-II PS 220 kV S/c line including 220 kV line bay at generation pooling station – under the scope of applicant. • 01 nos. of 220 kV line bays at Koppal-II PS for termination of above dedicated Connectivity line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission System for Connectivity – under ISTS • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (PhaseA) in Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission System for Connectivity – under ISTS • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (PhaseA) in Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 01-04-2025 | 01-04-2025 |  |  | 300 | 204 |  |  |  | 2026-06-30 | 2025-12-26 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 01-04-2025 |  | 2025-04-01 | 2026-10-31
9200000033 | Conn under 37.1_37.2_37.6 | 0251100006 | TP Saurya Ltd. | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 |  | 0 | 200 | 0 | 200 |  | Granted | 200 | 0 | 200 | Gadag-II | Karnataka | 2024-09-13 | 2025-12-27 | • Generation Pooling Station of Ms TP Saurya Ltd. - Gadag-II PS 220 kV Sc line including 220 kV terminal bays at generation pooling station – under the scope of applicant. • 01 nos. of 220 kV line bay at Gadag-II PS for termination of above dedicated Connectivity line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission System for Connectivity – under ISTS • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (PhaseA) in Karnataka • ISTS Network Expansion scheme in Western Region & Southern Reg | Common Transmission System for Connectivity – under ISTS • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (PhaseA) in Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 31-10-2024 | 31-10-2024 |  |  | 200 | 202 | 2026-12-29 |  | SECI vide letter dated 20.05.2024has extended the SCD of the project upto 24.02.2026 or ‘Actual date of connectivity+60 days’ whichever is later. |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-01-31 ¦ Status: Under Implementation ¦ Type: Wind | 30.06.2026 |  |  | 21/07/2026 | Pending with Level 2 | 31-10-2024 |  | 2024-10-31 | 2026-12-29
9200000034 | Conn under 37.1_37.2_37.6 | 0251100012 | Tata Power Renewable Energy Ltd. | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 170 |  | 0 | 170 | 0 | 170 |  | Granted | 170 | 0 | 170 | Gadag-II | Karnataka | 2024-09-13 | 2025-12-27 | • Generation Pooling Station of Ms Tata Power Renewables Energy Ltd. - Gadag-II PS 220 kV Sc line including 220 kV line bay at generation pooling station – under the scope of applicant. • 01 nos. of 220 kV line bays at Gadag-II PS for termination of above dedicated Connectivity line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission System for Connectivity – under ISTS • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (PhaseA) in Karnataka • ISTS Network Expansion scheme in Western Region & Southern Reg | Common Transmission System for Connectivity – under ISTS • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (PhaseA) in Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 01-04-2025 | 01-04-2025 |  |  | 170 | 206 |  |  |  | 2026-06-30 | 2025-12-26 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 170.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 01-04-2025 |  | 2025-04-01 | 2026-10-31
9200000064 | Conn under 37.1_37.2_37.6 | 0230700011 | Sarjan Realities Pvt. Ltd. (SRPL) | WR | L&A | (x) Renewable Power Park developer | Hybrid | 1240.40 | 0 | 1100 | 140.4 | 0 | 1240.4 | 0 | Granted | 1150 | 0 | 1150 | KPS-1 (Sec-II) | Gujarat | 2024-07-25 | 2025-12-26 | SRPL – KPS1 (GIS) (Bus Section-II) 400kV Sc line along with associated line bay at generation end (under the scope of applicant) | 1 |  | Aug without ATS |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line KPS1 Augmentation Scheme • Augmentation of transformation capacity at KPS1(GIS) by 765400kV, 4x1500MVA ICTs (4th, 5th ,6th & 7th on bus section-II) • KPS1 – KPS2 765kV Dc line Khavda Phase-II • KPS2 – L | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line KPS1 Augmentation Scheme • Augmentation of transformation capacity at KPS1(GIS) by 765400kV, 4x1500MVA ICTs (4th, 5th ,6th & 7th on bus section-II) • KPS1 – KPS2 765kV Dc line Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari (New) 765 kV Dc line | 30-04-2025 | 30-04-2025 |  |  | 1150 | 429 |  |  |  | 2025-02-18 | 2025-12-26 | 2026-12-31 |  | Not effective | 2026-12-31 | Under Construction | Part Commissioned | 630 | ¦ Phase 1 ¦ MW: 62.40 ¦ Date: 2024-12-27 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 36.40 ¦ Date: 2025-01-05 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 20.80 ¦ Date: 2025-01-15 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 10.40 ¦ Date: 2025-02-12 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 5 ¦ MW: 50.00 ¦ Date: 2025-09-10 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 50.00 ¦ Date: 2025-09-30 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 7 ¦ MW: 50.00 ¦ Date: 2025-02-21 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 8 ¦ MW: 50.00 ¦ Date: 2025-03-28 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 9 ¦ MW: 50.00 ¦ Date: 2025-03-30 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 10 ¦ MW: 75.00 ¦ Date: 2025-05-22 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 11 ¦ MW: 50.00 ¦ Date: 2025-06-28 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 12 ¦ MW: 75.00 ¦ Date: 2025-08-05 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 13 ¦ MW: 50.00 ¦ Date: 2025-08-30 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 14 ¦ MW: 600.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-04-2025 |  | 2025-04-30 | 2026-12-31
9200000065 | Conn under 37.1_37.2_37.6 | 0230700012 | Sarjan Realities Pvt. Ltd. (SRPL) | WR | L&A | (x) Renewable Power Park developer | Hybrid | 1332 |  | 1176 | 156 | 0 | 1332 | 0 | Granted | 1250 | 0 | 1250 | KPS-3 (Sec-I) | Gujarat | 2024-07-25 | 2025-12-26 | SRPL – KPS3 (GIS) (Bus Section-I) 400kV Sc line along with associated line bay at generation end (under the scope of applicant) | 1 |  | Aug without ATS |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line KPS1 Augmentation Scheme (part system) • KPS1 – KPS2 765kV Dc line Establishment Khavda Pooling Station-3 • Establishment of 765400 kV, 3x1500MVA, KPS3 (GIS) • KPS3 – KPS2 765kV Dc line Khavda Phase | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line KPS1 Augmentation Scheme (part system) • KPS1 – KPS2 765kV Dc line Establishment Khavda Pooling Station-3 • Establishment of 765400 kV, 3x1500MVA, KPS3 (GIS) • KPS3 – KPS2 765kV Dc line Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari (New) 765 kV Dc line Khavda Phase-IV Part E3 • Augmentation of transformation capacity at KPS3(GIS) by 765400kV, 1x1500MVA ICT (4th ICT on bus Section-I) | 30-04-2025 | 30-04-2025 |  |  | 1250 | 415 |  |  |  |  | 2025-07-07 | 2026-12-31 |  | Not effective | 2026-12-31 | Under Construction | Part Commissioned | 1098 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2025-04-24 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 75.00 ¦ Date: 2025-06-25 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 12.50 ¦ Date: 2025-09-01 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 87.50 ¦ Date: 2025-08-06 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 5 ¦ MW: 62.50 ¦ Date: 2025-06-11 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 6 ¦ MW: 37.50 ¦ Date: 2025-09-30 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 7 ¦ MW: 50.00 ¦ Date: 2025-09-30 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 8 ¦ MW: 75.00 ¦ Date: 2025-11-28 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 9 ¦ MW: 52.00 ¦ Date: 2025-06-19 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 10 ¦ MW: 67.60 ¦ Date: 2026-06-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 11 ¦ MW: 26.00 ¦ Date: 2025-08-01 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 12 ¦ MW: 10.40 ¦ Date: 2026-03-18 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 13 ¦ MW: 50.00 ¦ Date: 2025-09-16 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 14 ¦ MW: 50.00 ¦ Date: 2025-11-27 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 15 ¦ MW: 25.00 ¦ Date: 2025-12-29 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 16 ¦ MW: 17.00 ¦ Date: 2025-03-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 17 ¦ MW: 25.00 ¦ Date: 2025-12-29 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 18 ¦ MW: 50.00 ¦ Date: 2026-02-12 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 19 ¦ MW: 75.00 ¦ Date: 2026-03-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 20 ¦ MW: 50.00 ¦ Date: 2026-01-21 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 21 ¦ MW: 50.00 ¦ Date: 2026-03-26 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 22 ¦ MW: 50.00 ¦ Date: 2026-04-28 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 23 ¦ MW: 234.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  |  | Pending with Level 2 | 30-04-2025 |  | 2025-04-30 | 2026-12-31
9200000066 | Conn under 37.1_37.2_37.6 | 0230700013 | Sarjan Realities Pvt. Ltd. (SRPL) | WR | L&A | (x) Renewable Power Park developer | Hybrid | 1252.200 | 0 | 1065 | 187.2 | 0 | 1252.2 | 0 | Granted | 1250 | 0 | 1250 | KPS-3 (Sec-II) | Gujarat | 2025-01-27 | 2026-11-19 | SRPL – KPS3 (GIS) (Bus Section-II) 400kV S/c line along with associated line bay at generation end (under the scope of applicant) | 1 | 400 kV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA Khavda Phase-I: • KPS1 – Bhuj 765kV D/c line Establishment Khavda Pooling Station-3: • Establishment of 765/400 kV, 3x1500MVA, KPS3 (GIS) • KPS3 – KPS2 765kV D/c line Khavda Phase-II Khavda Phase-III Khavda Phase-IV (Part A to D) Khavda Phase-IV: Part E4 | Common Transmission System Augmentation for Connectivity under GNA Khavda Phase-I: • KPS1 – Bhuj 765kV D/c line Establishment Khavda Pooling Station-3: • Establishment of 765/400 kV, 3x1500MVA, KPS3 (GIS) • KPS3 – KPS2 765kV D/c line Khavda Phase-II Khavda Phase-III Khavda Phase-IV (Part A to D) Khavda Phase-IV: Part E4 | 30-04-2025 | 30-04-2025 |  |  | 1250 | 426M & 425T |  |  |  |  | 2026-11-19 | 2027-10-31 |  | Not effective | 2026-11-19 | Under Construction | Part Commissioned | 185 | ¦ Phase 1 ¦ MW: 185.00 ¦ Date: 2026-02-23 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 265.00 ¦ Date: 2027-10-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 300.00 ¦ Date: 2027-10-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 4 ¦ MW: 500.00 ¦ Date: 2027-10-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 30-04-2025 |  | 2025-04-30 | 2027-10-31
9200000067 | Conn under 37.1_37.2_37.6 | 0230700014 | Sarjan Realities Pvt. Ltd. (SRPL) | WR | L&A | (x) Renewable Power Park developer | Hybrid | 1100 | 0 | 1100 | 200 | 0 | 1300 | 0 | Granted | 1100 | 0 | 1100 | KPS-3 (Sec-I) | Gujarat | 2024-09-24 | 2026-07-31 | SRPL – KPS3 (GIS) (Bus Section-I) 400kV Sc line along with associated line bay at generation end (under the scope of applicant) | 1 | 400 KV | Aug without ATS |  |  | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line KPS1 Augmentation Scheme (part system) • KPS1 – KPS2 765kV Dc line Establishment Khavda Pooling Station-3 • Establishment of 765400 kV, 3x1500MVA, KPS3 (GIS) • KPS3 – KPS2 765kV Dc line Khavda Phase | Khavda Phase-I • KPS1 – Bhuj 765kV Dc line KPS1 Augmentation Scheme (part system) • KPS1 – KPS2 765kV Dc line Establishment Khavda Pooling Station-3 • Establishment of 765400 kV, 3x1500MVA, KPS3 (GIS) • KPS3 – KPS2 765kV Dc line Khavda Phase-II • KPS2 – Lakadia 765kV Dc line • Establishment of 3x1500 MVA, 765400 kV Ahmedabad Ss • Lakadia – Ahmedabad 765kV Dc line • Ahmedabad – Navsari (New) 765kV Dc line • LILO of Pirana (PG) – Pirana (T) 400kV Dc line at Ahmedabad Ss with twin HTLS along with reconductoring of Pirana (PG) – Pirana(T) line with twin HTLS conductor and Bay upgradation work at Pirana (PG) & Pirana (T) Khavda Phase-III • Establishment of 765 kV Halvad switching station • KPS2- Halvad 765 kV Dc line • LILO of Lakadia – Ahmedabad 765 kV Dc line at Halvad • Halvad – Vataman 765 kV Dc line • Establishment of 765 kV switching station near Vataman • LILO of Lakadia – Vadodara 765 kV Dc line at Vataman 765 kV switching station • Vataman switching station – Navsari (New) 765 kV Dc line Khavda Phase-IV Part E3 • Augmentation of transformation capacity at KPS3(GIS) by 765400kV, 1x1500MVA ICT (4th ICT on bus Section-I) | 30-04-2025 | 30-04-2025 |  |  | 1100 | [5 empty] | 2025-12-26 | 2026-12-31 |  | Not effective | 2026-12-31 | Under Construction | Part Commissioned | 137.5 | ¦ Phase 1 ¦ MW: 137.50 ¦ Date: 2026-03-20 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 300.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 400.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 4 ¦ MW: 262.50 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 30-04-2025 |  | 2025-04-30 | 2027-01-31
9200000070 | Conn under 37.1_37.2_37.6 | 1670426092248 | Adani Green Energy Ltd. | WR | L&A | (x) Renewable Power Park developer | Hybrid | 1050 | 0 | 1000 | 245 | 0 | 1245 | 0 | Granted | 1050 | 0 | 1050 | KPS-1 (Sec-I) | Gujarat | 2024-01-19 | 2025-12-25 | AGEL – KPS1 (Bus Section-I) 400kV Sc line along with associated bay at generation end (under the scope of applicant) | 1 |  | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA Khavda Phase-I • Establishment of 765400 kV, 3x1500MVA, KPS1 (GIS) • KPS1 – Bhuj 765kV Dc line KPS1 Augmentation Scheme • KPS1 – KPS2 765kV Dc line Khavda Phase-II Khavda Phase | Common Transmission System Augmentation for Connectivity under GNA Khavda Phase-I • Establishment of 765400 kV, 3x1500MVA, KPS1 (GIS) • KPS1 – Bhuj 765kV Dc line KPS1 Augmentation Scheme • KPS1 – KPS2 765kV Dc line Khavda Phase-II Khavda Phase-III Khavda Phase-IV Part E1 | 31-12-2024 | 31-12-2024 |  |  | 1050 | 412 |  |  |  |  | 2025-12-26 | 2026-12-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 800.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2026-12-31
9200000072 | Conn under 37.1_37.2_37.6 | 0230700015 | NHPC Limited | WR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 600 |  | 600 | 0 | 0 | 600 | 0 | Granted | 600 | 0 | 600 | KPS-3 (Sec-II) | Gujarat | 2025-01-27 | 2026-11-19 | NHPC – KPS3 400kV S/c line (on D/c tower) along with 400kV line bay at generation end (under the scope of applicant) | 1 | 400 kV | Aug without ATS |  |  | Common Transmission System Augmentation for Connectivity under GNA Khavda Phase-I: • KPS1 – Bhuj 765kV D/c line KPK3 Establishment scheme: a) Establishment of 765/400 kV, 3x1500MVA, KPS3 (GIS) b) KPS3 – KPS2 765kV D/c line Khavda Phase-II Khavda Phase-III Khavda Phase-IV | Common Transmission System Augmentation for Connectivity under GNA Khavda Phase-I: • KPS1 – Bhuj 765kV D/c line KPK3 Establishment scheme: a) Establishment of 765/400 kV, 3x1500MVA, KPS3 (GIS) b) KPS3 – KPS2 765kV D/c line Khavda Phase-II Khavda Phase-III Khavda Phase-IV | 11-11-2023 | 11-11-2023 |  |  | 600 | 429M & 428T |  |  |  | 2026-08-30 | 2026-08-30 | 2027-10-31 |  | Not effective | 2026-11-19 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 250.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 3 ¦ MW: 300.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Solar | 08-07-2026 | Yes |  |  | Pending with Level 2 | 11-11-2023 |  | 2023-11-11 | 2027-10-31
9200000099 | Conn under 37.1_37.2_37.6 | 0231300002 | Veh Jayin Renewables Private Limited | WR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 151.8 |  | 0 | 151.8 | 0 | 151.8 | 0 | Granted | 151.8 | 0 | 151.8 | Rajgarh (Sec-II) | Madhya Pradesh | 2024-03-11 | 2025-11-15 | • VJRPL – Rajgarh SS 220kV Sc line (on Dc tower) along with associated bay at Generator end (Under the scope of applicant) • 220kV GIS line bay at Rajgarh 400220kV (PG) Ss (on extended bus) for RE interconnection (under the scope of ISTS) | 1 | 220 KV | Aug without ATS |  |  | 1. 220kV bus extension (GIS) of Rajgarh (PG) 400220 kV Ss along with 220kV Bus Coupler Bay for extended bus (under the scope of ISTS) 2. 220kV bus sectionaliser bay (GIS) between existing & extended 220 kV bus of Rajgarh Ss. (under the scope of ISTS) 3. | 1. 220kV bus extension (GIS) of Rajgarh (PG) 400220 kV Ss along with 220kV Bus Coupler Bay for extended bus (under the scope of ISTS) 2. 220kV bus sectionaliser bay (GIS) between existing & extended 220 kV bus of Rajgarh Ss. (under the scope of ISTS) 3. 1x500MVA, 400220kV ICT (3rd) at Rajgarh Ss (on the sectionalized 220kV bus) along with associated bays at both ends (400kV AIS & 220kV GIS) | 29-03-2024 | 29-03-2024 |  |  | 151.8 | 215 |  |  |  | 2024-12-01 | 2025-11-15 | 2026-08-30 |  | Not effective | 2026-08-25 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 108.90 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 42.90 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 05/08/2026 | Pending with Level 2 | 29-03-2024 |  | 2024-03-29 | 2026-08-30
9200000101 | Conn under 37.1_37.2_37.6 | 0231300004 | Veh Wind Energy Private Limited | WR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 75 |  | 0 | 75 | 0 | 75 | 0 | Granted | 75 | 0 | 75 | Rajgarh (Sec-II) | Madhya Pradesh | 2024-03-11 | 2025-11-15 | VWEPL in application no. 0231300004 shall share the DTL identified to Veh Jayin Renewables Private Limited in application no. 0231300002 (151.8MW), which is detailed below • VJRPL – Rajgarh SS 220kV Sc line (on Dc tower) along with associated bay at Generator end (Under the scope of applicant) • 220kV GIS line bay at Rajgarh 400220kV (PG) Ss (on extended bus) for RE interconnection (under the scope of ISTS) | 0 |  | Aug without ATS |  |  | 1. 220kV bus extension (GIS) of Rajgarh (PG) 400220 kV Ss along with 220kV Bus Coupler Bay for extended bus (under the scope of ISTS) 2. 220kV bus sectionaliser bay (GIS) between existing & extended 220 kV bus of Rajgarh Ss. (under the scope of ISTS) 3. | 1. 220kV bus extension (GIS) of Rajgarh (PG) 400220 kV Ss along with 220kV Bus Coupler Bay for extended bus (under the scope of ISTS) 2. 220kV bus sectionaliser bay (GIS) between existing & extended 220 kV bus of Rajgarh Ss. (under the scope of ISTS) 3. 1x500MVA, 400220kV ICT (3rd) at Rajgarh Ss (on the sectionalized 220kV bus) along with associated bays at both ends (400kV AIS & 220kV GIS) | 31-10-2024 | 31-10-2024 |  |  | 75 | 215 |  |  |  | 2024-12-01 | 2025-11-15 | 2026-08-30 |  | Not effective | 2026-08-25 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 75.00 ¦ Date: 2027-07-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 05/08/2026 | Pending with Level 2 | 31-10-2024 |  | 2024-10-31 | 2026-08-30
9200000102 | Conn under 37.1_37.2_37.6 | 0331300007 | Sprng Vayu Vidyut Pvt Ltd (SVVPL) | WR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 100.8 |  | 0 | 100.8 | 0 | 100.8 | 0 | Granted | 100.8 | 0 | 100.8 | Rajgarh (Sec-II) | Madhya Pradesh | 2024-03-11 | 2026-12-31 | SVVPL in application no. 0331300007 shall share the DTL provided with SVVPL in application no. 02200000022 (100MW), which is detailed below: • SVVPL – Rajgarh (PG) 220kV S/c line (on D/c tower) along with associated bay at Generator end (Under the scope of applicant) • 220kV GIS line bay at Rajgarh 400/220kV (PG) S/s (on extended bus) for RE interconnection (under the scope of ISTS) | 0 | 220 kV | Aug without ATS |  |  | 1. 220kV bus extension (GIS) of Rajgarh (PG) 400/220 kV S/s along with 220kV Bus Coupler Bay for extended bus (under the scope of ISTS) 2. 220kV bus sectionaliser bay (GIS) between existing & extended 220 kV bus of Rajgarh S/s. (under the scope of ISTS) 3. 1x500MVA, 400/220kV ICT (3rd) at Rajgarh S/s (on the sectionalized 220kV bus) along with associated bays at both ends (400kV AIS & 220kV GIS) | 1. 220kV bus extension (GIS) of Rajgarh (PG) 400/220 kV S/s along with 220kV Bus Coupler Bay for extended bus (under the scope of ISTS) 2. 220kV bus sectionaliser bay (GIS) between existing & extended 220 kV bus of Rajgarh S/s. (under the scope of ISTS) 3. 1x500MVA, 400/220kV ICT (3rd) at Rajgarh S/s (on the sectionalized 220kV bus) along with associated bays at both ends (400kV AIS & 220kV GIS) | 31-08-2025 | 31-08-2025 |  |  | 100.8 | 217 |  |  |  | 2024-12-05 | 2025-11-15 | 2026-06-30 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.80 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  |  | Pending with Level 2 | 31-08-2025 |  | 2025-08-31 | 2027-06-30
9200000120 | Conn under 37.1_37.2_37.6 | 0231400004 | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) | WR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 10 |  | 0 | 10 | 0 | 10 | 0 | Granted | 10 | 0 | 10 | kallam | Maharashtra | 2024-05-30 | 2025-10-05 | SRI4PL in subject application shall share the DTL provided to SRI4PL in GNA intimation no. CTUW537.1 431400004 & 412100015, which is detailed below SRI4PL – Kallam PS 220kV Sc line (on Dc tower) (with minimum capacity of 350MW at nominal voltage) along with associated bay at Generation end (under the scope of applicant) | 1 |  | Aug without ATS |  |  | • Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 nos. 220 kV line bays for RE interconnection • LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | • Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 nos. 220 kV line bays for RE interconnection • LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | 01-07-2024 | 01-07-2024 |  |  | 10 | 209 |  |  |  |  | 2025-10-05 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 10.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 06-05-2026 |  |  | 06/05/2026 | Not Submitted For Approval | 01-07-2024 |  | 2024-07-01 | 2026-10-30
9200000121 | Conn under 37.1_37.2_37.6 | 0331400007 | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) | WR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 140 |  | 0 | 140 | 0 | 140 | 0 | Granted | 140 | 0 | 140 | kallam | Maharashtra | 2024-05-30 | 2025-10-05 | SRI4PL in subject application shall share the DTL provided to SRI4PL in GNA intimation no. CTUW537.1 431400004 & 412100015, which is detailed below SRI4PL – Kallam PS 220kV Sc line (on Dc tower) (with minimum capacity of 350MW at nominal voltage) along with associated bay at Generation end (under the scope of applicant) | 0 |  | Aug without ATS |  |  | • Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 nos. 220 kV line bays for RE interconnection • LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | • Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 nos. 220 kV line bays for RE interconnection • LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | 01-07-2024 | 01-07-2024 |  |  | 140 | 212 |  |  |  | 2025-01-01 | 2025-10-05 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 55.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 2 ¦ MW: 85.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: Wind | 06-05-2026 |  |  | 06/05/2026 | Pending with Level 2 | 01-07-2024 |  | 2024-07-01 | 2026-10-30
9200000123 | Conn under 37.1_37.2_37.6 | 1200003942 | ReNew Green (MHP One) Private Limited | WR | L&A | (i) Generating station(s), including REGS(s), without ESS | Wind | 33 |  | 0 | 33 | 0 | 33 | 0 | Granted | 33 | 0 | 33 | kallam | Maharashtra | 2024-05-30 | 2025-10-05 | RG(MO)PL in subject application (33MW) shall share the DTL provided to RG(MO)PL in application no. 1200003881 (117MW), which is detailed below RG(MO)PL – Kallam PS 220kV Sc line (on Dc tower) along with associated bay at Generation end (under the scope of applicant) | 0 |  | Aug without ATS |  |  | • Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 nos. 220 kV line bays for RE interconnection • LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | • Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 nos. 220 kV line bays for RE interconnection • LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | 30-06-2023 | 30-06-2023 |  |  | 33 | 202 |  |  |  |  | 2025-10-05 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Part Commissioned | 18.3 | ¦ Phase 1 ¦ MW: 13.20 ¦ Date: 2025-11-14 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 5.10 ¦ Date: 2025-12-14 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 14.70 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 06-05-2026 |  |  |  | Pending with Level 2 | 30-06-2023 |  | 2023-06-30 | 2026-10-30
9200000124 | Conn under 37.1_37.2_37.6 | 1200003901 | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) | WR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 200 |  | 0 | 200 | 0 | 200 | 0 | Granted | 200 | 0 | 200 | kallam | Maharashtra | 2024-05-30 | 2025-10-05 | TGPXIPL – Kallam PS 220kV Sc line (on Dc tower)along with associated bay at Generation end (under the scope of applicant) | 1 |  | Aug without ATS |  |  | • Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 nos. 220 kV line bays for RE interconnection • LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | • Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 nos. 220 kV line bays for RE interconnection • LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | 27-04-2024 | 27-04-2024 |  |  | 200 | 205 | 2025-12-02 |  | SECI extended SCOD of generation project till 02.12.2025 |  | 2025-10-05 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 27-04-2024 |  | 2024-04-27 | 2026-10-30
9200000125 | Conn under 37.1_37.2_37.6 | 1200003944 | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) | WR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 99 |  | 0 | 99 | 0 | 99 | 0 | Granted | 99 | 0 | 99 | kallam | Maharashtra | 2024-05-30 | 2025-10-05 | TGPXIPL in subject application (99MW) shall share the DTL provided to TGPXIPL in application no. 1200003901 (200MW), which is detailed below TGPXIPL – Kallam PS 220kV Sc line (on Dc tower) along with associated bay at Generation end (under the scope of applicant) | 0 |  | Aug without ATS |  |  | • Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 nos. 220 kV line bays for RE interconnection • LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | • Augmentation of transformation capacity at Kallam PS by 2x500 MVA, 400220 kV ICTs (3rd & 4th) alongwith 3 nos. 220 kV line bays for RE interconnection • LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | 27-04-2024 | 27-04-2024 |  |  | 99 | 205 |  |  |  |  | 2025-10-05 | 2026-10-30 |  | Not effective | 2026-10-31 | Under Construction | Part Commissioned | 48.2 | ¦ Phase 1 ¦ MW: 13.50 ¦ Date: 2025-07-31 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 2 ¦ MW: 13.50 ¦ Date: 2025-09-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 8.10 ¦ Date: 2025-08-16 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 8.10 ¦ Date: 2025-09-27 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 5 ¦ MW: 5.00 ¦ Date: 2026-05-14 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 6 ¦ MW: 31.50 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 21/07/2026 | Pending with Level 2 | 27-04-2024 |  | 2024-04-27 | 2026-10-30
9200000130 | Conn under 37.1_37.2_37.6 | 1670224223993 | Torrent Solar Power Private Limited (TSPPL) | WR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 66 |  | 0 | 66 | 0 | 66 | 0 | Granted | 66 | 0 | 66 | kallam | Maharashtra | 2024-07-15 | 2025-10-05 | TSPPL – Kallam PS 400kV Sc line along with associated bay at generator end (Under the scope of applicant) | 1 |  | Aug without ATS |  |  | LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | 31-12-2024 | 31-12-2024 |  |  | 66 | 421 |  |  |  | 2025-03-31 | 2025-10-05 | 2027-06-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 66.00 ¦ Date: 2027-07-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Group Head | 31-12-2024 |  | 2024-12-31 | 2027-06-30
9200000131 | Conn under 37.1_37.2_37.6 | 0331400013 | Torrent Solar Power Private Limited (TSPPL) | WR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 92 |  | 0 | 92 | 0 | 92 | 0 | Granted | 92 | 0 | 92 | kallam | Maharashtra | 2024-05-30 | 2025-10-05 | TSPPL in subject application (92MW) shall share the DTL provided to TSPPL in application no. 1670224223993 (66MW), which is detailed below TSPPL – Kallam PS 400kV Sc line along with associated bay at generator end (Under the scope of applicant) | 0 |  | Aug without ATS |  |  | LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | LILO of both circuits of Parli(M) – Karjat(M)LonikandII(M) 400kV Dc line (twin moose) at Kallam PS | 31-12-2024 | 31-12-2024 |  |  | 92 | 421 |  |  |  | 2025-03-31 | 2025-10-05 | 2027-06-30 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 92.00 ¦ Date: 2027-10-31 ¦ Status: Under Implementation ¦ Type: Wind | 08-07-2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2027-06-30
9200000146 | Conn under 37.1_37.2_37.6 | 212100042 | Proteus Energy Private Limited (Park) | NR | L&FC | (x) Renewable Power Park developer | Solar | 217 |  | 217 | 0 | 0 | 217 | 0 | Granted | 217 | 0 | 217 | Bikaner-III | Rajasthan | 2024-09-23 | 2026-08-22 | Proteus Energy Private Limited Solar Project–Bikaner-III PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW per circuit at nominal voltage)-under applicant scope Connectivity of 50 MW to Ms Avaada RJ (Application no.- 2200000013) at Bikaner-III PS is also granted in sharing with Ms Proteus through same DTL & bay ## | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x500MVA (1st & 2nd) 400220 kV ICTs at Bikaner –III PS Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (3rd & 4th) , 765400 kV ICTs at B | Transmission system for Connectivity under GNA Augmentation of 2x500MVA (1st & 2nd) 400220 kV ICTs at Bikaner –III PS Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (3rd & 4th) , 765400 kV ICTs at Bikaner-III Pooling Station LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation of 2x1500 MVA (3rd & 4th), 765400 kV ICTs at Neemrana-II Ss Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore (PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV Dc Line Or 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-03-2025 | 31-03-2025 |  |  | 217 | 203 |  |  |  | 2026-03-31 | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 117.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-03-2025 |  | 2025-03-31 | 2027-09-30
9200000149 | Conn under 37.1_37.2_37.6 | 212100026 | Abu Renewables India Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 340 |  | 340 | 0 | 0 | 340 | 0 | Granted | 340 | 0 | 340 | Bhadla-III | Rajasthan | 2024-09-12 | 2026-08-22 | Abu Renewables India Private Limited Solar Power Project – Bhadla-III PS 220 kV Sc line (high capacity) on Dc tower# (Suitable to carry minimum 340 MW at nominal voltage)-Under applicant scope | 1 | 220 KV | Aug without ATS |  |  |  | 1) Augmentation of 1x500 MVA (3rd), 400220kV ICT at Bhadla-III 2) Augmentation of 2x1500 MVA (2nd & 3rd), 765400kV ICTs at Bhadla-III 3) Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line 4) Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 5) Sikar-II – Khetri 765 kV Dc line 6) Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line 7) Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) 8) Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) * with minimum capacity of 2100 MVAckt at nominal voltage; Additional Transmission system for Inter-regional power transfer 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-12-2025 | 31-12-2025 |  |  | 340 | 210 |  |  |  |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 340.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-12-2025 |  | 2025-12-31 | 2027-03-31
9200000150 | Conn under 37.1_37.2_37.6 | 212100028 | Seven Renewable Power Pvt. Ltd. | NR | L&FC | (x) Renewable Power Park developer | Solar | 300 |  | 300 | 0 | 0 | 300 | 0 | Granted | 300 | 0 | 300 | Bhadla-III | Rajasthan | 2024-09-12 | 2026-08-30 | Seven Renewables Power Private Limited Solar Power Project – Bhadla-III PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage)-Under applicant | 1 | 220 KV | Aug without ATS |  |  |  | 1. Augmentation of 2x500 MVA (3rd & 4th) 400220kV ICTs at Bhadla-III 2. Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICTs at Bhadla-III 3. 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end 4. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line 5. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 6. Sikar-II – Khetri 765 kV Dc line 7. Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line 8. Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) 9. Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) * with minimum capacity of 2100 MVAckt at nominal voltage; Additional Transmission system for Inter-regional power transfer 1) Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 30-06-2024 | 30-06-2024 |  |  | 300 | 208 |  |  |  |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 150.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 30-06-2024 |  | 2024-06-30 | 2027-03-31
9200000151 | Conn under 37.1_37.2_37.6 | 212100031 | Frugal Energy Pvt. Ltd. | NR | L&A | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 | 0 | 50 | 0 | 0 | 50 | 0 | Granted | 50 | 0 | 50 | Bhadla-III | Rajasthan | 2024-09-23 | 2026-08-30 | Common pooling station of Ms Frugal Energy Pvt. Ltd. Renewable Power Park (App. No. 0212100031 - 50 MW & App. No. 2200000118 - 250 MW) – Bhadla-III PS 220 kV Sc line on Dc tower#(Suitable to carry minimum 300 MW at nominal voltage))- Under applicant scope Connectivity of 250 MW) to Ms Frugal Energy Pvt. Ltd.(Application no.- 2200000118) is granted in sharing with appliation of 50 MW (0212100031) through same DTL & bay | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (4th ) 400220kV ICT at Bhadla-III Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchab | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (4th ) 400220kV ICT at Bhadla-III Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICT at Bhadla-III 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line Sikar-II – Khetri 765 kV Dc line Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line Jhatikara – Dwarka 400kV Dc line (Quad) Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) Additional Transmission system for Inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-03-2025 | 31-03-2025 |  |  | 50 | 204 |  |  |  |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2028-04-01 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-03-2025 |  | 2025-03-31 | 2027-03-31
9200000153 | Conn under 37.1_37.2_37.6 | 1200003719 | Sprng Pavana Urja Private Limited | NR | L&FC | (x) Renewable Power Park developer | Solar | 50 |  | 50 | 0 | 0 | 50 | 0 | Granted | 50 | 0 | 50 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2027-06-30 | Common Pooling station of M/s Sprng Pavana Urja Pvt. Ltd for Solar Projects with App. Nos. 1200003719(50 MW) ,2200000018 (100 MW) & 2200000034(150 MW) – Fatehgarh-IV PS (Sec-II) 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage): Under applicant Scope Connectivity of 100 MW(Application no.- 2200000018) & 150 MW(App No. 2200000034) to M/s Sprng Pavana Urja Pvt. Ltd is granted in sharing with application of 50 MW (2200000003) through same DTL & bay | 1 | 220 KV | Aug without ATS |  |  | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (3rd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA, 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (3rd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA, 765/400 kV ICT at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line | 31-01-2025 | 31-01-2025 |  |  | 50 | 228 | 2026-03-30 |  |  | 2026-08-14 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-01-2025 |  | 2025-01-31 | 2027-12-30
9200000154 | Conn under 37.1_37.2_37.6 | 212100035 | Helia Energy Park Private Limited | NR | L&A | (x) Renewable Power Park developer | Solar | 200 | 0 | 200 | 0 | 0 | 200 | 0 | Granted | 200 | 0 | 200 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2026-10-15 | Common pooling station of M/s Helia Energy Park Private Limited Renewable Power Park (Appl. Nos. 2200000120 (100 MW) & Appl. Nos. 212100035(200 MW)) – Fatehgarh-IV PS (Section-2) 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage) - Under applicant scope Connectivity of 100 MW to M/s Helia Energy Pvt. Ltd.(Application no.- 2200000120) is granted in sharing with application of 200 MW by M/s Helia Energy Park Pvt. Ltd.(App No. 0212100035) through same DTL & bay | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 2x500 MVA (1st & 2nd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA (1st & 2nd ) , 765/400 kV ICTs at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV FatehgarhIV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | Transmission system for Connectivity under GNA: Augmentation of 2x500 MVA (1st & 2nd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA (1st & 2nd ) , 765/400 kV ICTs at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV FatehgarhIV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | 31-12-2024 | 31-12-2024 |  |  | 200 | 226 |  |  |  | 2026-08-14 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2027-06-30
9200000155 | Conn under 37.1_37.2_37.6 | 212100038 | Adani Solar Energy AP Three Ltd. | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 | 0 | 150 | 0 | 0 | 150 | 0 | Granted | 150 | 0 | 150 | Ramgarh | Rajasthan | 2024-09-23 | 2026-08-30 | Common Pooling station of M/s Adani Renewable Energy Holding Four Ltd. (500 MW) & M/s Adani Solar Energy AP Three Limited (150 MW) Solar Power Projects – Ramgarh PS 400 kV S/c line on D/c tower (Suitable to carry minimum 900 MW at nominal voltage) - under applicant scope. Connectivity of 150 MW to M/s Adani (Application no.- 0212100038) is granted in sharing with appliation of 500 MW (App No. 1200002432) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 2x1500 MVA (1st & 2nd), 765/400kV ICT at Ramgarh PS Ramgarh PS – Bhadla-III PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Ramgarh end Augmentation of 2x1500 MVA (3rd & 4th), 765/400kV ICT at Bhadla-III Bhadla-III – Bikaner-III 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end Fatehgarh-III – Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV D/c line Bhadla-III – Sikar-II 765 kV D/c line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV D/c line Sikar-II – Khetri 765 kV D/c line Sikar-II – Narela 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV D/c line Jhatikara – Dwarka 400kV D/c line (Quad) Augmentation of 1x1500 MVA ICT (3rd), 765/400kV ICT at Jhatikara Substation (Bamnoli/Dwarka section) Additional Transmission system for Inter-regional power transfer: Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Or 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | Transmission system for Connectivity under GNA: Augmentation of 2x1500 MVA (1st & 2nd), 765/400kV ICT at Ramgarh PS Ramgarh PS – Bhadla-III PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Ramgarh end Augmentation of 2x1500 MVA (3rd & 4th), 765/400kV ICT at Bhadla-III Bhadla-III – Bikaner-III 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end Fatehgarh-III – Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV D/c line Bhadla-III – Sikar-II 765 kV D/c line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV D/c line Sikar-II – Khetri 765 kV D/c line Sikar-II – Narela 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV D/c line Jhatikara – Dwarka 400kV D/c line (Quad) Augmentation of 1x1500 MVA ICT (3rd), 765/400kV ICT at Jhatikara Substation (Bamnoli/Dwarka section) Additional Transmission system for Inter-regional power transfer: Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Or 3b) Establishment of 765 kV Kurawar S/s with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line 3d) LILO of Indore – Bhopal 765 kV S/c line at Kurawar | 03-10-2023 | 03-10-2023 |  |  | 150 | 404(Main),405(Tie) | 2026-03-30 |  | 30.03.2026 OR 30 days subsequent to the readiness of the power evacuation infrastructure/operalisation of LTA'GNA at Ramgarh S/S whichever is earlier. |  | 2026-08-22 | 2027-03-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: |  | Yes |  | 08/07/2026 | Pending with Level 2 | 03-10-2023 |  | 2023-10-03 | 2027-03-31
9200000158 | Conn under 37.1_37.2_37.6 | 412100012, 0212100027 (St-II) | Juniper Green Beta Pvt. Ltd. | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 |  | 150 | 0 | 0 | 150 | 0 | Granted | 150 | 0 | 150 | Bhadla-III | Rajasthan | 2024-05-03 | 2026-02-28 | Common pooling station of Ms Juniper Green Beta Private Limited Solar power projects of 300 MW ((0212100027(150 MW), 0312100013 (40 MW), SW…1670400777119(70 MW) & 312100021(40 MW)) – Bhadla-III PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) - Under applicant scope Connectivity of 40 MW, 70 MW & 40 to Ms Juniper (Application nos.- 0312100013, SW…1670400777119 & 312100021 is granted in sharing with application of 150 MW (0212100027) through same DTL & bay | 1 | 220 KV | Aug without ATS |  |  |  | 1. 1x500 MVA (2nd), 400220 kV & 2x1500 MVA (1st & 2nd) 765400kV pooling station at Bhadla-III along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 2. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line 3. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 4. Sikar-II – Khetri 765 kV Dc line 5. Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line 6. Jhatikara – Dwarka 400kV Dc line (Twin HTLS) 7. Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) | 31-03-2025 | 31-03-2025 |  |  | 150 | 206 |  |  |  |  | 2026-02-28 | 2027-03-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-03-2025 |  | 2025-03-31 | 2027-03-31
9200000159 | Conn under 37.1_37.2_37.6 | 412100013, 0312100013 (St-II), 1670400777119 (St-II) | Juniper Green Beta Pvt. Ltd. | NR | L&FC | (x) Renewable Power Park developer | Solar | 100 |  | 100 | 0 | 0 | 100 | 0 | Granted | 100 | 0 | 100 | Bhadla-III | Rajasthan | 2024-05-03 | 2026-02-28 | Common pooling station of Ms Juniper Green Beta Private Limited Solar power projects of 300 MW ((0212100027(150 MW), 0312100013 (40 MW), SW…1670400777119(70 MW) & 312100021(40 MW)) – Bhadla-III PS 220 kV Sc line on Dc tower - under applicant scope (Suitable to carry minimum 300 MW at nominal voltage) Connectivity of 40 MW, 70 MW & 40 to Ms Juniper (Application nos.- 0312100013, SW…1670400777119 & 312100021 is granted in sharing with application of 150 MW (0212100027) through same DTL & bay | 0 | 220 KV | Aug without ATS |  |  |  | 1. 1x500 MVA (2nd), 400220 kV & 2x1500 MVA (1st & 2nd) 765400kV pooling station at Bhadla-III along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 2. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line 3. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 4. Sikar-II – Khetri 765 kV Dc line 5. Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line 6. Jhatikara – Dwarka 400kV Dc line (Twin HTLS) 7. Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) | 31-03-2025 | 31-03-2025 |  |  | 100 | 206 |  |  |  |  | 2026-02-28 | 2027-03-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: | 06.08.2026 |  |  | 06/08/2026 | Pending with Level 2 | 31-03-2025 |  | 2025-03-31 | 2027-03-31
9200000160 | Conn under 37.1_37.2_37.6 | SW9990897533- M029_D001_A007- 1672319027575, 0212100030 (St-II) | Tepsol Sun Sparkle Pvt. Ltd. | NR | L&A | (x) Renewable Power Park developer | Solar | 300 |  | 300 | 0 | 0 | 300 | 0 | Granted | 300 | 0 | 300 | Bhadla-III | Rajasthan | 2024-05-03 | 2026-02-28 | Tepsol Sun Sparkle Private Limited Renewable Power Park Project– Bhadla-III PS 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW per circuit at nominal voltage) - under applicant scope | 1 | 220 KV | Aug without ATS |  |  | Transmission System for Connectivity under GNA: 2x500 MVA (1st & 2nd), 400/220 kV & 2x1500 MVA (1st & 2nd) 765/400kV pooling station at Bhadla-III along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Fatehgarh-III – Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV D/c line Bhadla-III – Sikar-II 765 kV D/c line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV D/c line Sikar-II – Khetri 765 kV D/c line Sikar-II – Narela 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV D/c line Jhatikara – Dwarka 400kV D/c line (Quad) Augmentation of 1x1500 MVA ICT (3rd), 765/400kV ICT at Jhatikara Substation (Bamnoli/Dwarka section) | Transmission System for Connectivity under GNA: 2x500 MVA (1st & 2nd), 400/220 kV & 2x1500 MVA (1st & 2nd) 765/400kV pooling station at Bhadla-III along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor Fatehgarh-III – Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV D/c line Bhadla-III – Sikar-II 765 kV D/c line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV D/c line Sikar-II – Khetri 765 kV D/c line Sikar-II – Narela 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV D/c line Jhatikara – Dwarka 400kV D/c line (Quad) Augmentation of 1x1500 MVA ICT (3rd), 765/400kV ICT at Jhatikara Substation (Bamnoli/Dwarka section) | 31-03-2025 | 31-03-2025 |  |  | 300 | 212 |  |  |  |  | 2026-02-28 | 2027-03-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-03-2025 |  | 2025-03-31 | 2027-03-31
9200000161 | Conn under 37.1_37.2_37.6 | 212100033 | Bhadla Three SKP Green Ventures Pvt. Ltd. | NR | L&A | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 | 0 | 300 | 0 | 0 | 300 | 0 | Granted | 300 | 0 | 300 | Bhadla-III | Rajasthan | 2024-09-12 | 2026-08-30 | Bhadla Three SKP Green Ventures Private Limited Renewable Power Park – Bhadla-III PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage)-Under applicant scope | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (4th ) 400220kV ICT at Bhadla-III Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICTs at Bhadla-III 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switc | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (4th ) 400220kV ICT at Bhadla-III Augmentation of 2x1500 MVA (3rd & 4th), 765400kV ICTs at Bhadla-III 765 kV Bhadla-III – Bikaner-III Dc line along with 240 MVAr switchable line reactor for each circuit at Bhadla-III end Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line Sikar-II – Khetri 765 kV Dc line Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line Jhatikara – Dwarka 400kV Dc line (Quad) Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) Additional Transmission system for Inter-regional power transfer Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-03-2025 | 31-03-2025 |  |  | 300 | 216 |  |  |  |  | 2026-08-30 | 2027-03-31 |  | Not effective | 2027-03-31 | Under Construction | Part Commissioned | 296 | ¦ Phase 1 ¦ MW: 148.00 ¦ Date: 2026-04-15 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 96.20 ¦ Date: 2026-04-18 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 51.80 ¦ Date: 2026-05-08 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 4 ¦ MW: 4.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  |  | Pending with Level 2 | 31-03-2025 |  | 2025-03-31 | 2027-03-31
9200000162 | Conn under 37.1_37.2_37.6 | 412100027 (SW5102826596-M029_D001_A003-1670400777119 (10MW out of 70MW) + 0312100011 (40MW)) | Juniper Green Beta Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 50 |  | 50 | 0 | 0 | 50 | 0 | Granted | 50 | 0 | 50 | Bhadla-III | Rajasthan | 2024-05-03 | 2026-02-28 | Common pooling station of Ms Juniper Green Beta Private Limited Solar power projects of 300 MW ((0212100027(150 MW), 0312100013 (40 MW), SW…1670400777119(70 MW) & 312100021(40 MW)) – Bhadla-III PS 220 kV Sc line# (Suitable to carry minimum 300 MW at nominal voltage) - Under applicant scope Connectivity of 40 MW, 70 MW & 40 to Ms Juniper (Application nos.- 0312100013, SW…1670400777119 & 312100021 is granted in sharing with application of 150 MW (0212100027) through same DTL & bay | 0 | 220 KV | Aug without ATS |  |  |  | 1. 1x500 MVA (2nd), 400220 kV & 2x1500 MVA (1st & 2nd) 765400kV pooling station at Bhadla-III along with 2x330 MVAr (765kV) Bus Reactor & 2x125 MVAr (420kV) Bus Reactor 2. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line 3. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 4. Sikar-II – Khetri 765 kV Dc line 5. Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line 6. Jhatikara – Dwarka 400kV Dc line (Twin HTLS) 7. Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) | 31-10-2025 | 31-10-2025 |  |  | 50 | 206 |  |  |  |  | 2026-02-28 | 2027-03-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: | 06.08.2026 |  |  | 06/08/2026 | Pending with Level 2 | 31-10-2025 |  | 2025-10-31 | 2027-03-31
9200000163 | Conn under 37.1_37.2_37.6 | 1200003893 | Litsolaire Energy Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 | 0 | Granted | 100 | 0 | 100 | Bikaner-II | Rajasthan | 2024-02-08 | 2025-12-27 | Through sharing of dedicated transmission system of Ms ReNew Dinkar Urja Private Limited (Appl. No. 1200003380-200 MW) – Bikaner-II PS 220 kV Sc line on Dc tower (Suitable to carry minimum 300 MW at nominal voltage)- Under applicant scope Connectivity of 100 MW to Ms Litsolaire (Application no.- 1200003893) is granted in sharing with application of 200 MW by Ms Renew Dinkar Urja Private Limited (App No. 1200003380) through same DTL & bay | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500MVA (8th) 400220 kV ICT at Bikaner –II PS Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner- | Transmission system for Connectivity under GNA Augmentation of 1x500MVA (8th) 400220 kV ICT at Bikaner –II PS Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (3rd & 4th),765400 kV ICTs at Neemrana-II Ss LILO of both ckts of 400 kV Bikaner (PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) | 31-01-2024 | 31-01-2024 |  |  | 100 | 203 |  |  |  |  | 2025-12-27 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2026-08-15 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 31-01-2024 |  | 2024-01-31 | 2027-09-30
9200000164 | Conn under 37.1_37.2_37.6 | 212100025 | TP Saurya Limited | NR | L&A | (i) Generating station(s), including REGS(s), without ESS | Solar | 300 |  | 300 | 0 | 0 | 300 | 0 | Granted | 300 | 0 | 300 | Bikaner-III | Rajasthan | 2024-09-12 | 2026-08-22 | TP Saurya Limited Solar Power Project – Bikaner-III PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA 1x500MVA 400220kV ICT (1st) at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (3rd & 4th) , 765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 1x1500 MVA (4th) 765400kV I | Transmission system for Connectivity under GNA 1x500MVA 400220kV ICT (1st) at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (3rd & 4th) , 765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) LILO of both ckts of 400 kV Bikaner(PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation of 2x1500 MVA (3rd & 4th), 765400 kV ICTs Neemrana-II Ss Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for Inter-regional power transfer Establishment of 765kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-10-2024 | 31-10-2024 |  |  | 300 | 205 |  |  |  |  | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  | Bay anticipated CoD to be updated |  | Pending with Level 2 | 31-10-2024 |  | 2024-10-31 | 2027-02-28
9200000165 | Conn under 37.1_37.2_37.6 | 212100032 | Luceo Solar Pvt. Ltd. | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 200 |  | 200 | 0 | 0 | 200 | 0 | Granted | 200 | 0 | 200 | Fatehgarh-IV (Sec-I) | Rajasthan | 2024-09-12 | 2026-08-22 | Common Pooling station of Ms Luceo Solar Private Limited for Solar Power Projects with Appl. Nos. 0212100032 (200 MW) & 0312100018 (100 MW) – Fatehgarh-IV (Section-I) PS 220 kV Sc line on Dc tower# (Suitable to carry minimum 300 MW at nominal voltage) - Under applicant scope Connectivity of 100 MW to Ms Luceo (Application no.- 0312100018) is granted in sharing with application of 200 MW by Ms Luceo Solar Private Limited (App No. 0212100032) through same DTL & bay | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA (3rd & 4th) 400220 kV ICT at Fatehgarh-IV PS Augmentation of 2x1500 MVA (4th & 5th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Fatehgarh-IV- Fatehgarh-I | Transmission system for Connectivity under GNA Augmentation of 2x500 MVA (3rd & 4th) 400220 kV ICT at Fatehgarh-IV PS Augmentation of 2x1500 MVA (4th & 5th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Fatehgarh-IV- Fatehgarh-III 400 kV Dc (Twin HLTS*) line Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III- Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR * with minimum capacity of 2100 MVA on each circuit at nominal voltage Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-12-2024 | 31-12-2024 |  |  | 200 | 214 |  |  |  |  | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: |  |  | Bay Charged on 07.12.2025 | 08/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2027-02-28
9200000166 | Conn under 37.1_37.2_37.6 | 0312100018 (Enhancement) | Luceo Solar Pvt. Ltd. | NR | L&FC | (x) Renewable Power Park developer | Solar | 100 |  | 100 | 0 | 0 | 100 | 0 | Granted | 100 | 0 | 100 | Fatehgarh-IV (Sec-I) | Rajasthan | 2024-09-12 | 2026-08-22 | Common Pooling station of Ms Luceo Solar Private Limited for Solar Power Projects with Appl. Nos. 0212100032 (200 MW) & 0312100018 (100 MW) – Fatehgarh-IV (Section-1) PS 220 kV Sc line on Dc tower (Suitable to carry minimum 300 MW at nominal voltage)- Under applicant scope Connectivity of 100 MW to Ms Luceo Solar Private Limited (App. No.- 0312100018) is granted in sharing with application of 200 MW by Ms Luceo Solar Private Limited (App No. 0212100032) through same DTL & bay | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (4th) 400220 kV ICT at Fatehgarh-IV PS Augmentation of 2x1500 MVA (4th & 5th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Fatehgarh-IV- Fatehgarh-III 400 | Transmission system for Connectivity under GNA Augmentation of 1x500 MVA (4th) 400220 kV ICT at Fatehgarh-IV PS Augmentation of 2x1500 MVA (4th & 5th), 765400kV ICT at Fatehgarh-III pooling station (Section-II) Fatehgarh-IV- Fatehgarh-III 400 kV Dc (Twin HLTS*) line Establishment of 2x1500MVA 765400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV Dc (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV Dc line (2nd) Fatehgarh-III- Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV Dc line LILO of both circuit of Ajmer-Chittorgarh 765 kV Dc line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xSc at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV Dc line LILO of both circuits of Agra – Jaipur(south) 400kV Dc at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV Dc line Beawar – Dausa 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM Fatehgarh – III Ss STATCOM ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR * with minimum capacity of 2100 MVA on each circuit at nominal voltage Additional Transmission system for Inter-regional power transfer 1) Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2) Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line OR 3b) Establishment of 765kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-12-2024 | 31-12-2024 |  |  | 100 | 214 |  |  |  | 2025-12-07 | 2026-08-22 | 2027-02-28 |  | Not effective | 2027-02-28 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-12-31 ¦ Status: Under Implementation ¦ Type: |  |  | Bay Charged on 07.12.2025 | 08/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2027-02-28
9200000167 | Conn under 37.1_37.2_37.6 | 212100037 | Radiant Star Solar Park Private Limited | NR | L&A | (x) Renewable Power Park developer | Solar | 200 | 0 | 200 | 0 | 0 | 200 | 0 | Granted | 200 | 0 | 200 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2026-10-15 | M/s Radiant Star Solar Park Private Limited Renewable Power Park – Fatehgarh-IV PS (Section-II) 220 kV S/c line on D/c tower# (Suitable to carry minimum 300 MW at nominal voltage)-under applicant scope Connectivity of 50 MW to M/s Avaada Energy Pvt. Ltd.(Application no.- 2200000077) is also granted in sharing with M/s Radiant Star Solar Park Pvt. Ltd through same DTL & bay## | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Establishment of 2x1500 MVA, 765/400 kV & 2x500 MVA, (1st & 2nd) 400/220 kV Fatehgarh-IV (Section-2) Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR (420kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | Transmission system for Connectivity under GNA: Establishment of 2x1500 MVA, 765/400 kV & 2x500 MVA, (1st & 2nd) 400/220 kV Fatehgarh-IV (Section-2) Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR (420kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | 31-12-2024 | 31-12-2024 |  |  | 200 | 224 |  |  |  | 2026-08-14 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2027-06-30
9200000168 | Conn under 37.1_37.2_37.6 | 1200003848 | ReNew Solar (Shakti Six) Private Limited | NR | L&A | (x) Renewable Power Park developer | Solar | 550 |  | 550 | 0 | 0 | 550 | 0 | Granted | 550 | 0 | 550 | Bhadla-III | Rajasthan | 2024-09-12 | 2026-06-30 | Under Applicant Scope • Establishment Of Common Pooling Sub—Station I (PSS-I) of MS ReNew solar (Shakti Six) Pvt. Ltd (App. Nos. 1200003848 for 550 MW & 0312100004 for 450 MW) • Common Pooling Sub-station 1 (PSS-I) - Bhadla-lll PS 400kV Sic line Dc tower# (high capaclty) line (Suitable to carry minimum 1000 MW at nominal voltage) • Establishment of Common Pooling Sub-station 2 (PSS-2) Of MS ReNew Solar (Shakti Six) Pvt. Ltd (App. Nos. 1200003848 for 550 MW & 0312100004 for 450 MW) • Common Pooling Sub-station 2 (PSS-2)— Common Pooling Substation 1 (PSS-I) 400kV Sc line Dc tower# (high capacity) line Connectivity Of 450 MW (App no.- 0312100004) to Ms ReNew Solar Shakti Six) Pvt. Ltd is granted in sharing with application of 550 MW (App No. 1200003848) through same DTL & bay | 1 | 400 KV | Aug without ATS |  |  |  | 1. Augmentation of 2x1500 MVA (1st & 2nd), 765400kV ICT at Bhadla-III PS 2. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line 3. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 4. Sikar-II – Khetri 765 kV Dc line 5. Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line 6. Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) 7. Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) * with minimum capacity of 2100 MVAckt at nominal voltage; | 31-03-2024 | 31-03-2024 |  |  | 550 | 427(Main),428(Tie) |  |  |  | 2026-06-30 | 2026-02-28 | 2027-03-31 |  | Not effective | 2027-03-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-07-15 ¦ Status: Under Implementation ¦ Type: ¦ Phase 2 ¦ MW: 400.00 ¦ Date: 2026-11-30 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-03-2024 |  | 2024-03-31 | 2027-03-31
9200000169 | Conn under 37.1_37.2_37.6 | 312100004 (Enh.) | ReNew Solar (Shakti Six) Private Limited | NR | L&A | (x) Renewable Power Park developer | Solar | 450 |  | 450 | 0 | 0 | 450 | 0 | Granted | 450 | 0 | 450 | Bhadla-III | Rajasthan | 2024-09-12 | 2026-06-30 | Under Applicant Scope • Establishment Of Common Pooling Sub—Station I (PSS-I) of MS ReNew solar (Shakti Six) Pvt. Ltd (App. Nos. 1200003848 for 550 MW & 0312100004 for 450 MW) • Common Pooling Sub-station 1 (PSS-I) - Bhadla-lll PS 400kV Sc line Dc tower# (high capaclty) line (Suitable to carry minimum 1000 MW at nominal voltage) • Establishment of Common Pooling Sub-station 2 (PSS-2) Of MS ReNew Solar (Shakti Six) Pvt. Ltd (App. Nos. 1200003848 for 550 MW & 0312100004 for 450 MW) • Common Pooling Sub-station 2 (PSS-2)— Common Pooling Substation 1 (PSS-I) 400kV Sc line Dc tower# (high capacity) line Connectivity Of 450 MW (App no.- 0312100004) to Ms ReNew Solar (Shakti Six) Pvt. Ltd is granted in sharing with application of 550 MW (App No. 1200003848) through same DTL & bay | 0 | 400 KV | Aug without ATS |  |  |  | 1. Augmentation of 2x1500 MVA (2nd & 3rd ), 765400kV ICT at Bhadla-III PS 2. Fatehgarh-III – Bhadla-III 400kV Dc line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III- Bhadla-III 400kV Dc line 3. Bhadla-III – Sikar-II 765 kV Dc line along with 330 MVAr Switchable line reactor for each circuit at each end of Bhadla-III – Sikar-II 765 kV Dc line 4. Sikar-II – Khetri 765 kV Dc line 5. Sikar-II – Narela 765 kV Dc line along with 240 MVAr Switchable line reactor for each circuit at each end of Sikar-II – Narela 765 kV Dc line 6. Jhatikara – Dwarka 400kV Dc line (Twin HTLS*) 7. Augmentation of 1x1500 MVA ICT (3rd), 765400kV ICT at Jhatikara Substation (BamnoliDwarka section) * with minimum capacity of 2100 MVAckt at nominal voltage; | 31-12-2024 | 31-12-2024 |  |  | 450 | 427(Main),428(Tie) |  |  |  | 2026-06-30 | 2026-02-28 | 2027-03-31 |  | Not effective | 2027-03-31 | Under Construction | Part Commissioned | 150 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-06-28 ¦ Status: COD Declared ¦ Type: ¦ Phase 2 ¦ MW: 300.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: | 10.07.2026 |  |  | 10/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2027-03-31
9200000170 | Conn under 37.1_37.2_37.6 | 1200003785 | ALF Solar Amarsar Private Limited | NR | L&FC | (x) Renewable Power Park developer | Solar | 400 | 0 | 400 | 0 | 0 | 400 | 0 | Granted | 400 | 0 | 400 | Bikaner-II | Rajasthan | 2024-02-21 | 2025-12-27 | ALF Solar Amarsar Private Limited Solar Power Project – Bikaner-II PS 220 kV Dc line (Suitable to carry minimum 300 MW per circuit at nominal voltage) - Under applicant scope (220 kV Dc line to be clubbed for Application Nos. 1200003785, 1200003831 & 0312100008 for 400 MW, 150 & 50 MW respectively of Ms ALF Solar Amarsar Private Limited) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA 1) Augmentation of 2x500MVA (6th & 7th) 400220 kV ICTs at Bikaner –II PS 2) Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) 3) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikane | Transmission system for Connectivity under GNA 1) Augmentation of 2x500MVA (6th & 7th) 400220 kV ICTs at Bikaner –II PS 2) Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) 3) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-III Pooling Station 4) Augmentation of 2x1500 MVA (3rd & 4th),765400 kV ICTs at Neemrana-II Ss 5) LILO of both ckts of 400 kV Bikaner (PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS 6) Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) 7) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end 8) Neemrana-II -Kotputli 400 kV Dc line (Quad) 9) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss 10) Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 11) Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end 12) Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) • Additional Scheme to relieve overloading of 400 kV Bhinmal-Zerda line (Twin Moose) 1) Bypassing of 400 kV Kankroli - Bhinmal-Zerda line at Bhinmal to form 400 kV Kankroli – Zerda (direct) line # 2) Reconductoring of 400 kV Jodhpur (Surpura)(RVPN) – Kankroli Sc (twin moose) line with twin HTLS conductor* # with necessary arrangement for bypassing Kankroli- Zerda line at Bhinmal with suitable switching equipment inside the Bhinmal substation. * with minimum capacity of 2100 MVAckt at nominal voltage; Upgradation of existing 400kV bay equipments each at Jodhpur (Surpura)(RVPN) and Kankroli Ss(3150 A) | 31-12-2023 | 31-12-2023 |  |  | 400 | 226,227 |  |  |  |  | 2025-12-27 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 400.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2023 |  | 2023-12-31 | 2027-09-30
9200000171 | Conn under 37.1_37.2_37.6 | 1200003831 (Enh.) | ALF Solar Amarsar Private Limited | NR | L&FC | (x) Renewable Power Park developer | Solar | 150 |  | 150 | 0 | 0 | 150 | 0 | Granted | 150 | 0 | 150 | Bikaner-II | Rajasthan | 2024-02-21 | 2025-12-27 | ALF Solar Amarsar Private Limited Solar Power Project – Bikaner-II PS 220 kV Dc line (Suitable to carry minimum 300 MW per circuit at nominal voltage) - Under applicant scope (220 kV Dc line to be clubbed for Application Nos. 1200003785, 1200003831 & 0312100008 for 400 MW, 150 & 50 MW respectively of Ms ALF Solar Amarsar Private Limited) | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA 1) Augmentation of 1x500MVA (7th) 400220 kV ICTs at Bikaner –II PS 2) Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) 3) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-II | Transmission system for Connectivity under GNA 1) Augmentation of 1x500MVA (7th) 400220 kV ICTs at Bikaner –II PS 2) Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) 3) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-III Pooling Station 4) Augmentation of 2x1500 MVA (3rd & 4th),765400 kV ICTs at Neemrana-II Ss 5) LILO of both ckts of 400 kV Bikaner (PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS 6) Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) 7) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end 8) Neemrana-II -Kotputli 400 kV Dc line (Quad) 9) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss 10) Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 11) Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end 12) Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) • Additional Scheme to relieve overloading of 400 kV Bhinmal-Zerda line (Twin Moose) 1) Bypassing of 400 kV Kankroli - Bhinmal-Zerda line at Bhinmal to form 400 kV Kankroli – Zerda (direct) line # 2) Reconductoring of 400 kV Jodhpur (Surpura)(RVPN) – Kankroli Sc (twin moose) line with twin HTLS conductor* # with necessary arrangement for bypassing Kankroli- Zerda line at Bhinmal with suitable switching equipment inside the Bhinmal substation. * with minimum capacity of 2100 MVAckt at nominal voltage; Upgradation of existing 400kV bay equipments each at Jodhpur (Surpura)(RVPN) and Kankroli Ss (3150 A) | 31-12-2023 | 31-12-2023 |  |  | 150 | 226,227 |  |  |  |  | 2025-12-27 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: |  |  |  |  | Pending with Level 2 | 31-12-2023 |  | 2023-12-31 | 2027-09-30
9200000172 | Conn under 37.1_37.2_37.6 | 312100008 (Enh.) | ALF Solar Amarsar Private Limited | NR | L&FC | (x) Renewable Power Park developer | Solar | 50 | 0 | 50 | 0 | 0 | 50 | 0 | Granted | 50 | 0 | 50 | Bikaner-II | Rajasthan | 2024-09-12 | 2026-08-22 | ALF Solar Amarsar Private Limited Solar Power Project – Bikaner-II PS 220 kV Dc line (Suitable to carry minimum 300 MW per circuit at nominal voltage) - Under applicant scope (220 kV Dc line to be clubbed for Application nos. 1200003785, 1200003831 & 0312100008 for 400 MW, 150 & 50 MW respectively of Ms ALF Solar Amarsar Private Limited) | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500MVA (8th) 400220 kV ICT at Bikaner –II PS Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA, 765400 kV ICTs at Bikaner-III Pooling Sta | Transmission system for Connectivity under GNA Augmentation of 1x500MVA (8th) 400220 kV ICT at Bikaner –II PS Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA, 765400 kV ICTs at Bikaner-III Pooling Station LILO of both ckts of 400 kV Bikaner (PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation of 2x1500 MVA (3rd & 4th),765400 kV ICTs at Neemrana-II Ss Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for inter-regional power transfer Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc Line Or 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-12-2023 | 31-12-2023 |  |  | 50 | 226,227 |  |  |  |  | 2026-11-07 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2023 |  | 2023-12-31 | 2027-09-30
9200000174 | Conn under 37.1_37.2_37.6 | 212100040 | JSW Renew Energy Five Limited | NR | LOA or PPA | (vii) Standalone ESS | Standalone ESS | 250 |  | 0 | 0 | 250 | 250 | 0 | Granted | 250 | 0 | 250 | Fatehgarh-III (Sec-I) | Rajasthan | 2024-03-22 | 2025-06-30 | JSW Renew Energy Five Limited BESS Project-2 (250 MW) – Fatehgarh-III PS(Sec-1) 220 kV cable (Suitable to carry minimum 300 MW at nominal voltage) - Under applicant scope | 1 | 220 KV | Existing |  |  | Existing System | Existing System | 15-10-2024 | 15-10-2024 |  |  | 250 | 218 |  |  |  | 2027-03-31 |  |  |  | Not effective | 2027-03-31 |  | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 250.00 ¦ Date: 2027-03-31 ¦ Status: Under Implementation ¦ Type: |  |  | Generation status is not updated due petition in HC | 08/07/2026 | Pending with Level 2 | 15-10-2024 |  | 2024-10-15 | 2027-03-31
9200000175 | Conn under 37.1_37.2_37.6 | 1200003502 | Khaba Renewable Energy Private Limited | NR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Solar | 250 |  | 250 | 0 | 0 | 250 | 0 | Granted | 250 | 0 | 250 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-05-31 | 2025-09-19 | Khaba Renewable Power Pvt Ltd Solar Power Project – Fatehgarh-III PS(Sec-II) 220 kV S/c line on D/c towers# (Suitable to carry minimum 300 MW at nominal voltage) Under applicant scope Connectivity of 10 MW to M/s Renew Surya Vihaan Pvt. Ltd. is granted in sharing with M/s Khaba Renewable Energy Pvt. Ltd. through same bay & DTL## | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 2x1500 MVA (4th & 5th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 2x1500 MVA (4th & 5th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR | 31-12-2024 | 31-12-2024 |  |  | 250 | 227 |  |  |  | 2026-01-24 | 2025-02-01 | 2026-11-30 |  | Not effective | 2026-11-30 | Under Construction | Part Commissioned | 200 | ¦ Phase 1 ¦ MW: 100.00 ¦ Date: 2026-03-11 ¦ Status: COD Declared ¦ Type: ¦ Phase 2 ¦ MW: 50.00 ¦ Date: 2026-03-25 ¦ Status: COD Declared ¦ Type: ¦ Phase 3 ¦ MW: 50.00 ¦ Date: 2026-06-20 ¦ Status: COD Declared ¦ Type: ¦ Phase 4 ¦ MW: 50.00 ¦ Date: 2026-08-18 ¦ Status: Under Implementation ¦ Type: |  | Yes | Bay Charged on 24.01.2026 |  | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2026-11-30
9200000176 | Conn under 37.1_37.2_37.6 | 412100009 (St-II: 1200003827, 1200003910, 1200003958, 0312100010 & 0312100012) | Juniper Green Stellar Private Limited | NR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | 150 |  | 50 | 100 | 22.5 | 172.5 | 0 | Granted | 150 | 0 | 150 | Fatehgarh-IV (Sec-I) | Rajasthan | 2024-05-31 | 2025-09-19 | Amended Provision M/s Juniper Green Stellar Private Limited Solar PSS - Fatehgarh-IV PS (Sec-l) (high capacity) 220kV S/c line on D/c towers (Suitable to carry minimum 365 MW at nominal voltage) - Under Applicant Scope Internal Interconnection: M/s Juniper Green Stellar Private Limited Wind PSS Solar PSS 220kV S/c line on D/c towers Connectivity of application no. 0412100010 (150MW) and 0412100011 (65MW) is granted in -2822547, sharing with application по. 0412100009 (150MW). 220kV bay at Fatehgarh-IV PS (Sec-l) shall be implemented under ISTS. | 1 | 220 KV | Aug without ATS |  |  | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (2nd) 400/220 kV ICT at Fatehgarh-IV PS Fatehgarh-IV PS- Fatehgarh-III 400 kV D/c (Twin HLTS*) line Augmentation of 2x1500 MVA (2nd & 3rd), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR *with minimum capacity of 2100 MVA on each circuit at nominal voltage | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (2nd) 400/220 kV ICT at Fatehgarh-IV PS Fatehgarh-IV PS- Fatehgarh-III 400 kV D/c (Twin HLTS*) line Augmentation of 2x1500 MVA (2nd & 3rd), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR *with minimum capacity of 2100 MVA on each circuit at nominal voltage | 31-01-2025 | 31-01-2025 |  |  | 150 | 207 | 2026-07-30 | 2027-01-31 |  | 2025-12-07 | 2025-09-19 | 2026-11-30 |  | Not effective | 2026-11-30 | Under Construction | Part Commissioned | 131.9 | ¦ Phase 1 ¦ MW: 50.00 ¦ Date: 2026-03-27 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 50.40 ¦ Date: 2026-06-10 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 3 ¦ MW: 12.60 ¦ Date: 2026-06-18 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 4 ¦ MW: 9.45 ¦ Date: 2026-06-21 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 5 ¦ MW: 9.45 ¦ Date: 2026-06-30 ¦ Status: COD Declared ¦ Type: Wind ¦ Phase 6 ¦ MW: 18.10 ¦ Date: 2026-07-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 7 ¦ MW: 22.50 ¦ Date: 2026-04-08 ¦ Status: COD Declared ¦ Type: Standalone | 10.07.2026 | Yes | Bay Charged on 07.12.2025 | 10/07/2026 | Pending with Level 2 | 31-01-2025 |  | 2025-01-31 | 2027-01-31
9200000177 | Conn under 37.1_37.2_37.6 | 412100010 (St-II: 1200003827, 1200003910, 1200003958, 0312100010 & 0312100012) | Juniper Green Stellar Private Limited | NR | LOA or PPA | (iii) Generating station(s), including REGS(s), with ESS | Hybrid | 150 |  | 50 | 100 | 22.5 | 172.5 | 0 | Granted | 150 | 0 | 150 | Fatehgarh-IV (Sec-I) | Rajasthan | 2024-05-31 | 2026-03-31 | Amended Provision M/s Juniper Green Stellar Private Limited Solar PSS - Fatehgarh-IV PS (Sec-l) (high capacity) 220kV S/c line on D/c towers (Suitable to carry minimum 365 MW at nominal voltage) - Under Applicant Scope Internal Interconnection: M/s Juniper Green Stellar Private Limited Wind PSS Solar PSS 220kV S/c line on D/c towers Connectivity of application no. 0412100010 (150MW) and 0412100011 (65MW) is granted in -2822547, sharing with application по. 0412100009 (150MW). 220kV bay at Fatehgarh-IV PS (Sec-l) shall be implemented under ISTS. | 0 | 220 KV | Aug without ATS |  |  | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (2nd) 400/220 kV ICT at Fatehgarh-IV PS Fatehgarh-IV- Fatehgarh-III 400 kV D/c (Twin HLTS*) line Augmentation of 2x1500 MVA (2nd & 3rd), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR *with minimum capacity of 2100 MVA on each circuit at nominal voltage | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (2nd) 400/220 kV ICT at Fatehgarh-IV PS Fatehgarh-IV- Fatehgarh-III 400 kV D/c (Twin HLTS*) line Augmentation of 2x1500 MVA (2nd & 3rd), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR *with minimum capacity of 2100 MVA on each circuit at nominal voltage | 31-01-2025 | 31-01-2025 |  |  | 150 | 207 |  |  |  |  | 2025-09-19 | 2026-11-30 |  | Not effective | 2026-11-30 | Under Construction | Part Commissioned | 92.5 | ¦ Phase 1 ¦ MW: 38.00 ¦ Date: 2026-03-27 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 32.00 ¦ Date: 2026-04-12 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 3 ¦ MW: 80.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Wind ¦ Phase 4 ¦ MW: 22.50 ¦ Date: 2026-04-08 ¦ Status: COD Declared ¦ Type: Standalone | 10.07.2026 | Yes | Bay Charged on 07.12.2025 | 10/07/2026 | Pending with Level 2 | 31-01-2025 |  | 2025-01-31 | 2026-11-30
9200000180 | Conn under 37.1_37.2_37.6 | 212100043 | EG Saur Urja Pvt. Ltd.(earlier Tepsol Saur Urja Private Limited) | NR | L&FC | (x) Renewable Power Park developer | Hybrid | 300 | 0 | 200 | 100 | 0 | 300 |  | Granted | 300 | 0 | 300 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2026-10-15 | Tepsol Saur Urja Private Limited Solar Park Pooling Station – Fatehgarh-IV PS(Sec-II) 220 kV S/c line (Suitable to carry minimum 300 MW at nominal voltage) - under applicant scope | 1 | 220 KV | Aug without ATS |  |  | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (2nd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA, 765/400 kV ICTs at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV FatehgarhIV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (2nd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA, 765/400 kV ICTs at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV FatehgarhIV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore (PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore (PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | 31-12-2025 | 31-12-2025 |  |  | 300 | 229 |  |  |  | 2026-08-14 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 300.00 ¦ Date: 2027-06-30 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2025 |  | 2025-12-31 | 2027-06-30
9200000194 | Conn under 37.1_37.2_37.6 | 1200003749 (Enh) | ReNew Solar (Shakti Five) Private Limited | NR | L&A | (i) Generating station(s), including REGS(s), without ESS | Solar | 100 |  | 100 | 0 | 0 | 100 | 0 | Granted | 100 | 0 | 100 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-05-31 | 2025-09-19 | Common Pooling Station for ReNew Dinkar Jyoti(100 MW), ReNew Solar Shakti(Three)(300 MW), ReNew Shakti(Five) (400 MW) & ReNew Samir Shakti(300 MW) – Fatehgarh-III PS(Sec-II) 400 kV S/c (high capacity) line on D/c towers (Suitable to carry minimum 1100 MW at nominal voltage)-Under Applicant Scope Connectivity of 300 MW to ReNew Solar Shakti(Three) Pvt. Ltd. , 400 MW to ReNew Shakti(Five) Pvt. Ltd. & 300 MW to ReNew Samir Shakti Pvt. Ltd. is granted in sharing with Renew Dinkar Jyoti Pvt. Ltd. (100 MW) through same bay & DTL | 0 | 400 kV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 2x1500 MVA (4th & 5th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR | Transmission system for Connectivity under GNA: Augmentation of 2x1500 MVA (4th & 5th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR | 30-12-2023 | 30-12-2023 |  |  | 100 | 423 |  |  |  | 2026-02-10 | 2025-02-01 | 2026-11-30 |  | Not effective | 2026-11-30 | Under Construction | Part Commissioned | 27.7 | ¦ Phase 1 ¦ MW: 27.70 ¦ Date: 2026-06-04 ¦ Status: COD Declared ¦ Type: Solar ¦ Phase 2 ¦ MW: 72.30 ¦ Date: 2026-07-30 ¦ Status: Under Implementation ¦ Type: Solar |  |  | Bay Charged on 10-02-2026 | 08/07/2026 | Pending with Level 2 | 30-12-2023 |  | 2023-12-30 | 2026-11-30
9200000195 | Conn under 37.1_37.2_37.6 | 1200002907 | Energizent Power Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 125 |  | 125 | 0 | 0 | 125 | 0 | Granted | 125 | 0 | 125 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-04-25 | 2025-09-19 | Energizent Power Pvt. Ltd Hybrid Power Project – Fatehgarh-III PS(Sec-II) 220 kV S/c line on D/c tower# $(Suitable to carry minimum 300 MW at nominal voltage): Under applicant Scope Connectivity of 80 MW(App no.- 1200002939) to M/s Energizent Power Pvt. Ltd & 95 MW(App No. 2200000123) to M/s Teq Green Power XV Pvt. Ltd. is granted in sharing with application of 125 MW (App No.1200002907) through same DTL & bay## | 1 | 220 KV | Aug without ATS |  |  | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 2x1500 MVA (3rd & 4th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-III PS pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 2x1500 MVA (3rd & 4th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-III PS pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR | 31-08-2022 | 31-08-2022 |  |  | 125 | 229 |  |  |  | 2025-10-18 | 2025-02-01 | 2026-11-30 |  | Not effective | 2026-11-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 125.00 ¦ Date: 2026-09-30 ¦ Status: Under Implementation ¦ Type: |  |  | Bay charged on 18.10.2025 |  | Pending with Level 2 | 31-08-2022 |  | 2022-08-31 | 2026-11-30
9200000196 | Conn under 37.1_37.2_37.6 | 1200002939 | Energizent Power Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 80 |  | 80 | 0 | 0 | 80 | 0 | Granted | 80 | 0 | 80 | Fatehgarh-III (Sec-II) | Rajasthan | 2024-04-25 | 2025-09-19 | Energizent Power Pvt. Ltd Hybrid Power Project – Fatehgarh-III PS(Sec-II) 220 kV S/c line on D/c tower (Suitable to carry minimum 300 MW at nominal voltage): Under applicant Scope Connectivity of 80 MW(App no.- 1200002939) to M/s Energizent Power Pvt. Ltd & 95 MW(App No. 2200000123) to M/s Teq Green Power XV Pvt. Ltd. is granted in sharing with application of 125 MW (App No.1200002907) through same DTL & bay | 0 | 220 KV | Aug without ATS |  |  | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 2x1500 MVA (3rd & 4th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-III PS pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR | Transmission System for Connectivity under GNA: Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 2x1500 MVA (3rd & 4th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Augmentation of 1x500 MVA (4th), 400/220kV ICT at Fatehgarh-III PS pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR | 31-08-2022 | 31-08-2022 |  |  | 80 | 229 |  |  |  | 2025-10-18 | 2025-02-01 | 2026-11-30 |  | Not effective | 2026-11-30 | Under Construction | Part Commissioned | 69 | ¦ Phase 1 ¦ MW: 69.00 ¦ Date: 2025-11-07 ¦ Status: COD Declared ¦ Type: ¦ Phase 2 ¦ MW: 11.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: |  |  | Bay charged on 18.10.2025 | 08/07/2026 | Pending with Level 2 | 31-08-2022 |  | 2022-08-31 | 2026-11-30
9200000201 | Conn under 37.1_37.2_37.6 | 1200003772 | Shikhar Surya (One) Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 105 |  | 105 | 0 | 0 | 105 | 0 | Granted | 105 | 0 | 105 | Bikaner | Rajasthan | 2024-03-15 | 2025-12-27 | Shikhar Surya (One) Private Limited Solar Power Project – Bikaner PS 220 kV Sc line on Dc tower Suitable to carry minimum 300 MW at nominal voltage)– Under Applicant Scope Connectivity of 105 MW & 125 MW to Ms Shikhar Surya (Application Nos. 1200003772 & 0312100003 respectively) is granted in sharing with application of 70 MW (Application No. 1200003115) through same DTL & bay | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500MVA (3rd) 400220 kV ICT at Bikaner (PG) Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-II | Transmission system for Connectivity under GNA Augmentation of 1x500MVA (3rd) 400220 kV ICT at Bikaner (PG) Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (3rd & 4th),765400 kV ICTs at Neemrana-II Ss LILO of both ckts of 400 kV Bikaner (PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) | 31-12-2024 | 31-12-2024 |  |  | 105 | 207 |  |  |  | 2022-02-07 | 2025-12-27 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 105.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: |  |  | Bay Charged on 07.02.22, Generation Status not provided by Grantee. |  | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2027-09-30
9200000203 | Conn under 37.1_37.2_37.6 | 312100003 | Shikhar Surya (One) Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 125 |  | 125 | 0 | 0 | 125 | 0 | Granted | 125 | 0 | 125 | Bikaner | Rajasthan | 2024-03-15 | 2025-12-27 | Shikhar Surya (One) Private Limited Solar Power Project – Bikaner PS 220 kV Sc line on Dc tower Suitable to carry minimum 300 MW at nominal voltage)– Under Applicant Scope Connectivity of 105 MW & 125 MW to Ms Shikhar Surya (Application Nos. 1200003772 & 0312100003 respectively) is granted in sharing with application of 70 MW (Application No. 1200003115) through same DTL & bay | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA Augmentation of 1x500MVA (3rd) 400220 kV ICT at Bikaner (PG) Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-III | Transmission system for Connectivity under GNA Augmentation of 1x500MVA (3rd) 400220 kV ICT at Bikaner (PG) Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-III Pooling Station LILO of both ckts of 400 kV Bikaner (PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation of 2x1500 MVA (3rd & 4th),765400 kV ICTs at Neemrana-II Ss Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) | 30-06-2025 | 30-06-2025 |  |  | 125 | 207 |  |  |  | 2022-02-07 | 2025-12-27 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 125.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: |  |  | Bay charged on 07.02.22. Generation status not provided. |  | Pending with Level 2 | 30-06-2025 |  | 2025-06-30 | 2027-09-30
9200000205 | Conn under 37.1_37.2_37.6 | 312100019 | Cannice Renewables Energy Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Hybrid | 90 |  | 70 | 20 | 0 | 90 | 0 | Granted | 90 | 0 | 90 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2026-10-15 | Common Pooling Station for M/s Cannice Renewable Projects of 320 MW (80 MW (0212100004) + 150 MW(SW..671600589106)+ 90 MW(0312100019) – Fatehgarh-IV PS(Sec-I) 220 kV S/c line on D/c towers# (Suitable to carry minimum 320 MW at nominal voltage) – Under Applicant Scope Connectivity of 150 MW & 90 MW to M/s Cannice (Application Nos. SW..671600589106 & 0312100019) is granted in sharing with application of 80 MW (Application No. 0212100004) through same DTL & bay | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 2x500 MVA (2nd & 3rd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA, 765/400 kV ICTs at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | Transmission system for Connectivity under GNA: Augmentation of 2x500 MVA (2nd & 3rd), 400/220kV ICT at Fatehgarh-IV (Section-2) Pooling Station 2x1500 MVA, 765/400 kV ICTs at Fatehgarh-IV (Section-2) Pooling Station Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo - Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | 31-01-2025 | 31-01-2025 |  |  | 90 | 220 |  |  |  | 2026-08-14 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 90.00 ¦ Date: 2026-10-15 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-01-2025 |  | 2025-01-31 | 2027-06-30
9200000206 | Conn under 37.1_37.2_37.6 | SW…1671600589106 | Cannice Renewables Energy Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 150 |  | 150 | 0 | 0 | 150 | 0 | Granted | 150 | 0 | 150 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2026-10-15 | Common Pooling Station for M/s Cannice Renewable Projects of 320 MW (80 MW (0212100004) + 150 MW(SW..671600589106)+ 90 MW(0312100019) – Fatehgarh-IV PS(Sec-I) 220 kV S/c line on D/c towers# (Suitable to carry minimum 320 MW at nominal voltage) – Under Applicant Scope Connectivity of 150 MW & 90 MW to M/s Cannice (Application Nos. SW..671600589106 & 0312100019) is granted in sharing with application of 80 MW (Application No. 0212100004) through same DTL & bay | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Establishment of 2x1500 MVA (1st & 2nd), 765/400 kV & 2x500 MVA (1st & 2nd), 400/220 kV Fatehgarh-IV (Section-2) Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR (420 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo – Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | Transmission system for Connectivity under GNA: Establishment of 2x1500 MVA (1st & 2nd), 765/400 kV & 2x500 MVA (1st & 2nd), 400/220 kV Fatehgarh-IV (Section-2) Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR (420 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo – Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | 31-01-2025 | 31-01-2025 |  |  | 150 | 220 |  |  |  | 2026-08-14 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 150.00 ¦ Date: 2026-10-15 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-01-2025 |  | 2025-01-31 | 2027-06-30
9200000207 | Conn under 37.1_37.2_37.6 | 212100004 | Cannice Renewable Energy Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 80 |  | 80 | 0 | 0 | 80 | 0 | Granted | 80 | 0 | 80 | Fatehgarh-IV (Sec-II) | Rajasthan | 2024-12-20 | 2026-10-15 | Common Pooling Station for M/s Cannice Renewable Projects of 320 MW (80 MW (0212100004) + 150 MW (SW..671600589106)+ 90 MW(0312100019) – Fatehgarh-IV PS(Sec-I) 220 kV S/c line on D/c towers# (Suitable to carry minimum 320 MW at nominal voltage) – Under Applicant Scope Connectivity of 150 MW & 90 MW to M/s Cannice (Application Nos. SW..671600589106 & 0312100019) is granted in sharing with application of 80 MW (Application No. 0212100004) through same DTL & bay | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Establishment of 2x1500 MVA (1st & 2nd), 765/400 kV & 2x500 MVA (1st & 2nd), 400/220 kV Fatehgarh-IV (Section-2) Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR (420 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo – Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | Transmission system for Connectivity under GNA: Establishment of 2x1500 MVA (1st & 2nd), 765/400 kV & 2x500 MVA (1st & 2nd), 400/220 kV Fatehgarh-IV (Section-2) Pooling Station along with 2x240 MVAR (765 kV) Bus Reactor & 2x125 MVAR (420 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Bhinmal (PG) 400 kV D/c line (Twin HTLS*) along with 50 MVAr switchable line reactor on each ckt at each end LILO of both ckts of 765 kV Fatehgarh-III- Beawar D/c line at Fatehgarh-IV (Section-2) PS along with 330 MVAr switchable line reactor at Fatehgarh-IV PS end of each ckt of 765 kV Fatehgarh-IV- Beawar D/c line (formed after LILO) Establishment of 3x1500 MVA, 765/400 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors & 2x125 MVAR, 420 kV Bus Reactor Beawar- Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Establishment of 2x1500 MVA, 765/400 kV Substation at suitable location near Sirohi along with 2x240 MVAr (765 kV) & 2x125 MVAr (400 kV) Bus Reactor Fatehgarh-IV (Section-2) PS – Sirohi PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at each end Sirohi PS-Chittorgarh (PG) 400 kV D/c line along with 80 MVAr switchable line reactor for each circuit at Sirohi PS end (Quad) Establishment of, 765 kV Substation at suitable location near Rishabdeo (Distt. Udaipur) along with 2x240 MVAr (765 kV) Bus Reactor Sirohi PS- Rishabdeo 765 kV D/c line along with 330 MVAr switchable line reactor for each circuit at Sirohi end Rishabdeo – Mandsaur PS 765 kV D/c line along with 240 MVAr switchable line reactor for each circuit at Rishabdeo end LILO of one circuit of 765 kV Chittorgarh-Banaskanta D/c line at Rishabdeo S/s Mandsaur PS – Indore(PG) 765 kV D/c Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV D/c Line Establishment of 765/400 kV (2x1500 MVA Kurawar S/s (with 1x500 MVA spare single phase transformer unit) with 2x330 MVAr 765 kV bus reactor and 1x125 MVAr 420 kV bus reactor (with 1x110 MVAr & 1x80 MVAr, 765 kV spare single phase reactor unit for line/bus reactor) Mandsaur – Kurawar 765 kV D/c line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV D/c line LILO of Indore – Bhopal 765 kV S/c line at Kurawar Kurawar – Ashtha 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line LILO of one circuit of Indore – Itarsi 400 kV D/c line at Astha Shujalpur – Kurawar 400 kV D/c (Quad ACSR/AAAC/AL59 moose equivalent) line * with minimum capacity of 2100 MVA on each circuit at nominal voltage | 31-01-2025 | 31-01-2025 |  |  | 80 | 220 |  |  |  | 2026-08-14 | 2026-10-15 | 2027-06-30 |  | Not effective | 2027-06-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 80.00 ¦ Date: 2026-10-15 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-01-2025 |  | 2025-01-31 | 2027-06-30
9200000212 | Conn under 37.1_37.2_37.6 | 1200003332 | ABC RJ Land 01 Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 110 |  | 110 | 0 | 0 | 110 | 0 | Granted | 110 | 0 | 110 | Fatehgarh-IV (Sec-I) | Rajasthan | 2024-04-16 | 2025-09-19 | Common pooling station of ABC RJ Land 01 Private Limited Solar Power Project (110 MW & 270 MW for Application Nos. 1200003332 & 1200003575) – Fatehgarh-IV PS(Sec-I) 220 kV S/c (high capacity) line on D/c tower# (Suitable to carry minimum 380 MW at nominal voltage)-Under Applicant Scope Connectivity of 270 MW to ABC RJ Land 01 Pvt. Ltd.(App No. 1200003575) is granted in sharing with ABC RJ Land 01 Pvt. Ltd. (110 MW)(App No. 1200003332) through same bay & DTL## | 1 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 2x500 MVA (2nd & 3rd) 400/220 kV ICTs at Fatehgarh-IV PS(Sec-I) Fatehgarh-IV- Fatehgarh-III 400 kV D/c (Twin HLTS*) line Augmentation of 2x1500 MVA (3rd & 4th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA: Augmentation of 2x500 MVA (2nd & 3rd) 400/220 kV ICTs at Fatehgarh-IV PS(Sec-I) Fatehgarh-IV- Fatehgarh-III 400 kV D/c (Twin HLTS*) line Augmentation of 2x1500 MVA (3rd & 4th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR * with minimum capacity of 2100 MVA/ckt at nominal voltage | 31-12-2022 | 31-12-2022 |  |  | 110 | 205 |  |  |  | 2025-12-07 | 2025-02-01 | 2026-11-30 |  | Not effective | 2026-11-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 110.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: |  |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2022 |  | 2022-12-31 | 2026-11-30
9200000213 | Conn under 37.1_37.2_37.6 | 1200003575 | ABC RJ Land 01 Private Limited | NR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Solar | 270 |  | 270 | 0 | 0 | 270 | 0 | Granted | 270 | 0 | 270 | Fatehgarh-IV (Sec-I) | Rajasthan | 2024-04-16 | 2025-09-19 | Common pooling station of ABC RJ Land 01 Private Limited Solar Power Project (110 MW & 270 MW for Application Nos. 1200003332 & 1200003575) – Fatehgarh-IV PS(Sec-I) 220 kV S/c (high capacity) line on D/c tower (Suitable to carry minimum 380 MW at nominal voltage)-Under Applicant Scope Connectivity of 270 MW to ABC RJ Land 01 Pvt. Ltd.(App No. 1200003575) is granted in sharing with ABC RJ Land 01 Pvt. Ltd. (110 MW)(App No. 1200003332) through same bay & DTL | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (3rd) 400/220 kV ICTs at Fatehgarh-IV PS(Sec-I) Fatehgarh-IV- Fatehgarh-III 400 kV D/c (Twin HLTS*) line Augmentation of 2x1500 MVA (4th & 5th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR * with minimum capacity of 2100 MVA/ckt at nominal voltage | Transmission system for Connectivity under GNA: Augmentation of 1x500 MVA (3rd) 400/220 kV ICTs at Fatehgarh-IV PS(Sec-I) Fatehgarh-IV- Fatehgarh-III 400 kV D/c (Twin HLTS*) line Augmentation of 2x1500 MVA (4th & 5th), 765/400kV ICT at Fatehgarh-III pooling station (Section-II) Establishment of 2x1500MVA 765/400kV Substation at suitable location near Beawar along with 2x330 MVAr,765kV Bus Reactor & 2x125 MVAr,420kV bus Reactor Fatehgarh-III– Beawar 765 kV D/c (2nd) along with 330 MVAr Switchable line reactor for each circuit at each end of Fatehgarh-III– Beawar 765 kV D/c line (2nd) Fatehgarh-III- Bhadla-III 400kV D/c line (Quad) along with 63 MVAr Switchable line reactor for each circuit at both ends of Fatehgarh-III-Bhadla-III 400kV D/c line LILO of both circuit of Ajmer-Chittorgarh 765 kV D/c line at Beawar substation LILO of 400kV Kota –Merta line at Beawar substation Establishment of 2x1500 MVA 765/400kV substation at suitable location near Dausa along with 2x330 MVAr, 765 kV Bus Reactor & 2x125 MVAr, 420 kV bus Reactor LILO of both circuits of Jaipur (Phagi)- Gwalior 765 kV 2xS/c at Dausa along with 240 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Gwalior 765 kV D/c line LILO of both circuits of Agra – Jaipur(south) 400kV D/c at Dausa along with 50 MVAr Switchable line reactor for each circuit at Dausa end of Dausa – Agra 400kV D/c line Beawar – Dausa 765 kV D/c line along with 240 MVAr Switchable line reactor for each circuit at each end STATCOM: Fatehgarh – III S/s: STATCOM: ± 2x300 MVAr, 4x125 MVAr MSC, 2x125 MVAr MSR * with minimum capacity of 2100 MVA/ckt at nominal voltage | 30-06-2024 | 30-06-2024 |  |  | 270 | 205 |  |  |  | 2025-12-07 | 2025-02-01 | 2026-11-30 |  | Not effective | 2026-11-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 270.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: |  |  | Bay charge on 07-12-2025 |  | Pending with Level 2 | 30-06-2024 |  | 2024-06-30 | 2026-11-30
9200000231 | Conn under 37.1_37.2_37.6 | 0351100009 | Tata Power Renewable Energy Ltd. | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 170 |  | 0 | 170 | 0 | 170 |  | Granted | 170 | 0 | 170 | Gadag-II | Karnataka | 2024-09-13 | 2025-12-27 | Through dedicated Connectivity transmission system granted to Tata Power Renewables Energy Ltd. for application no. 0251100012. i.e. Generation Pooling Station of M/s Tata Power Renewables Energy Ltd. – Gadag-II PS 220 kV S/c line – under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | Common Transmission System for Connectivity – under ISTS • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (PhaseA) in Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission System for Connectivity – under ISTS • Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (PhaseA) in Karnataka • ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 01-04-2025 | 01-04-2025 |  |  | 170 | 206 |  |  |  | 2026-06-30 | 2025-12-26 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 170.00 ¦ Date: 2027-02-28 ¦ Status: Under Implementation ¦ Type: Wind | 08.07.2026 |  |  | 08/07/2026 | Pending with Level 2 | 01-04-2025 |  | 2025-04-01 | 2026-10-31
9200000232 | Conn under 37.1_37.2_37.6 | 0251100013 | TATA Power Renewable Energy Ltd. | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 85 |  | 85 | 0 | 0 | 85 |  | Granted | 85 | 0 | 85 | Koppal-II | Karnataka | 2025-03-03 | 2025-12-27 | •Generation Pooling station of M/s Tata Power Renewable Energy Ltd.- Koppal-II PS 220 kV S/c line along with line bays at generation pooling station end – under the scope of applicant. •01 nos. of 220 kV line bays at Koppal-II PS for termination of above mentioned dedicated Connectivity line – under the scope of ISTS | 1 | 220 KV | Aug without ATS |  |  | Common Transmission System for Connectivity – under ISTS •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (Phase- A) in Karnataka •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | Common Transmission System for Connectivity – under ISTS •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (Phase- A) in Karnataka •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 01-04-2025 | 01-04-2025 |  |  | 85 | 202 |  |  |  | 2026-06-30 | 2025-12-26 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 85.00 ¦ Date: 2026-10-31 ¦ Status: Under Implementation ¦ Type: Solar | 16.03.2026 |  |  | 06/05/2026 | Pending with Level 2 | 01-04-2025 |  | 2025-04-01 | 2026-10-31
9200000233 | Conn under 37.1_37.2_37.6 | 0351100008 | TATA Power Renewable Energy Ltd. | SR | LOA or PPA | (i) Generating station(s), including REGS(s), without ESS | Wind | 85 |  | 85 | 0 | 0 | 85 |  | Granted | 85 | 0 | 85 | Koppal-II | Karnataka | 2025-03-03 | 2025-12-27 | •Through dedicated Connectivity transmission system of Ms Tata Power Renewable Energy Ltd. granted connectivity at Koppal-II PS for application no. 0251100013 (85 MW) i.e. Generation Pooling station of Ms Tata Power Renewable Energy Ltd.- Koppal-II PS 220 kV Sc line – all arrangement under the scope of applicant. | 0 | 220 KV | Aug without ATS |  |  | Common Transmission System for Connectivity – under ISTS •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (Phase- A) in Karnataka •ISTS Network Expansion scheme in Western Region & Southern Reg | Common Transmission System for Connectivity – under ISTS •Transmission Scheme for integration of Renewable Energy Zone (Phase-II) in Koppal-II (Phase-A) and Gadag-II (Phase- A) in Karnataka •ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region | 01-04-2025 | 01-04-2025 |  |  | 85 | 202 |  |  |  |  | 2025-12-26 | 2026-10-31 |  | Not effective | 2026-10-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 85.00 ¦ Date: 2027-12-31 ¦ Status: Under Implementation ¦ Type: | 16.03.2026 |  |  |  | Pending with Level 2 | 01-04-2025 |  | 2025-04-01 | 2026-10-31
9200000242 | Conn under 37.1_37.2_37.6 | 1200003889 (Enh.) | Soltown Infra Private Limited (Park) | NR | L&A | (x) Renewable Power Park developer | Solar | 200 |  | 200 | 0 | 0 | 200 | 0 | Granted | 200 | 0 | 200 | Bikaner-II | Rajasthan | 2024-12-20 | 2025-12-31 | Common Pooling Station of Soltown Infra Private Limited (1200003889-200 MW & 0212100008-125 MW) RE Power Parks – Bikaner-II PS 220 kV Sc line on Dc tower# (suitable to carry minimum 325 MW at nominal voltage). | 1 | 220 KV | Aug without ATS |  |  | Augmentation of 1x500MVA (8th) 400220 kV ICT at Bikaner –II PS Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (3rd & | Augmentation of 1x500MVA (8th) 400220 kV ICT at Bikaner –II PS Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-III Pooling Station Augmentation of 2x1500 MVA (3rd & 4th),765400 kV ICTs at Neemrana-II Ss LILO of both ckts of 400 kV Bikaner (PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II -Kotputli 400 kV Dc line (Quad) LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) | 31-12-2023 | 31-12-2023 |  |  | 200 | 230,232 |  |  |  |  | 2025-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 200.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  |  | Pending with Level 2 | 31-12-2023 |  | 2023-12-31 | 2027-09-30
9200000244 | Conn under 37.1_37.2_37.6 | 212100008 | Soltown Infra Private Limited (Park) | NR | L&A | (x) Renewable Power Park developer | Solar | 150 |  | 125 | 0 | 0 | 125 | 0 | Granted | 125 | 0 | 125 | Bikaner-II | Rajasthan | 2024-12-20 | 2026-08-22 | Common Pooling Station of Soltown Infra Private Limited (1200003889-200 MW & 0212100008-125 MW) RE Power Parks – Bikaner-II PS 220 kV Sc line on Dc tower (suitable to carry minimum 325 MW at nominal voltage). | 0 | 220 KV | Aug without ATS |  |  | Transmission system for Connectivity under GNA 1. Augmentation of 1x500MVA (9th) 400220 kV ICT at Bikaner –II PS 2. Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) 3. Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-III P | Transmission system for Connectivity under GNA 1. Augmentation of 1x500MVA (9th) 400220 kV ICT at Bikaner –II PS 2. Augmentation of 1x1500 MVA (4th) 765400kV ICT at Bikaner (PG) 3. Augmentation of 2x1500 MVA (3rd & 4th)765400 kV ICTs at Bikaner-III Pooling Station 4. Augmentation of 2x1500 MVA (3rd & 4th),765400 kV ICTs at Neemrana-II Ss 5. LILO of both ckts of 400 kV Bikaner (PG)-Bikaner-II Dc line (Quad) at Bikaner-III PS 6. Bikaner-II PS – Bikaner-III PS 400 kV Dc line (Quad) 7. Bikaner-III - Neemrana-II 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end 8. Neemrana-II -Kotputli 400 kV Dc line (Quad) 9. LILO of both ckts of 400 kV Gurgaon (PG) - Sohna Road (GPTL) Dc line (Quad) at Neemrana-II Ss 10. Bikaner-III - Neemrana-II 765 kV Dc line (2nd) along with 330 MVAr switchable line reactor for each circuit at each end 11. Neemrana-II- Bareilly (PG) 765 kV Dc line along with 330 MVAr switchable line reactor for each circuit at each end 12. Augmentation by 400220 kV, 1x500 MVA ICT (3rd) at Kotputli (PG) Additional Transmission system for inter-regional power transfer 1. Establishment of 765 kV Mandsaur Pooling Station along with 2x330 MVAR (765 kV) Bus Reactors 2. Beawar- Mandsaur PS 765 kV Dc line along with 240 MVAr switchable line reactor for each circuit at each end and 3a) Mandsaur PS – Indore(PG) 765 kV Dc Line along with 1x330 MVAR switchable line reactor on each ckt at Mandsaur end of Mandsaur PS – Indore(PG) 765 kV Dc line OR 3b) Establishment of 765 kV Kurawar Ss with 2x330 MVAr 765 kV bus reactor 3c) Mandsaur – Kurawar 765 kV Dc line along with 240 MVAr switchable line reactors on each ckt at both ends of Mandsaur – Kurawar 765 kV Dc line 3d) LILO of Indore – Bhopal 765 kV Sc line at Kurawar | 31-12-2024 | 31-12-2024 |  |  | 125 | 230,232 |  |  |  |  | 2026-08-22 | 2027-09-30 |  | Not effective | 2027-09-30 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 125.00 ¦ Date: 2026-08-31 ¦ Status: Under Implementation ¦ Type: Solar |  |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2027-09-30
9200000247 | Conn under 37.1_37.2_37.6 | 0251100015 | Halvad Renewables Pvt. Ltd. | SR | L&FC | (i) Generating station(s), including REGS(s), without ESS | Wind | 130 |  | 0 | 130 | 0 | 130 |  | Granted | 130 | 0 | 130 | Gadag | Karnataka | 2025-05-20 | 2026-12-31 | •Connectivity through sharing of dedicated Connectivity infrastructure of M/s Azure Power India Pvt. Ltd., granted Connectivity at Gadag PS for application nos. 1200003497 (120 MW) & 1200003534 (50 MW) i.e. Pooling Station at switchyard of M/s Azure Power India Pvt. Ltd. at Gadag – Gadag PS 220kV S/c line on D/c tower including terminal bays at generation pooling station- all the arrangement under the scope of applicant | 0 | 220 KV | Aug without ATS |  |  | • ISTS Network Expansion scheme in WR & SR for export of surplus power during high RE scenario in SR • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) | • ISTS Network Expansion scheme in WR & SR for export of surplus power during high RE scenario in SR • Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A (Phase-I & Phase-II) | 31-12-2024 | 31-12-2024 |  |  | 130 | 201 |  |  |  |  | 2024-07-16 | 2026-10-31 |  | Not effective | 2026-12-31 | Under Construction | Not Commissioned | 0 | ¦ Phase 1 ¦ MW: 130.00 ¦ Date: 2028-09-30 ¦ Status: Under Implementation ¦ Type: Wind | 16.03.2026 |  |  | 08/07/2026 | Pending with Level 2 | 31-12-2024 |  | 2024-12-31 | 2027-06-30

## Next 3 Months
Application ID | Applicant Name | Region | Revised Criterion | Type Of Project Installed Capacity (MW) | Solar | Wind | ESS | Present Connectivity Deemed GNA | Substation Generation Connected | Connectivity GNA Start Date Firm | SCOD Phasewise Date | SCOD Phasewise MW | Connectivity GNA Made Effective MW | Start Date Connectivity GNA Made Effective/ To be made Effective | Connectivity GNA To Be Made Effective MW | Revised SCOD Generation Project | Maximum Delay Permitted By REIA DL | Anticipated COD Of Terminal Bay | Anticipated COD/Charging Date Of Transmission System Last Element | Connectivity Status | Generation Commissioning Status | CoD Declared For Total Quantum | Quantum consider for 24.6 compliance of GNA Reg. | 24.6 Compliance due date
2200000012 | AM GREEN ENERGY PRIVATE LIMITED | SR | Land BG Route | Hybrid 989 (Solar-675MW, Wind314MW) | 675 | 314 | 0 | 989 | Kurnool (new) | 2025-09-27 | 2023-11-15 |  |  | 2026-10-31 | 989 |  |  |  | 2026-10-31 | Not effective | Part Commissioned | 914 | 75 | 2026-10-31
2200000032 | RENEW VIKRAM SHAKTI PRIVATE LIMITED | SR | LOA or PPA | Hybrid Solar-750MW, Wind:960MW, BESS-288) | 810 | 900 | 288 | 1484 | Ananthapuram | 2026-03-31 | 2025-07-31 |  |  | 2026-10-31 | 1484 | 2026-10-27 |  | 2026-03-31 | 2026-10-31 | Not effective | Not Commissioned | 0 | 1484 | 2026-10-31
2200000035 | TEQ GREEN POWER XI PRIVATE LIMITED | WR | Land BG Route | Wind 29.7 | 0 | 29.7 | 0 | 29.7 | kallam | 2025-10-05 | 2024-09-30 |  |  | 2026-10-31 | 29.7 |  |  |  | 2026-10-31 | Not effective | Part Commissioned | 13.5 | 16.2 | 2026-10-31
2200000057 | SOLAR ENERGY CORPORATION OF INDIA LIMITED | SR | LOA or PPA | Solar 100 | 100 | 0 | 0 | 100 | Pavagada | 2025-08-17 | 2025-06-23 |  |  | 2026-10-31 | 100 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 100 | 2026-10-31
2200000058 | TORRENT SAURYA URJA 2 PRIVATE LIMITED | SR | LOA or PPA | Wind 300 | 0 | 300 | 0 | 300 | Koppal-II | 2025-12-27 | 2025-03-29 |  |  | 2026-10-31 | 300 | 2026-01-23 |  | 2026-06-30 | 2026-10-31 | Not effective | Not Commissioned | 0 | 300 | 2026-10-31
2200000061 | ZENATARIS RENEWABLE ENERGY PRIVATE LIMITED | SR | Land BG Route | Wind 171.6 | 100 | 71.6 | 0 | 171.6 | Hiriyur | 2025-06-30 | 2024-12-31 |  |  | 2026-10-31 | 171.6 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 171.6 | 2026-10-31
2200000074 | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | Hybrid 109 | 0 | 50 | 0 | 50 | Gadag-II | 2025-12-31 | 2025-03-31 |  |  | 2026-10-31 | 50 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 50 | 2026-10-31
2200000074 | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | Hybrid 109 | 0 | 50 | 0 | 50 | Gadag-II | 2025-12-31 | 2025-03-31 |  |  | 2026-10-31 | 50 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 50 | 2026-10-31
2200000075 | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | Wind 50 | 0 | 50 | 0 | 50 | kallam | 2026-09-30 | 2024-12-31 |  |  | 2026-10-30 | 50 |  |  | 2026-06-30 | 2026-10-30 | Not effective | Not Commissioned | 0 | 50 | 2026-10-30
2200000086 | Oyster Renewable Energy Private Limited (formerly Known as ABENERGIA RENEWABLES PRIVATE LIMITED) | WR | Land BG Route | Hybrid 100 | 33 | 67 | 0 | 100 | Pachora (Sec-II) | 2026-02-14 | 2024-09-30 | 33 | 100 | 2026-06-26 |  |  |  |  | 2026-05-30 | Effective | Not Commissioned | 0 | 100 | 2026-08-14
2200000086 | Oyster Renewable Energy Private Limited (formerly Known as ABENERGIA RENEWABLES PRIVATE LIMITED) | WR | Land BG Route | Hybrid 100 | 33 | 67 | 0 | 100 | Pachora (Sec-II) | 2026-02-14 | 2024-12-31 | 67 | 100 | 2026-06-26 |  |  |  |  | 2026-05-30 | Effective | Not Commissioned | 0 | 100 | 2026-08-14
2200000096 | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | Hybrid 109 | 0 | 50 | 0 | 50 | Gadag-II | 2025-12-31 | 2025-03-31 | 51 |  | 2026-10-31 | 50 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 50 | 2026-10-31
2200000096 | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | Hybrid 109 | 0 | 50 | 0 | 50 | Gadag-II | 2025-12-31 | 2025-03-31 | 58 |  | 2026-10-31 | 50 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 50 | 2026-10-31
2200000099 | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | Hybrid 109 | 0 | 50 | 0 | 50 | Gadag-II | 2025-12-31 | 2025-03-31 | 51 |  | 2026-10-31 | 50 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 50 | 2026-10-31
2200000100 | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | Hybrid 109 | 0 | 50 | 0 | 50 | Gadag-II | 2025-12-31 | 2025-03-31 |  |  | 2026-10-31 | 50 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 50 | 2026-10-31
2200000100 | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | Hybrid 109 | 0 | 50 | 0 | 50 | Gadag-II | 2025-12-31 | 2025-03-31 |  |  | 2026-10-31 | 50 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 50 | 2026-10-31
2200000121 | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | Hybrid 327MW [Solar-153 MW & Wind-174MW] | 0 | 150 | 0 | 150 | Gadag-II | 2025-12-31 | 2025-06-30 | 153 |  | 2026-10-31 | 150 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 150 | 2026-10-31
2200000121 | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | SR | Land BG Route | Hybrid 327MW [Solar-153 MW & Wind-174MW] | 0 | 150 | 0 | 150 | Gadag-II | 2025-12-31 | 2025-06-30 | 174 |  | 2026-10-31 | 150 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 150 | 2026-10-31
2200000126 | VEH GREEN ENERGY PRIVATE LIMITED | SR | Land Route | Wind 153.6 | 0 | 153.6 | 0 | 153.6 | Koppal-II | 2025-12-27 | 2025-05-30 |  |  | 2026-10-31 | 153.6 |  |  | 2026-06-30 | 2026-10-31 | Not effective | Not Commissioned | 0 | 153.6 | 2026-10-31
2200000141 | ABREL (RJ) PROJECTS LIMITED | SR | Land BG Route | Wind 184 | 0 | 184 | 0 | 184 | Koppal-II | 2025-12-27 | 2025-05-31 |  |  | 2026-10-31 | 184 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 184 | 2026-10-31
2200000154 | NTPC RENEWABLE ENERGY LIMITED | WR | LOA or PPA | Wind 200 | 0 | 200 | 0 | 200 | Bhuj-II (Sec-I) | 2025-03-29 | 2025-03-29 |  | 200 | 2025-03-29 |  | 2026-01-23 | 2026-10-20 |  |  | Effective | Not Commissioned | 0 | 200 | 2026-10-20
2200000193 | TATA POWER RENEWABLE ENERGY LIMITED | WR | Land Route | Wind 101 | 0 | 101 | 0 | 100.8 | kallam | 2025-10-05 | 2025-06-01 |  |  | 2026-10-31 | 100.8 |  |  | 2025-03-31 | 2026-10-31 | Not effective | Not Commissioned | 0 | 100.8 | 2026-10-31
2200000213 | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED | WR | Land Route | Wind 50 | 0 | 50 | 0 | 50 | Solapur Pool (Sec-I) | 2026-03-20 | 2025-09-30 |  |  | 2026-10-30 | 50 |  |  | 2026-10-30 | 2026-10-30 | Not effective | Not Commissioned | 0 | 50 | 2026-10-30
2200000231 | AMP ENERGY C&I TWELVE PRIVATE LIMITED | SR | Land BG Route | Solar 100 | 100 | 0 | 0 | 100 | Kurnool-III | 2025-06-30 | 2024-11-30 |  |  | 2026-10-31 | 100 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 100 | 2026-10-31
2200000247 | SPRNG POWER EARTH PRIVATE LIMITED | WR | LOA or PPA | Solar 250 | 250 | 0 | 0 | 250 | Radhanesda | 2026-06-30 | 2026-06-30 |  | 250 | 2026-06-30 |  | 2026-08-29 |  |  |  | Effective | Not Commissioned | 0 | 250 | 2026-08-29
2200000250 | NHPC LIMITED | SR | LOA or PPA | Solar 100 | 100 | 0 | 0 | 100 | NP Kunta | 2025-03-23 | 2024-09-30 |  |  | 2026-10-31 | 100 | 2026-06-30 |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 100 | 2026-10-31
2200000270 | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED | WR | Land Route | Wind 52.8 | 0 | 52.8 | 0 | 52.8 | Solapur Pool (Sec-I) | 2026-03-20 | 2025-09-30 |  |  | 2026-10-30 | 52.8 |  |  | 2026-10-30 | 2026-10-30 | Not effective | Not Commissioned | 0 | 52.8 | 2026-10-30
2200000271 | ABC CLEANTECH PRIVATE LIMITED | SR | Land BG Route | Wind 250 | 0 | 250 | 0 | 250 | Ananthapuram | 2026-03-31 | 2026-03-31 |  |  | 2026-10-31 | 250 |  |  | 2026-03-31 | 2026-10-31 | Not effective | Not Commissioned | 0 | 250 | 2026-10-31
2200000273 | ABC CT RE PARK (03) PRIVATE LIMITED | SR | Land BG Route | Wind 250 | 0 | 250 | 0 | 250 | Ananthapuram | 2026-03-31 | 2025-06-30 |  |  | 2026-10-31 | 250 |  |  | 2026-03-31 | 2026-10-31 | Not effective | Not Commissioned | 0 | 250 | 2026-10-31
2200000298 | RENEW SAMIR URJA PRIVATE LIMITED | WR | Land BG Route | Wind 300 | 0 | 300 | 0 | 300 | Indore | 2026-03-31 | 2025-06-30 |  |  | 2026-03-31 | 300 |  |  | 2025-12-02 |  | Not effective | Not Commissioned | 0 | 300 | 2026-09-30
2200000302 | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | WR | Land BG Route | Wind 100 | 0 | 100 | 0 | 100 | kallam | 2025-10-05 | 2025-03-31 |  |  | 2026-10-31 | 100 |  |  | 2025-03-31 | 2026-10-31 | Not effective | Not Commissioned | 0 | 100 | 2026-10-31
2200000318 | AYANA RENEWABLE POWER FOUR PRIVATE LIMITED | SR | Land BG Route | Wind 50 | 0 | 50 | 0 | 50 | Ananthapuram | 2025-09-28 | 2025-03-31 |  |  | 2026-10-31 | 50 |  |  | 2026-03-31 | 2026-10-31 | Not effective | Not Commissioned | 0 | 50 | 2026-10-31
2200000342 | Oyster Renewable Energy Private Limited (formerly Known as ABENERGIA RENEWABLES PRIVATE LIMITED) | WR | Land BG Route | Hybrid 81 | 67 | 14 | 0 | 81 | Pachora (Sec-I) | 2026-02-14 | 2025-03-31 |  | 81 | 2026-06-27 |  |  |  |  | 2026-05-30 | Effective | Part Commissioned | 52.8 | 28.2 | 2026-08-14
2200000353 | AVAADA ENERGY PRIVATE LIMITED | WR | LOA or PPA | Wind 250 | 0 | 250 | 0 | 250 | kallam | 2026-09-30 | 2024-12-31 |  |  | 2026-10-30 | 250 |  |  | 2026-06-30 | 2026-10-30 | Not effective | Not Commissioned | 0 | 250 | 2026-10-30
2200000356 | VEH DAMEN POWER PRIVATE LIMITED | WR | Land Route | Wind 76.8 | 0 | 76.8 | 0 | 76.8 | Pachora (Sec-II) | 2026-03-30 | 2026-03-31 |  | 76.8 | 2026-06-27 |  |  |  | 2024-04-02 | 2026-05-30 | Effective | Not Commissioned | 0 | 76.8 | 2026-09-30
2200000383 | HERO SOLAR ENERGY PRIVATE LIMITED | SR | LOA or PPA | Hybrid Solar: 150MW Wind: 150MW BESS: 30MWh | 150 | 150 | 27 | 270 | Kurnool-III | 2026-06-30 | 2026-06-30 |  |  | 2026-10-31 | 270 | 2026-06-03 |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 270 | 2026-10-31
2200000388 | FIRST ENERGY PRIVATE LIMITED | SR | Land BG Route | Solar 100 | 100 | 0 | 0 | 100 | NP Kunta | 2025-09-23 | 2025-06-15 |  |  | 2026-10-31 | 100 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 100 | 2026-10-31
2200000394 | TATA POWER RENEWABLE ENERGY LIMITED | SR | LOA or PPA | Wind 151 | 0 | 151 | 0 | 151 | Pugalur | 2026-03-01 | 2026-03-01 |  |  | 2026-10-31 | 151 |  |  | 2026-08-31 | 2026-10-31 | Not effective | Not Commissioned | 0 | 151 | 2026-10-31
2200000404 | BHOJRAJ DEVELOPERS PRIVATE LIMITED | WR | Land Route | Hybrid Wind: 160 MW Solar: 26 MW | 26 | 160 | 0 | 186 | Pachora (Sec-II) | 2026-02-14 | 2025-06-30 |  | 186 | 2026-06-27 |  |  |  | 2026-04-15 | 2026-05-30 | Effective | Not Commissioned | 0 | 186 | 2026-08-14
2200000409 | SOLARCRAFT POWER INDIA 7 PRIVATE LIMITED | WR | Land Route | Wind 47.2 | 0 | 47.2 | 0 | 47.2 | Solapur Pool (Sec-I) | 2026-03-20 | 2025-12-31 |  |  | 2026-10-30 | 47.2 |  |  | 2026-06-30 | 2026-10-30 | Not effective | Not Commissioned | 0 | 47.2 | 2026-10-30
2200000438 | Jindal Green Wind 1 Private Limited (Formerly known as JSP GREEN WIND 1 PRIVATE LIMITED) | SR | Land BG Route | Wind 300 | 0 | 300 | 0 | 300 | Karur | 2025-12-25 | 2025-05-31 |  |  | 2026-10-31 | 300 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 300 | 2026-10-31
2200000440 | SOLARCRAFT POWER INDIA 16 PRIVATE LIMITED | WR | LOA or PPA | Hybrid Wind - 191.4 MW, Solar - 56 MW, BESS - 91 MW) | 56 | 191.4 | 91 | 150 | Solapur Pool (Sec-I) | 2026-04-01 | 2026-04-01 |  |  | 2026-10-31 | 150 | 2026-07-30 |  | 2026-08-31 | 2026-10-31 | Not effective | Not Commissioned | 0 | 150 | 2026-10-31
2200000449 | TATA POWER RENEWABLE ENERGY LIMITED | SR | LOA or PPA | Wind 151.2 | 0 | 151.2 | 0 | 151.2 | Pugalur | 2026-03-01 | 2026-03-01 |  |  | 2026-10-31 | 151.2 |  |  | 2026-08-31 | 2026-10-31 | Not effective | Not Commissioned | 0 | 151.2 | 2026-10-31
2200000450 | TATA POWER RENEWABLE ENERGY LIMITED | WR | LOA or PPA | Wind 100.8 | 0 | 100.8 | 0 | 100.8 | kallam | 2026-03-01 | 2026-03-01 |  |  | 2026-10-30 | 100.8 |  |  | 2025-03-31 | 2026-10-30 | Not effective | Not Commissioned | 0 | 100.8 | 2026-10-30
2200000594 | GRT JEWELLERS (INDIA) PRIVATE LIMITED | SR | LOA or PPA | Solar 150 | 150 | 0 | 0 | 150 | Tuticorin-II | 2026-05-04 | 2026-05-04 |  |  | 2026-10-31 | 150 | 2026-06-28 |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 150 | 2026-10-31
2200000633 | JINDAL POWER LIMITED | SR | Land Route | Solar 52.6 | 52.6 | 0 | 0 | 52.6 | Nellore | 2025-01-01 | 2024-06-29 |  |  | 2026-10-31 | 52.6 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 52.6 | 2026-10-31
2200000709 | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | WR | Land BG Route | Solar 300 | 300 | 0 | 0 | 300 | Neemuch | 2026-01-31 | 2025-04-30 |  |  | 2026-10-31 | 300 |  |  | 2026-10-31 |  | Not effective | Not Commissioned | 0 | 300 | 2026-10-31
2200000718 | JSW NEO ENERGY LIMITED | WR | LOA or PPA | Wind 300 | 0 | 300 | 0 | 300 | Solapur Pool (Sec-I) | 2026-03-31 | 2026-03-31 |  |  | 2026-10-30 | 300 |  |  | 2026-08-30 | 2026-10-30 | Not effective | Not Commissioned | 0 | 300 | 2026-10-30
2200000920 | ZENATARIS RENEWABLE ENERGY PRIVATE LIMITED | SR | Land Route | Wind 62.7 | 0 | 62.7 | 0 | 62.7 | Hiriyur | 2025-12-31 | 2025-06-30 |  |  | 2026-10-31 | 62.7 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 62.7 | 2026-10-31
2200001047 | SOLARCRAFT POWER INDIA 16 PRIVATE LIMITED | WR | LOA or PPA | Hybrid 247.4 MW(Wind - 191.4 MW, Solar - 56 MW) | 10.59 | 36.21 | 17.22 | 35 | Solapur Pool (Sec-I) | 2026-04-01 | 2026-04-01 |  |  | 2026-10-30 | 35 | 2026-07-30 |  | 2026-08-30 | 2026-10-30 | Not effective | Not Commissioned | 0 | 35 | 2026-10-30
2200001090 | SERENTICA RENEWABLES INDIA PRIVATE LIMITED | WR | Land BG Route | Wind 150 | 0 | 150 | 0 | 150 | kallam | 2025-10-05 | 2025-05-31 |  |  | 2026-10-30 | 150 |  |  | 2025-01-04 | 2026-10-30 | Not effective | Not Commissioned | 0 | 150 | 2026-10-30
2200001115 | JSW RENEW ENERGY TWELVE LIMITED | SR | Land BG Route | Hybrid 175 (Solar-65 MW, Wind-110 MW) | 65 | 110 | 0 | 140 | Tuticorin-II | 2025-12-23 | 2025-03-01 |  |  | 2026-10-31 | 140 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 140 | 2026-10-31
2200001120 | JSW GREEN ENERGY ONE LIMITED | SR | Land BG Route | Solar 50 | 40 | 0 | 0 | 40 | Tuticorin-II | 2025-12-23 | 2025-05-31 |  |  | 2026-10-31 | 40 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 40 | 2026-10-31
2200001148 | JSW RENEW ENERGY THIRTEEN LIMITED | WR | Land BG Route | Solar 300 | 300 | 0 | 0 | 300 | Solapur | 2026-03-31 | 2026-03-31 |  | 300 | 2026-03-31 | [5 empty] | Effective | Not Commissioned | 0 | 300 | 2026-09-30
2200001158 | WAAREE FOREVER ENERGIES PRIVATE LIMITED | WR | Land BG Route | Solar 1000 | 700 | 0 | 350 | 700 | Solapur | 2026-03-31 | 2026-03-31 | 300 | 700 | 2026-03-31 | [5 empty] | Effective | Not Commissioned | 0 | 700 | 2026-09-30
2200001244 | TATA POWER RENEWABLE ENERGY LIMITED | WR | Land Route | Wind 111.8 | 0 | 10.8 | 0 | 10.8 | kallam | 2025-10-05 | 2025-03-31 |  |  | 2026-10-31 | 10.8 |  |  | 2025-03-31 | 2026-10-31 | Not effective | Not Commissioned | 0 | 10.8 | 2026-10-31
9100000037 | Tunga Renewables Energy Pvt. Ltd. Connectivity Appl No.- 1200003577 | SR | LOA or PPA | Wind 189.84 | 0 | 189.84 | 0 | 189.84 | Koppal | 2024-07-16 | 2023-06-30 |  |  | 2026-10-31 | 189.84 | 2022-09-05 |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 189.84 | 2026-10-31
9100000038 | Project Ten Renewable Power Pvt. Ltd. ( Connectivity Appl No.-1200003530) | SR | LOA or PPA | Wind 150 | 0 | 150 | 0 | 150 | Koppal | 2024-07-16 | 2023-06-05 |  |  | 2026-10-31 | 150 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 150 | 2026-10-31
9100000041 | Azure Power India Pvt. Ltd. | SR | LOA or PPA | Wind 170 | 0 | 170 | 0 | 120 | Gadag | 2024-12-31 | 2023-06-30 |  |  | 2026-10-31 | 120 | 2025-07-26 |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 120 | 2026-10-31
9100000042 | Green Infra Wind Connectivity Appl No.- 0451100007 | SR | LOA or PPA | Wind 178.5 | 0 | 178.5 | 0 | 178.5 | Gadag | 2024-07-16 | 2023-06-20 |  |  | 2026-10-31 | 123.9 | 2025-07-26 |  |  | 2026-10-31 | Not Effective | Part Commissioned | 54.6 | 123.9 | 2026-10-31
9100000043 | ReNew Naveen Urja Pvt. Ltd | SR | LOA or PPA | Wind 300 | 0 | 297.5 | 0 | 297.5 | Gadag | 2024-07-16 | 2023-07-31 |  |  | 2026-10-31 | 297.5 | 2025-07-26 |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 297.5 | 2026-10-31
9100000045 | JSW Renew Energy Connectivity Appl No.-1200002868 | SR | LOA or PPA | Wind 170 | 0 | 170 | 0 | 170 | Karur | 2024-07-16 | 2022-10-31 |  |  | 2026-10-31 | 170 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 170 | 2026-10-31
9100000047 | Project Ten Renewable Power Pvt. Ltd. | SR | LOA or PPA | Wind 300 | 300 | 0 | 0 | 300 | Pavagada | 2024-07-16 | 2023-06-05 |  |  | 2026-10-31 | 300 | 2024-09-14 |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 300 | 2026-10-31
9100000143 | Renew Solar Power Pvt. Ltd. (RSPPL) Connectivity: 1200003241 (300MW); LTA: 1200003270 (300MW); | WR | LOA or PPA | Wind 300 | 0 | 300 | 0 | 300 | kallam | 2024-08-10 | 2022-10-30 |  | 300 | 2024-08-10 |  | 2026-04-11 | 2026-10-09 |  |  | Effective | Part Commissioned | 138.6 | 161.4 | 2026-10-09
9100000391 | Adani Renewable Energy Holding Seventeen Private Limited | NR | LOA or PPA | Solar 600 | 600 | 0 | 0 | 600 | Fatehgarh-III (Sec-I) | 2023-10-01 | 2022-03-01 |  | 600 | 2025-01-22 |  | 2026-03-31 | 2026-09-30 |  | 2024-12-19 | Effective | Part Commissioned | 251 | 349 | 2026-09-30
9200000013 | Serentica Renewables India Pvt. Ltd | SR | L&FC | Hybrid 132 | 56 | 24 | 0 | 80 | Gadag | 2024-10-01 | 2024-07-01 |  |  | 2026-10-31 | 80 |  |  |  | 2026-10-31 | Not effective | Part Commissioned | 0 | 80 | 2026-10-31
9200000016 | Serentica Renewables India Pvt. Ltd | SR | L&FC | Hybrid 165 | 70 | 30 | 0 | 100 | Gadag | 2024-10-01 | 2024-07-01 |  |  | 2026-10-31 | 100 |  |  |  | 2026-10-31 | Not effective | Part Commissioned | 41.47 | 58.53 | 2026-10-31
9200000017 | Tunga Renewable Energy Pvt. Ltd. | SR | L&FC | Wind 45.07 | 0 | 45.07 | 0 | 45.07 | Koppal | 2025-06-30 | 2024-06-30 |  |  | 2026-10-31 | 45.07 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 45.07 | 2026-10-31
9200000018 | Tunga Renewable Energy Pvt. Ltd. | SR | L&FC | Wind 115 | 0 | 115 | 0 | 115 | Koppal | 2025-06-30 | 2023-06-30 |  |  | 2026-10-31 | 115 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 115 | 2026-10-31
9200000021 | Serentica Renewable India 1 Pvt. | SR | L&FC | Hybrid 133.3333333 | 100 | 0 | 0 | 100 | Koppal | 2024-09-30 | 2024-07-01 |  |  | 2026-10-31 | 100 |  |  |  | 2026-10-31 | Not effective | Part Commissioned | 106.25 | -6.25 | 2026-10-31
9200000022 | Serentica Renewable India 1 Pvt. | SR | L&FC | Hybrid 133.3333333 | 100 | 0 | 0 | 100 | Koppal | 2024-07-16 | 2024-01-07 |  |  | 2026-10-31 | 100 |  |  |  | 2026-10-31 | Not effective | Part Commissioned | 106.25 | -6.25 | 2026-10-31
9200000024 | Ircon Renewable Power Ltd. | SR | LOA or PPA | Solar 500 | 500 | 0 | 0 | 500 | Pavagada | 2025-08-17 | 2024-01-30 |  |  | 2026-10-31 | 100 |  |  |  | 2026-10-31 | Not Effective | Part Commissioned | 400 | 100 | 2026-10-31
9200000025 | Solar Energy Corporation of India Ltd. | SR | L&A | Solar 200 | 200 | 0 | 0 | 200 | Pavagada | 2025-06-23 | 2024-12-31 |  |  | 2026-10-31 | 200 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 200 | 2026-10-31
9200000026 | Sembcorp Green Infra Private Limited (Formerly known as Green Infra Wind Energy Limited) | SR | L&FC | Wind 70 | 0 | 70 | 0 | 70 | Gadag | 2025-05-31 | 2024-12-31 |  |  | 2026-10-31 | 70 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 70 | 2026-10-31
9200000027 | Sembcorp Green Infra Private Limited (Formerly known as Green Infra Wind Energy Limited) | SR | LOA or PPA | Wind 50 | 0 | 50 | 0 | 50 | Gadag | 2024-09-30 | 2024-01-31 |  |  | 2026-10-31 | 50 | 2026-08-31 |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 50 | 2026-10-31
9200000028 | Sembcorp Green Infra Private Limited (Formerly known as Green Infra Wind Energy Limited) | SR | LOA or PPA | Wind 1.5 | 0 | 1.5 | 0 | 1.5 | Gadag | 2024-07-16 | 2023-06-20 |  |  | 2026-10-31 | 1.5 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 1.5 | 2026-10-31
9200000030 | Sembcorp Green Infra Private Limited (Formerly known as Green Infra Wind Energy Limited) | SR | L&FC | Wind 300 | 0 | 300 | 0 | 300 | Gadag-II | 2025-12-27 | 2025-04-01 |  |  | 2026-10-31 | 300 |  |  | 2026-06-30 | 2026-10-31 | Not effective | Not Commissioned | 0 | 300 | 2026-10-31
9200000032 | Tata Power Renewable Energy Ltd. | SR | L&A | Wind 300 | 300 | 0 | 0 | 300 | Koppal-II | 2025-12-27 | 2025-04-01 |  |  | 2026-10-31 | 300 |  |  | 2026-06-30 | 2026-10-31 | Not effective | Not Commissioned | 0 | 300 | 2026-10-31
9200000034 | Tata Power Renewable Energy Ltd. | SR | LOA or PPA | Wind 170 | 0 | 170 | 0 | 170 | Gadag-II | 2025-12-27 | 2025-04-01 |  |  | 2026-10-31 | 170 |  |  | 2026-06-30 | 2026-10-31 | Not effective | Not Commissioned | 0 | 170 | 2026-10-31
9200000099 | Veh Jayin Renewables Private Limited | WR | L&FC | Wind 151.8 | 0 | 151.8 | 0 | 151.8 | Rajgarh (Sec-II) | 2025-11-15 | 2024-03-29 |  |  | 2026-08-30 | 151.8 |  |  | 2024-12-01 | 2026-08-30 | Not effective | Not Commissioned | 0 | 151.8 | 2026-08-30
9200000101 | Veh Wind Energy Private Limited | WR | L&FC | Wind 75 | 0 | 75 | 0 | 75 | Rajgarh (Sec-II) | 2025-11-15 | 2024-10-31 |  |  | 2026-08-30 | 75 |  |  | 2024-12-01 | 2026-08-30 | Not effective | Not Commissioned | 0 | 75 | 2026-08-30
9200000120 | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) | WR | L&FC | Wind 10 | 0 | 10 | 0 | 10 | kallam | 2025-10-05 | 2024-07-01 |  |  | 2026-10-30 | 10 |  |  |  | 2026-10-30 | Not effective | Not Commissioned | 0 | 10 | 2026-10-30
9200000121 | Serentica Renewables India 4 Pvt. Ltd. (SRI4PL) | WR | L&FC | Wind 140 | 0 | 140 | 0 | 140 | kallam | 2025-10-05 | 2024-07-01 |  |  | 2026-10-30 | 140 |  |  | 2025-01-01 | 2026-10-30 | Not effective | Not Commissioned | 0 | 140 | 2026-10-30
9200000123 | ReNew Green (MHP One) Private Limited | WR | L&A | Wind 33 | 0 | 33 | 0 | 33 | kallam | 2025-10-05 | 2023-06-30 |  |  | 2026-10-30 | 33 |  |  |  | 2026-10-30 | Not effective | Part Commissioned | 18.3 | 14.7 | 2026-10-30
9200000124 | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) | WR | L&FC | Wind 200 | 0 | 200 | 0 | 200 | kallam | 2025-10-05 | 2024-04-27 |  |  | 2026-10-30 | 200 | 2025-12-02 |  |  | 2026-10-30 | Not effective | Not Commissioned | 0 | 200 | 2026-10-30
9200000125 | TEQ Green Power XI Pvt. Ltd.(TGPXIPL) | WR | L&FC | Wind 99 | 0 | 99 | 0 | 99 | kallam | 2025-10-05 | 2024-04-27 |  |  | 2026-10-30 | 99 |  |  |  | 2026-10-30 | Not effective | Part Commissioned | 48.2 | 50.8 | 2026-10-30
9200000231 | Tata Power Renewable Energy Ltd. | SR | LOA or PPA | Wind 170 | 0 | 170 | 0 | 170 | Gadag-II | 2025-12-27 | 2025-04-01 |  |  | 2026-10-31 | 170 |  |  | 2026-06-30 | 2026-10-31 | Not effective | Not Commissioned | 0 | 170 | 2026-10-31
9200000232 | TATA Power Renewable Energy Ltd. | SR | LOA or PPA | Wind 85 | 85 | 0 | 0 | 85 | Koppal-II | 2025-12-27 | 2025-04-01 |  |  | 2026-10-31 | 85 |  |  | 2026-06-30 | 2026-10-31 | Not effective | Not Commissioned | 0 | 85 | 2026-10-31
9200000233 | TATA Power Renewable Energy Ltd. | SR | LOA or PPA | Wind 85 | 85 | 0 | 0 | 85 | Koppal-II | 2025-12-27 | 2025-04-01 |  |  | 2026-10-31 | 85 |  |  |  | 2026-10-31 | Not effective | Not Commissioned | 0 | 85 | 2026-10-31